## Task_Table1
ID | Indicators | Task_Mode | name | Duration | Start_Date | Finish_Date | PercentC | preds | Scheduled_Work | RN | status | waiting | row_type | Owner | source | notes_2 | Deadline | Constraint_Type | OL
1 |  | Auto Scheduled | תכנית מרה"ס שלב ג | 763.25 days | 08 December 2019 8:00 | 22 August 2022 13:00 | 0.33000000000000002 |  | 27,066h | 00 |  |  | header |  | nan |  | NA | As Soon As Possible | 1
2 |  | Auto Scheduled | מוכנות זכיין לסביבת אינטגרציה | 375.63 days | 23 November 2020 8:00 | 13 April 2022 8:00 | 0.13 |  | 0h | 00.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 2
3 |  | Auto Scheduled | SRR | 1.13 days | 19 January 2021 8:00 | 19 January 2021 17:00 | 1 |  | 0h | 00.01.01 |  |  | header |  | 17464 |  | NA | Must Finish On | 3
4 |  | Auto Scheduled | PDR - סביבת אינטגרציה - המערך היעודי | 1.13 days | 17 November 2021 8:00 | 18 November 2021 8:00 | 0 |  | 0h | 00.01.02 |  |  | header |  | 2492 |  | NA | Must Finish On | 3
5 |  | Auto Scheduled | CDR - סביבת אינטגרציה - המערך הייעודי | 1.13 days | 20 January 2022 8:00 | 23 January 2022 8:00 | 0 |  | 0h | 00.01.03 |  |  | header |  | 2495 |  | NA | Must Finish On | 3
6 |  | Auto Scheduled | סיום הקמת המתחם ותשתית תקשוב לסביבת אינטגרציה | 0 days | 11 March 2022 8:00 | 11 March 2022 8:00 | 0 |  | 0h | 00.01.04 |  |  | header |  | 2493 |  | NA | Must Finish On | 3
7 |  | Auto Scheduled | מוכנות סביבת האינטגרציה לתחילת התממשקות עם מערכת ERP | 1.13 days | 12 April 2022 8:00 | 13 April 2022 8:00 | 0 |  | 0h | 00.01.04 |  |  | header |  | 2498 |  | NA | Must Finish On | 3
8 |  | Auto Scheduled | מערכות מידע לתפעול ייעודי - אפליקציה - PDR | 237.25 days | 23 November 2020 8:00 | 24 October 2021 8:00 | 0.17999999999999999 |  | 0h | 00.01.05 |  |  | header |  | nan |  | NA | As Soon As Possible | 3
9 |  | Auto Scheduled | הכנה והגשת PDR | 1.13 days | 23 November 2020 8:00 | 23 November 2020 17:00 | 0.90000000000000002 |  | 0h | 00.01.05.01 |  |  | header |  | 16794 |  | NA | Must Finish On | 4
10 |  | Auto Scheduled | הסכמת מזמין לקיום הסקר | 1.13 days | 29 August 2021 8:00 | 30 August 2021 8:00 | 0 |  | 0h | 00.01.05.02 |  |  | header |  | 16795 |  | NA | Must Finish On | 4
11 |  | Auto Scheduled | סקר PDR | 0 days | 28 September 2021 8:00 | 28 September 2021 8:00 | 0 |  | 0h | 00.01.05.03 |  |  | header |  | 16796 |  | NA | Must Finish On | 4
12 |  | Auto Scheduled | סיכום סקר PDR ע"י המזמין | 1.13 days | 19 September 2021 8:00 | 29 September 2021 8:00 | 0 |  | 0h | 00.01.05.04 |  |  | header |  | 16797 |  | NA | Must Finish On | 4
13 |  | Auto Scheduled | תיקון והגשת PDR | 1.13 days | 13 October 2021 8:00 | 14 October 2021 8:00 | 0 |  | 0h | 00.01.05.05 |  |  | header |  | 16798 |  | NA | Must Finish On | 4
14 |  | Auto Scheduled | בדיקה ואישור PDR | 1.13 days | 21 October 2021 8:00 | 24 October 2021 8:00 | 0 |  | 0h | 00.01.05.06 |  |  | header |  | 16799 |  | NA | Must Finish On | 4
15 |  | Auto Scheduled | מערכות מידע לתפעול ייעודי- אפליקציה - CDR | 55.13 days | 21 October 2021 8:00 | 29 December 2021 8:00 | 0 |  | 0h | 00.01.06 |  |  | header |  | nan |  | NA | As Soon As Possible | 3
16 |  | Auto Scheduled | הכנה והגשת CDR | 1.13 days | 21 October 2021 8:00 | 24 October 2021 8:00 | 0 |  | 0h | 00.01.06.01 |  |  | header |  | 16802 |  | NA | Must Finish On | 4
17 |  | Auto Scheduled | הסכמת מזמין לקיום הסקר | 1.13 days | 18 November 2021 8:00 | 21 November 2021 8:00 | 0 |  | 0h | 00.01.06.02 |  |  | header |  | 16803 |  | NA | Must Finish On | 4
18 |  | Auto Scheduled | סקר CDR | 1.13 days | 05 December 2021 8:00 | 06 December 2021 8:00 | 0 |  | 0h | 00.01.06.03 |  |  | header |  | 16804 |  | NA | Must Finish On | 4
19 |  | Auto Scheduled | סיכום סקר CDR ע"י המזמין | 1.13 days | 06 December 2021 8:00 | 07 December 2021 8:00 | 0 |  | 0h | 00.01.06.04 |  |  | header |  | 16805 |  | NA | Must Finish On | 4
20 |  | Auto Scheduled | תיקון והגשת CDR | 1.13 days | 21 December 2021 8:00 | 22 December 2021 8:00 | 0 |  | 0h | 00.01.06.05 |  |  | header |  | 16806 |  | NA | Must Finish On | 4
21 |  | Auto Scheduled | בדיקה ואישור CDR | 1.13 days | 28 December 2021 8:00 | 29 December 2021 8:00 | 0 |  | 0h | 00.01.06.06 |  |  | header |  | 16807 |  | NA | Must Finish On | 4
22 |  | Auto Scheduled | מוכנות אמל"ח לסביבת אינטגרציה | 269.38 days | 05 September 2021 9:00 | 22 August 2022 13:00 | 0 |  | 0h | 00.10 |  |  | header |  | nan |  | NA | As Soon As Possible | 2
23 |  | Auto Scheduled | אבני דרך פנימיות | 269.38 days | 05 September 2021 9:00 | 22 August 2022 13:00 | 0 |  | 0h | 00.10.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 3
24 |  | Auto Scheduled | סיום ואישור מסמכי בלו-פרינט | 0 days | 05 September 2021 9:00 | 05 September 2021 9:00 | 0 | 65,441,764,831,888,979,1104,1125,1151,1439,1572,1705,1829,2051,2273,2476,2538,2838,2860,2954,3133,3233,3457,3582,3604,3627,3685,3930,4162,4208,4230,4253,4318 | 0h | 00.10.01.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 4
25 |  | Auto Scheduled | סיום משימות פיתוח | 0 days | 31 July 2022 13:00 | 31 July 2022 13:00 | 0 | 41,42,43,44,46,47,48,49 | 0h | 00.10.01.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 4
26 |  | Auto Scheduled | סיום משימות ממשקים | 0 days | 22 August 2022 13:00 | 22 August 2022 13:00 | 0 | 30,31,32,33,35,36,37,38 | 0h | 00.10.01.03 |  |  | header |  | nan |  | NA | As Soon As Possible | 4
27 |  | Auto Scheduled | אבני דרך חצויות | 114.75 days | 31 March 2022 13:00 | 22 August 2022 13:00 | 0 |  | 0h | 00.10.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 3
28 |  | Auto Scheduled | אבני דרך ממשקים | 114.75 days | 31 March 2022 13:00 | 22 August 2022 13:00 | 0 |  | 0h | 00.10.02.INT |  |  | header |  | nan |  | NA | As Soon As Possible | 4
29 |  | Auto Scheduled | אבני דרך ממשקים - מלאי | 114.75 days | 31 March 2022 13:00 | 22 August 2022 13:00 | 0 |  | 0h | 00.10.02.INT.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 5
30 |  | Auto Scheduled | 01:I1 | 0 days | 22 August 2022 13:00 | 22 August 2022 13:00 | 0 | 86,130,174,462,506,550,931,1183,1227,1271,1759,1883,2305,2349 | 0h | 00.10.02.INT.01.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
31 |  | Auto Scheduled | 01:I2 | 0 days | 31 March 2022 13:00 | 31 March 2022 13:00 | 0 | 97,141,185,473,517,785,1002,1194,1238,1726,1850,2072,2316,2360 | 0h | 00.10.02.INT.01.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
32 |  | Auto Scheduled | 01:I3 | 0 days | 04 August 2022 13:00 | 04 August 2022 13:00 | 0 | 108,152,196,484,528,909,1013,1205,1249,1737,1861,2083,2327 | 0h | 00.10.02.INT.01.03 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
33 |  | Auto Scheduled | 01:I4 | 0 days | 14 August 2022 13:00 | 14 August 2022 13:00 | 0 | 119,163,207,495,539,920,1172,1216,1260,1748,1872,2294,2338 | 0h | 00.10.02.INT.01.04 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
34 |  | Auto Scheduled | אבני דרך ממשקים - שרשרת | 24.75 days | 10 April 2022 13:00 | 10 May 2022 13:00 | 0 |  | 0h | 00.10.02.INT.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 5
35 |  | Auto Scheduled | 02:I1 | 0 days | 10 April 2022 13:00 | 10 April 2022 13:00 | 0 | 2559,2603,2647,2691,2986,3030,3256,3300,3489 | 0h | 00.10.02.INT.02.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
36 |  | Auto Scheduled | 02:I1 | 0 days | 02 May 2022 13:00 | 02 May 2022 13:00 | 0 | 2570,2614,2658,2881,2997,3154,3267,3311,3706 | 0h | 00.10.02.INT.02.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
37 |  | Auto Scheduled | 02:I1 | 0 days | 19 April 2022 13:00 | 19 April 2022 13:00 | 0 | 2581,2625,2669,2892,3008,3165,3278,3322,3717 | 0h | 00.10.02.INT.02.03 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
38 |  | Auto Scheduled | 02:I1 | 0 days | 10 May 2022 13:00 | 10 May 2022 13:00 | 0 | 2592,2636,2680,2975,3019,3176,3289,3478 | 0h | 00.10.02.INT.02.04 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
39 |  | Auto Scheduled | אבני דרך סאפ | 87.75 days | 12 April 2022 13:00 | 31 July 2022 13:00 | 0 |  | 0h | 00.10.02.SAP |  |  | header |  | nan |  | NA | As Soon As Possible | 4
40 |  | Auto Scheduled | אבני דרך סאפ - מלאי | 54 days | 24 May 2022 13:00 | 31 July 2022 13:00 | 0 |  | 0h | 00.10.02.SAP.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 5
41 |  | Auto Scheduled | 01:S1 | 0 days | 30 June 2022 13:00 | 30 June 2022 13:00 | 0 | 219,263,307,351,395,562,606,650,694,738,819,943,1036,1080,1305,1349,1393,1460,1504,1548,1615,1659,1771,1815,1928,1972,2016,2106,2150,2194,2238,2383,2427 | 0h | 00.10.02.SAP.01.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
42 |  | Auto Scheduled | 01:S2 | 0 days | 31 July 2022 13:00 | 31 July 2022 13:00 | 0 | 230,274,318,362,406,573,617,661,705,749,852,954,1047,1091,1316,1360,1404,1471,1515,1559,1626,1670,1782,1895,1939,1983,2027,2117,2161,2205,2249,2394,2438 | 0h | 00.10.02.SAP.01.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
43 |  | Auto Scheduled | 01:S3 | 0 days | 24 May 2022 13:00 | 24 May 2022 13:00 | 0 | 241,285,329,373,417,584,628,672,716,797,863,965,1058,1283,1327,1371,1415,1482,1526,1593,1637,1681,1793,1906,1950,1994,2038,2128,2172,2216,2260,2405,2449 | 0h | 00.10.02.SAP.01.03 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
44 |  | Auto Scheduled | 01:S4 | 0 days | 29 May 2022 13:00 | 29 May 2022 13:00 | 0 | 252,296,340,384,428,595,639,683,727,808,874,1025,1069,1294,1338,1382,1426,1493,1537,1604,1648,1692,1804,1917,1961,2005,2095,2139,2183,2227,2372,2416,2460 | 0h | 00.10.02.SAP.01.04 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
45 |  | Auto Scheduled | אבני דרך סאפ - שרשרת | 46.13 days | 12 April 2022 13:00 | 08 June 2022 13:00 | 0 |  | 0h | 00.10.02.SAP.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 5
46 |  | Auto Scheduled | 02:S1 | 0 days | 12 April 2022 13:00 | 12 April 2022 13:00 | 0 | 2497,2714,2758,2802,2915,3053,3097,3199,3345,3389,3433,3523,3567,3729 | 0h | 00.10.02.SAP.02.01 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
47 |  | Auto Scheduled | 02:S2 | 0 days | 23 May 2022 13:00 | 23 May 2022 13:00 | 0 | 2508,2725,2769,2813,2926,3064,3108,3210,3356,3400,3444,3534,3648,3740 | 0h | 00.10.02.SAP.02.02 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
48 |  | Auto Scheduled | 02:S3 | 0 days | 08 May 2022 13:00 | 08 May 2022 13:00 | 0 | 2519,2736,2780,2824,2937,3075,3119,3221,3367,3411,3501,3545,3659,3751 | 0h | 00.10.02.SAP.02.03 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
49 |  | Auto Scheduled | 02:S4 | 0 days | 08 June 2022 13:00 | 08 June 2022 13:00 | 0 | 2703,2747,2791,2904,3042,3086,3188,3334,3378,3422,3512,3556,3670 | 0h | 00.10.02.SAP.02.04 |  |  | header |  | nan |  | NA | As Soon As Possible | 6
50 |  | Auto Scheduled | 01: מלאי ואחסנה | 606.88 days | 18 June 2020 8:00 | 22 August 2022 13:00 | 0.33000000000000002 |  | 15,583h | 01 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
51 |  | Auto Scheduled | 01.01: קבלה מרכש | 466.25 days | 04 August 2020 8:00 | 14 April 2022 13:00 | 0.23000000000000001 |  | 2,640h | 01.01 | חתום | עינת | hd | עינת | nan | BP | NA | As Soon As Possible | 3
52 |  | Auto Scheduled | 01.01: קבלה מרכש.BP | 125.75 days | 04 August 2020 8:00 | 06 January 2021 15:00 | 1 |  | 400h | 01.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
53 |  | Auto Scheduled | 01.01: קבלה מרכש | 125.75 days | 04 August 2020 8:00 | 06 January 2021 15:00 | 1 |  | 400h | 01.01.BP.01 | חתום | עינת | parent | עינת | nan | BP | NA | As Soon As Possible | 5
54 |  | Auto Scheduled | Sub Tasks | 125.75 days | 04 August 2020 8:00 | 06 January 2021 15:00 | 1 |  | 360h | 01.01.BP.01.01 |  | עינת | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
55 |  | Auto Scheduled | עבור מחסנים מנוהלי WMS ,השינויים המרכזים בתהליך העבודה החזרה לספק לביטול מלאי טרם אחסנה פיזית: לא מבוצע תהליך קליטה למלאי מראש ניתן לבטל רק את האספקה הנכנסת. ובנוסף בפסילת בוחן לאחר קליטה למלאי בכושר1 לא מבטלים קליטה למלאי מבצעים נוהל החזרה לספק, כלומר | 0.13 days | 04 August 2020 8:00 | 04 August 2020 9:00 | 1 |  | 1h | 01.01.BP.01.01.01 | בוצע | אמל"ח | MoM | עינת | שרון רחמים | INT | NA | Must Start On | 7
56 |  | Auto Scheduled | מערכת SAP תנחה את מערכת WMS לצפי קבלות מלאי מרכש ע"י שידור אספקות נכנסות הכוללות את פריטי המשלוח: מדובר במכולה לא ניתן לדעת אילו פריטים מכילה, נדרשת גישה לקצין קישור נמלים למערכת שינוע נמלים (מערכת של משרד הביטחון). בנוסף נדרש לעדכן נוהל החזרה לספק חו"ל | 0.13 days | 13 August 2020 8:00 | 13 August 2020 9:00 | 1 |  | 1h | 01.01.BP.01.01.02 | בוצע | אמל"ח | MoM | עינת | שרון רחמים | INT | NA | As Soon As Possible | 7
57 |  | Auto Scheduled | כתיבת מסמך | 1.75 days | 13 August 2020 8:00 | 16 August 2020 13:00 | 1 | 56 | 14h | 01.01.BP.01.01.20 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
58 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.13 days | 01 September 2020 8:00 | 01 September 2020 17:00 | 1 | 57 | 9h | 01.01.BP.01.01.21 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
59 |  | Auto Scheduled | אישור מקל"ר | 3 days | 13 September 2020 8:00 | 15 September 2020 14:00 | 1 | 58 | 24h | 01.01.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
60 |  | Auto Scheduled | אישור מפקדת | 0.38 days | 14 October 2020 8:00 | 14 October 2020 11:00 | 1 | 59 | 3h | 01.01.BP.01.01.23 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
61 |  | Auto Scheduled | אישור אבי | 0.88 days | 18 October 2020 8:00 | 18 October 2020 15:00 | 1 | 60 | 7h | 01.01.BP.01.01.24 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
62 |  | Auto Scheduled | אישור המנהלת | 0.63 days | 26 October 2020 8:00 | 26 October 2020 13:00 | 1 | 61 | 5h | 01.01.BP.01.01.25 | בוצע | סיגל | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
63 |  | Auto Scheduled | אישור חטלו"ג | 2.38 days | 01 November 2020 8:00 | 03 November 2020 9:00 | 1 | 62 | 19h | 01.01.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
64 |  | Auto Scheduled | אישור ניר בשן | 34.63 days | 25 November 2020 8:00 | 06 January 2021 15:00 | 1 | 63 | 277h | 01.01.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
65 |  | Auto Scheduled | אישור שגיב שרביט | 0 days | 17 December 2020 17:00 | 17 December 2020 17:00 | 1 | 64 | 0h | 01.01.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
66 |  | Auto Scheduled | LifeCycle Tasks | 35 days | 18 November 2020 8:00 | 31 December 2020 9:00 | 1 |  | 40h | 01.01.BP.01.02 |  | עינת | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
67 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 17 December 2020 8:00 | 17 December 2020 17:00 | 1 | 65 | 0h | 01.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
68 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 01.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
69 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 68 | 10h | 01.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
70 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 69 | 5h | 01.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
71 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 70 | 10h | 01.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
72 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 71 | 10h | 01.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
73 |  | Auto Scheduled | בחתימה | 0 days | 17 December 2020 8:00 | 17 December 2020 8:00 | 1 | 72,67 | 0h | 01.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
74 |  | Auto Scheduled | חתום | 0 days | 17 December 2020 8:00 | 17 December 2020 8:00 | 1 | 73 | 0h | 01.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
75 |  | Auto Scheduled | 01.01: קבלה מרכש.INT | 357.13 days | 17 December 2020 8:00 | 14 April 2022 13:00 | 0.13 |  | 840h | 01.01.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
76 |  | Auto Scheduled | מערכות זכיין וסאפ יאפשרו העברות שדרים לעדכון דו צדדי של שינויים באספקות כגון כמויות. | 327.88 days | 17 December 2020 8:00 | 09 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.01.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
77 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
78 |  | Auto Scheduled | LifeCycle Tasks | 327.88 days | 17 December 2020 8:00 | 09 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.01.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
79 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
80 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
81 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 24.75 days | 31 January 2022 8:00 | 01 March 2022 17:00 | 0 |  | 0h | 01.01.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
82 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 March 2022 8:00 | 06 March 2022 15:00 | 0 | 81 | 25h | 01.01.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
83 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 March 2022 15:00 | 07 March 2022 16:00 | 0 | 82 | 10h | 01.01.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
84 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 March 2022 16:00 | 08 March 2022 17:00 | 0 | 83 | 10h | 01.01.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
85 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 March 2022 8:00 | 09 March 2022 13:00 | 0 | 84 | 5h | 01.01.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
86 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 09 March 2022 13:00 | 09 March 2022 13:00 | 0 | 85,79 | 0h | 01.01.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
87 |  | Auto Scheduled | מערכת סאפ תאפשר העברת שדרים למערכת זכיין ע"ב אספקה נכנסת ומשלוח. כולל קשר בין הזמנת מנה"ר להזמנה חדשהזי הייצ' 92 בעת הצורך | 312.13 days | 17 December 2020 8:00 | 17 February 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.01.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
88 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
89 |  | Auto Scheduled | LifeCycle Tasks | 312.13 days | 17 December 2020 8:00 | 17 February 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.01.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
90 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
91 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
92 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 32.63 days | 02 January 2022 8:00 | 09 February 2022 17:00 | 0 |  | 0h | 01.01.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
93 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 February 2022 8:00 | 14 February 2022 15:00 | 0 | 92 | 25h | 01.01.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
94 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 February 2022 15:00 | 15 February 2022 16:00 | 0 | 93 | 10h | 01.01.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
95 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 February 2022 16:00 | 16 February 2022 17:00 | 0 | 94 | 10h | 01.01.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
96 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 February 2022 8:00 | 17 February 2022 13:00 | 0 | 95 | 5h | 01.01.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
97 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 17 February 2022 13:00 | 17 February 2022 13:00 | 0 | 96,90 | 0h | 01.01.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
98 |  | Auto Scheduled | מערכת מרקט תשלח שדר למערכת סאפ עם נתוני הזמנת רכש. | 191.13 days | 17 December 2020 8:00 | 05 September 2021 8:00 | 0.11 |  | 70h | 01.01.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
99 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
100 |  | Auto Scheduled | LifeCycle Tasks | 191.13 days | 17 December 2020 8:00 | 05 September 2021 8:00 | 0.11 |  | 70h | 01.01.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
101 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
102 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
103 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 13.5 days | 25 July 2021 8:00 | 09 August 2021 17:00 | 0 |  | 0h | 01.01.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
104 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 August 2021 8:00 | 12 August 2021 15:00 | 0 | 103 | 25h | 01.01.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
105 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 August 2021 15:00 | 15 August 2021 16:00 | 0 | 104 | 10h | 01.01.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
106 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 August 2021 16:00 | 16 August 2021 17:00 | 0 | 105 | 10h | 01.01.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
107 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 August 2021 8:00 | 17 August 2021 13:00 | 0 | 106 | 5h | 01.01.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
108 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 107,101 | 0h | 01.01.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
109 |  | Auto Scheduled | מערכת סאפ תשלח שדר למערכת מרקט קבלת טובין שמקורה ב זכיין. | 311 days | 17 December 2020 8:00 | 16 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.01.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
110 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
111 |  | Auto Scheduled | LifeCycle Tasks | 311 days | 17 December 2020 8:00 | 16 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.01.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
112 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
113 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
114 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 20 January 2022 8:00 | 08 February 2022 17:00 | 0 |  | 0h | 01.01.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
115 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 February 2022 8:00 | 13 February 2022 15:00 | 0 | 114 | 25h | 01.01.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
116 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 February 2022 15:00 | 14 February 2022 16:00 | 0 | 115 | 10h | 01.01.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
117 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 February 2022 16:00 | 15 February 2022 17:00 | 0 | 116 | 10h | 01.01.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
118 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 February 2022 8:00 | 16 February 2022 13:00 | 0 | 117 | 5h | 01.01.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
119 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 16 February 2022 13:00 | 16 February 2022 13:00 | 0 | 118,112 | 0h | 01.01.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
120 |  | Auto Scheduled | מערכת מרקט תשלח שדר למערכת סאפ עם נתוני אספקה נכנסת תעודת משלוח דיגיטלית. | 305.38 days | 17 December 2020 8:00 | 09 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.01.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
121 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
122 |  | Auto Scheduled | LifeCycle Tasks | 305.38 days | 17 December 2020 8:00 | 09 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.01.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
123 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
124 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
125 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 13 January 2022 8:00 | 01 February 2022 17:00 | 0 |  | 0h | 01.01.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
126 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 February 2022 8:00 | 06 February 2022 15:00 | 0 | 125 | 25h | 01.01.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
127 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 February 2022 15:00 | 07 February 2022 16:00 | 0 | 126 | 10h | 01.01.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
128 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 February 2022 16:00 | 08 February 2022 17:00 | 0 | 127 | 10h | 01.01.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
129 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 February 2022 8:00 | 09 February 2022 13:00 | 0 | 128 | 5h | 01.01.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
130 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 09 February 2022 13:00 | 09 February 2022 13:00 | 0 | 129,123 | 0h | 01.01.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
131 |  | Auto Scheduled | מערכת זכיין תשלח שדר למערכת סאפ עם נתוני קבלות למלאי. | 293 days | 17 December 2020 8:00 | 25 January 2022 13:00 | 0.19 |  | 70h | 01.01.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
132 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
133 |  | Auto Scheduled | LifeCycle Tasks | 293 days | 17 December 2020 8:00 | 25 January 2022 13:00 | 0.19 |  | 70h | 01.01.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
134 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
135 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
136 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 13.5 days | 02 January 2022 8:00 | 17 January 2022 17:00 | 0.13 |  | 0h | 01.01.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
137 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 January 2022 8:00 | 20 January 2022 15:00 | 0 | 136 | 25h | 01.01.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
138 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 January 2022 15:00 | 23 January 2022 16:00 | 0 | 137 | 10h | 01.01.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
139 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 January 2022 16:00 | 24 January 2022 17:00 | 0 | 138 | 10h | 01.01.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
140 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 January 2022 8:00 | 25 January 2022 13:00 | 0 | 139 | 5h | 01.01.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
141 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 25 January 2022 13:00 | 25 January 2022 13:00 | 0 | 140,134 | 0h | 01.01.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
142 |  | Auto Scheduled | מערכת זכיין תשדר סגירת אספקת החזרה. | 357.13 days | 17 December 2020 8:00 | 14 April 2022 13:00 | 0.12 |  | 70h | 01.01.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
143 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
144 |  | Auto Scheduled | LifeCycle Tasks | 357.13 days | 17 December 2020 8:00 | 14 April 2022 13:00 | 0.12 |  | 70h | 01.01.INT.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
145 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.07.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
146 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.07.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
147 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 23 March 2022 8:00 | 06 April 2022 17:00 | 0 |  | 0h | 01.01.INT.07.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
148 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 April 2022 8:00 | 11 April 2022 15:00 | 0 | 147 | 25h | 01.01.INT.07.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
149 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 April 2022 15:00 | 12 April 2022 16:00 | 0 | 148 | 10h | 01.01.INT.07.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
150 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 April 2022 16:00 | 13 April 2022 17:00 | 0 | 149 | 10h | 01.01.INT.07.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
151 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 April 2022 8:00 | 14 April 2022 13:00 | 0 | 150 | 5h | 01.01.INT.07.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
152 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 14 April 2022 13:00 | 14 April 2022 13:00 | 0 | 151,145 | 0h | 01.01.INT.07.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
153 |  | Auto Scheduled | בעת הקבלה למלאי מסימול חוץ ובאם לא נמצא מלאי בסימול החוץ נדרש לבטל את הקבלה בסאפ ולהעביר את הפרטים לסטאטוס לבירור בזכיין | 291.88 days | 17 December 2020 8:00 | 24 January 2022 13:00 | 0.38 |  | 70h | 01.01.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
154 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
155 |  | Auto Scheduled | LifeCycle Tasks | 291.88 days | 17 December 2020 8:00 | 24 January 2022 13:00 | 0.38 |  | 70h | 01.01.INT.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
156 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.08.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
157 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.08.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
158 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 02 January 2022 8:00 | 16 January 2022 17:00 | 0.45000000000000001 |  | 0h | 01.01.INT.08.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
159 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 January 2022 8:00 | 19 January 2022 15:00 | 0 | 158 | 25h | 01.01.INT.08.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
160 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 January 2022 15:00 | 20 January 2022 16:00 | 0 | 159 | 10h | 01.01.INT.08.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
161 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 January 2022 16:00 | 23 January 2022 17:00 | 0 | 160 | 10h | 01.01.INT.08.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
162 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 January 2022 8:00 | 24 January 2022 13:00 | 0 | 161 | 5h | 01.01.INT.08.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
163 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 January 2022 13:00 | 24 January 2022 13:00 | 0 | 162,156 | 0h | 01.01.INT.08.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
164 |  | Auto Scheduled | מערכת סאפ תשדר אספקת החזרה לספק | 345.88 days | 17 December 2020 8:00 | 31 March 2022 13:00 | 0.11 |  | 70h | 01.01.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
165 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
166 |  | Auto Scheduled | LifeCycle Tasks | 345.88 days | 17 December 2020 8:00 | 31 March 2022 13:00 | 0.11 |  | 70h | 01.01.INT.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
167 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.09.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
168 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.09.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
169 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 13.5 days | 08 March 2022 8:00 | 23 March 2022 17:00 | 0 |  | 0h | 01.01.INT.09.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
170 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 March 2022 8:00 | 28 March 2022 15:00 | 0 | 169 | 25h | 01.01.INT.09.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
171 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 March 2022 15:00 | 29 March 2022 16:00 | 0 | 170 | 10h | 01.01.INT.09.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
172 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 March 2022 16:00 | 30 March 2022 17:00 | 0 | 171 | 10h | 01.01.INT.09.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
173 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 March 2022 8:00 | 31 March 2022 13:00 | 0 | 172 | 5h | 01.01.INT.09.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
174 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 31 March 2022 13:00 | 31 March 2022 13:00 | 0 | 173,167 | 0h | 01.01.INT.09.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
175 |  | Auto Scheduled | מערכת סאפ תסגור אספקות אל מול הכמות שהגיעה בפועל ויתרת המלאי תחזור להזמנה באופן אוטומטי | 342.5 days | 17 December 2020 8:00 | 28 March 2022 13:00 | 0.10000000000000001 |  | 70h | 01.01.INT.10 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
176 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
177 |  | Auto Scheduled | LifeCycle Tasks | 342.5 days | 17 December 2020 8:00 | 28 March 2022 13:00 | 0.10000000000000001 |  | 70h | 01.01.INT.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
178 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.10.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
179 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.10.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
180 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 01 March 2022 8:00 | 20 March 2022 17:00 | 0 |  | 0h | 01.01.INT.10.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
181 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 March 2022 8:00 | 23 March 2022 15:00 | 0 | 180 | 25h | 01.01.INT.10.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
182 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 March 2022 15:00 | 24 March 2022 16:00 | 0 | 181 | 10h | 01.01.INT.10.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
183 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 March 2022 16:00 | 27 March 2022 17:00 | 0 | 182 | 10h | 01.01.INT.10.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
184 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 March 2022 8:00 | 28 March 2022 13:00 | 0 | 183 | 5h | 01.01.INT.10.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
185 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 28 March 2022 13:00 | 28 March 2022 13:00 | 0 | 184,178 | 0h | 01.01.INT.10.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
186 |  | Auto Scheduled | מערכות זכיין וסאפ יאפשרו העברת שדרים לעדכון קבלה בפועל ע"ב תנועות מלאי לאתרי האחסון הרלוונטים בסאפ גם עבור אספקות חלקיות | 333.5 days | 17 December 2020 8:00 | 16 March 2022 13:00 | 0.14999999999999999 |  | 70h | 01.01.INT.11 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
187 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
188 |  | Auto Scheduled | LifeCycle Tasks | 333.5 days | 17 December 2020 8:00 | 16 March 2022 13:00 | 0.14999999999999999 |  | 70h | 01.01.INT.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
189 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.11.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
190 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.11.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
191 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 11.25 days | 23 February 2022 8:00 | 08 March 2022 17:00 | 5.0000000000000003E-2 |  | 0h | 01.01.INT.11.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
192 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 March 2022 8:00 | 13 March 2022 15:00 | 0 | 191 | 25h | 01.01.INT.11.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
193 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 March 2022 15:00 | 14 March 2022 16:00 | 0 | 192 | 10h | 01.01.INT.11.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
194 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 March 2022 16:00 | 15 March 2022 17:00 | 0 | 193 | 10h | 01.01.INT.11.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
195 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 March 2022 8:00 | 16 March 2022 13:00 | 0 | 194 | 5h | 01.01.INT.11.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
196 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 16 March 2022 13:00 | 16 March 2022 13:00 | 0 | 195,189 | 0h | 01.01.INT.11.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
197 |  | Auto Scheduled | מערכת זכיין תשדר סגירת אספקת החזרה. | 351.5 days | 17 December 2020 8:00 | 07 April 2022 13:00 | 0.11 |  | 70h | 01.01.INT.12 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
198 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
199 |  | Auto Scheduled | LifeCycle Tasks | 351.5 days | 17 December 2020 8:00 | 07 April 2022 13:00 | 0.11 |  | 70h | 01.01.INT.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
200 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.INT.12.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
201 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.INT.12.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
202 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 13.5 days | 15 March 2022 8:00 | 30 March 2022 17:00 | 0 |  | 0h | 01.01.INT.12.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
203 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 31 March 2022 8:00 | 04 April 2022 15:00 | 0 | 202 | 25h | 01.01.INT.12.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
204 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 04 April 2022 15:00 | 05 April 2022 16:00 | 0 | 203 | 10h | 01.01.INT.12.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
205 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 05 April 2022 16:00 | 06 April 2022 17:00 | 0 | 204 | 10h | 01.01.INT.12.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
206 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 April 2022 8:00 | 07 April 2022 13:00 | 0 | 205 | 5h | 01.01.INT.12.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
207 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 07 April 2022 13:00 | 07 April 2022 13:00 | 0 | 206,200 | 0h | 01.01.INT.12.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
208 |  | Auto Scheduled | 01.01: קבלה מרכש.SAP | 271.63 days | 17 December 2020 8:00 | 29 December 2021 13:00 | 0.20999999999999999 |  | 1,400h | 01.01.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
209 |  | Auto Scheduled | נדרש כי יוקם מק"ט גנרי כגון מכולה | 267.13 days | 17 December 2020 8:00 | 23 December 2021 13:00 | 5.9999999999999998E-2 |  | 70h | 01.01.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
210 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
211 |  | Auto Scheduled | LifeCycle Tasks | 267.13 days | 17 December 2020 8:00 | 23 December 2021 13:00 | 5.9999999999999998E-2 |  | 70h | 01.01.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
212 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
213 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
214 |  | Auto Scheduled | יישום ופיתוח סאפ | 34.88 days | 03 November 2021 8:00 | 15 December 2021 17:00 | 0 |  | 0h | 01.01.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
215 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 December 2021 8:00 | 20 December 2021 15:00 | 0 | 214 | 25h | 01.01.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
216 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 December 2021 15:00 | 21 December 2021 16:00 | 0 | 215 | 10h | 01.01.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
217 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 December 2021 16:00 | 22 December 2021 17:00 | 0 | 216 | 10h | 01.01.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
218 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 December 2021 8:00 | 23 December 2021 13:00 | 0 | 217 | 5h | 01.01.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
219 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 23 December 2021 13:00 | 23 December 2021 13:00 | 0 | 218,212 | 0h | 01.01.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
220 |  | Auto Scheduled | נדרשת אינדיקציה באספקה נכנסת האם נדרש קליטה למלאי | 237.88 days | 17 December 2020 8:00 | 17 November 2021 13:00 | 0.13 |  | 70h | 01.01.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
221 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
222 |  | Auto Scheduled | LifeCycle Tasks | 237.88 days | 17 December 2020 8:00 | 17 November 2021 13:00 | 0.13 |  | 70h | 01.01.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
223 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
224 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
225 |  | Auto Scheduled | יישום ופיתוח סאפ | 10.13 days | 28 October 2021 8:00 | 09 November 2021 17:00 | 0 |  | 0h | 01.01.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
226 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 November 2021 8:00 | 14 November 2021 15:00 | 0 | 225 | 25h | 01.01.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
227 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 November 2021 15:00 | 15 November 2021 16:00 | 0 | 226 | 10h | 01.01.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
228 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 November 2021 16:00 | 16 November 2021 17:00 | 0 | 227 | 10h | 01.01.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
229 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 November 2021 8:00 | 17 November 2021 13:00 | 0 | 228 | 5h | 01.01.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
230 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 November 2021 13:00 | 17 November 2021 13:00 | 0 | 229,223 | 0h | 01.01.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
231 |  | Auto Scheduled | נדרשת אינדיקציה באספקה נכנסת האם המטען הגיע ונמצא במחסני הזכיין לא נכנס למלאי | 233.38 days | 17 December 2020 8:00 | 11 November 2021 13:00 | 0.13 |  | 70h | 01.01.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
232 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
233 |  | Auto Scheduled | LifeCycle Tasks | 233.38 days | 17 December 2020 8:00 | 11 November 2021 13:00 | 0.13 |  | 70h | 01.01.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
234 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
235 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
236 |  | Auto Scheduled | יישום ופיתוח סאפ | 10.13 days | 24 October 2021 8:00 | 03 November 2021 17:00 | 0 |  | 0h | 01.01.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
237 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 November 2021 8:00 | 08 November 2021 15:00 | 0 | 236 | 25h | 01.01.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
238 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 November 2021 15:00 | 09 November 2021 16:00 | 0 | 237 | 10h | 01.01.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
239 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 November 2021 16:00 | 10 November 2021 17:00 | 0 | 238 | 10h | 01.01.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
240 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 November 2021 8:00 | 11 November 2021 13:00 | 0 | 239 | 5h | 01.01.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
241 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 11 November 2021 13:00 | 11 November 2021 13:00 | 0 | 240,234 | 0h | 01.01.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
242 |  | Auto Scheduled | נדרש עבור כלל המשקים | 204.13 days | 17 December 2020 8:00 | 06 October 2021 13:00 | 0.12 |  | 70h | 01.01.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
243 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
244 |  | Auto Scheduled | LifeCycle Tasks | 204.13 days | 17 December 2020 8:00 | 06 October 2021 13:00 | 0.12 |  | 70h | 01.01.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
245 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
246 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
247 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 29 August 2021 8:00 | 19 September 2021 17:00 | 0 |  | 0h | 01.01.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
248 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 September 2021 8:00 | 03 October 2021 15:00 | 0 | 247 | 25h | 01.01.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
249 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 October 2021 15:00 | 04 October 2021 16:00 | 0 | 248 | 10h | 01.01.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
250 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 October 2021 16:00 | 05 October 2021 17:00 | 0 | 249 | 10h | 01.01.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
251 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 October 2021 8:00 | 06 October 2021 13:00 | 0 | 250 | 5h | 01.01.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
252 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 October 2021 13:00 | 06 October 2021 13:00 | 0 | 251,245 | 0h | 01.01.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
253 |  | Auto Scheduled | בסוג אספקה של סימולי חוץ,מש"א נדרש להגדיר בסיבה לתועה את סימול החוץ במערכת סאפ | 198.5 days | 17 December 2020 8:00 | 29 September 2021 13:00 | 0.32000000000000001 |  | 70h | 01.01.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
254 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
255 |  | Auto Scheduled | LifeCycle Tasks | 198.5 days | 17 December 2020 8:00 | 29 September 2021 13:00 | 0.32000000000000001 |  | 70h | 01.01.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
256 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
257 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
258 |  | Auto Scheduled | יישום ופיתוח סאפ | 27 days | 03 August 2021 8:00 | 05 September 2021 17:00 | 0.33000000000000002 |  | 0h | 01.01.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
259 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 September 2021 8:00 | 13 September 2021 15:00 | 0 | 258 | 25h | 01.01.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
260 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 September 2021 15:00 | 14 September 2021 16:00 | 0 | 259 | 10h | 01.01.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
261 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 September 2021 16:00 | 19 September 2021 17:00 | 0 | 260 | 10h | 01.01.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
262 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 September 2021 8:00 | 29 September 2021 13:00 | 0 | 261 | 5h | 01.01.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
263 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 September 2021 13:00 | 29 September 2021 13:00 | 0 | 262,256 | 0h | 01.01.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
264 |  | Auto Scheduled | נדרש לקבל אינדיקציה כי לא קיים מלאי בסימול חוץ,מש"א בתהליך האספקות במערכת סאפ | 198.5 days | 17 December 2020 8:00 | 29 September 2021 13:00 | 0.55000000000000004 |  | 70h | 01.01.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
265 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
266 |  | Auto Scheduled | LifeCycle Tasks | 198.5 days | 17 December 2020 8:00 | 29 September 2021 13:00 | 0.55000000000000004 |  | 70h | 01.01.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
267 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
268 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
269 |  | Auto Scheduled | יישום ופיתוח סאפ | 29.25 days | 01 August 2021 8:00 | 05 September 2021 17:00 | 0.63 |  | 0h | 01.01.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
270 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 September 2021 8:00 | 13 September 2021 15:00 | 0 | 269 | 25h | 01.01.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
271 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 September 2021 15:00 | 14 September 2021 16:00 | 0 | 270 | 10h | 01.01.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
272 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 September 2021 16:00 | 19 September 2021 17:00 | 0 | 271 | 10h | 01.01.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
273 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 September 2021 8:00 | 29 September 2021 13:00 | 0 | 272 | 5h | 01.01.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
274 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 September 2021 13:00 | 29 September 2021 13:00 | 0 | 273,267 | 0h | 01.01.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
275 |  | Auto Scheduled | מערכת סאפ תאפשר ניהול מעקב וטיפול אחר הקבלות, ההפרשים בדו"ח זי אמ די די | 215.38 days | 17 December 2020 8:00 | 20 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.01.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
276 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
277 |  | Auto Scheduled | LifeCycle Tasks | 215.38 days | 17 December 2020 8:00 | 20 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.01.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
278 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
279 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
280 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 10 October 2021 8:00 | 12 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
281 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 280 | 25h | 01.01.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
282 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 281 | 10h | 01.01.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
283 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 282 | 10h | 01.01.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
284 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 283 | 5h | 01.01.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
285 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 284,278 | 0h | 01.01.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
286 |  | Auto Scheduled | עבור מחסנים מיוחדים מנוהלים סאפ התהליך ימשיך לעבוד כפי שקיים היום. | 215.38 days | 17 December 2020 8:00 | 20 October 2021 13:00 | 0.12 |  | 70h | 01.01.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
287 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
288 |  | Auto Scheduled | LifeCycle Tasks | 215.38 days | 17 December 2020 8:00 | 20 October 2021 13:00 | 0.12 |  | 70h | 01.01.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
289 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
290 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
291 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 19 September 2021 8:00 | 12 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
292 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 291 | 25h | 01.01.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
293 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 292 | 10h | 01.01.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
294 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 293 | 10h | 01.01.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
295 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 294 | 5h | 01.01.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
296 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 295,289 | 0h | 01.01.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
297 |  | Auto Scheduled | מערכת סאפ תאפשר זיכוי מלאי בהזמנת רכש בסאפ בהנחה שהאספקה הנכנסת תבוטל באופן ידני ע"י המשתמש. לוודא כי תהליך סאפ STANDARD תומך. | 204.13 days | 17 December 2020 8:00 | 06 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.01.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
298 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
299 |  | Auto Scheduled | LifeCycle Tasks | 204.13 days | 17 December 2020 8:00 | 06 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.01.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
300 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
301 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
302 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 14 September 2021 8:00 | 19 September 2021 17:00 | 0 |  | 0h | 01.01.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
303 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 September 2021 8:00 | 03 October 2021 15:00 | 0 | 302 | 25h | 01.01.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
304 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 October 2021 15:00 | 04 October 2021 16:00 | 0 | 303 | 10h | 01.01.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
305 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 October 2021 16:00 | 05 October 2021 17:00 | 0 | 304 | 10h | 01.01.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
306 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 October 2021 8:00 | 06 October 2021 13:00 | 0 | 305 | 5h | 01.01.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
307 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 October 2021 13:00 | 06 October 2021 13:00 | 0 | 306,300 | 0h | 01.01.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
308 |  | Auto Scheduled | נשתמש ב משלוח אאוטבאונט מסוג אר אל אל עם תנועה 122. ניתן ליצור עם טרנזקציה מיגו או אמ בי אר אל. לטובת תנועה 161 ניתן להשתמש בסוג אספקה אר אל בשלב זה אין צורך. | 209.75 days | 17 December 2020 8:00 | 13 October 2021 13:00 | 0.11 |  | 70h | 01.01.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
309 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
310 |  | Auto Scheduled | LifeCycle Tasks | 209.75 days | 17 December 2020 8:00 | 13 October 2021 13:00 | 0.11 |  | 70h | 01.01.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
311 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
312 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
313 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 02 September 2021 8:00 | 05 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
314 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 October 2021 8:00 | 10 October 2021 15:00 | 0 | 313 | 25h | 01.01.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
315 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 October 2021 15:00 | 11 October 2021 16:00 | 0 | 314 | 10h | 01.01.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
316 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 October 2021 16:00 | 12 October 2021 17:00 | 0 | 315 | 10h | 01.01.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
317 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 October 2021 8:00 | 13 October 2021 13:00 | 0 | 316 | 5h | 01.01.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
318 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 13 October 2021 13:00 | 13 October 2021 13:00 | 0 | 317,311 | 0h | 01.01.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
319 |  | Auto Scheduled | מערכת סאפ תאפשר המשך ביצוע תהליך ההחזרות בשני הסוגים עבור מחסנים מיוחדים בתפעול סאפ. | 207.5 days | 17 December 2020 8:00 | 11 October 2021 13:00 | 0.10000000000000001 |  | 70h | 01.01.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
320 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
321 |  | Auto Scheduled | LifeCycle Tasks | 207.5 days | 17 December 2020 8:00 | 11 October 2021 13:00 | 0.10000000000000001 |  | 70h | 01.01.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
322 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
323 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
324 |  | Auto Scheduled | יישום ופיתוח סאפ | 15.75 days | 29 August 2021 8:00 | 03 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
325 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 October 2021 8:00 | 06 October 2021 15:00 | 0 | 324 | 25h | 01.01.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
326 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 October 2021 15:00 | 07 October 2021 16:00 | 0 | 325 | 10h | 01.01.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
327 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 October 2021 16:00 | 10 October 2021 17:00 | 0 | 326 | 10h | 01.01.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
328 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 October 2021 8:00 | 11 October 2021 13:00 | 0 | 327 | 5h | 01.01.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
329 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 11 October 2021 13:00 | 11 October 2021 13:00 | 0 | 328,322 | 0h | 01.01.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
330 |  | Auto Scheduled | הסבות הזמנות רכש-יש לשלוח למערכת הזכיין את הזמנת המקור והקשר בין הזמנת המקור מנה"ר להזמנה החדשה זי אמ01 +זי הייצ' 92 | 226.63 days | 17 December 2020 8:00 | 03 November 2021 13:00 | 0.11 |  | 70h | 01.01.SAP.12 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
331 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
332 |  | Auto Scheduled | LifeCycle Tasks | 226.63 days | 17 December 2020 8:00 | 03 November 2021 13:00 | 0.11 |  | 70h | 01.01.SAP.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
333 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.12.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
334 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.12.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
335 |  | Auto Scheduled | יישום ופיתוח סאפ | 14.63 days | 10 October 2021 8:00 | 26 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.12.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
336 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 27 October 2021 8:00 | 31 October 2021 15:00 | 0 | 335 | 25h | 01.01.SAP.12.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
337 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 31 October 2021 15:00 | 01 November 2021 16:00 | 0 | 336 | 10h | 01.01.SAP.12.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
338 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 November 2021 16:00 | 02 November 2021 17:00 | 0 | 337 | 10h | 01.01.SAP.12.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
339 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 November 2021 8:00 | 03 November 2021 13:00 | 0 | 338 | 5h | 01.01.SAP.12.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
340 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 November 2021 13:00 | 03 November 2021 13:00 | 0 | 339,333 | 0h | 01.01.SAP.12.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
341 |  | Auto Scheduled | מערכת סאפ תשמור את הקשר בין הזמנת המקורמנה"ר לבין ההזמנה החדשה | 219.88 days | 17 December 2020 8:00 | 26 October 2021 13:00 | 0.11 |  | 70h | 01.01.SAP.13 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
342 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.13.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
343 |  | Auto Scheduled | LifeCycle Tasks | 219.88 days | 17 December 2020 8:00 | 26 October 2021 13:00 | 0.11 |  | 70h | 01.01.SAP.13.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
344 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.13.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
345 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.13.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
346 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 03 October 2021 8:00 | 18 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.13.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
347 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 October 2021 8:00 | 21 October 2021 15:00 | 0 | 346 | 25h | 01.01.SAP.13.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
348 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 October 2021 15:00 | 24 October 2021 16:00 | 0 | 347 | 10h | 01.01.SAP.13.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
349 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 October 2021 16:00 | 25 October 2021 17:00 | 0 | 348 | 10h | 01.01.SAP.13.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
350 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 26 October 2021 8:00 | 26 October 2021 13:00 | 0 | 349 | 5h | 01.01.SAP.13.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
351 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 26 October 2021 13:00 | 26 October 2021 13:00 | 0 | 350,344 | 0h | 01.01.SAP.13.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
352 |  | Auto Scheduled | מערכת סאפ לא תשדר למערכת הזכיין סוגי הזמנות ש"י | 215.38 days | 17 December 2020 8:00 | 20 October 2021 13:00 | 0.13 |  | 70h | 01.01.SAP.14 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
353 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.14.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
354 |  | Auto Scheduled | LifeCycle Tasks | 215.38 days | 17 December 2020 8:00 | 20 October 2021 13:00 | 0.13 |  | 70h | 01.01.SAP.14.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
355 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.14.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
356 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.14.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
357 |  | Auto Scheduled | יישום ופיתוח סאפ | 11.25 days | 29 September 2021 8:00 | 12 October 2021 17:00 | 0 |  | 0h | 01.01.SAP.14.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
358 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 357 | 25h | 01.01.SAP.14.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
359 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 358 | 10h | 01.01.SAP.14.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
360 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 359 | 10h | 01.01.SAP.14.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
361 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 360 | 5h | 01.01.SAP.14.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
362 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 361,355 | 0h | 01.01.SAP.14.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
363 |  | Auto Scheduled | מערכת סאפ תאפשר המשך ביצוע תהליכי קבלה מרכש עבור מחסנים מיוחדים בתפעול סאפ. | 208.63 days | 17 December 2020 8:00 | 12 October 2021 13:00 | 0.31 |  | 70h | 01.01.SAP.15 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
364 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.15.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
365 |  | Auto Scheduled | LifeCycle Tasks | 208.63 days | 17 December 2020 8:00 | 12 October 2021 13:00 | 0.31 |  | 70h | 01.01.SAP.15.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
366 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.15.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
367 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.15.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
368 |  | Auto Scheduled | יישום ופיתוח סאפ | 36 days | 04 August 2021 8:00 | 04 October 2021 17:00 | 0.32000000000000001 |  | 0h | 01.01.SAP.15.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
369 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 October 2021 8:00 | 07 October 2021 15:00 | 0 | 368 | 25h | 01.01.SAP.15.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
370 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 October 2021 15:00 | 10 October 2021 16:00 | 0 | 369 | 10h | 01.01.SAP.15.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
371 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 October 2021 16:00 | 11 October 2021 17:00 | 0 | 370 | 10h | 01.01.SAP.15.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
372 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 October 2021 8:00 | 12 October 2021 13:00 | 0 | 371 | 5h | 01.01.SAP.15.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
373 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 12 October 2021 13:00 | 12 October 2021 13:00 | 0 | 372,366 | 0h | 01.01.SAP.15.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
374 |  | Auto Scheduled | נדרשת אינדיקציה באספקה נכנסת האם נדרש קבלה מרכש למלאי למחסן מנוהל צבאי, מנהול זכיין | 191.13 days | 17 December 2020 8:00 | 05 September 2021 8:00 | 0.53000000000000003 |  | 70h | 01.01.SAP.16 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
375 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.16.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
376 |  | Auto Scheduled | LifeCycle Tasks | 191.13 days | 17 December 2020 8:00 | 05 September 2021 8:00 | 0.53000000000000003 |  | 70h | 01.01.SAP.16.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
377 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.16.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
378 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.16.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
379 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 17 August 2021 8:00 | 22 August 2021 17:00 | 1 |  | 0h | 01.01.SAP.16.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
380 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 August 2021 8:00 | 25 August 2021 15:00 | 0 | 379 | 25h | 01.01.SAP.16.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
381 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 August 2021 15:00 | 26 August 2021 16:00 | 0 | 380 | 10h | 01.01.SAP.16.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
382 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 August 2021 16:00 | 29 August 2021 17:00 | 0 | 381 | 10h | 01.01.SAP.16.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
383 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 August 2021 8:00 | 30 August 2021 13:00 | 0 | 382 | 5h | 01.01.SAP.16.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
384 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 383,377 | 0h | 01.01.SAP.16.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
385 |  | Auto Scheduled | מערכת סאפ תיצור ישויות של אספקה נכנסת ומשלוח אל מול אתר אחסון רלוונטי לכושר | 201.88 days | 17 December 2020 8:00 | 04 October 2021 13:00 | 0.19 |  | 70h | 01.01.SAP.17 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
386 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.17.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
387 |  | Auto Scheduled | LifeCycle Tasks | 201.88 days | 17 December 2020 8:00 | 04 October 2021 13:00 | 0.19 |  | 70h | 01.01.SAP.17.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
388 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.17.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
389 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.17.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
390 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 05 September 2021 8:00 | 13 September 2021 17:00 | 0 |  | 0h | 01.01.SAP.17.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
391 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 September 2021 8:00 | 29 September 2021 15:00 | 0 | 390 | 25h | 01.01.SAP.17.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
392 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 September 2021 15:00 | 30 September 2021 16:00 | 0 | 391 | 10h | 01.01.SAP.17.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
393 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 September 2021 16:00 | 03 October 2021 17:00 | 0 | 392 | 10h | 01.01.SAP.17.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
394 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 04 October 2021 8:00 | 04 October 2021 13:00 | 0 | 393 | 5h | 01.01.SAP.17.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
395 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 04 October 2021 13:00 | 04 October 2021 13:00 | 0 | 394,388 | 0h | 01.01.SAP.17.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
396 |  | Auto Scheduled | יאוחסן בכושר 1 במערכת ה סאפ | 271.63 days | 17 December 2020 8:00 | 29 December 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 01.01.SAP.18 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
397 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.18.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
398 |  | Auto Scheduled | LifeCycle Tasks | 271.63 days | 17 December 2020 8:00 | 29 December 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 01.01.SAP.18.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
399 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.18.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
400 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.18.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
401 |  | Auto Scheduled | יישום ופיתוח סאפ | 24.75 days | 22 November 2021 8:00 | 21 December 2021 17:00 | 0 |  | 0h | 01.01.SAP.18.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
402 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 December 2021 8:00 | 26 December 2021 15:00 | 0 | 401 | 25h | 01.01.SAP.18.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
403 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 December 2021 15:00 | 27 December 2021 16:00 | 0 | 402 | 10h | 01.01.SAP.18.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
404 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 December 2021 16:00 | 28 December 2021 17:00 | 0 | 403 | 10h | 01.01.SAP.18.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
405 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 December 2021 8:00 | 29 December 2021 13:00 | 0 | 404 | 5h | 01.01.SAP.18.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
406 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 December 2021 13:00 | 29 December 2021 13:00 | 0 | 405,399 | 0h | 01.01.SAP.18.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
407 |  | Auto Scheduled | מערכת סאפ תאפשר בדיקת חוקות המלאי בשלב אספקה נכנסת במקום החוקות הקיימות בשלב הקבלה למלאי לדוגמא איזה מלאי נכנס לכל סוג כושר בקבלה מרכש. | 209.75 days | 17 December 2020 8:00 | 13 October 2021 13:00 | 0.23999999999999999 |  | 70h | 01.01.SAP.19 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
408 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.19.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
409 |  | Auto Scheduled | LifeCycle Tasks | 209.75 days | 17 December 2020 8:00 | 13 October 2021 13:00 | 0.23999999999999999 |  | 70h | 01.01.SAP.19.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
410 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.19.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
411 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.19.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
412 |  | Auto Scheduled | יישום ופיתוח סאפ | 27 days | 17 August 2021 8:00 | 05 October 2021 17:00 | 0.23000000000000001 |  | 0h | 01.01.SAP.19.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
413 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 October 2021 8:00 | 10 October 2021 15:00 | 0 | 412 | 25h | 01.01.SAP.19.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
414 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 October 2021 15:00 | 11 October 2021 16:00 | 0 | 413 | 10h | 01.01.SAP.19.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
415 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 October 2021 16:00 | 12 October 2021 17:00 | 0 | 414 | 10h | 01.01.SAP.19.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
416 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 October 2021 8:00 | 13 October 2021 13:00 | 0 | 415 | 5h | 01.01.SAP.19.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
417 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 13 October 2021 13:00 | 13 October 2021 13:00 | 0 | 416,410 | 0h | 01.01.SAP.19.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
418 |  | Auto Scheduled | מערכת סאפ תאפשר זיכוי מלאי בהזמנת רכש בסאפ בהנחה שהאספקה הנכנסת תבוטל באופן ידני ע"י המשתמש. | 206.38 days | 17 December 2020 8:00 | 10 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.01.SAP.20 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
419 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.20.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
420 |  | Auto Scheduled | LifeCycle Tasks | 206.38 days | 17 December 2020 8:00 | 10 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.01.SAP.20.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
421 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.01.SAP.20.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
422 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 17 December 2020 8:00 | 21 December 2020 10:00 | 1 | 65 | 20h | 01.01.SAP.20.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
423 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 29 September 2021 8:00 | 30 September 2021 17:00 | 0 |  | 0h | 01.01.SAP.20.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
424 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 October 2021 8:00 | 05 October 2021 15:00 | 0 | 423 | 25h | 01.01.SAP.20.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
425 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 October 2021 15:00 | 06 October 2021 16:00 | 0 | 424 | 10h | 01.01.SAP.20.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
426 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 October 2021 16:00 | 07 October 2021 17:00 | 0 | 425 | 10h | 01.01.SAP.20.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
427 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 October 2021 8:00 | 10 October 2021 13:00 | 0 | 426 | 5h | 01.01.SAP.20.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
428 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 October 2021 13:00 | 10 October 2021 13:00 | 0 | 427,421 | 0h | 01.01.SAP.20.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
429 |  | Auto Scheduled | 01.02: ערכות | 606.88 days | 18 June 2020 8:00 | 22 August 2022 13:00 | 0.16 |  | 2,099h | 01.02 | חתום | מאור | hd | מאור | nan | BP | NA | As Soon As Possible | 3
430 |  | Auto Scheduled | 01.02: ערכות.BP | 181.13 days | 18 June 2020 8:00 | 28 January 2021 17:00 | 1 |  | 209h | 01.02.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
431 |  | Auto Scheduled | 01.02: ערכות | 181.13 days | 18 June 2020 8:00 | 28 January 2021 17:00 | 1 |  | 209h | 01.02.BP.01 | חתום | מאור | parent | מאור | nan | BP | NA | As Soon As Possible | 5
432 |  | Auto Scheduled | Sub Tasks | 179.13 days | 18 June 2020 8:00 | 27 January 2021 10:00 | 1 |  | 169h | 01.02.BP.01.01 |  | מאור | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
433 |  | Auto Scheduled | כתיבת מסמך | 9.5 days | 18 June 2020 8:00 | 30 June 2020 12:00 | 1 |  | 76h | 01.02.BP.01.01.20 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | Must Start On | 7
434 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 4 days | 01 October 2020 8:00 | 06 October 2020 13:00 | 1 | 433 | 32h | 01.02.BP.01.01.21 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
435 |  | Auto Scheduled | אישור אבי | 6.38 days | 15 November 2020 8:00 | 22 November 2020 14:00 | 1 | 434 | 51h | 01.02.BP.01.01.22 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
436 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 24 January 2021 8:00 | 24 January 2021 10:00 | 1 | 435 | 2h | 01.02.BP.01.01.23 | בוצע | סיגל | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
437 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 25 January 2021 8:00 | 25 January 2021 10:00 | 1 | 436 | 2h | 01.02.BP.01.01.24 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
438 |  | Auto Scheduled | אישור מקל"ר | 0.25 days | 26 January 2021 8:00 | 26 January 2021 10:00 | 1 | 437 | 2h | 01.02.BP.01.01.25 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
439 |  | Auto Scheduled | אישור ניר בשן | 0.13 days | 27 January 2021 8:00 | 27 January 2021 9:00 | 1 | 438 | 1h | 01.02.BP.01.01.26 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
440 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 27 January 2021 8:00 | 27 January 2021 9:00 | 1 | 439 | 1h | 01.02.BP.01.01.27 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
441 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 27 January 2021 8:00 | 27 January 2021 10:00 | 1 | 440 | 2h | 01.02.BP.01.01.28 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
442 |  | Auto Scheduled | LifeCycle Tasks | 96.75 days | 01 October 2020 8:00 | 28 January 2021 17:00 | 1 |  | 40h | 01.02.BP.01.02 |  | מאור | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
443 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 28 January 2021 8:00 | 28 January 2021 17:00 | 1 | 441 | 0h | 01.02.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
444 |  | Auto Scheduled | טרם החל | 0.63 days | 01 October 2020 8:00 | 01 October 2020 13:00 | 1 |  | 5h | 01.02.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
445 |  | Auto Scheduled | בעבודה | 1.25 days | 08 October 2020 8:00 | 11 October 2020 9:00 | 1 | 444 | 10h | 01.02.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
446 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 22 October 2020 8:00 | 22 October 2020 13:00 | 1 | 445 | 5h | 01.02.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
447 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 29 October 2020 8:00 | 01 November 2020 9:00 | 1 | 446 | 10h | 01.02.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
448 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 12 November 2020 8:00 | 15 November 2020 9:00 | 1 | 447 | 10h | 01.02.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
449 |  | Auto Scheduled | בחתימה | 0 days | 28 January 2021 8:00 | 28 January 2021 8:00 | 1 | 448,443 | 0h | 01.02.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
450 |  | Auto Scheduled | חתום | 0 days | 28 January 2021 8:00 | 28 January 2021 8:00 | 1 | 449 | 0h | 01.02.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
451 |  | Auto Scheduled | 01.02: ערכות.INT | 426.88 days | 28 January 2021 8:00 | 22 August 2022 13:00 | 0.11 |  | 630h | 01.02.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
452 |  | Auto Scheduled | מערכת הסאפ תשלח את עצי המוצר הרלוונטים למערכת הזכיין זכיין | 165.88 days | 28 January 2021 8:00 | 30 September 2021 13:00 | 0.13 |  | 70h | 01.02.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
453 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
454 |  | Auto Scheduled | LifeCycle Tasks | 165.88 days | 28 January 2021 8:00 | 30 September 2021 13:00 | 0.13 |  | 70h | 01.02.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
455 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
456 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
457 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 11.25 days | 24 August 2021 8:00 | 09 September 2021 17:00 | 0 |  | 0h | 01.02.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
458 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 September 2021 8:00 | 14 September 2021 15:00 | 0 | 457 | 25h | 01.02.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
459 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 September 2021 15:00 | 19 September 2021 16:00 | 0 | 458 | 10h | 01.02.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
460 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 September 2021 16:00 | 29 September 2021 17:00 | 0 | 459 | 10h | 01.02.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
461 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 September 2021 8:00 | 30 September 2021 13:00 | 0 | 460 | 5h | 01.02.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
462 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 30 September 2021 13:00 | 30 September 2021 13:00 | 0 | 461,455 | 0h | 01.02.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
463 |  | Auto Scheduled | מערכת סאפ תאפשר יצירה ושידור פק"ע ייצור עבור תהליך ייצור ערכה ב זכיין. | 209.75 days | 28 January 2021 8:00 | 24 November 2021 13:00 | 0.16 |  | 70h | 01.02.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
464 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
465 |  | Auto Scheduled | LifeCycle Tasks | 209.75 days | 28 January 2021 8:00 | 24 November 2021 13:00 | 0.16 |  | 70h | 01.02.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
466 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
467 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
468 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 09 November 2021 8:00 | 16 November 2021 17:00 | 0 |  | 0h | 01.02.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
469 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 November 2021 8:00 | 21 November 2021 15:00 | 0 | 468 | 25h | 01.02.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
470 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 November 2021 15:00 | 22 November 2021 16:00 | 0 | 469 | 10h | 01.02.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
471 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 November 2021 16:00 | 23 November 2021 17:00 | 0 | 470 | 10h | 01.02.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
472 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 November 2021 8:00 | 24 November 2021 13:00 | 0 | 471 | 5h | 01.02.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
473 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 November 2021 13:00 | 24 November 2021 13:00 | 0 | 472,466 | 0h | 01.02.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
474 |  | Auto Scheduled | מערכת ה זכיין תאפשר שליחת שדרים למערכת הסאפ עבור קבלה למלאי של ערכה מושלמת. | 296.38 days | 28 January 2021 8:00 | 13 March 2022 13:00 | 0.11 |  | 70h | 01.02.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
475 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
476 |  | Auto Scheduled | LifeCycle Tasks | 296.38 days | 28 January 2021 8:00 | 13 March 2022 13:00 | 0.11 |  | 70h | 01.02.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
477 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
478 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
479 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 14.63 days | 15 February 2022 8:00 | 03 March 2022 17:00 | 0 |  | 0h | 01.02.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
480 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 March 2022 8:00 | 08 March 2022 15:00 | 0 | 479 | 25h | 01.02.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
481 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 March 2022 15:00 | 09 March 2022 16:00 | 0 | 480 | 10h | 01.02.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
482 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 March 2022 16:00 | 10 March 2022 17:00 | 0 | 481 | 10h | 01.02.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
483 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 March 2022 8:00 | 13 March 2022 13:00 | 0 | 482 | 5h | 01.02.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
484 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 13 March 2022 13:00 | 13 March 2022 13:00 | 0 | 483,477 | 0h | 01.02.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
485 |  | Auto Scheduled | מערכת ה זכיין תאפשר שליחת שדר חיווי עבור פעולת הוצאה\הכנסה של רכיב לערכה קיימת | 352.63 days | 28 January 2021 8:00 | 22 May 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.02.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
486 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
487 |  | Auto Scheduled | LifeCycle Tasks | 352.63 days | 28 January 2021 8:00 | 22 May 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.02.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
488 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
489 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
490 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 37.13 days | 29 March 2022 8:00 | 12 May 2022 17:00 | 0 |  | 0h | 01.02.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
491 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 15 May 2022 8:00 | 17 May 2022 15:00 | 0 | 490 | 25h | 01.02.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
492 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 May 2022 15:00 | 18 May 2022 16:00 | 0 | 491 | 10h | 01.02.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
493 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 May 2022 16:00 | 19 May 2022 17:00 | 0 | 492 | 10h | 01.02.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
494 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 22 May 2022 8:00 | 22 May 2022 13:00 | 0 | 493 | 5h | 01.02.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
495 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 22 May 2022 13:00 | 22 May 2022 13:00 | 0 | 494,488 | 0h | 01.02.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
496 |  | Auto Scheduled | מערכת זכיין תאפשר שליחת עדכון סטאטוס הפק"ע עם סיום בניית הערכה | 304.25 days | 28 January 2021 8:00 | 22 March 2022 13:00 | 0.11 |  | 70h | 01.02.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
497 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
498 |  | Auto Scheduled | LifeCycle Tasks | 304.25 days | 28 January 2021 8:00 | 22 March 2022 13:00 | 0.11 |  | 70h | 01.02.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
499 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
500 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
501 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 14.63 days | 24 February 2022 8:00 | 14 March 2022 17:00 | 0 |  | 0h | 01.02.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
502 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 15 March 2022 8:00 | 17 March 2022 15:00 | 0 | 501 | 25h | 01.02.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
503 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 March 2022 15:00 | 20 March 2022 16:00 | 0 | 502 | 10h | 01.02.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
504 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 March 2022 16:00 | 21 March 2022 17:00 | 0 | 503 | 10h | 01.02.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
505 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 22 March 2022 8:00 | 22 March 2022 13:00 | 0 | 504 | 5h | 01.02.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
506 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 22 March 2022 13:00 | 22 March 2022 13:00 | 0 | 505,499 | 0h | 01.02.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
507 |  | Auto Scheduled | מערכת ה זכיין תאפשר שליחת שדרים למערכת הסאפ עבור ניפוק מלאי רכיבי הבנים לערכה | 288.5 days | 28 January 2021 8:00 | 02 March 2022 13:00 | 0.11 |  | 70h | 01.02.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
508 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
509 |  | Auto Scheduled | LifeCycle Tasks | 288.5 days | 28 January 2021 8:00 | 02 March 2022 13:00 | 0.11 |  | 70h | 01.02.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
510 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
511 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
512 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 13.5 days | 07 February 2022 8:00 | 22 February 2022 17:00 | 0 |  | 0h | 01.02.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
513 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 February 2022 8:00 | 27 February 2022 15:00 | 0 | 512 | 25h | 01.02.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
514 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 February 2022 15:00 | 28 February 2022 16:00 | 0 | 513 | 10h | 01.02.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
515 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 February 2022 16:00 | 01 March 2022 17:00 | 0 | 514 | 10h | 01.02.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
516 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 March 2022 8:00 | 02 March 2022 13:00 | 0 | 515 | 5h | 01.02.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
517 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 02 March 2022 13:00 | 02 March 2022 13:00 | 0 | 516,510 | 0h | 01.02.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
518 |  | Auto Scheduled | מערכת סאפ תדע לשדר לזכיין נתוני פק"ע לפירוק לטובת פירוק ערכות בזכיין | 413.38 days | 28 January 2021 8:00 | 04 August 2022 13:00 | 0.12 |  | 70h | 01.02.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
519 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
520 |  | Auto Scheduled | LifeCycle Tasks | 413.38 days | 28 January 2021 8:00 | 04 August 2022 13:00 | 0.12 |  | 70h | 01.02.INT.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
521 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.07.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
522 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.07.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
523 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 13 July 2022 8:00 | 27 July 2022 17:00 | 0 |  | 0h | 01.02.INT.07.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
524 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 28 July 2022 8:00 | 01 August 2022 15:00 | 0 | 523 | 25h | 01.02.INT.07.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
525 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 01 August 2022 15:00 | 02 August 2022 16:00 | 0 | 524 | 10h | 01.02.INT.07.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
526 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 02 August 2022 16:00 | 03 August 2022 17:00 | 0 | 525 | 10h | 01.02.INT.07.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
527 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 04 August 2022 8:00 | 04 August 2022 13:00 | 0 | 526 | 5h | 01.02.INT.07.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
528 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 04 August 2022 13:00 | 04 August 2022 13:00 | 0 | 527,521 | 0h | 01.02.INT.07.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
529 |  | Auto Scheduled | מערכתזכיין תדע לשדר לסאפ על קבלת פריטים למלאי המחסן מערכות המפורקות בזכיין | 420.13 days | 28 January 2021 8:00 | 14 August 2022 13:00 | 0.12 |  | 70h | 01.02.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
530 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
531 |  | Auto Scheduled | LifeCycle Tasks | 420.13 days | 28 January 2021 8:00 | 14 August 2022 13:00 | 0.12 |  | 70h | 01.02.INT.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
532 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.08.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
533 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.08.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
534 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 21 July 2022 8:00 | 04 August 2022 17:00 | 0 |  | 0h | 01.02.INT.08.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
535 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 August 2022 8:00 | 09 August 2022 15:00 | 0 | 534 | 25h | 01.02.INT.08.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
536 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 August 2022 15:00 | 10 August 2022 16:00 | 0 | 535 | 10h | 01.02.INT.08.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
537 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 August 2022 16:00 | 11 August 2022 17:00 | 0 | 536 | 10h | 01.02.INT.08.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
538 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 August 2022 8:00 | 14 August 2022 13:00 | 0 | 537 | 5h | 01.02.INT.08.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
539 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 14 August 2022 13:00 | 14 August 2022 13:00 | 0 | 538,532 | 0h | 01.02.INT.08.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
540 |  | Auto Scheduled | מערכתזכיין תדע לשדר לסאפ על הורדת הערכה ממלאי המחסן לאחר פירוק ערכה בזכיין | 426.88 days | 28 January 2021 8:00 | 22 August 2022 13:00 | 0.12 |  | 70h | 01.02.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
541 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
542 |  | Auto Scheduled | LifeCycle Tasks | 426.88 days | 28 January 2021 8:00 | 22 August 2022 13:00 | 0.12 |  | 70h | 01.02.INT.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
543 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.INT.09.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
544 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.INT.09.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
545 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 31 July 2022 8:00 | 14 August 2022 17:00 | 0 |  | 0h | 01.02.INT.09.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
546 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 15 August 2022 8:00 | 17 August 2022 15:00 | 0 | 545 | 25h | 01.02.INT.09.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
547 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 August 2022 15:00 | 18 August 2022 16:00 | 0 | 546 | 10h | 01.02.INT.09.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
548 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 August 2022 16:00 | 21 August 2022 17:00 | 0 | 547 | 10h | 01.02.INT.09.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
549 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 22 August 2022 8:00 | 22 August 2022 13:00 | 0 | 548 | 5h | 01.02.INT.09.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
550 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 22 August 2022 13:00 | 22 August 2022 13:00 | 0 | 549,543 | 0h | 01.02.INT.09.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
551 |  | Auto Scheduled | 01.02: ערכות.SAP | 408.88 days | 28 January 2021 8:00 | 31 July 2022 13:00 | 0.13 |  | 1,260h | 01.02.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
552 |  | Auto Scheduled | מערכת סאפ תאפשר שחרור הזמנות פק"ע ייצור באתר המרהס עבור אתרי אחסון מנהלים זכיין | 239 days | 28 January 2021 8:00 | 30 December 2021 13:00 | 0.23000000000000001 |  | 70h | 01.02.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
553 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
554 |  | Auto Scheduled | LifeCycle Tasks | 239 days | 28 January 2021 8:00 | 30 December 2021 13:00 | 0.23000000000000001 |  | 70h | 01.02.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
555 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
556 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
557 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 21 December 2021 8:00 | 22 December 2021 17:00 | 0 |  | 0h | 01.02.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
558 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 December 2021 8:00 | 27 December 2021 15:00 | 0 | 557 | 25h | 01.02.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
559 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 December 2021 15:00 | 28 December 2021 16:00 | 0 | 558 | 10h | 01.02.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
560 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 December 2021 16:00 | 29 December 2021 17:00 | 0 | 559 | 10h | 01.02.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
561 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 December 2021 8:00 | 30 December 2021 13:00 | 0 | 560 | 5h | 01.02.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
562 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 30 December 2021 13:00 | 30 December 2021 13:00 | 0 | 561,555 | 0h | 01.02.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
563 |  | Auto Scheduled | מערכת הסאפ תאפשר ניפוק פריטים לפק"ע עבור ייצור ערכות | 273.88 days | 28 January 2021 8:00 | 13 February 2022 13:00 | 0.17000000000000001 |  | 70h | 01.02.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
564 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
565 |  | Auto Scheduled | LifeCycle Tasks | 273.88 days | 28 January 2021 8:00 | 13 February 2022 13:00 | 0.17000000000000001 |  | 70h | 01.02.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
566 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
567 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
568 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 30 January 2022 8:00 | 03 February 2022 17:00 | 0 |  | 0h | 01.02.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
569 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 February 2022 8:00 | 08 February 2022 15:00 | 0 | 568 | 25h | 01.02.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
570 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 February 2022 15:00 | 09 February 2022 16:00 | 0 | 569 | 10h | 01.02.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
571 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 February 2022 16:00 | 10 February 2022 17:00 | 0 | 570 | 10h | 01.02.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
572 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 February 2022 8:00 | 13 February 2022 13:00 | 0 | 571 | 5h | 01.02.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
573 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 13 February 2022 13:00 | 13 February 2022 13:00 | 0 | 572,566 | 0h | 01.02.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
574 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת הזמנת\אספקת ויסות בתוך המרחב לזכיין עבור ליקוט פריטי בנים הקיימים במחסני המרה"ס וניפוקם למחסן מנוהל סאפ לצורך בניית ערכות | 270.5 days | 28 January 2021 8:00 | 08 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.02.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
575 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
576 |  | Auto Scheduled | LifeCycle Tasks | 270.5 days | 28 January 2021 8:00 | 08 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.02.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
577 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
578 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
579 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 11 January 2022 8:00 | 31 January 2022 17:00 | 0 |  | 0h | 01.02.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
580 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 February 2022 8:00 | 03 February 2022 15:00 | 0 | 579 | 25h | 01.02.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
581 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 February 2022 15:00 | 06 February 2022 16:00 | 0 | 580 | 10h | 01.02.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
582 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 February 2022 16:00 | 07 February 2022 17:00 | 0 | 581 | 10h | 01.02.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
583 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 08 February 2022 8:00 | 08 February 2022 13:00 | 0 | 582 | 5h | 01.02.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
584 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 08 February 2022 13:00 | 08 February 2022 13:00 | 0 | 583,577 | 0h | 01.02.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
585 |  | Auto Scheduled | מערכת סאפ תאפשר יצירת\שינוי – עצי מוצר עבור אתר המרהס | 160.25 days | 28 January 2021 8:00 | 12 September 2021 13:00 | 0.27000000000000002 |  | 70h | 01.02.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
586 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
587 |  | Auto Scheduled | LifeCycle Tasks | 160.25 days | 28 January 2021 8:00 | 12 September 2021 13:00 | 0.27000000000000002 |  | 70h | 01.02.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
588 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
589 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
590 |  | Auto Scheduled | יישום ופיתוח סאפ | 19.13 days | 08 August 2021 8:00 | 30 August 2021 17:00 | 0.27000000000000002 |  | 0h | 01.02.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
591 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 31 August 2021 8:00 | 02 September 2021 15:00 | 0 | 590 | 25h | 01.02.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
592 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 02 September 2021 15:00 | 05 September 2021 16:00 | 0 | 591 | 10h | 01.02.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
593 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 05 September 2021 16:00 | 09 September 2021 17:00 | 0 | 592 | 10h | 01.02.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
594 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 September 2021 8:00 | 12 September 2021 13:00 | 0 | 593 | 5h | 01.02.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
595 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 12 September 2021 13:00 | 12 September 2021 13:00 | 0 | 594,588 | 0h | 01.02.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
596 |  | Auto Scheduled | מערכת סאפ תדע לתמוך בתהליך בחירת סדרות לפריטי הבנים בעת יצירת הפק"ע | 196.25 days | 28 January 2021 8:00 | 08 November 2021 13:00 | 0.13 |  | 70h | 01.02.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
597 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
598 |  | Auto Scheduled | LifeCycle Tasks | 196.25 days | 28 January 2021 8:00 | 08 November 2021 13:00 | 0.13 |  | 70h | 01.02.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
599 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
600 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
601 |  | Auto Scheduled | יישום ופיתוח סאפ | 37.13 days | 30 August 2021 8:00 | 31 October 2021 17:00 | 8.9999999999999997E-2 |  | 0h | 01.02.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
602 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 November 2021 8:00 | 03 November 2021 15:00 | 0 | 601 | 25h | 01.02.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
603 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 November 2021 15:00 | 04 November 2021 16:00 | 0 | 602 | 10h | 01.02.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
604 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 November 2021 16:00 | 07 November 2021 17:00 | 0 | 603 | 10h | 01.02.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
605 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 08 November 2021 8:00 | 08 November 2021 13:00 | 0 | 604 | 5h | 01.02.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
606 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 08 November 2021 13:00 | 08 November 2021 13:00 | 0 | 605,599 | 0h | 01.02.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
607 |  | Auto Scheduled | מערכת סאפ תאפשר יצירת\שחרור הזמנות פק"ע ייצור באתר המרה"ס עבור אתרי אחסון מנהלים סאפ | 204.13 days | 28 January 2021 8:00 | 17 November 2021 13:00 | 0.26000000000000001 |  | 70h | 01.02.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
608 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
609 |  | Auto Scheduled | LifeCycle Tasks | 204.13 days | 28 January 2021 8:00 | 17 November 2021 13:00 | 0.26000000000000001 |  | 70h | 01.02.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
610 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
611 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
612 |  | Auto Scheduled | יישום ופיתוח סאפ | 15.75 days | 21 October 2021 8:00 | 09 November 2021 17:00 | 0.25 |  | 0h | 01.02.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
613 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 November 2021 8:00 | 14 November 2021 15:00 | 0 | 612 | 25h | 01.02.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
614 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 November 2021 15:00 | 15 November 2021 16:00 | 0 | 613 | 10h | 01.02.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
615 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 November 2021 16:00 | 16 November 2021 17:00 | 0 | 614 | 10h | 01.02.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
616 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 November 2021 8:00 | 17 November 2021 13:00 | 0 | 615 | 5h | 01.02.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
617 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 November 2021 13:00 | 17 November 2021 13:00 | 0 | 616,610 | 0h | 01.02.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
618 |  | Auto Scheduled | מערכת סאפ תבצע בדיקת אחוז ההרכבה האפשרי והפריטים הזמינים בעת יצירת הפק"ע המיועדת לבנייה באתר זכיין. לפי החלטת המשתמש נמשיך לשלבים הבאים או נבחר שלא לייצר עד לקבלת הפריטים למלאי הזכיין. | 252.5 days | 28 January 2021 8:00 | 17 January 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.02.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
619 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
620 |  | Auto Scheduled | LifeCycle Tasks | 252.5 days | 28 January 2021 8:00 | 17 January 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.02.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
621 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
622 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
623 |  | Auto Scheduled | יישום ופיתוח סאפ | 46.13 days | 14 November 2021 8:00 | 09 January 2022 17:00 | 0 |  | 0h | 01.02.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
624 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 January 2022 8:00 | 12 January 2022 15:00 | 0 | 623 | 25h | 01.02.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
625 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 January 2022 15:00 | 13 January 2022 16:00 | 0 | 624 | 10h | 01.02.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
626 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 January 2022 16:00 | 16 January 2022 17:00 | 0 | 625 | 10h | 01.02.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
627 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 January 2022 8:00 | 17 January 2022 13:00 | 0 | 626 | 5h | 01.02.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
628 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 January 2022 13:00 | 17 January 2022 13:00 | 0 | 627,621 | 0h | 01.02.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
629 |  | Auto Scheduled | מערכת סאפ תאפשר ליקוט וזיכוי פרטי בנים הקיימים במחסני המרכזים המנוהלים סאפ וניפוקם לבימ"ל | 263.75 days | 28 January 2021 8:00 | 31 January 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.02.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
630 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
631 |  | Auto Scheduled | LifeCycle Tasks | 263.75 days | 28 January 2021 8:00 | 31 January 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.02.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
632 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
633 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
634 |  | Auto Scheduled | יישום ופיתוח סאפ | 27 days | 21 December 2021 8:00 | 23 January 2022 17:00 | 0 |  | 0h | 01.02.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
635 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 January 2022 8:00 | 26 January 2022 15:00 | 0 | 634 | 25h | 01.02.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
636 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 January 2022 15:00 | 27 January 2022 16:00 | 0 | 635 | 10h | 01.02.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
637 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 January 2022 16:00 | 30 January 2022 17:00 | 0 | 636 | 10h | 01.02.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
638 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 January 2022 8:00 | 31 January 2022 13:00 | 0 | 637 | 5h | 01.02.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
639 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 31 January 2022 13:00 | 31 January 2022 13:00 | 0 | 638,632 | 0h | 01.02.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
640 |  | Auto Scheduled | מערכת הסאפ תאפשר פתיחת פקע להוצאה \הכנסה של רכיבים מערכה קיימת | 326.75 days | 28 January 2021 8:00 | 19 April 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 01.02.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
641 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
642 |  | Auto Scheduled | LifeCycle Tasks | 326.75 days | 28 January 2021 8:00 | 19 April 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 01.02.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
643 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
644 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
645 |  | Auto Scheduled | יישום ופיתוח סאפ | 23.63 days | 14 March 2022 8:00 | 11 April 2022 17:00 | 0 |  | 0h | 01.02.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
646 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 April 2022 8:00 | 14 April 2022 15:00 | 0 | 645 | 25h | 01.02.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
647 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 April 2022 15:00 | 17 April 2022 16:00 | 0 | 646 | 10h | 01.02.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
648 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 April 2022 16:00 | 18 April 2022 17:00 | 0 | 647 | 10h | 01.02.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
649 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 April 2022 8:00 | 19 April 2022 13:00 | 0 | 648 | 5h | 01.02.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
650 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 April 2022 13:00 | 19 April 2022 13:00 | 0 | 649,643 | 0h | 01.02.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
651 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי הרשאות בהתאם לתהליכי העבודה המשתנים | 357.13 days | 28 January 2021 8:00 | 26 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
652 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
653 |  | Auto Scheduled | LifeCycle Tasks | 357.13 days | 28 January 2021 8:00 | 26 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
654 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
655 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
656 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 16 May 2022 8:00 | 18 May 2022 17:00 | 0 |  | 0h | 01.02.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
657 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 May 2022 8:00 | 23 May 2022 15:00 | 0 | 656 | 25h | 01.02.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
658 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 May 2022 15:00 | 24 May 2022 16:00 | 0 | 657 | 10h | 01.02.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
659 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 May 2022 16:00 | 25 May 2022 17:00 | 0 | 658 | 10h | 01.02.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
660 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 26 May 2022 8:00 | 26 May 2022 13:00 | 0 | 659 | 5h | 01.02.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
661 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 26 May 2022 13:00 | 26 May 2022 13:00 | 0 | 660,654 | 0h | 01.02.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
662 |  | Auto Scheduled | ניפוק הערכה ישירות מבימ"ל – מערכת סאפ תאפשר ניפוק הערכה מהבימ"ל ליחידות | 278.38 days | 28 January 2021 8:00 | 17 February 2022 13:00 | 0.17000000000000001 |  | 70h | 01.02.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
663 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
664 |  | Auto Scheduled | LifeCycle Tasks | 278.38 days | 28 January 2021 8:00 | 17 February 2022 13:00 | 0.17000000000000001 |  | 70h | 01.02.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
665 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
666 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
667 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 03 February 2022 8:00 | 09 February 2022 17:00 | 0 |  | 0h | 01.02.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
668 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 February 2022 8:00 | 14 February 2022 15:00 | 0 | 667 | 25h | 01.02.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
669 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 February 2022 15:00 | 15 February 2022 16:00 | 0 | 668 | 10h | 01.02.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
670 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 February 2022 16:00 | 16 February 2022 17:00 | 0 | 669 | 10h | 01.02.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
671 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 February 2022 8:00 | 17 February 2022 13:00 | 0 | 670 | 5h | 01.02.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
672 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 February 2022 13:00 | 17 February 2022 13:00 | 0 | 671,665 | 0h | 01.02.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
673 |  | Auto Scheduled | מערכת הסאפ תאפשר קבלה למלאי של ערכות לאחר ייצור | 276.13 days | 28 January 2021 8:00 | 15 February 2022 13:00 | 0.17000000000000001 |  | 70h | 01.02.SAP.12 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
674 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
675 |  | Auto Scheduled | LifeCycle Tasks | 276.13 days | 28 January 2021 8:00 | 15 February 2022 13:00 | 0.17000000000000001 |  | 70h | 01.02.SAP.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
676 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.12.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
677 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.12.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
678 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 01 February 2022 8:00 | 07 February 2022 17:00 | 0 |  | 0h | 01.02.SAP.12.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
679 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 February 2022 8:00 | 10 February 2022 15:00 | 0 | 678 | 25h | 01.02.SAP.12.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
680 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 February 2022 15:00 | 13 February 2022 16:00 | 0 | 679 | 10h | 01.02.SAP.12.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
681 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 February 2022 16:00 | 14 February 2022 17:00 | 0 | 680 | 10h | 01.02.SAP.12.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
682 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 February 2022 8:00 | 15 February 2022 13:00 | 0 | 681 | 5h | 01.02.SAP.12.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
683 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 15 February 2022 13:00 | 15 February 2022 13:00 | 0 | 682,676 | 0h | 01.02.SAP.12.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
684 |  | Auto Scheduled | מערכת סאפ תעדכן את העיתוד על פעולות מלאיות שיבוצעו כתוצאה משדרי עידכון המלאי שהזכיין ישלח | 356 days | 28 January 2021 8:00 | 25 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.13 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
685 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.13.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
686 |  | Auto Scheduled | LifeCycle Tasks | 356 days | 28 January 2021 8:00 | 25 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.13.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
687 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.13.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
688 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.13.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
689 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 15 May 2022 8:00 | 17 May 2022 17:00 | 0 |  | 0h | 01.02.SAP.13.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
690 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 May 2022 8:00 | 22 May 2022 15:00 | 0 | 689 | 25h | 01.02.SAP.13.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
691 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 May 2022 15:00 | 23 May 2022 16:00 | 0 | 690 | 10h | 01.02.SAP.13.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
692 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 May 2022 16:00 | 24 May 2022 17:00 | 0 | 691 | 10h | 01.02.SAP.13.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
693 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 May 2022 8:00 | 25 May 2022 13:00 | 0 | 692 | 5h | 01.02.SAP.13.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
694 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 May 2022 13:00 | 25 May 2022 13:00 | 0 | 693,687 | 0h | 01.02.SAP.13.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
695 |  | Auto Scheduled | מערכת הסאפ תאפשר קליטת תנועות מלאי יעודיות מהזכיין על מנת לעדכן תכולת ערכה הוצאה\הכנסה עבור ערכה שנמצאת במלאי | 343.63 days | 28 January 2021 8:00 | 10 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.14 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
696 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.14.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
697 |  | Auto Scheduled | LifeCycle Tasks | 343.63 days | 28 January 2021 8:00 | 10 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.14.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
698 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.14.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
699 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.14.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
700 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 28 April 2022 8:00 | 02 May 2022 17:00 | 0 |  | 0h | 01.02.SAP.14.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
701 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 May 2022 8:00 | 05 May 2022 15:00 | 0 | 700 | 25h | 01.02.SAP.14.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
702 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 May 2022 15:00 | 08 May 2022 16:00 | 0 | 701 | 10h | 01.02.SAP.14.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
703 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 May 2022 16:00 | 09 May 2022 17:00 | 0 | 702 | 10h | 01.02.SAP.14.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
704 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 May 2022 8:00 | 10 May 2022 13:00 | 0 | 703 | 5h | 01.02.SAP.14.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
705 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 May 2022 13:00 | 10 May 2022 13:00 | 0 | 704,698 | 0h | 01.02.SAP.14.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
706 |  | Auto Scheduled | מערכת ה סאפ תשנה את הסטאטוס בפק"ע בהתאם לשדר מה זכיין | 354.88 days | 28 January 2021 8:00 | 24 May 2022 13:00 | 0.11 |  | 70h | 01.02.SAP.15 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
707 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.15.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
708 |  | Auto Scheduled | LifeCycle Tasks | 354.88 days | 28 January 2021 8:00 | 24 May 2022 13:00 | 0.11 |  | 70h | 01.02.SAP.15.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
709 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.15.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
710 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.15.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
711 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 01 May 2022 8:00 | 16 May 2022 17:00 | 0 |  | 0h | 01.02.SAP.15.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
712 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 May 2022 8:00 | 19 May 2022 15:00 | 0 | 711 | 25h | 01.02.SAP.15.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
713 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 May 2022 15:00 | 22 May 2022 16:00 | 0 | 712 | 10h | 01.02.SAP.15.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
714 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 May 2022 16:00 | 23 May 2022 17:00 | 0 | 713 | 10h | 01.02.SAP.15.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
715 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 May 2022 8:00 | 24 May 2022 13:00 | 0 | 714 | 5h | 01.02.SAP.15.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
716 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 May 2022 13:00 | 24 May 2022 13:00 | 0 | 715,709 | 0h | 01.02.SAP.15.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
717 |  | Auto Scheduled | יש להקים במערכת סאפ אזורי אמ אר פי לייצור ערכות בהתאם לשינויים במבנה הארגוני | 358.25 days | 28 January 2021 8:00 | 29 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.16 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
718 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.16.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
719 |  | Auto Scheduled | LifeCycle Tasks | 358.25 days | 28 January 2021 8:00 | 29 May 2022 13:00 | 0.20999999999999999 |  | 70h | 01.02.SAP.16.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
720 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.16.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
721 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.16.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
722 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 17 May 2022 8:00 | 19 May 2022 17:00 | 0 |  | 0h | 01.02.SAP.16.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
723 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 May 2022 8:00 | 24 May 2022 15:00 | 0 | 722 | 25h | 01.02.SAP.16.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
724 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 May 2022 15:00 | 25 May 2022 16:00 | 0 | 723 | 10h | 01.02.SAP.16.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
725 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 May 2022 16:00 | 26 May 2022 17:00 | 0 | 724 | 10h | 01.02.SAP.16.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
726 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 May 2022 8:00 | 29 May 2022 13:00 | 0 | 725 | 5h | 01.02.SAP.16.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
727 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 May 2022 13:00 | 29 May 2022 13:00 | 0 | 726,720 | 0h | 01.02.SAP.16.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
728 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת של פק"ע מסוג פירוק ערכה | 385.25 days | 28 January 2021 8:00 | 30 June 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.02.SAP.17 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
729 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.17.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
730 |  | Auto Scheduled | LifeCycle Tasks | 385.25 days | 28 January 2021 8:00 | 30 June 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.02.SAP.17.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
731 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.17.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
732 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.17.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
733 |  | Auto Scheduled | יישום ופיתוח סאפ | 29.25 days | 18 May 2022 8:00 | 22 June 2022 17:00 | 0 |  | 0h | 01.02.SAP.17.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
734 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 June 2022 8:00 | 27 June 2022 15:00 | 0 | 733 | 25h | 01.02.SAP.17.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
735 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 June 2022 15:00 | 28 June 2022 16:00 | 0 | 734 | 10h | 01.02.SAP.17.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
736 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 June 2022 16:00 | 29 June 2022 17:00 | 0 | 735 | 10h | 01.02.SAP.17.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
737 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 June 2022 8:00 | 30 June 2022 13:00 | 0 | 736 | 5h | 01.02.SAP.17.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
738 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 30 June 2022 13:00 | 30 June 2022 13:00 | 0 | 737,731 | 0h | 01.02.SAP.17.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
739 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת של פק"ע מסוג הוצאה והכנסה של פריט לערכה | 408.88 days | 28 January 2021 8:00 | 31 July 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.02.SAP.18 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
740 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.18.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
741 |  | Auto Scheduled | LifeCycle Tasks | 408.88 days | 28 January 2021 8:00 | 31 July 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.02.SAP.18.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
742 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.02.SAP.18.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
743 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 28 January 2021 8:00 | 01 February 2021 10:00 | 1 | 441 | 20h | 01.02.SAP.18.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
744 |  | Auto Scheduled | יישום ופיתוח סאפ | 29.25 days | 16 June 2022 8:00 | 21 July 2022 17:00 | 0 |  | 0h | 01.02.SAP.18.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
745 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 July 2022 8:00 | 26 July 2022 15:00 | 0 | 744 | 25h | 01.02.SAP.18.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
746 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 July 2022 15:00 | 27 July 2022 16:00 | 0 | 745 | 10h | 01.02.SAP.18.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
747 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 July 2022 16:00 | 28 July 2022 17:00 | 0 | 746 | 10h | 01.02.SAP.18.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
748 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 July 2022 8:00 | 31 July 2022 13:00 | 0 | 747 | 5h | 01.02.SAP.18.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
749 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 31 July 2022 13:00 | 31 July 2022 13:00 | 0 | 748,742 | 0h | 01.02.SAP.18.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
750 |  | Auto Scheduled | 01.03: חיובים וזיכויים | 394.25 days | 06 August 2020 8:00 | 18 January 2022 13:00 | 0.38 |  | 439h | 01.03 | חתום | אבי פרישמן | hd | מאור | nan | BP | NA | As Soon As Possible | 3
751 |  | Auto Scheduled | 01.03: חיובים וזיכויים.BP | 121.5 days | 06 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 159h | 01.03.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
752 |  | Auto Scheduled | 01.03: חיובים וזיכויים | 121.5 days | 06 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 159h | 01.03.BP.01 | חתום | אבי פרישמן | parent | מאור | nan | BP | NA | As Soon As Possible | 5
753 |  | Auto Scheduled | Sub Tasks | 119.5 days | 06 August 2020 8:00 | 03 January 2021 10:00 | 1 |  | 119h | 01.03.BP.01.01 |  | אבי פרישמן | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
754 |  | Auto Scheduled | 03/09: תגובה של תקווה--1. ביטול חיוב עצמי וכל פעולת רוורס אחרת – במעבר למבנה ארגוני חדש יפתחו מחסנים / א"א חדשים לכן לא ניתן יהיה לבצע ביטולים היסטוריים. צריך לציין במסמך.--2. יש יותר מדי נושאים פתוחים בסוף המסמך – לא חושבת ששגיב יחתום במצב כזה.--3. עיצו | 0.25 days | 17 August 2020 8:00 | 17 August 2020 10:00 | 1 |  | 2h | 01.03.BP.01.01.01 | בוצע | מאור | MoM | מאור | תקווה רובינצ'יק | BP | NA | Must Start On | 7
755 |  | Auto Scheduled | 23/09: חסרות סיבה לתנועה 262 וסיבות של סימולי החוץ--תוצרת גמורה המגיעה מהמשא/בימל שמבצעים 101 על סמך אספקה נכנסת עם סיבה לתנועה שבו רושמים סימול חוץ/ סימול של המשא , מתבצע שרשור של 902 זיכוי עם סיבה 262 | 0.25 days | 18 August 2020 8:00 | 18 August 2020 10:00 | 1 | 754 | 2h | 01.03.BP.01.01.02 | בוצע | מאור | MoM | מאור | שרון רחמים | BP | NA | As Soon As Possible | 7
756 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 06 August 2020 8:00 | 09 August 2020 10:00 | 1 |  | 11h | 01.03.BP.01.01.20 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
757 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 3 days | 20 August 2020 8:00 | 24 August 2020 14:00 | 1 | 756 | 24h | 01.03.BP.01.01.21 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
758 |  | Auto Scheduled | אישור מקל"ר | 1 day | 22 September 2020 8:00 | 22 September 2020 16:00 | 1 | 757 | 8h | 01.03.BP.01.01.22 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
759 |  | Auto Scheduled | אישור מפקדת | 1.38 days | 01 October 2020 8:00 | 04 October 2020 10:00 | 1 | 758 | 11h | 01.03.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
760 |  | Auto Scheduled | אישור אבי | 2.13 days | 15 October 2020 8:00 | 18 October 2020 16:00 | 1 | 759 | 17h | 01.03.BP.01.01.24 | בוצע | סיגל | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
761 |  | Auto Scheduled | אישור המנהלת | 1.38 days | 08 November 2020 8:00 | 09 November 2020 10:00 | 1 | 760 | 11h | 01.03.BP.01.01.25 | בוצע |  | MoM |  | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
762 |  | Auto Scheduled | אישור חטלו"ג | 2.63 days | 22 November 2020 8:00 | 24 November 2020 11:00 | 1 | 761 | 21h | 01.03.BP.01.01.26 | בוצע | מאור | MoM | מאור | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
763 |  | Auto Scheduled | אישור ניר בשן | 1.25 days | 20 December 2020 8:00 | 21 December 2020 9:00 | 1 | 762 | 10h | 01.03.BP.01.01.27 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
764 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 02 January 2021 8:00 | 03 January 2021 10:00 | 1 | 763 | 2h | 01.03.BP.01.01.28 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
765 |  | Auto Scheduled | LifeCycle Tasks | 110.25 days | 20 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 01.03.BP.01.02 |  | אבי פרישמן | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
766 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 764 | 0h | 01.03.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
767 |  | Auto Scheduled | טרם החל | 0.63 days | 20 August 2020 8:00 | 20 August 2020 13:00 | 1 |  | 5h | 01.03.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
768 |  | Auto Scheduled | בעבודה | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 767 | 10h | 01.03.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
769 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 10 September 2020 8:00 | 10 September 2020 13:00 | 1 | 768 | 5h | 01.03.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
770 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 769 | 10h | 01.03.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
771 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 770 | 10h | 01.03.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
772 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 771,766 | 0h | 01.03.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
773 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 772 | 0h | 01.03.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
774 |  | Auto Scheduled | 01.03: חיובים וזיכויים.INT | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.14999999999999999 |  | 70h | 01.03.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
775 |  | Auto Scheduled | מערכות סאפ ו זכיין יאפשרו העברת שדרים לתנועות שבוצעו ע"ב טבלת ההמרות | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.14999999999999999 |  | 70h | 01.03.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
776 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
777 |  | Auto Scheduled | LifeCycle Tasks | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.14999999999999999 |  | 70h | 01.03.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
778 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
779 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 764 | 20h | 01.03.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
780 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 7.88 days | 02 January 2022 8:00 | 10 January 2022 17:00 | 0 |  | 0h | 01.03.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
781 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 January 2022 8:00 | 13 January 2022 15:00 | 0 | 780 | 25h | 01.03.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
782 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 January 2022 15:00 | 16 January 2022 16:00 | 0 | 781 | 10h | 01.03.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
783 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 January 2022 16:00 | 17 January 2022 17:00 | 0 | 782 | 10h | 01.03.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
784 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 January 2022 8:00 | 18 January 2022 13:00 | 0 | 783 | 5h | 01.03.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
785 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 18 January 2022 13:00 | 18 January 2022 13:00 | 0 | 784,778 | 0h | 01.03.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
786 |  | Auto Scheduled | 01.03: חיובים וזיכויים.SAP | 230 days | 04 January 2021 8:00 | 24 November 2021 13:00 | 0.17000000000000001 |  | 210h | 01.03.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
787 |  | Auto Scheduled | מערכות זכיין סאפ יאפשרו שינוי הרשאות בהתאם לתהליכי העבודה המשתנים | 225.5 days | 04 January 2021 8:00 | 18 November 2021 13:00 | 0.17000000000000001 |  | 70h | 01.03.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
788 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
789 |  | Auto Scheduled | LifeCycle Tasks | 225.5 days | 04 January 2021 8:00 | 18 November 2021 13:00 | 0.17000000000000001 |  | 70h | 01.03.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
790 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
791 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 764 | 20h | 01.03.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
792 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 04 November 2021 8:00 | 10 November 2021 17:00 | 0 |  | 0h | 01.03.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
793 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 November 2021 8:00 | 15 November 2021 15:00 | 0 | 792 | 25h | 01.03.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
794 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 15 November 2021 15:00 | 16 November 2021 16:00 | 0 | 793 | 10h | 01.03.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
795 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 November 2021 16:00 | 17 November 2021 17:00 | 0 | 794 | 10h | 01.03.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
796 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 November 2021 8:00 | 18 November 2021 13:00 | 0 | 795 | 5h | 01.03.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
797 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 18 November 2021 13:00 | 18 November 2021 13:00 | 0 | 796,790 | 0h | 01.03.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
798 |  | Auto Scheduled | מערכת סאפ תאפשר המשך תהליך כפי שקיים היום בחיובים וזיכויים עבור מחסנים מיוחדים מחסנים בתפעול מערכת סאפ | 224.38 days | 04 January 2021 8:00 | 17 November 2021 13:00 | 0.17000000000000001 |  | 70h | 01.03.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
799 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
800 |  | Auto Scheduled | LifeCycle Tasks | 224.38 days | 04 January 2021 8:00 | 17 November 2021 13:00 | 0.17000000000000001 |  | 70h | 01.03.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
801 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
802 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 764 | 20h | 01.03.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
803 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 03 November 2021 8:00 | 09 November 2021 17:00 | 0 |  | 0h | 01.03.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
804 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 November 2021 8:00 | 14 November 2021 15:00 | 0 | 803 | 25h | 01.03.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
805 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 November 2021 15:00 | 15 November 2021 16:00 | 0 | 804 | 10h | 01.03.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
806 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 November 2021 16:00 | 16 November 2021 17:00 | 0 | 805 | 10h | 01.03.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
807 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 November 2021 8:00 | 17 November 2021 13:00 | 0 | 806 | 5h | 01.03.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
808 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 November 2021 13:00 | 17 November 2021 13:00 | 0 | 807,801 | 0h | 01.03.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
809 |  | Auto Scheduled | מערכת סאפ תאפשר איחוד קודי מאשר | 230 days | 04 January 2021 8:00 | 24 November 2021 13:00 | 0.16 |  | 70h | 01.03.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
810 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
811 |  | Auto Scheduled | LifeCycle Tasks | 230 days | 04 January 2021 8:00 | 24 November 2021 13:00 | 0.16 |  | 70h | 01.03.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
812 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.03.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
813 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 764 | 20h | 01.03.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
814 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 09 November 2021 8:00 | 16 November 2021 17:00 | 0 |  | 0h | 01.03.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
815 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 November 2021 8:00 | 21 November 2021 15:00 | 0 | 814 | 25h | 01.03.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
816 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 November 2021 15:00 | 22 November 2021 16:00 | 0 | 815 | 10h | 01.03.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
817 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 November 2021 16:00 | 23 November 2021 17:00 | 0 | 816 | 10h | 01.03.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
818 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 November 2021 8:00 | 24 November 2021 13:00 | 0 | 817 | 5h | 01.03.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
819 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 November 2021 13:00 | 24 November 2021 13:00 | 0 | 818,812 | 0h | 01.03.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
820 |  | Auto Scheduled | 01.04: השקעות ופירוקים | 294.63 days | 11 August 2020 8:00 | 05 September 2021 8:00 | 0.64000000000000001 |  | 344h | 01.04 | חתום | 5 avi | hd | גל | nan | BP | NA | As Soon As Possible | 3
821 |  | Auto Scheduled | 01.04: השקעות ופירוקים.BP | 97.88 days | 11 August 2020 8:00 | 09 December 2020 17:00 | 1 |  | 134h | 01.04.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
822 |  | Auto Scheduled | 01.04: השקעות ופירוקים | 97.88 days | 11 August 2020 8:00 | 09 December 2020 17:00 | 1 |  | 134h | 01.04.BP.01 | חתום | 5 avi | parent | גל | nan | BP | NA | As Soon As Possible | 5
823 |  | Auto Scheduled | Sub Tasks | 95.88 days | 11 August 2020 8:00 | 08 December 2020 10:00 | 1 |  | 94h | 01.04.BP.01.01 |  | 5 avi | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
824 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 11 August 2020 8:00 | 12 August 2020 10:00 | 1 |  | 11h | 01.04.BP.01.01.20 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | Must Start On | 7
825 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 3.5 days | 25 August 2020 8:00 | 30 August 2020 9:00 | 1 | 824 | 28h | 01.04.BP.01.01.21 | בוצע |  | MoM |  | 2020-09-22 00:00:00 | BP | NA | As Soon As Possible | 7
826 |  | Auto Scheduled | אישור מקל"ר | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 825 | 10h | 01.04.BP.01.01.22 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
827 |  | Auto Scheduled | אישור מפקדת | 4.25 days | 14 October 2020 8:00 | 19 October 2020 15:00 | 1 | 826 | 34h | 01.04.BP.01.01.23 | בוצע | סיגל | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
828 |  | Auto Scheduled | אישור חטלו"ג | 0.38 days | 30 November 2020 8:00 | 30 November 2020 11:00 | 1 | 827 | 3h | 01.04.BP.01.01.24 | בוצע |  | MoM |  | 2020-10-20 00:00:00 | BP | NA | As Soon As Possible | 7
829 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 02 December 2020 8:00 | 02 December 2020 10:00 | 1 | 828 | 2h | 01.04.BP.01.01.25 | בוצע | סיגל | MoM | ואל | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
830 |  | Auto Scheduled | אישור ניר בשן | 0.5 days | 03 December 2020 8:00 | 03 December 2020 12:00 | 1 | 829 | 4h | 01.04.BP.01.01.26 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
831 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 08 December 2020 8:00 | 08 December 2020 10:00 | 1 | 830 | 2h | 01.04.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
832 |  | Auto Scheduled | LifeCycle Tasks | 90 days | 20 August 2020 8:00 | 09 December 2020 17:00 | 1 |  | 40h | 01.04.BP.01.02 |  | 5 avi | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
833 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 09 December 2020 8:00 | 09 December 2020 17:00 | 1 | 831 | 0h | 01.04.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
834 |  | Auto Scheduled | טרם החל | 0.63 days | 20 August 2020 8:00 | 20 August 2020 13:00 | 1 |  | 5h | 01.04.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
835 |  | Auto Scheduled | בעבודה | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 834 | 10h | 01.04.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
836 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 10 September 2020 8:00 | 10 September 2020 13:00 | 1 | 835 | 5h | 01.04.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
837 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 836 | 10h | 01.04.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
838 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 837 | 10h | 01.04.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
839 |  | Auto Scheduled | בחתימה | 0 days | 09 December 2020 8:00 | 09 December 2020 8:00 | 1 | 838,833 | 0h | 01.04.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
840 |  | Auto Scheduled | חתום | 0 days | 09 December 2020 8:00 | 09 December 2020 8:00 | 1 | 839 | 0h | 01.04.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
841 |  | Auto Scheduled | 01.04: השקעות ופירוקים.SAP | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.45000000000000001 |  | 210h | 01.04.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
842 |  | Auto Scheduled | מערכת סאפ תאפשר המשך עבודה תקינה בתהליך פירוק והשקעה מתוך הזמנות אחזקה ע"ב אתרי אחסון ב-6100,6200,6300 חדשים שייפתחו | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.47999999999999998 |  | 70h | 01.04.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
843 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.04.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
844 |  | Auto Scheduled | LifeCycle Tasks | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.47999999999999998 |  | 70h | 01.04.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
845 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.04.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
846 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 831 | 20h | 01.04.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
847 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 09 May 2021 8:00 | 11 May 2021 17:00 | 1 |  | 0h | 01.04.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
848 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 May 2021 8:00 | 18 May 2021 15:00 | 0 | 847 | 25h | 01.04.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
849 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 May 2021 15:00 | 19 May 2021 16:00 | 0 | 848 | 10h | 01.04.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
850 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 May 2021 16:00 | 30 May 2021 17:00 | 0 | 849 | 10h | 01.04.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
851 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 May 2021 8:00 | 31 May 2021 13:00 | 0 | 850 | 5h | 01.04.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
852 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 851,845 | 0h | 01.04.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
853 |  | Auto Scheduled | איו שינוי בחוקות ובמיקום החוקות של השקעות ופירוקים ע"פ חוקת המלאי | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.42999999999999999 |  | 70h | 01.04.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
854 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.04.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
855 |  | Auto Scheduled | LifeCycle Tasks | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.42999999999999999 |  | 70h | 01.04.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
856 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.04.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
857 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 831 | 20h | 01.04.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
858 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 11 May 2021 8:00 | 12 May 2021 17:00 | 1 |  | 0h | 01.04.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
859 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 May 2021 8:00 | 19 May 2021 15:00 | 0 | 858 | 25h | 01.04.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
860 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 May 2021 15:00 | 30 May 2021 16:00 | 0 | 859 | 10h | 01.04.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
861 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 May 2021 16:00 | 31 May 2021 17:00 | 0 | 860 | 10h | 01.04.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
862 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 June 2021 8:00 | 01 June 2021 13:00 | 0 | 861 | 5h | 01.04.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
863 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 862,856 | 0h | 01.04.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
864 |  | Auto Scheduled | מערכת סאפ תאפשר המשך עבודה תקינה בתהליך פתיחה, עדכון וסגירת הזמנות אחזקה ע"ב מרכזי עבודה וקבוצות מתכנן חדשות שייפתחו | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.42999999999999999 |  | 70h | 01.04.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
865 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.04.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
866 |  | Auto Scheduled | LifeCycle Tasks | 197.88 days | 09 December 2020 8:00 | 05 September 2021 8:00 | 0.42999999999999999 |  | 70h | 01.04.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
867 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.04.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
868 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 831 | 20h | 01.04.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
869 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 06 May 2021 8:00 | 09 May 2021 17:00 | 1 |  | 0h | 01.04.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
870 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 May 2021 8:00 | 12 May 2021 15:00 | 0 | 869 | 25h | 01.04.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
871 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 May 2021 15:00 | 13 May 2021 16:00 | 0 | 870 | 10h | 01.04.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
872 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 May 2021 16:00 | 18 May 2021 17:00 | 0 | 871 | 10h | 01.04.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
873 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 May 2021 8:00 | 19 May 2021 13:00 | 0 | 872 | 5h | 01.04.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
874 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 873,867 | 0h | 01.04.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
875 |  | Auto Scheduled | 01.05: ויסותים פנימיים | 406.63 days | 30 August 2020 8:00 | 24 February 2022 13:00 | 0.38 |  | 565h | 01.05 | חתום | מוריה | hd | מאור | nan | BP | NA | As Soon As Possible | 3
876 |  | Auto Scheduled | 01.05: ויסותים פנימיים.BP | 103.5 days | 30 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 145h | 01.05.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
877 |  | Auto Scheduled | 01.05: ויסותים פנימיים | 103.5 days | 30 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 145h | 01.05.BP.01 | חתום | מוריה | parent | מאור | nan | BP | NA | As Soon As Possible | 5
878 |  | Auto Scheduled | Sub Tasks | 101.5 days | 30 August 2020 8:00 | 03 January 2021 10:00 | 1 |  | 105h | 01.05.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
879 |  | Auto Scheduled | 23/09: הערות של גלית אדרי | 0.75 days | 17 September 2020 8:00 | 17 September 2020 14:00 | 1 |  | 6h | 01.05.BP.01.01.01 | בוצע |  | MoM |  | גלית אדרי | BP | NA | Must Start On | 7
880 |  | Auto Scheduled | כתיבת מסמך | 2.5 days | 30 August 2020 8:00 | 01 September 2020 10:00 | 1 |  | 20h | 01.05.BP.01.01.20 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
881 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.5 days | 25 September 2020 8:00 | 27 September 2020 12:00 | 1 | 880 | 4h | 01.05.BP.01.01.21 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
882 |  | Auto Scheduled | אישור מקל"ר | 1.38 days | 30 September 2020 8:00 | 01 October 2020 10:00 | 1 | 881 | 11h | 01.05.BP.01.01.22 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
883 |  | Auto Scheduled | אישור אבי | 2.38 days | 14 October 2020 8:00 | 18 October 2020 9:00 | 1 | 882 | 19h | 01.05.BP.01.01.23 | בוצע | אבי | MoM | ואל | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
884 |  | Auto Scheduled | אישור המנהלת | 0.38 days | 09 November 2020 8:00 | 09 November 2020 11:00 | 1 | 883 | 3h | 01.05.BP.01.01.24 | בוצע | סיגל | MoM | ואל | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
885 |  | Auto Scheduled | אישור מפקדת | 0.38 days | 11 November 2020 8:00 | 11 November 2020 11:00 | 1 | 884 | 3h | 01.05.BP.01.01.25 | בוצע | מוריה | MoM | ואל | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
886 |  | Auto Scheduled | אישור חטלו"ג | 0.63 days | 15 November 2020 8:00 | 15 November 2020 13:00 | 1 | 885 | 5h | 01.05.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
887 |  | Auto Scheduled | אישור ניר בשן | 4 days | 19 November 2020 8:00 | 24 November 2020 13:00 | 1 | 886 | 32h | 01.05.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
888 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 887 | 2h | 01.05.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
889 |  | Auto Scheduled | LifeCycle Tasks | 38.25 days | 18 November 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 01.05.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
890 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 888 | 0h | 01.05.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
891 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 01.05.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
892 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 891 | 10h | 01.05.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
893 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 892 | 5h | 01.05.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
894 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 893 | 10h | 01.05.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
895 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 894 | 10h | 01.05.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
896 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 895,890 | 0h | 01.05.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
897 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 896 | 0h | 01.05.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
898 |  | Auto Scheduled | 01.05: ויסותים פנימיים.INT | 304.25 days | 04 January 2021 8:00 | 24 February 2022 13:00 | 7.0000000000000007E-2 |  | 210h | 01.05.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
899 |  | Auto Scheduled | מערכות זכיין וסאפ יאפשרו תיאום קבלה של המלאי | 296.38 days | 04 January 2021 8:00 | 15 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.05.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
900 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
901 |  | Auto Scheduled | LifeCycle Tasks | 296.38 days | 04 January 2021 8:00 | 15 February 2022 13:00 | 0.10000000000000001 |  | 70h | 01.05.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
902 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
903 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 888 | 20h | 01.05.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
904 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 19 January 2022 8:00 | 07 February 2022 17:00 | 0 |  | 0h | 01.05.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
905 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 February 2022 8:00 | 10 February 2022 15:00 | 0 | 904 | 25h | 01.05.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
906 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 February 2022 15:00 | 13 February 2022 16:00 | 0 | 905 | 10h | 01.05.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
907 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 February 2022 16:00 | 14 February 2022 17:00 | 0 | 906 | 10h | 01.05.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
908 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 February 2022 8:00 | 15 February 2022 13:00 | 0 | 907 | 5h | 01.05.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
909 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 15 February 2022 13:00 | 15 February 2022 13:00 | 0 | 908,902 | 0h | 01.05.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
910 |  | Auto Scheduled | מערכת סאפ תעביר את נתוני האספקות ונתוני הויסות שנפתחות למערכת הזכיין למרחבים הרלוונטים | 304.25 days | 04 January 2021 8:00 | 24 February 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.05.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
911 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
912 |  | Auto Scheduled | LifeCycle Tasks | 304.25 days | 04 January 2021 8:00 | 24 February 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.05.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
913 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
914 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 888 | 20h | 01.05.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
915 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 31.5 days | 10 January 2022 8:00 | 16 February 2022 17:00 | 0 |  | 0h | 01.05.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
916 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 February 2022 8:00 | 21 February 2022 15:00 | 0 | 915 | 25h | 01.05.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
917 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 February 2022 15:00 | 22 February 2022 16:00 | 0 | 916 | 10h | 01.05.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
918 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 February 2022 16:00 | 23 February 2022 17:00 | 0 | 917 | 10h | 01.05.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
919 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 February 2022 8:00 | 24 February 2022 13:00 | 0 | 918 | 5h | 01.05.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
920 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 February 2022 13:00 | 24 February 2022 13:00 | 0 | 919,913 | 0h | 01.05.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
921 |  | Auto Scheduled | מערכת סאפ תעביר את נתוני האספקות ונתוני הויסות שנפתחות למערכת הזכיין במרחב הנדרש | 296.38 days | 04 January 2021 8:00 | 15 February 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.05.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
922 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
923 |  | Auto Scheduled | LifeCycle Tasks | 296.38 days | 04 January 2021 8:00 | 15 February 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.05.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
924 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
925 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 888 | 20h | 01.05.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
926 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 30.38 days | 02 January 2022 8:00 | 07 February 2022 17:00 | 0 |  | 0h | 01.05.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
927 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 February 2022 8:00 | 10 February 2022 15:00 | 0 | 926 | 25h | 01.05.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
928 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 February 2022 15:00 | 13 February 2022 16:00 | 0 | 927 | 10h | 01.05.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
929 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 February 2022 16:00 | 14 February 2022 17:00 | 0 | 928 | 10h | 01.05.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
930 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 February 2022 8:00 | 15 February 2022 13:00 | 0 | 929 | 5h | 01.05.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
931 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 15 February 2022 13:00 | 15 February 2022 13:00 | 0 | 930,924 | 0h | 01.05.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
932 |  | Auto Scheduled | 01.05: ויסותים פנימיים.SAP | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.60999999999999999 |  | 210h | 01.05.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
933 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת הזמנת העברה מסוג 08 עם אספקה אוטומטית שנפתחת מאתר מספק לאתר מקבל | 190.63 days | 04 January 2021 8:00 | 06 October 2021 13:00 | 0.80000000000000004 |  | 70h | 01.05.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
934 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
935 |  | Auto Scheduled | LifeCycle Tasks | 190.63 days | 04 January 2021 8:00 | 06 October 2021 13:00 | 0.80000000000000004 |  | 70h | 01.05.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
936 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
937 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 888 | 20h | 01.05.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
938 |  | Auto Scheduled | יישום ופיתוח סאפ | 22.5 days | 16 August 2021 8:00 | 19 September 2021 17:00 | 1 |  | 0h | 01.05.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
939 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 September 2021 8:00 | 03 October 2021 15:00 | 0 | 938 | 25h | 01.05.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
940 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 October 2021 15:00 | 04 October 2021 16:00 | 0 | 939 | 10h | 01.05.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
941 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 October 2021 16:00 | 05 October 2021 17:00 | 0 | 940 | 10h | 01.05.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
942 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 October 2021 8:00 | 06 October 2021 13:00 | 0 | 941 | 5h | 01.05.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
943 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 October 2021 13:00 | 06 October 2021 13:00 | 0 | 942,936 | 0h | 01.05.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
944 |  | Auto Scheduled | מערכת סאפ תאפשר ויסות מלאים בין מרה"ס למרת"ח | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.10000000000000001 |  | 70h | 01.05.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
945 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
946 |  | Auto Scheduled | LifeCycle Tasks | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.10000000000000001 |  | 70h | 01.05.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
947 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
948 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 888 | 20h | 01.05.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
949 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 05 September 2021 8:00 | 11 October 2021 17:00 | 0 |  | 0h | 01.05.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
950 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 October 2021 8:00 | 14 October 2021 15:00 | 0 | 949 | 25h | 01.05.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
951 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 October 2021 15:00 | 17 October 2021 16:00 | 0 | 950 | 10h | 01.05.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
952 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 October 2021 16:00 | 18 October 2021 17:00 | 0 | 951 | 10h | 01.05.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
953 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 October 2021 8:00 | 19 October 2021 13:00 | 0 | 952 | 5h | 01.05.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
954 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 October 2021 13:00 | 19 October 2021 13:00 | 0 | 953,947 | 0h | 01.05.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
955 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת הזמנת העברה מסוג 07 עם אספקה אוטומטית שנפתחת מאתר מספק לאתר מקבל | 180.5 days | 04 January 2021 8:00 | 12 September 2021 13:00 | 0.81000000000000005 |  | 70h | 01.05.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
956 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
957 |  | Auto Scheduled | LifeCycle Tasks | 180.5 days | 04 January 2021 8:00 | 12 September 2021 13:00 | 0.81000000000000005 |  | 70h | 01.05.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
958 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.05.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
959 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 888 | 20h | 01.05.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
960 |  | Auto Scheduled | יישום ופיתוח סאפ | 24.75 days | 01 August 2021 8:00 | 30 August 2021 17:00 | 1 |  | 0h | 01.05.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
961 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 31 August 2021 8:00 | 02 September 2021 15:00 | 0 | 960 | 25h | 01.05.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
962 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 02 September 2021 15:00 | 05 September 2021 16:00 | 0 | 961 | 10h | 01.05.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
963 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 05 September 2021 16:00 | 09 September 2021 17:00 | 0 | 962 | 10h | 01.05.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
964 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 September 2021 8:00 | 12 September 2021 13:00 | 0 | 963 | 5h | 01.05.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
965 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 12 September 2021 13:00 | 12 September 2021 13:00 | 0 | 964,958 | 0h | 01.05.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
966 |  | Auto Scheduled | 01.06: אחסנה | 412.25 days | 20 July 2020 8:00 | 23 January 2022 13:00 | 0.28000000000000003 |  | 799h | 01.06 | חתום | מוריה | hd | מורן | nan | BP | NA | As Soon As Possible | 3
967 |  | Auto Scheduled | 01.06: אחסנה.BP | 132.88 days | 20 July 2020 8:00 | 31 December 2020 9:00 | 1 |  | 167h | 01.06.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
968 |  | Auto Scheduled | 01.06: אחסנה | 132.88 days | 20 July 2020 8:00 | 31 December 2020 9:00 | 1 |  | 167h | 01.06.BP.01 | חתום | מוריה | parent | מורן | nan | BP | NA | As Soon As Possible | 5
969 |  | Auto Scheduled | Sub Tasks | 130.75 days | 20 July 2020 8:00 | 29 December 2020 10:00 | 1 |  | 127h | 01.06.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
970 |  | Auto Scheduled | נדרש להתייחס שיהיו סטטוסים נוספים ל-10 כושרים (כגון ספירה, מלאי לפרויקט, מלאי חסום לחירום וכו')--יש להוסיף ולהתייחס למנפ"ר לאפשר לו לבצע באופן ידני בחירת פריט מכושר מסוים בזמן יצירת הדרישה / אישור הדרישה. | 0.13 days | 06 September 2020 8:00 | 06 September 2020 9:00 | 1 |  | 1h | 01.06.BP.01.01.01 | בוצע | מאיה | MoM | עינת | שרון רחמים | BP | NA | Must Start On | 7
971 |  | Auto Scheduled | כתיבת מסמך | 4.5 days | 20 July 2020 8:00 | 23 July 2020 17:00 | 1 |  | 36h | 01.06.BP.01.01.20 | בוצע | אבי | MoM | ואל | 2020-09-07 00:00:00 | BP | NA | As Soon As Possible | 7
972 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.88 days | 07 September 2020 8:00 | 07 September 2020 15:00 | 1 | 971 | 7h | 01.06.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
973 |  | Auto Scheduled | אישור אבי | 1.5 days | 15 September 2020 8:00 | 16 September 2020 11:00 | 1 | 972 | 12h | 01.06.BP.01.01.22 | בוצע | אבי | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
974 |  | Auto Scheduled | אישור מקל"ר | 1.38 days | 30 September 2020 8:00 | 01 October 2020 10:00 | 1 | 973 | 11h | 01.06.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
975 |  | Auto Scheduled | אישור מפקדת | 1.88 days | 14 October 2020 8:00 | 15 October 2020 14:00 | 1 | 974 | 15h | 01.06.BP.01.01.24 | בוצע | ואל | MoM | ואל | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
976 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 03 November 2020 8:00 | 03 November 2020 12:00 | 1 | 975 | 4h | 01.06.BP.01.01.25 | בוצע | סיגל | MoM | 2020-10-18 00:00:00 | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
977 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 08 November 2020 8:00 | 08 November 2020 9:00 | 1 | 976 | 1h | 01.06.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
978 |  | Auto Scheduled | אישור ניר בשן | 4.75 days | 08 November 2020 8:00 | 12 November 2020 10:00 | 1 | 977 | 38h | 01.06.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
979 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 29 December 2020 8:00 | 29 December 2020 10:00 | 1 | 978 | 2h | 01.06.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
980 |  | Auto Scheduled | LifeCycle Tasks | 35 days | 18 November 2020 8:00 | 31 December 2020 9:00 | 1 |  | 40h | 01.06.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
981 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 30 December 2020 8:00 | 30 December 2020 17:00 | 1 | 979 | 0h | 01.06.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
982 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 01.06.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
983 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 982 | 10h | 01.06.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
984 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 983 | 5h | 01.06.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
985 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 984 | 10h | 01.06.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
986 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 985 | 10h | 01.06.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
987 |  | Auto Scheduled | בחתימה | 0 days | 30 December 2020 8:00 | 30 December 2020 8:00 | 1 | 986,981 | 0h | 01.06.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
988 |  | Auto Scheduled | חתום | 0 days | 30 December 2020 8:00 | 30 December 2020 8:00 | 1 | 987 | 0h | 01.06.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
989 |  | Auto Scheduled | 01.06: אחסנה.INT | 352.63 days | 01 October 2020 8:00 | 23 January 2022 13:00 | 0.19 |  | 142h | 01.06.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
990 |  | Auto Scheduled | מערכת סאפ תשלח שדר למערכת זכיין עם נתוני המלאי הנדרשים לחסימה,לשחרור מק"ט, כמות וכושר, כולל סיבת חסימה. | 352.63 days | 01 October 2020 8:00 | 23 January 2022 13:00 | 0.17999999999999999 |  | 72h | 01.06.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
991 |  | Auto Scheduled | Sub Tasks | 0.13 days | 01 October 2020 8:00 | 01 October 2020 9:00 | 1 |  | 2h | 01.06.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
992 |  | Auto Scheduled | נדרש לבחון מול הזכיין חסימה אוטומטית | 0.13 days | 01 October 2020 8:00 | 01 October 2020 9:00 | 1 |  | 1h | 01.06.INT.01.01.01 | בוצע | ואל | MoM | ואל | BP | WMS | NA | Must Start On | 7
993 |  | Auto Scheduled | מע’ זכיין מובילה מחסן מלאי באחריות זכיין שיקוף חסימת המלאי במע' SAP נדרש להחליט באיזה רמה יסוכם בדיון מבנה ארגוני (אתר / אתר אחסון) | 0.13 days | 01 October 2020 8:00 | 01 October 2020 9:00 | 1 |  | 1h | 01.06.INT.01.01.02 | בוצע | ואל | MoM | ואל | BP | INT | NA | As Soon As Possible | 7
994 |  | Auto Scheduled | LifeCycle Tasks | 352.63 days | 01 October 2020 8:00 | 23 January 2022 13:00 | 0.17000000000000001 |  | 70h | 01.06.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
995 |  | Auto Scheduled | סיום משימות משנה לממשק | 1.13 days | 01 October 2020 8:00 | 01 October 2020 17:00 | 1 | 993 | 0h | 01.06.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
996 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
997 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 11.25 days | 02 January 2022 8:00 | 13 January 2022 17:00 | 0 |  | 0h | 01.06.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
998 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 January 2022 8:00 | 18 January 2022 15:00 | 0 | 997 | 25h | 01.06.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
999 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 January 2022 15:00 | 19 January 2022 16:00 | 0 | 998 | 10h | 01.06.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1000 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 January 2022 16:00 | 20 January 2022 17:00 | 0 | 999 | 10h | 01.06.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1001 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 January 2022 8:00 | 23 January 2022 13:00 | 0 | 1000 | 5h | 01.06.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1002 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 23 January 2022 13:00 | 23 January 2022 13:00 | 0 | 1001,995 | 0h | 01.06.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1003 |  | Auto Scheduled | מערכת זכיין תשלח שדר למערכת סאפ עם נתוני המלאי שנחסמו כולל סיבת חסימה. | 275 days | 30 December 2020 8:00 | 16 January 2022 13:00 | 0.20999999999999999 |  | 70h | 01.06.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1004 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1005 |  | Auto Scheduled | LifeCycle Tasks | 275 days | 30 December 2020 8:00 | 16 January 2022 13:00 | 0.20999999999999999 |  | 70h | 01.06.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1006 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1007 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1008 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 04 January 2022 8:00 | 06 January 2022 17:00 | 0 |  | 0h | 01.06.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1009 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 January 2022 8:00 | 11 January 2022 15:00 | 0 | 1008 | 25h | 01.06.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1010 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 January 2022 15:00 | 12 January 2022 16:00 | 0 | 1009 | 10h | 01.06.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1011 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 January 2022 16:00 | 13 January 2022 17:00 | 0 | 1010 | 10h | 01.06.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1012 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 January 2022 8:00 | 16 January 2022 13:00 | 0 | 1011 | 5h | 01.06.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1013 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 16 January 2022 13:00 | 16 January 2022 13:00 | 0 | 1012,1006 | 0h | 01.06.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1014 |  | Auto Scheduled | 01.06: אחסנה.SAP | 214.25 days | 30 December 2020 8:00 | 01 November 2021 13:00 | 0.16 |  | 490h | 01.06.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1015 |  | Auto Scheduled | מערכת סאפ תמשיך לאפשר את היכולת חסימה,שחרור בשגרה ובחירום ע"ב טרנ' זי אל קיו02 זי בי אל קיי אס טי קיי ברמת הניהול המלאי | 191.75 days | 30 December 2020 8:00 | 04 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.06.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1016 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1017 |  | Auto Scheduled | LifeCycle Tasks | 191.75 days | 30 December 2020 8:00 | 04 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.06.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1018 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1019 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1020 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 09 September 2021 8:00 | 13 September 2021 17:00 | 0 |  | 0h | 01.06.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1021 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 September 2021 8:00 | 29 September 2021 15:00 | 0 | 1020 | 25h | 01.06.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1022 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 September 2021 15:00 | 30 September 2021 16:00 | 0 | 1021 | 10h | 01.06.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1023 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 September 2021 16:00 | 03 October 2021 17:00 | 0 | 1022 | 10h | 01.06.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1024 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 04 October 2021 8:00 | 04 October 2021 13:00 | 0 | 1023 | 5h | 01.06.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1025 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 04 October 2021 13:00 | 04 October 2021 13:00 | 0 | 1024,1018 | 0h | 01.06.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1026 |  | Auto Scheduled | מערכת סאפ תאפשר את תהליכי האחסנה ובדיקת החוקות כפי שקיים היום | 190.63 days | 30 December 2020 8:00 | 03 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.06.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1027 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1028 |  | Auto Scheduled | LifeCycle Tasks | 190.63 days | 30 December 2020 8:00 | 03 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.06.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1029 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1030 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1031 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 05 September 2021 8:00 | 12 September 2021 17:00 | 0 |  | 0h | 01.06.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1032 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 September 2021 8:00 | 19 September 2021 15:00 | 0 | 1031 | 25h | 01.06.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1033 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 September 2021 15:00 | 29 September 2021 16:00 | 0 | 1032 | 10h | 01.06.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1034 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 September 2021 16:00 | 30 September 2021 17:00 | 0 | 1033 | 10h | 01.06.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1035 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 October 2021 8:00 | 03 October 2021 13:00 | 0 | 1034 | 5h | 01.06.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1036 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 October 2021 13:00 | 03 October 2021 13:00 | 0 | 1035,1029 | 0h | 01.06.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1037 |  | Auto Scheduled | מערכת סאפ תפתח שריון עם נתוני המלאי הנדרשים לחסימה,לשחרור בזכיין. | 207.5 days | 30 December 2020 8:00 | 24 October 2021 13:00 | 0.10000000000000001 |  | 70h | 01.06.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1038 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1039 |  | Auto Scheduled | LifeCycle Tasks | 207.5 days | 30 December 2020 8:00 | 24 October 2021 13:00 | 0.10000000000000001 |  | 70h | 01.06.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1040 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1041 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1042 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 13 September 2021 8:00 | 14 October 2021 17:00 | 0 |  | 0h | 01.06.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1043 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 October 2021 8:00 | 19 October 2021 15:00 | 0 | 1042 | 25h | 01.06.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1044 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 October 2021 15:00 | 20 October 2021 16:00 | 0 | 1043 | 10h | 01.06.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1045 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 October 2021 16:00 | 21 October 2021 17:00 | 0 | 1044 | 10h | 01.06.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1046 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 October 2021 8:00 | 24 October 2021 13:00 | 0 | 1045 | 5h | 01.06.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1047 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 October 2021 13:00 | 24 October 2021 13:00 | 0 | 1046,1040 | 0h | 01.06.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1048 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי סטאטוס המלאי ע"ב הנתונים שהגיעו מזכיין . | 214.25 days | 30 December 2020 8:00 | 01 November 2021 13:00 | 0.13 |  | 70h | 01.06.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1049 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1050 |  | Auto Scheduled | LifeCycle Tasks | 214.25 days | 30 December 2020 8:00 | 01 November 2021 13:00 | 0.13 |  | 70h | 01.06.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1051 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1052 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1053 |  | Auto Scheduled | יישום ופיתוח סאפ | 10.13 days | 12 October 2021 8:00 | 24 October 2021 17:00 | 0 |  | 0h | 01.06.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1054 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 October 2021 8:00 | 27 October 2021 15:00 | 0 | 1053 | 25h | 01.06.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1055 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 October 2021 15:00 | 28 October 2021 16:00 | 0 | 1054 | 10h | 01.06.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1056 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 October 2021 16:00 | 31 October 2021 17:00 | 0 | 1055 | 10h | 01.06.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1057 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 November 2021 8:00 | 01 November 2021 13:00 | 0 | 1056 | 5h | 01.06.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1058 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 01 November 2021 13:00 | 01 November 2021 13:00 | 0 | 1057,1051 | 0h | 01.06.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1059 |  | Auto Scheduled | קיסטום סיבות לתנועה 977,978 על פי סיבות החסימה שברשימת קודי הסיבות המאוחד. | 208.63 days | 30 December 2020 8:00 | 25 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.06.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1060 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1061 |  | Auto Scheduled | LifeCycle Tasks | 208.63 days | 30 December 2020 8:00 | 25 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.06.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1062 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1063 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1064 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 14 October 2021 8:00 | 17 October 2021 17:00 | 0 |  | 0h | 01.06.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1065 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 October 2021 8:00 | 20 October 2021 15:00 | 0 | 1064 | 25h | 01.06.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1066 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 October 2021 15:00 | 21 October 2021 16:00 | 0 | 1065 | 10h | 01.06.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1067 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 October 2021 16:00 | 24 October 2021 17:00 | 0 | 1066 | 10h | 01.06.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1068 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 October 2021 8:00 | 25 October 2021 13:00 | 0 | 1067 | 5h | 01.06.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1069 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 October 2021 13:00 | 25 October 2021 13:00 | 0 | 1068,1062 | 0h | 01.06.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1070 |  | Auto Scheduled | תחזוק חוקת הרשאות ב-סאפ לבע"ת צבאיים לביצוע הפעולה לחסימה ב-זכיין | 214.25 days | 30 December 2020 8:00 | 01 November 2021 13:00 | 0.16 |  | 70h | 01.06.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1071 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1072 |  | Auto Scheduled | LifeCycle Tasks | 214.25 days | 30 December 2020 8:00 | 01 November 2021 13:00 | 0.16 |  | 70h | 01.06.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1073 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1074 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1075 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 17 October 2021 8:00 | 24 October 2021 17:00 | 0 |  | 0h | 01.06.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1076 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 October 2021 8:00 | 27 October 2021 15:00 | 0 | 1075 | 25h | 01.06.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1077 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 October 2021 15:00 | 28 October 2021 16:00 | 0 | 1076 | 10h | 01.06.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1078 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 October 2021 16:00 | 31 October 2021 17:00 | 0 | 1077 | 10h | 01.06.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1079 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 November 2021 8:00 | 01 November 2021 13:00 | 0 | 1078 | 5h | 01.06.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1080 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 01 November 2021 13:00 | 01 November 2021 13:00 | 0 | 1079,1073 | 0h | 01.06.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1081 |  | Auto Scheduled | ביצוע הפעולה ב-סאפ תתבצע ע"ב הרשאות ייעודיות לבע"ת ע"י אוכלוסיית אנשים ספציפית שתקבע בהמשך דוגמא הנחיית מנפ"ר. | 195.13 days | 30 December 2020 8:00 | 07 October 2021 13:00 | 0.17000000000000001 |  | 70h | 01.06.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1082 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1083 |  | Auto Scheduled | LifeCycle Tasks | 195.13 days | 30 December 2020 8:00 | 07 October 2021 13:00 | 0.17000000000000001 |  | 70h | 01.06.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1084 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.06.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1085 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 30 December 2020 8:00 | 03 January 2021 10:00 | 1 | 979 | 20h | 01.06.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1086 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 12 September 2021 8:00 | 29 September 2021 17:00 | 0 |  | 0h | 01.06.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1087 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 30 September 2021 8:00 | 04 October 2021 15:00 | 0 | 1086 | 25h | 01.06.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1088 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 04 October 2021 15:00 | 05 October 2021 16:00 | 0 | 1087 | 10h | 01.06.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1089 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 05 October 2021 16:00 | 06 October 2021 17:00 | 0 | 1088 | 10h | 01.06.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1090 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 October 2021 8:00 | 07 October 2021 13:00 | 0 | 1089 | 5h | 01.06.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1091 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 07 October 2021 13:00 | 07 October 2021 13:00 | 0 | 1090,1084 | 0h | 01.06.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1092 |  | Auto Scheduled | 01.07: חוקת המלאי | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 200h | 01.07 | חתום | מוריה | hd | עינת | nan | BP | NA | As Soon As Possible | 3
1093 |  | Auto Scheduled | 01.07: חוקת המלאי.BP | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 200h | 01.07.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1094 |  | Auto Scheduled | 01.07: חוקת המלאי | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 200h | 01.07.BP.01 | חתום | מוריה | parent | עינת | nan | BP | NA | As Soon As Possible | 5
1095 |  | Auto Scheduled | Sub Tasks | 125 days | 24 September 2020 8:00 | 28 February 2021 9:00 | 1 |  | 160h | 01.07.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1096 |  | Auto Scheduled | כתיבת מסמך | 7 days | 24 September 2020 8:00 | 04 October 2020 10:00 | 1 |  | 56h | 01.07.BP.01.01.20 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | Must Start On | 7
1097 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.5 days | 10 December 2020 8:00 | 13 December 2020 11:00 | 1 | 1096 | 12h | 01.07.BP.01.01.21 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1098 |  | Auto Scheduled | אישור אבי | 5.75 days | 27 December 2020 8:00 | 03 January 2021 9:00 | 1 | 1097 | 46h | 01.07.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1099 |  | Auto Scheduled | אישור המנהלת | 0 days | 31 December 2020 17:00 | 31 December 2020 17:00 | 1 | 1098 | 0h | 01.07.BP.01.01.23 | בוצע | סיגל | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1100 |  | Auto Scheduled | אישור מפקדת | 5.25 days | 31 December 2020 8:00 | 06 January 2021 14:00 | 1 | 1099 | 42h | 01.07.BP.01.01.24 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1101 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 28 February 2021 8:00 | 28 February 2021 9:00 | 1 | 1100 | 1h | 01.07.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1102 |  | Auto Scheduled | אישור מקל"ר | 0.13 days | 28 February 2021 8:00 | 28 February 2021 9:00 | 1 | 1101 | 1h | 01.07.BP.01.01.26 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1103 |  | Auto Scheduled | אישור ניר בשן | 0.13 days | 28 February 2021 8:00 | 28 February 2021 9:00 | 1 | 1102 | 1h | 01.07.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1104 |  | Auto Scheduled | אישור שגיב שרביט | 0.13 days | 28 February 2021 8:00 | 28 February 2021 9:00 | 1 | 1103 | 1h | 01.07.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1105 |  | Auto Scheduled | LifeCycle Tasks | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 40h | 01.07.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1106 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 28 February 2021 8:00 | 28 February 2021 17:00 | 1 | 1104 | 0h | 01.07.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1107 |  | Auto Scheduled | טרם החל | 0.63 days | 20 August 2020 8:00 | 20 August 2020 13:00 | 1 |  | 5h | 01.07.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1108 |  | Auto Scheduled | בעבודה | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 1107 | 10h | 01.07.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1109 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 10 September 2020 8:00 | 10 September 2020 13:00 | 1 | 1108 | 5h | 01.07.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1110 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 1109 | 10h | 01.07.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1111 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 1110 | 10h | 01.07.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1112 |  | Auto Scheduled | בחתימה | 0 days | 28 February 2021 8:00 | 28 February 2021 8:00 | 1 | 1111,1106 | 0h | 01.07.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1113 |  | Auto Scheduled | חתום | 0 days | 28 February 2021 8:00 | 28 February 2021 8:00 | 1 | 1112 | 0h | 01.07.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1114 |  | Auto Scheduled | 01.09: 1003 | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 175h | 01.09 | חתום | מוריה | hd | מורן | nan | BP | NA | As Soon As Possible | 3
1115 |  | Auto Scheduled | 01.09: 1003.BP | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 175h | 01.09.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1116 |  | Auto Scheduled | 01.09: 1003 | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 175h | 01.09.BP.01 | חתום | מוריה | parent | מורן | nan | BP | NA | As Soon As Possible | 5
1117 |  | Auto Scheduled | Sub Tasks | 87.25 days | 31 August 2020 8:00 | 16 December 2020 13:00 | 1 |  | 135h | 01.09.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1118 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 31 August 2020 8:00 | 01 September 2020 10:00 | 1 |  | 11h | 01.09.BP.01.01.20 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | Must Start On | 7
1119 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.38 days | 17 September 2020 8:00 | 20 September 2020 10:00 | 1 |  | 11h | 01.09.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1120 |  | Auto Scheduled | אישור מקל"ר | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 1119 | 10h | 01.09.BP.01.01.22 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1121 |  | Auto Scheduled | אישור אבי | 1.38 days | 14 October 2020 8:00 | 15 October 2020 10:00 | 1 | 1120 | 11h | 01.09.BP.01.01.23 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1122 |  | Auto Scheduled | אישור המנהלת | 0.38 days | 28 October 2020 8:00 | 28 October 2020 11:00 | 1 | 1121 | 3h | 01.09.BP.01.01.24 | בוצע | ואל | MoM | ואל | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1123 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 01 November 2020 8:00 | 01 November 2020 10:00 | 1 | 1122 | 2h | 01.09.BP.01.01.25 | בוצע | ואל | MoM | ואל | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1124 |  | Auto Scheduled | אישור חטלו"ג | 0.63 days | 02 November 2020 8:00 | 02 November 2020 13:00 | 1 | 1123 | 5h | 01.09.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1125 |  | Auto Scheduled | אישור שגיב שרביט | 2.88 days | 08 November 2020 8:00 | 10 November 2020 13:00 | 1 | 1124 | 23h | 01.09.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1126 |  | Auto Scheduled | אישור ניר בשן | 7.38 days | 08 December 2020 8:00 | 16 December 2020 13:00 | 1 | 1125 | 59h | 01.09.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1127 |  | Auto Scheduled | LifeCycle Tasks | 154.13 days | 20 August 2020 8:00 | 28 February 2021 17:00 | 1 |  | 40h | 01.09.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1128 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 28 February 2021 8:00 | 28 February 2021 17:00 | 1 | 1126 | 0h | 01.09.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1129 |  | Auto Scheduled | טרם החל | 0.63 days | 20 August 2020 8:00 | 20 August 2020 13:00 | 1 |  | 5h | 01.09.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1130 |  | Auto Scheduled | בעבודה | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 1129 | 10h | 01.09.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1131 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 10 September 2020 8:00 | 10 September 2020 13:00 | 1 | 1130 | 5h | 01.09.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1132 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 1131 | 10h | 01.09.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1133 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 1132 | 10h | 01.09.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1134 |  | Auto Scheduled | בחתימה | 0 days | 08 December 2020 8:00 | 08 December 2020 8:00 | 1 | 1133,1128 | 0h | 01.09.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1135 |  | Auto Scheduled | חתום | 0 days | 08 December 2020 8:00 | 08 December 2020 8:00 | 1 | 1134 | 0h | 01.09.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1136 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים | 456.13 days | 12 August 2020 8:00 | 11 April 2022 13:00 | 0.39000000000000001 |  | 1,839h | 01.11 | חתום | מאיה | hd | עינת | nan | BP | NA | As Soon As Possible | 3
1137 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.BP | 114.75 days | 12 August 2020 8:00 | 31 December 2020 17:00 | 1 |  | 159h | 01.11.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1138 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים | 114.75 days | 12 August 2020 8:00 | 31 December 2020 17:00 | 1 |  | 159h | 01.11.BP.01 | חתום | מאיה | parent | עינת | nan | BP | NA | As Soon As Possible | 5
1139 |  | Auto Scheduled | Sub Tasks | 113.75 days | 12 August 2020 8:00 | 31 December 2020 9:00 | 1 |  | 119h | 01.11.BP.01.01 |  | מאיה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1140 |  | Auto Scheduled | יש להגדיר כיצד יתבצע ספירת פריטים מיוחדים | 0.13 days | 18 August 2020 8:00 | 18 August 2020 9:00 | 1 |  | 1h | 01.11.BP.01.01.01 | בוצע | עינת | MoM | עינת | BP | BP | NA | Must Start On | 7
1141 |  | Auto Scheduled | יש להתאים בSAP את תדירות הספירה | 0.13 days | 19 August 2020 8:00 | 19 August 2020 9:00 | 1 |  | 1h | 01.11.BP.01.01.02 | בוצע | עינת | MoM | עינת | BP | BP | NA | As Soon As Possible | 7
1142 |  | Auto Scheduled | 1. טענה: הזכיין לא יכול לדווח על אי הילום מבלי להשלים /להיקנס--2. ממולץ להוסיף סטטוס נוסף במערכת הSAP לפני הסטטוס המומלץ לסגירת ההפרש --3. כיום בודקים האם פריט שנמצא בחוסר מול המרחב ובמידה ולא נמצא בודקים מול כל המרחבים, האם לזכיין תהיה האפשרות לחפש מלאי | 0.13 days | 25 August 2020 8:00 | 25 August 2020 9:00 | 1 |  | 1h | 01.11.BP.01.01.03 | בוצע | עינת | MoM | עינת | שרון רחמים | BP | NA | As Soon As Possible | 7
1143 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 12 August 2020 8:00 | 13 August 2020 10:00 | 1 |  | 11h | 01.11.BP.01.01.20 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1144 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.38 days | 18 August 2020 8:00 | 19 August 2020 10:00 | 1 |  | 11h | 01.11.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1145 |  | Auto Scheduled | אישור אבי | 1.25 days | 01 September 2020 8:00 | 02 September 2020 9:00 | 1 | 1144 | 10h | 01.11.BP.01.01.22 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1146 |  | Auto Scheduled | אישור מפקדת | 0.5 days | 14 September 2020 8:00 | 14 September 2020 12:00 | 1 | 1145 | 4h | 01.11.BP.01.01.23 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1147 |  | Auto Scheduled | אישור מקל"ר | 2.75 days | 17 September 2020 8:00 | 21 September 2020 12:00 | 1 | 1146 | 22h | 01.11.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1148 |  | Auto Scheduled | אישור חטלו"ג | 2 days | 18 October 2020 8:00 | 19 October 2020 15:00 | 1 | 1147 | 16h | 01.11.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1149 |  | Auto Scheduled | אישור המנהלת | 1.75 days | 08 November 2020 8:00 | 09 November 2020 13:00 | 1 | 1148 | 14h | 01.11.BP.01.01.26 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1150 |  | Auto Scheduled | אישור ניר בשן | 3.38 days | 25 November 2020 8:00 | 29 November 2020 17:00 | 1 | 1149 | 27h | 01.11.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1151 |  | Auto Scheduled | אישור שגיב שרביט | 0.13 days | 31 December 2020 8:00 | 31 December 2020 9:00 | 1 | 1150 | 1h | 01.11.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1152 |  | Auto Scheduled | LifeCycle Tasks | 36 days | 18 November 2020 8:00 | 31 December 2020 17:00 | 1 |  | 40h | 01.11.BP.01.02 |  | מאיה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1153 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 31 December 2020 8:00 | 31 December 2020 17:00 | 1 | 1151 | 0h | 01.11.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1154 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 01.11.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1155 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 1154 | 10h | 01.11.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1156 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 1155 | 5h | 01.11.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1157 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 1156 | 10h | 01.11.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1158 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 1157 | 10h | 01.11.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1159 |  | Auto Scheduled | בחתימה | 0 days | 31 December 2020 8:00 | 31 December 2020 8:00 | 1 | 1158,1153 | 0h | 01.11.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1160 |  | Auto Scheduled | חתום | 0 days | 31 December 2020 8:00 | 31 December 2020 8:00 | 1 | 1159 | 0h | 01.11.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1161 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.INT | 342.5 days | 31 December 2020 8:00 | 11 April 2022 13:00 | 8.0000000000000002E-2 |  | 700h | 01.11.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1162 |  | Auto Scheduled | מערכת סאפ תדרש להעביר את הפריטים המיוחדים מקטים עבורם תדרש לפתוח ולבצע ספירה בזכיין | 308.75 days | 31 December 2020 8:00 | 28 February 2022 13:00 | 0.16 |  | 70h | 01.11.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1163 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1164 |  | Auto Scheduled | LifeCycle Tasks | 308.75 days | 31 December 2020 8:00 | 28 February 2022 13:00 | 0.16 |  | 70h | 01.11.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1165 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1166 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1167 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 13 February 2022 8:00 | 20 February 2022 17:00 | 0 |  | 0h | 01.11.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1168 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 February 2022 8:00 | 23 February 2022 15:00 | 0 | 1167 | 25h | 01.11.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1169 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 February 2022 15:00 | 24 February 2022 16:00 | 0 | 1168 | 10h | 01.11.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1170 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 February 2022 16:00 | 27 February 2022 17:00 | 0 | 1169 | 10h | 01.11.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1171 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 February 2022 8:00 | 28 February 2022 13:00 | 0 | 1170 | 5h | 01.11.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1172 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 28 February 2022 13:00 | 28 February 2022 13:00 | 0 | 1171,1165 | 0h | 01.11.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1173 |  | Auto Scheduled | מערכת הפי או די תתמוך בשליחת שדר אודות סטטוס האספקה למערכת הסאפ לטובת הפקת דוחות. | 332.38 days | 31 December 2020 8:00 | 29 March 2022 13:00 | 2.9999999999999999E-2 |  | 70h | 01.11.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1174 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1175 |  | Auto Scheduled | LifeCycle Tasks | 332.38 days | 31 December 2020 8:00 | 29 March 2022 13:00 | 2.9999999999999999E-2 |  | 70h | 01.11.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1176 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1177 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1178 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 64.13 days | 02 January 2022 8:00 | 21 March 2022 17:00 | 0 |  | 0h | 01.11.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1179 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 March 2022 8:00 | 24 March 2022 15:00 | 0 | 1178 | 25h | 01.11.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1180 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 March 2022 15:00 | 27 March 2022 16:00 | 0 | 1179 | 10h | 01.11.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1181 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 March 2022 16:00 | 28 March 2022 17:00 | 0 | 1180 | 10h | 01.11.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1182 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 March 2022 8:00 | 29 March 2022 13:00 | 0 | 1181 | 5h | 01.11.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1183 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 29 March 2022 13:00 | 29 March 2022 13:00 | 0 | 1182,1176 | 0h | 01.11.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1184 |  | Auto Scheduled | מערכת הזכיין תתמוך בביצוע ניפוק המלאי ושידור הפעולה למערכת הסאפ. | 316.63 days | 31 December 2020 8:00 | 09 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1185 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1186 |  | Auto Scheduled | LifeCycle Tasks | 316.63 days | 31 December 2020 8:00 | 09 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1187 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1188 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1189 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 24.75 days | 31 January 2022 8:00 | 01 March 2022 17:00 | 0 |  | 0h | 01.11.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1190 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 March 2022 8:00 | 06 March 2022 15:00 | 0 | 1189 | 25h | 01.11.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1191 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 March 2022 15:00 | 07 March 2022 16:00 | 0 | 1190 | 10h | 01.11.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1192 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 March 2022 16:00 | 08 March 2022 17:00 | 0 | 1191 | 10h | 01.11.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1193 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 March 2022 8:00 | 09 March 2022 13:00 | 0 | 1192 | 5h | 01.11.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1194 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 09 March 2022 13:00 | 09 March 2022 13:00 | 0 | 1193,1187 | 0h | 01.11.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1195 |  | Auto Scheduled | מערכת הזכיין תאפשר ביצוע פעולת רוורס לתנועת ניפוק ושליחת שדר למערכת הסאפ כאשר משלוח יצא מהמרה"ס אבל מסיבה כלשהי לא הגיע ליחידה, והמשאית חזרה עם הציוד למחסן הפצה. | 327.88 days | 31 December 2020 8:00 | 23 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1196 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1197 |  | Auto Scheduled | LifeCycle Tasks | 327.88 days | 31 December 2020 8:00 | 23 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1198 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1199 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1200 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 24.75 days | 14 February 2022 8:00 | 15 March 2022 17:00 | 0 |  | 0h | 01.11.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1201 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 March 2022 8:00 | 20 March 2022 15:00 | 0 | 1200 | 25h | 01.11.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1202 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 March 2022 15:00 | 21 March 2022 16:00 | 0 | 1201 | 10h | 01.11.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1203 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 March 2022 16:00 | 22 March 2022 17:00 | 0 | 1202 | 10h | 01.11.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1204 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 March 2022 8:00 | 23 March 2022 13:00 | 0 | 1203 | 5h | 01.11.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1205 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 23 March 2022 13:00 | 23 March 2022 13:00 | 0 | 1204,1198 | 0h | 01.11.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1206 |  | Auto Scheduled | מערכת הזכיין תשלח בממשק למערכת הסאפ את תיקון המלאי שבוצע ובקישור לאספקה | 334.63 days | 31 December 2020 8:00 | 31 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1207 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1208 |  | Auto Scheduled | LifeCycle Tasks | 334.63 days | 31 December 2020 8:00 | 31 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1209 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1210 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1211 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 25.88 days | 21 February 2022 8:00 | 23 March 2022 17:00 | 0 |  | 0h | 01.11.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1212 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 March 2022 8:00 | 28 March 2022 15:00 | 0 | 1211 | 25h | 01.11.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1213 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 March 2022 15:00 | 29 March 2022 16:00 | 0 | 1212 | 10h | 01.11.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1214 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 March 2022 16:00 | 30 March 2022 17:00 | 0 | 1213 | 10h | 01.11.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1215 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 March 2022 8:00 | 31 March 2022 13:00 | 0 | 1214 | 5h | 01.11.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1216 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 31 March 2022 13:00 | 31 March 2022 13:00 | 0 | 1215,1209 | 0h | 01.11.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1217 |  | Auto Scheduled | מערכת הזכיין ומערכת הסאפ נדרשות לאפשר ניפוק בדחיפה וניפוק במשיכה. | 342.5 days | 31 December 2020 8:00 | 11 April 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 01.11.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1218 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1219 |  | Auto Scheduled | LifeCycle Tasks | 342.5 days | 31 December 2020 8:00 | 11 April 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 01.11.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1220 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1221 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1222 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 23.63 days | 06 March 2022 8:00 | 03 April 2022 17:00 | 0 |  | 0h | 01.11.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1223 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 April 2022 8:00 | 06 April 2022 15:00 | 0 | 1222 | 25h | 01.11.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1224 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 April 2022 15:00 | 07 April 2022 16:00 | 0 | 1223 | 10h | 01.11.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1225 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 April 2022 16:00 | 10 April 2022 17:00 | 0 | 1224 | 10h | 01.11.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1226 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 April 2022 8:00 | 11 April 2022 13:00 | 0 | 1225 | 5h | 01.11.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1227 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 11 April 2022 13:00 | 11 April 2022 13:00 | 0 | 1226,1220 | 0h | 01.11.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1228 |  | Auto Scheduled | מערכת זכיין ומערכת סאפ יאפשרו העברת שדרים בכדי לעדכן על שינויים במלאי בעקבות ספירה ומציאת הפרש | 306.5 days | 31 December 2020 8:00 | 24 February 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.11.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1229 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1230 |  | Auto Scheduled | LifeCycle Tasks | 306.5 days | 31 December 2020 8:00 | 24 February 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.11.INT.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1231 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.07.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1232 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.07.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1233 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 38.25 days | 02 January 2022 8:00 | 16 February 2022 17:00 | 0 |  | 0h | 01.11.INT.07.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1234 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 February 2022 8:00 | 21 February 2022 15:00 | 0 | 1233 | 25h | 01.11.INT.07.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1235 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 February 2022 15:00 | 22 February 2022 16:00 | 0 | 1234 | 10h | 01.11.INT.07.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1236 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 February 2022 16:00 | 23 February 2022 17:00 | 0 | 1235 | 10h | 01.11.INT.07.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1237 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 February 2022 8:00 | 24 February 2022 13:00 | 0 | 1236 | 5h | 01.11.INT.07.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1238 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 February 2022 13:00 | 24 February 2022 13:00 | 0 | 1237,1231 | 0h | 01.11.INT.07.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1239 |  | Auto Scheduled | מערכת סאפ ומערכת זכיין יאפשרו העברת שדרים לסיריאלים וסדרות חדשות במלאי | 285.13 days | 31 December 2020 8:00 | 30 January 2022 13:00 | 0.16 |  | 70h | 01.11.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1240 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1241 |  | Auto Scheduled | LifeCycle Tasks | 285.13 days | 31 December 2020 8:00 | 30 January 2022 13:00 | 0.16 |  | 70h | 01.11.INT.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1242 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.08.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1243 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.08.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1244 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 13 January 2022 8:00 | 20 January 2022 17:00 | 0 |  | 0h | 01.11.INT.08.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1245 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 January 2022 8:00 | 25 January 2022 15:00 | 0 | 1244 | 25h | 01.11.INT.08.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1246 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 January 2022 15:00 | 26 January 2022 16:00 | 0 | 1245 | 10h | 01.11.INT.08.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1247 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 January 2022 16:00 | 27 January 2022 17:00 | 0 | 1246 | 10h | 01.11.INT.08.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1248 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 January 2022 8:00 | 30 January 2022 13:00 | 0 | 1247 | 5h | 01.11.INT.08.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1249 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 30 January 2022 13:00 | 30 January 2022 13:00 | 0 | 1248,1242 | 0h | 01.11.INT.08.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1250 |  | Auto Scheduled | מערכת זכיין תאפשר העברת שדרים למערכת סאפ בכדי לעדכן את המלאי בעקבות אי הילום לא חלוט עוד בטרם אישור גורם צבאי במערכת זכיין | 317.75 days | 31 December 2020 8:00 | 10 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.11.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1251 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1252 |  | Auto Scheduled | LifeCycle Tasks | 317.75 days | 31 December 2020 8:00 | 10 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.11.INT.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1253 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.09.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1254 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.09.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1255 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 38.25 days | 16 January 2022 8:00 | 02 March 2022 17:00 | 0 |  | 0h | 01.11.INT.09.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1256 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 March 2022 8:00 | 07 March 2022 15:00 | 0 | 1255 | 25h | 01.11.INT.09.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1257 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 March 2022 15:00 | 08 March 2022 16:00 | 0 | 1256 | 10h | 01.11.INT.09.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1258 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 March 2022 16:00 | 09 March 2022 17:00 | 0 | 1257 | 10h | 01.11.INT.09.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1259 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 March 2022 8:00 | 10 March 2022 13:00 | 0 | 1258 | 5h | 01.11.INT.09.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1260 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 March 2022 13:00 | 10 March 2022 13:00 | 0 | 1259,1253 | 0h | 01.11.INT.09.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1261 |  | Auto Scheduled | מערכת זכיין תאפשר העברת שדרים למערכת סאפ בכדי לעדכן את סטאטוס ההפרשים | 329 days | 31 December 2020 8:00 | 24 March 2022 13:00 | 0.13 |  | 70h | 01.11.INT.10 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1262 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1263 |  | Auto Scheduled | LifeCycle Tasks | 329 days | 31 December 2020 8:00 | 24 March 2022 13:00 | 0.13 |  | 70h | 01.11.INT.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1264 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.INT.10.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1265 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.INT.10.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1266 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 38.25 days | 30 January 2022 8:00 | 16 March 2022 17:00 | 8.9999999999999997E-2 |  | 0h | 01.11.INT.10.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
1267 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 March 2022 8:00 | 21 March 2022 15:00 | 0 | 1266 | 25h | 01.11.INT.10.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1268 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 March 2022 15:00 | 22 March 2022 16:00 | 0 | 1267 | 10h | 01.11.INT.10.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1269 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 March 2022 16:00 | 23 March 2022 17:00 | 0 | 1268 | 10h | 01.11.INT.10.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1270 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 March 2022 8:00 | 24 March 2022 13:00 | 0 | 1269 | 5h | 01.11.INT.10.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1271 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 March 2022 13:00 | 24 March 2022 13:00 | 0 | 1270,1264 | 0h | 01.11.INT.10.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1272 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.SAP | 284 days | 31 December 2020 8:00 | 27 January 2022 13:00 | 0.56999999999999995 |  | 980h | 01.11.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1273 |  | Auto Scheduled | מערכת סאפ תאפשר ביצוע קיזוז ידני וקיזוז אוטומטי לפי החוקות הקיימות | 189.5 days | 31 December 2020 8:00 | 03 October 2021 13:00 | 0.87 |  | 70h | 01.11.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1274 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1275 |  | Auto Scheduled | LifeCycle Tasks | 189.5 days | 31 December 2020 8:00 | 03 October 2021 13:00 | 0.87 |  | 70h | 01.11.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1276 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1277 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1278 |  | Auto Scheduled | יישום ופיתוח סאפ | 84.38 days | 18 May 2021 8:00 | 12 September 2021 17:00 | 0.93000000000000005 |  | 0h | 01.11.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1279 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 September 2021 8:00 | 19 September 2021 15:00 | 0 | 1278 | 25h | 01.11.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1280 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 September 2021 15:00 | 29 September 2021 16:00 | 0 | 1279 | 10h | 01.11.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1281 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 September 2021 16:00 | 30 September 2021 17:00 | 0 | 1280 | 10h | 01.11.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1282 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 October 2021 8:00 | 03 October 2021 13:00 | 0 | 1281 | 5h | 01.11.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1283 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 October 2021 13:00 | 03 October 2021 13:00 | 0 | 1282,1276 | 0h | 01.11.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1284 |  | Auto Scheduled | מערכת הסאפ תתמוך בביצוע ניפוק המלאי. | 204.13 days | 31 December 2020 8:00 | 20 October 2021 13:00 | 0.14000000000000001 |  | 70h | 01.11.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1285 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1286 |  | Auto Scheduled | LifeCycle Tasks | 204.13 days | 31 December 2020 8:00 | 20 October 2021 13:00 | 0.14000000000000001 |  | 70h | 01.11.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1287 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1288 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1289 |  | Auto Scheduled | יישום ופיתוח סאפ | 9 days | 03 October 2021 8:00 | 12 October 2021 17:00 | 0 |  | 0h | 01.11.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1290 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 1289 | 25h | 01.11.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1291 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 1290 | 10h | 01.11.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1292 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 1291 | 10h | 01.11.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1293 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 1292 | 5h | 01.11.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1294 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 1293,1287 | 0h | 01.11.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1295 |  | Auto Scheduled | מערכת הסאפ תאפשר להגדיר סטטוס "מלאי בדרך" לפני קליטתו ביחידה בפועל. | 203 days | 31 December 2020 8:00 | 19 October 2021 13:00 | 0.17000000000000001 |  | 70h | 01.11.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1296 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1297 |  | Auto Scheduled | LifeCycle Tasks | 203 days | 31 December 2020 8:00 | 19 October 2021 13:00 | 0.17000000000000001 |  | 70h | 01.11.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1298 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1299 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1300 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 05 October 2021 8:00 | 11 October 2021 17:00 | 0 |  | 0h | 01.11.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1301 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 October 2021 8:00 | 14 October 2021 15:00 | 0 | 1300 | 25h | 01.11.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1302 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 October 2021 15:00 | 17 October 2021 16:00 | 0 | 1301 | 10h | 01.11.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1303 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 October 2021 16:00 | 18 October 2021 17:00 | 0 | 1302 | 10h | 01.11.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1304 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 October 2021 8:00 | 19 October 2021 13:00 | 0 | 1303 | 5h | 01.11.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1305 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 October 2021 13:00 | 19 October 2021 13:00 | 0 | 1304,1298 | 0h | 01.11.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1306 |  | Auto Scheduled | מערכת הסאפ תאפשר תיקון מלאי המקושר לאספקה בהתאם לשדר שהתקבל ממערכת הזכיין. | 250.25 days | 31 December 2020 8:00 | 16 December 2021 13:00 | 4.0000000000000001E-2 |  | 70h | 01.11.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1307 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1308 |  | Auto Scheduled | LifeCycle Tasks | 250.25 days | 31 December 2020 8:00 | 16 December 2021 13:00 | 4.0000000000000001E-2 |  | 70h | 01.11.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1309 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1310 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1311 |  | Auto Scheduled | יישום ופיתוח סאפ | 50.63 days | 07 October 2021 8:00 | 08 December 2021 17:00 | 0 |  | 0h | 01.11.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1312 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 December 2021 8:00 | 13 December 2021 15:00 | 0 | 1311 | 25h | 01.11.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1313 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 December 2021 15:00 | 14 December 2021 16:00 | 0 | 1312 | 10h | 01.11.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1314 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 December 2021 16:00 | 15 December 2021 17:00 | 0 | 1313 | 10h | 01.11.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1315 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 December 2021 8:00 | 16 December 2021 13:00 | 0 | 1314 | 5h | 01.11.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1316 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 16 December 2021 13:00 | 16 December 2021 13:00 | 0 | 1315,1309 | 0h | 01.11.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1317 |  | Auto Scheduled | מערכת הסאפ תתמוך בזיכוי , חיוב תקציב היחידה בכל טיפול בהפרשים | 267.13 days | 31 December 2020 8:00 | 06 January 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1318 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1319 |  | Auto Scheduled | LifeCycle Tasks | 267.13 days | 31 December 2020 8:00 | 06 January 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.11.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1320 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1321 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1322 |  | Auto Scheduled | יישום ופיתוח סאפ | 28.13 days | 25 November 2021 8:00 | 29 December 2021 17:00 | 0 |  | 0h | 01.11.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1323 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 30 December 2021 8:00 | 03 January 2022 15:00 | 0 | 1322 | 25h | 01.11.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1324 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 January 2022 15:00 | 04 January 2022 16:00 | 0 | 1323 | 10h | 01.11.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1325 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 January 2022 16:00 | 05 January 2022 17:00 | 0 | 1324 | 10h | 01.11.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1326 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 January 2022 8:00 | 06 January 2022 13:00 | 0 | 1325 | 5h | 01.11.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1327 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 January 2022 13:00 | 06 January 2022 13:00 | 0 | 1326,1320 | 0h | 01.11.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1328 |  | Auto Scheduled | מערכת הסאפ תתמוך בעדכון מלאי היחידה לאחר ביצוע קבלת מלאי בדרך . | 261.5 days | 31 December 2020 8:00 | 30 December 2021 13:00 | 0.17000000000000001 |  | 70h | 01.11.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1329 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1330 |  | Auto Scheduled | LifeCycle Tasks | 261.5 days | 31 December 2020 8:00 | 30 December 2021 13:00 | 0.17000000000000001 |  | 70h | 01.11.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1331 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1332 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1333 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 16 December 2021 8:00 | 22 December 2021 17:00 | 0 |  | 0h | 01.11.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1334 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 December 2021 8:00 | 27 December 2021 15:00 | 0 | 1333 | 25h | 01.11.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1335 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 December 2021 15:00 | 28 December 2021 16:00 | 0 | 1334 | 10h | 01.11.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1336 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 December 2021 16:00 | 29 December 2021 17:00 | 0 | 1335 | 10h | 01.11.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1337 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 December 2021 8:00 | 30 December 2021 13:00 | 0 | 1336 | 5h | 01.11.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1338 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 30 December 2021 13:00 | 30 December 2021 13:00 | 0 | 1337,1331 | 0h | 01.11.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1339 |  | Auto Scheduled | מערכת הסאפ תתמוך בקבלת סטאטוס האספקה ממערכת הפי או די. | 277.25 days | 31 December 2020 8:00 | 19 January 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 01.11.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1340 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1341 |  | Auto Scheduled | LifeCycle Tasks | 277.25 days | 31 December 2020 8:00 | 19 January 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 01.11.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1342 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1343 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1344 |  | Auto Scheduled | יישום ופיתוח סאפ | 19.13 days | 20 December 2021 8:00 | 11 January 2022 17:00 | 0 |  | 0h | 01.11.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1345 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 January 2022 8:00 | 16 January 2022 15:00 | 0 | 1344 | 25h | 01.11.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1346 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 16 January 2022 15:00 | 17 January 2022 16:00 | 0 | 1345 | 10h | 01.11.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1347 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 January 2022 16:00 | 18 January 2022 17:00 | 0 | 1346 | 10h | 01.11.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1348 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 January 2022 8:00 | 19 January 2022 13:00 | 0 | 1347 | 5h | 01.11.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1349 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 January 2022 13:00 | 19 January 2022 13:00 | 0 | 1348,1342 | 0h | 01.11.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1350 |  | Auto Scheduled | מערכת סאפ תתמוך באפשרות לעדכן פערים בין הכמות באספקה לכמות בפועל . | 284 days | 31 December 2020 8:00 | 27 January 2022 13:00 | 0.12 |  | 70h | 01.11.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1351 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1352 |  | Auto Scheduled | LifeCycle Tasks | 284 days | 31 December 2020 8:00 | 27 January 2022 13:00 | 0.12 |  | 70h | 01.11.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1353 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1354 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1355 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 05 January 2022 8:00 | 19 January 2022 17:00 | 0 |  | 0h | 01.11.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1356 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 January 2022 8:00 | 24 January 2022 15:00 | 0 | 1355 | 25h | 01.11.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1357 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 January 2022 15:00 | 25 January 2022 16:00 | 0 | 1356 | 10h | 01.11.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1358 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 January 2022 16:00 | 26 January 2022 17:00 | 0 | 1357 | 10h | 01.11.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1359 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 January 2022 8:00 | 27 January 2022 13:00 | 0 | 1358 | 5h | 01.11.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1360 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 27 January 2022 13:00 | 27 January 2022 13:00 | 0 | 1359,1353 | 0h | 01.11.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1361 |  | Auto Scheduled | בדומה לדרג הנפרש נדרש כי יישלח מייל עבור פתיחת אובדן לדרג המטכ"ל ובע"ת רלוונטיים | 179.88 days | 31 December 2020 8:00 | 05 September 2021 8:00 | 0.89000000000000001 |  | 70h | 01.11.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1362 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1363 |  | Auto Scheduled | LifeCycle Tasks | 179.88 days | 31 December 2020 8:00 | 05 September 2021 8:00 | 0.89000000000000001 |  | 70h | 01.11.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1364 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1365 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1366 |  | Auto Scheduled | יישום ופיתוח סאפ | 81 days | 06 May 2021 8:00 | 25 August 2021 17:00 | 0.94999999999999996 |  | 0h | 01.11.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1367 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 26 August 2021 8:00 | 30 August 2021 15:00 | 0 | 1366 | 25h | 01.11.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1368 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 30 August 2021 15:00 | 31 August 2021 16:00 | 0 | 1367 | 10h | 01.11.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1369 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 31 August 2021 16:00 | 01 September 2021 17:00 | 0 | 1368 | 10h | 01.11.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1370 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 September 2021 8:00 | 02 September 2021 13:00 | 0 | 1369 | 5h | 01.11.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1371 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1370,1364 | 0h | 01.11.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1372 |  | Auto Scheduled | שליחת מייל כאשר יש אי הילום לא חלוט עבור פריטים ייעודיים שהמטכ"ל ייקבע | 180.5 days | 31 December 2020 8:00 | 05 September 2021 13:00 | 0.90000000000000002 |  | 70h | 01.11.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1373 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1374 |  | Auto Scheduled | LifeCycle Tasks | 180.5 days | 31 December 2020 8:00 | 05 September 2021 13:00 | 0.90000000000000002 |  | 70h | 01.11.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1375 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1376 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1377 |  | Auto Scheduled | יישום ופיתוח סאפ | 75.38 days | 18 May 2021 8:00 | 26 August 2021 17:00 | 0.96999999999999997 |  | 0h | 01.11.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1378 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 August 2021 8:00 | 31 August 2021 15:00 | 0 | 1377 | 25h | 01.11.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1379 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 31 August 2021 15:00 | 01 September 2021 16:00 | 0 | 1378 | 10h | 01.11.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1380 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 September 2021 16:00 | 02 September 2021 17:00 | 0 | 1379 | 10h | 01.11.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1381 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 0 | 1380 | 5h | 01.11.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1382 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 13:00 | 05 September 2021 13:00 | 0 | 1381,1375 | 0h | 01.11.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1383 |  | Auto Scheduled | מערכת סאפ תאפשר תהליך דיווח אובדנים שהתקבל דרך הפרש ממערכת סאפ או ממערכת זכיין | 179.88 days | 31 December 2020 8:00 | 05 September 2021 8:00 | 0.66000000000000003 |  | 70h | 01.11.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1384 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1385 |  | Auto Scheduled | LifeCycle Tasks | 179.88 days | 31 December 2020 8:00 | 05 September 2021 8:00 | 0.66000000000000003 |  | 70h | 01.11.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1386 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1387 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1388 |  | Auto Scheduled | יישום ופיתוח סאפ | 15.75 days | 12 July 2021 8:00 | 29 July 2021 17:00 | 0.87 |  | 0h | 01.11.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1389 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 August 2021 8:00 | 03 August 2021 15:00 | 0 | 1388 | 25h | 01.11.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1390 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 August 2021 15:00 | 04 August 2021 16:00 | 0 | 1389 | 10h | 01.11.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1391 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 August 2021 16:00 | 05 August 2021 17:00 | 0 | 1390 | 10h | 01.11.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1392 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 08 August 2021 8:00 | 08 August 2021 13:00 | 0 | 1391 | 5h | 01.11.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1393 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1392,1386 | 0h | 01.11.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1394 |  | Auto Scheduled | תנועת המלאי בסאפ יתבצעו בעקבות יצירת מסמך ספירה עבור המק"טים שיש להם הפרש.--מסמך הספירה יקושר למסמכ,י הספירה שנוצרו בזכיין.-- | 196.25 days | 31 December 2020 8:00 | 11 October 2021 13:00 | 0.82999999999999996 |  | 70h | 01.11.SAP.12 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1395 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1396 |  | Auto Scheduled | LifeCycle Tasks | 196.25 days | 31 December 2020 8:00 | 11 October 2021 13:00 | 0.82999999999999996 |  | 70h | 01.11.SAP.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1397 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.12.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1398 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.12.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1399 |  | Auto Scheduled | יישום ופיתוח סאפ | 45 days | 22 July 2021 8:00 | 03 October 2021 17:00 | 0.93000000000000005 |  | 0h | 01.11.SAP.12.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1400 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 October 2021 8:00 | 06 October 2021 15:00 | 0 | 1399 | 25h | 01.11.SAP.12.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1401 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 October 2021 15:00 | 07 October 2021 16:00 | 0 | 1400 | 10h | 01.11.SAP.12.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1402 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 October 2021 16:00 | 10 October 2021 17:00 | 0 | 1401 | 10h | 01.11.SAP.12.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1403 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 October 2021 8:00 | 11 October 2021 13:00 | 0 | 1402 | 5h | 01.11.SAP.12.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1404 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 11 October 2021 13:00 | 11 October 2021 13:00 | 0 | 1403,1397 | 0h | 01.11.SAP.12.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1405 |  | Auto Scheduled | נדרש להציג אי הילום לא חלוט במערכת ה-סאפ | 188.38 days | 31 December 2020 8:00 | 30 September 2021 13:00 | 0.58999999999999997 |  | 70h | 01.11.SAP.13 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1406 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.13.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1407 |  | Auto Scheduled | LifeCycle Tasks | 188.38 days | 31 December 2020 8:00 | 30 September 2021 13:00 | 0.58999999999999997 |  | 70h | 01.11.SAP.13.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1408 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.13.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1409 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.13.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1410 |  | Auto Scheduled | יישום ופיתוח סאפ | 9 days | 26 August 2021 8:00 | 09 September 2021 17:00 | 0.89000000000000001 |  | 0h | 01.11.SAP.13.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1411 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 September 2021 8:00 | 14 September 2021 15:00 | 0 | 1410 | 25h | 01.11.SAP.13.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1412 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 September 2021 15:00 | 19 September 2021 16:00 | 0 | 1411 | 10h | 01.11.SAP.13.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1413 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 September 2021 16:00 | 29 September 2021 17:00 | 0 | 1412 | 10h | 01.11.SAP.13.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1414 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 September 2021 8:00 | 30 September 2021 13:00 | 0 | 1413 | 5h | 01.11.SAP.13.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1415 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 30 September 2021 13:00 | 30 September 2021 13:00 | 0 | 1414,1408 | 0h | 01.11.SAP.13.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1416 |  | Auto Scheduled | מערכת סאפ תאפשר תהליך השוואה בין האובדנים המדווחים לבין מציאת פריט מאובדן "בעודף" במערכת סאפ,זכיין | 195.13 days | 31 December 2020 8:00 | 10 October 2021 13:00 | 0.13 |  | 70h | 01.11.SAP.14 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1417 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.14.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1418 |  | Auto Scheduled | LifeCycle Tasks | 195.13 days | 31 December 2020 8:00 | 10 October 2021 13:00 | 0.13 |  | 70h | 01.11.SAP.14.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1419 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.11.SAP.14.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1420 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 31 December 2020 8:00 | 04 January 2021 10:00 | 1 | 1151 | 20h | 01.11.SAP.14.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1421 |  | Auto Scheduled | יישום ופיתוח סאפ | 10.13 days | 02 September 2021 8:00 | 30 September 2021 17:00 | 0 |  | 0h | 01.11.SAP.14.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1422 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 October 2021 8:00 | 05 October 2021 15:00 | 0 | 1421 | 25h | 01.11.SAP.14.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1423 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 October 2021 15:00 | 06 October 2021 16:00 | 0 | 1422 | 10h | 01.11.SAP.14.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1424 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 October 2021 16:00 | 07 October 2021 17:00 | 0 | 1423 | 10h | 01.11.SAP.14.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1425 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 October 2021 8:00 | 10 October 2021 13:00 | 0 | 1424 | 5h | 01.11.SAP.14.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1426 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 October 2021 13:00 | 10 October 2021 13:00 | 0 | 1425,1419 | 0h | 01.11.SAP.14.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1427 |  | Auto Scheduled | 01.12: גריטות והשמדות | 308.75 days | 12 August 2020 8:00 | 10 October 2021 13:00 | 0.57999999999999996 |  | 836h | 01.12 | חתום | מוריה | hd | גל | nan | BP | NA | As Soon As Possible | 3
1428 |  | Auto Scheduled | 01.12: גריטות והשמדות.BP | 105.75 days | 12 August 2020 8:00 | 21 December 2020 17:00 | 1 |  | 136h | 01.12.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1429 |  | Auto Scheduled | 01.12: גריטות והשמדות | 105.75 days | 12 August 2020 8:00 | 21 December 2020 17:00 | 1 |  | 136h | 01.12.BP.01 | חתום | מוריה | parent | גל | nan | BP | NA | As Soon As Possible | 5
1430 |  | Auto Scheduled | Sub Tasks | 104.75 days | 12 August 2020 8:00 | 21 December 2020 9:00 | 1 |  | 96h | 01.12.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1431 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 12 August 2020 8:00 | 13 August 2020 10:00 | 1 |  | 11h | 01.12.BP.01.01.20 | בוצע | אבי | MoM | ואל | תע - מוריה | BP | NA | Must Start On | 7
1432 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.38 days | 19 August 2020 8:00 | 20 August 2020 10:00 | 1 |  | 11h | 01.12.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1433 |  | Auto Scheduled | אישור אבי | 1.38 days | 16 September 2020 8:00 | 17 September 2020 10:00 | 1 |  | 11h | 01.12.BP.01.01.22 | בוצע | אבי | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1434 |  | Auto Scheduled | אישור מקל"ר | 1.38 days | 30 September 2020 8:00 | 01 October 2020 10:00 | 1 | 1433 | 11h | 01.12.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1435 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 14 October 2020 8:00 | 14 October 2020 10:00 | 1 | 1434 | 2h | 01.12.BP.01.01.24 | בוצע | סיגל | MoM | ואל | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1436 |  | Auto Scheduled | אישור מפקדת | 1.38 days | 16 October 2020 8:00 | 19 October 2020 10:00 | 1 | 1435 | 11h | 01.12.BP.01.01.25 | בוצע | סיגל | MoM | ואל | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1437 |  | Auto Scheduled | אישור חטלו"ג | 0.75 days | 01 November 2020 8:00 | 01 November 2020 14:00 | 1 | 1436 | 6h | 01.12.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1438 |  | Auto Scheduled | אישור ניר בשן | 4 days | 08 November 2020 8:00 | 11 November 2020 13:00 | 1 | 1437 | 32h | 01.12.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1439 |  | Auto Scheduled | אישור שגיב שרביט | 0.13 days | 21 December 2020 8:00 | 21 December 2020 9:00 | 1 | 1438 | 1h | 01.12.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1440 |  | Auto Scheduled | LifeCycle Tasks | 37.13 days | 05 November 2020 8:00 | 21 December 2020 17:00 | 1 |  | 40h | 01.12.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1441 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 21 December 2020 8:00 | 21 December 2020 17:00 | 1 | 1439 | 0h | 01.12.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1442 |  | Auto Scheduled | טרם החל | 0.63 days | 05 November 2020 8:00 | 05 November 2020 13:00 | 1 |  | 5h | 01.12.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1443 |  | Auto Scheduled | בעבודה | 1.25 days | 12 November 2020 8:00 | 15 November 2020 9:00 | 1 | 1442 | 10h | 01.12.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1444 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 26 November 2020 8:00 | 26 November 2020 13:00 | 1 | 1443 | 5h | 01.12.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1445 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 03 December 2020 8:00 | 06 December 2020 9:00 | 1 | 1444 | 10h | 01.12.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1446 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 17 December 2020 8:00 | 20 December 2020 9:00 | 1 | 1445 | 10h | 01.12.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1447 |  | Auto Scheduled | בחתימה | 0 days | 21 December 2020 8:00 | 21 December 2020 8:00 | 1 | 1446,1441 | 0h | 01.12.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1448 |  | Auto Scheduled | חתום | 0 days | 21 December 2020 8:00 | 21 December 2020 8:00 | 1 | 1447 | 0h | 01.12.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1449 |  | Auto Scheduled | 01.12: גריטות והשמדות.SAP | 204.13 days | 21 December 2020 8:00 | 10 October 2021 13:00 | 0.56000000000000005 |  | 700h | 01.12.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1450 |  | Auto Scheduled | מערכת סאפ תאפשר בחירת פריטים לועדת הגריטה ע"ב מסך זי וי פי 1 | 188.88 days | 21 December 2020 8:00 | 05 September 2021 8:00 | 0.88 |  | 70h | 01.12.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1451 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1452 |  | Auto Scheduled | LifeCycle Tasks | 188.88 days | 21 December 2020 8:00 | 05 September 2021 8:00 | 0.88 |  | 70h | 01.12.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1453 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1454 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1455 |  | Auto Scheduled | יישום ופיתוח סאפ | 45 days | 23 May 2021 8:00 | 22 July 2021 17:00 | 1 |  | 0h | 01.12.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1456 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 July 2021 8:00 | 27 July 2021 15:00 | 0 | 1455 | 25h | 01.12.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1457 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 July 2021 15:00 | 28 July 2021 16:00 | 0 | 1456 | 10h | 01.12.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1458 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 July 2021 16:00 | 29 July 2021 17:00 | 0 | 1457 | 10h | 01.12.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1459 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 August 2021 8:00 | 01 August 2021 13:00 | 0 | 1458 | 5h | 01.12.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1460 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1459,1453 | 0h | 01.12.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1461 |  | Auto Scheduled | מערכת סאפ תאפשר בדיקת כושר לפריט ע"ב מסך זי וי פי 1 | 204.13 days | 21 December 2020 8:00 | 10 October 2021 13:00 | 0.34999999999999998 |  | 70h | 01.12.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1462 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1463 |  | Auto Scheduled | LifeCycle Tasks | 204.13 days | 21 December 2020 8:00 | 10 October 2021 13:00 | 0.34999999999999998 |  | 70h | 01.12.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1464 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1465 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1466 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 19 September 2021 8:00 | 30 September 2021 17:00 | 0.5 |  | 0h | 01.12.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1467 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 October 2021 8:00 | 05 October 2021 15:00 | 0 | 1466 | 25h | 01.12.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1468 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 October 2021 15:00 | 06 October 2021 16:00 | 0 | 1467 | 10h | 01.12.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1469 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 October 2021 16:00 | 07 October 2021 17:00 | 0 | 1468 | 10h | 01.12.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1470 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 October 2021 8:00 | 10 October 2021 13:00 | 0 | 1469 | 5h | 01.12.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1471 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 October 2021 13:00 | 10 October 2021 13:00 | 0 | 1470,1464 | 0h | 01.12.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1472 |  | Auto Scheduled | מערכת סאפ תאפשר קבלת החלטה על סוג הפעולה שתבוצע לפריט ע"ב מסך זי וי פי 2 | 203 days | 21 December 2020 8:00 | 07 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.12.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1473 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1474 |  | Auto Scheduled | LifeCycle Tasks | 203 days | 21 December 2020 8:00 | 07 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.12.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1475 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1476 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1477 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 19 September 2021 8:00 | 29 September 2021 17:00 | 0 |  | 0h | 01.12.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1478 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 30 September 2021 8:00 | 04 October 2021 15:00 | 0 | 1477 | 25h | 01.12.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1479 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 04 October 2021 15:00 | 05 October 2021 16:00 | 0 | 1478 | 10h | 01.12.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1480 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 05 October 2021 16:00 | 06 October 2021 17:00 | 0 | 1479 | 10h | 01.12.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1481 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 October 2021 8:00 | 07 October 2021 13:00 | 0 | 1480 | 5h | 01.12.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1482 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 07 October 2021 13:00 | 07 October 2021 13:00 | 0 | 1481,1475 | 0h | 01.12.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1483 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת שריון עם נתוני המק"ט הישן והחדש ללא ביצוע תנועות מלאי ,השמדות לפריט ע"ב מסך זי וי פי 2 | 200.75 days | 21 December 2020 8:00 | 05 October 2021 13:00 | 0.52000000000000002 |  | 70h | 01.12.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1484 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1485 |  | Auto Scheduled | LifeCycle Tasks | 200.75 days | 21 December 2020 8:00 | 05 October 2021 13:00 | 0.52000000000000002 |  | 70h | 01.12.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1486 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1487 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1488 |  | Auto Scheduled | יישום ופיתוח סאפ | 83.25 days | 31 May 2021 8:00 | 14 September 2021 17:00 | 0.54000000000000004 |  | 0h | 01.12.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1489 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 September 2021 8:00 | 30 September 2021 15:00 | 0 | 1488 | 25h | 01.12.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1490 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 30 September 2021 15:00 | 03 October 2021 16:00 | 0 | 1489 | 10h | 01.12.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1491 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 October 2021 16:00 | 04 October 2021 17:00 | 0 | 1490 | 10h | 01.12.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1492 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 05 October 2021 8:00 | 05 October 2021 13:00 | 0 | 1491 | 5h | 01.12.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1493 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 October 2021 13:00 | 05 October 2021 13:00 | 0 | 1492,1486 | 0h | 01.12.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1494 |  | Auto Scheduled | מערכת סאפ תבצע איחוד תהליך העבודה למשקי ציוד לחימה וחלפים ומזון כפי שמתואר עבור מר"ץ ודלק | 188.88 days | 21 December 2020 8:00 | 05 September 2021 8:00 | 0.40000000000000002 |  | 70h | 01.12.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1495 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1496 |  | Auto Scheduled | LifeCycle Tasks | 188.88 days | 21 December 2020 8:00 | 05 September 2021 8:00 | 0.40000000000000002 |  | 70h | 01.12.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1497 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1498 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1499 |  | Auto Scheduled | יישום ופיתוח סאפ | 10.13 days | 06 May 2021 8:00 | 30 May 2021 17:00 | 0.5 |  | 0h | 01.12.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1500 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 31 May 2021 8:00 | 02 June 2021 15:00 | 0 | 1499 | 25h | 01.12.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1501 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 02 June 2021 15:00 | 03 June 2021 16:00 | 0 | 1500 | 10h | 01.12.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1502 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 June 2021 16:00 | 06 June 2021 17:00 | 0 | 1501 | 10h | 01.12.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1503 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 June 2021 8:00 | 07 June 2021 13:00 | 0 | 1502 | 5h | 01.12.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1504 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1503,1497 | 0h | 01.12.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1505 |  | Auto Scheduled | מערכת סאפ תאפשר ביצוע תנועות מלאי לעדכון כושר הפריט והוצאתו ממלאי חסום | 200.75 days | 21 December 2020 8:00 | 05 October 2021 13:00 | 0.34999999999999998 |  | 70h | 01.12.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1506 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1507 |  | Auto Scheduled | LifeCycle Tasks | 200.75 days | 21 December 2020 8:00 | 05 October 2021 13:00 | 0.34999999999999998 |  | 70h | 01.12.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1508 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1509 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1510 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 12 September 2021 8:00 | 14 September 2021 17:00 | 0.5 |  | 0h | 01.12.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1511 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 September 2021 8:00 | 30 September 2021 15:00 | 0 | 1510 | 25h | 01.12.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1512 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 30 September 2021 15:00 | 03 October 2021 16:00 | 0 | 1511 | 10h | 01.12.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1513 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 October 2021 16:00 | 04 October 2021 17:00 | 0 | 1512 | 10h | 01.12.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1514 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 05 October 2021 8:00 | 05 October 2021 13:00 | 0 | 1513 | 5h | 01.12.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1515 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 October 2021 13:00 | 05 October 2021 13:00 | 0 | 1514,1508 | 0h | 01.12.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1516 |  | Auto Scheduled | מערכת סאפ תאפשר תמיכה בתהליכי העבודה בהתאם לשינוי בעמ"ט הכושרים החדשה | 201.88 days | 21 December 2020 8:00 | 06 October 2021 13:00 | 0.47999999999999998 |  | 70h | 01.12.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1517 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1518 |  | Auto Scheduled | LifeCycle Tasks | 201.88 days | 21 December 2020 8:00 | 06 October 2021 13:00 | 0.47999999999999998 |  | 70h | 01.12.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1519 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1520 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1521 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 13 September 2021 8:00 | 19 September 2021 17:00 | 1 |  | 0h | 01.12.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1522 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 September 2021 8:00 | 03 October 2021 15:00 | 0 | 1521 | 25h | 01.12.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1523 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 October 2021 15:00 | 04 October 2021 16:00 | 0 | 1522 | 10h | 01.12.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1524 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 October 2021 16:00 | 05 October 2021 17:00 | 0 | 1523 | 10h | 01.12.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1525 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 October 2021 8:00 | 06 October 2021 13:00 | 0 | 1524 | 5h | 01.12.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1526 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 October 2021 13:00 | 06 October 2021 13:00 | 0 | 1525,1519 | 0h | 01.12.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1527 |  | Auto Scheduled | מערכת סאפ תאפשר המשך גריטות למחסנים מיוחדים ולתהליכי משקי הדלק כפי שקיים היום | 196.25 days | 21 December 2020 8:00 | 29 September 2021 13:00 | 0.83999999999999997 |  | 70h | 01.12.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1528 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1529 |  | Auto Scheduled | LifeCycle Tasks | 196.25 days | 21 December 2020 8:00 | 29 September 2021 13:00 | 0.83999999999999997 |  | 70h | 01.12.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1530 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1531 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1532 |  | Auto Scheduled | יישום ופיתוח סאפ | 92.25 days | 03 May 2021 8:00 | 05 September 2021 17:00 | 0.89000000000000001 |  | 0h | 01.12.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1533 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 September 2021 8:00 | 13 September 2021 15:00 | 0 | 1532 | 25h | 01.12.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1534 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 September 2021 15:00 | 14 September 2021 16:00 | 0 | 1533 | 10h | 01.12.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1535 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 September 2021 16:00 | 19 September 2021 17:00 | 0 | 1534 | 10h | 01.12.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1536 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 September 2021 8:00 | 29 September 2021 13:00 | 0 | 1535 | 5h | 01.12.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1537 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 September 2021 13:00 | 29 September 2021 13:00 | 0 | 1536,1530 | 0h | 01.12.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1538 |  | Auto Scheduled | מערכת סאפ תעדכן את כושר הפריטים ע"ב הנתונים שהתקבלו מזכיין. העדכון יכול להיות מבוצע במספר פעימות. עבור מצל"ח, מר"צ, דלק | 203 days | 21 December 2020 8:00 | 07 October 2021 13:00 | 0.34999999999999998 |  | 70h | 01.12.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1539 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1540 |  | Auto Scheduled | LifeCycle Tasks | 203 days | 21 December 2020 8:00 | 07 October 2021 13:00 | 0.34999999999999998 |  | 70h | 01.12.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1541 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1542 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1543 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 14 September 2021 8:00 | 29 September 2021 17:00 | 0.5 |  | 0h | 01.12.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1544 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 30 September 2021 8:00 | 04 October 2021 15:00 | 0 | 1543 | 25h | 01.12.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1545 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 04 October 2021 15:00 | 05 October 2021 16:00 | 0 | 1544 | 10h | 01.12.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1546 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 05 October 2021 16:00 | 06 October 2021 17:00 | 0 | 1545 | 10h | 01.12.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1547 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 October 2021 8:00 | 07 October 2021 13:00 | 0 | 1546 | 5h | 01.12.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1548 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 07 October 2021 13:00 | 07 October 2021 13:00 | 0 | 1547,1541 | 0h | 01.12.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1549 |  | Auto Scheduled | מערכת סאפ תאפשר בחירת סיבה לפסילה עבור כל תהליך ע"ב מסך זי וי פי 1 | 196.25 days | 21 December 2020 8:00 | 29 September 2021 13:00 | 0.25 |  | 70h | 01.12.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1550 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1551 |  | Auto Scheduled | LifeCycle Tasks | 196.25 days | 21 December 2020 8:00 | 29 September 2021 13:00 | 0.25 |  | 70h | 01.12.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1552 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.12.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1553 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 21 December 2020 8:00 | 23 December 2020 10:00 | 1 | 1439 | 20h | 01.12.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1554 |  | Auto Scheduled | יישום ופיתוח סאפ | 79.88 days | 23 May 2021 8:00 | 05 September 2021 17:00 | 0.25 |  | 0h | 01.12.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1555 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 September 2021 8:00 | 13 September 2021 15:00 | 0 | 1554 | 25h | 01.12.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1556 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 September 2021 15:00 | 14 September 2021 16:00 | 0 | 1555 | 10h | 01.12.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1557 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 September 2021 16:00 | 19 September 2021 17:00 | 0 | 1556 | 10h | 01.12.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1558 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 September 2021 8:00 | 29 September 2021 13:00 | 0 | 1557 | 5h | 01.12.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1559 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 September 2021 13:00 | 29 September 2021 13:00 | 0 | 1558,1552 | 0h | 01.12.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1560 |  | Auto Scheduled | 01.14: מבנה ארגוני | 312.13 days | 16 August 2020 8:00 | 17 October 2021 13:00 | 0.48999999999999999 |  | 854h | 01.14 | חתום | ואל | hd | מאור | nan | BP | NA | As Soon As Possible | 3
1561 |  | Auto Scheduled | 01.14: מבנה ארגוני.BP | 119.25 days | 16 August 2020 8:00 | 10 January 2021 17:00 | 1 |  | 154h | 01.14.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1562 |  | Auto Scheduled | 01.14: מבנה ארגוני | 119.25 days | 16 August 2020 8:00 | 10 January 2021 17:00 | 1 |  | 154h | 01.14.BP.01 | חתום | ואל | parent | מאור | nan | BP | NA | As Soon As Possible | 5
1563 |  | Auto Scheduled | Sub Tasks | 118.25 days | 16 August 2020 8:00 | 10 January 2021 9:00 | 1 |  | 114h | 01.14.BP.01.01 |  | ואל | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1564 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 16 August 2020 8:00 | 17 August 2020 10:00 | 1 |  | 11h | 01.14.BP.01.01.20 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | Must Start On | 7
1565 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 4.13 days | 30 August 2020 8:00 | 02 September 2020 14:00 | 1 | 1564 | 33h | 01.14.BP.01.01.21 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1566 |  | Auto Scheduled | אישור אבי | 6.63 days | 13 October 2020 8:00 | 20 October 2020 16:00 | 1 | 1565 | 53h | 01.14.BP.01.01.22 | בוצע | אבי | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
1567 |  | Auto Scheduled | אישור מפקדת | 0.75 days | 24 December 2020 8:00 | 24 December 2020 14:00 | 1 | 1566 | 6h | 01.14.BP.01.01.23 | בוצע | ואל | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
1568 |  | Auto Scheduled | אישור מקל"ר | 0.13 days | 31 December 2020 8:00 | 31 December 2020 9:00 | 1 | 1567 | 1h | 01.14.BP.01.01.24 | בוצע |  | MoM |  | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
1569 |  | Auto Scheduled | אישור המנהלת | 0.13 days | 31 December 2020 8:00 | 31 December 2020 9:00 | 1 | 1568 | 1h | 01.14.BP.01.01.25 | בוצע | סיגל | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
1570 |  | Auto Scheduled | אישור ניר בשן | 0.88 days | 31 December 2020 8:00 | 31 December 2020 15:00 | 1 | 1569 | 7h | 01.14.BP.01.01.26 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1571 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 10 January 2021 8:00 | 10 January 2021 9:00 | 1 | 1570 | 1h | 01.14.BP.01.01.27 | בוצע |  | MoM |  | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
1572 |  | Auto Scheduled | אישור שגיב שרביט | 0.13 days | 10 January 2021 8:00 | 10 January 2021 9:00 | 1 | 1571 | 1h | 01.14.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1573 |  | Auto Scheduled | LifeCycle Tasks | 114.75 days | 20 August 2020 8:00 | 10 January 2021 17:00 | 1 |  | 40h | 01.14.BP.01.02 |  | ואל | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1574 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 10 January 2021 8:00 | 10 January 2021 17:00 | 1 | 1572 | 0h | 01.14.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1575 |  | Auto Scheduled | טרם החל | 0.63 days | 20 August 2020 8:00 | 20 August 2020 13:00 | 1 |  | 5h | 01.14.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1576 |  | Auto Scheduled | בעבודה | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 1575 | 10h | 01.14.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1577 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 10 September 2020 8:00 | 10 September 2020 13:00 | 1 | 1576 | 5h | 01.14.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1578 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 1577 | 10h | 01.14.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1579 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 1578 | 10h | 01.14.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1580 |  | Auto Scheduled | בחתימה | 0 days | 10 January 2021 8:00 | 10 January 2021 8:00 | 1 | 1579,1574 | 0h | 01.14.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1581 |  | Auto Scheduled | חתום | 0 days | 10 January 2021 8:00 | 10 January 2021 8:00 | 1 | 1580 | 0h | 01.14.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1582 |  | Auto Scheduled | 01.14: מבנה ארגוני.SAP | 194 days | 10 January 2021 8:00 | 17 October 2021 13:00 | 0.41999999999999998 |  | 700h | 01.14.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1583 |  | Auto Scheduled | יוגדרו שלושה אתרים חדשים במערכת סאפ שייצגו את שלושת המרחבים הפיזיים צפון, מרכז, דרום ויכילו את מלאי מרה"ס | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.14.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1584 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1585 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.14.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1586 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1587 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1588 |  | Auto Scheduled | יישום ופיתוח סאפ | 1.13 days | 03 March 2021 8:00 | 03 March 2021 17:00 | 1 |  | 0h | 01.14.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1589 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 March 2021 8:00 | 08 March 2021 15:00 | 0 | 1588 | 25h | 01.14.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1590 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 March 2021 15:00 | 09 March 2021 16:00 | 0 | 1589 | 10h | 01.14.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1591 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 March 2021 16:00 | 10 March 2021 17:00 | 0 | 1590 | 10h | 01.14.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1592 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 March 2021 8:00 | 11 March 2021 13:00 | 0 | 1591 | 5h | 01.14.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1593 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1592,1586 | 0h | 01.14.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1594 |  | Auto Scheduled | הגדרת אתר אחסון מצ"מ תיקונים . | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.14.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1595 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1596 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.14.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1597 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1598 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1599 |  | Auto Scheduled | יישום ופיתוח סאפ | 1.13 days | 09 March 2021 8:00 | 09 March 2021 17:00 | 1 |  | 0h | 01.14.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1600 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 March 2021 8:00 | 14 March 2021 15:00 | 0 | 1599 | 25h | 01.14.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1601 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 March 2021 15:00 | 15 March 2021 16:00 | 0 | 1600 | 10h | 01.14.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1602 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 March 2021 16:00 | 16 March 2021 17:00 | 0 | 1601 | 10h | 01.14.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1603 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 March 2021 8:00 | 17 March 2021 13:00 | 0 | 1602 | 5h | 01.14.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1604 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1603,1597 | 0h | 01.14.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1605 |  | Auto Scheduled | עבור כל מרחב יוגדרו 10 אתרי אחסון במערכת סאפ חדשים לכל בסיס במרחב המייצגים המלאי וכושרים-- | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.42999999999999999 |  | 70h | 01.14.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1606 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1607 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.42999999999999999 |  | 70h | 01.14.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1608 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1609 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1610 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 03 March 2021 8:00 | 04 March 2021 17:00 | 1 |  | 0h | 01.14.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1611 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 March 2021 8:00 | 09 March 2021 15:00 | 0 | 1610 | 25h | 01.14.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1612 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 March 2021 15:00 | 10 March 2021 16:00 | 0 | 1611 | 10h | 01.14.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1613 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 March 2021 16:00 | 11 March 2021 17:00 | 0 | 1612 | 10h | 01.14.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1614 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 March 2021 8:00 | 14 March 2021 13:00 | 0 | 1613 | 5h | 01.14.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1615 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1614,1608 | 0h | 01.14.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1616 |  | Auto Scheduled | הכושר יוצג ע"ב הספרה האחרונה בספרור אתר האחסון במערכת סאפ | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.40999999999999998 |  | 70h | 01.14.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1617 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1618 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.40999999999999998 |  | 70h | 01.14.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1619 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1620 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1621 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 04 March 2021 8:00 | 07 March 2021 17:00 | 0.90000000000000002 |  | 0h | 01.14.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1622 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 March 2021 8:00 | 10 March 2021 15:00 | 0 | 1621 | 25h | 01.14.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1623 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 March 2021 15:00 | 11 March 2021 16:00 | 0 | 1622 | 10h | 01.14.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1624 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 March 2021 16:00 | 14 March 2021 17:00 | 0 | 1623 | 10h | 01.14.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1625 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 March 2021 8:00 | 15 March 2021 13:00 | 0 | 1624 | 5h | 01.14.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1626 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1625,1619 | 0h | 01.14.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1627 |  | Auto Scheduled | לכל אתר אחסון יוגדר סימול אפסנאי חדש בהתאם לשינוי בצו ארגון שיבוצע במערכת הסאפ. | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.20999999999999999 |  | 70h | 01.14.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1628 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1629 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.20999999999999999 |  | 70h | 01.14.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1630 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1631 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1632 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 03 March 2021 8:00 | 07 March 2021 17:00 | 0 |  | 0h | 01.14.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1633 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 March 2021 8:00 | 10 March 2021 15:00 | 0 | 1632 | 25h | 01.14.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1634 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 March 2021 15:00 | 11 March 2021 16:00 | 0 | 1633 | 10h | 01.14.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1635 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 March 2021 16:00 | 14 March 2021 17:00 | 0 | 1634 | 10h | 01.14.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1636 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 March 2021 8:00 | 15 March 2021 13:00 | 0 | 1635 | 5h | 01.14.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1637 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1636,1630 | 0h | 01.14.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1638 |  | Auto Scheduled | אתרי אחסון ברמת איי אם,ניהול המלאי הקיימים כיום תחת אתר וקוד חברה של המרכז יקושרו,יוקמו לקוד חברה צה"ל ולאתר המרחבי החדש במערכת סאפ | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.46000000000000002 |  | 70h | 01.14.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1639 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1640 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.46000000000000002 |  | 70h | 01.14.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1641 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1642 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1643 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 07 March 2021 8:00 | 09 March 2021 17:00 | 0.90000000000000002 |  | 0h | 01.14.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1644 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 March 2021 8:00 | 14 March 2021 15:00 | 0 | 1643 | 25h | 01.14.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1645 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 March 2021 15:00 | 15 March 2021 16:00 | 0 | 1644 | 10h | 01.14.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1646 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 March 2021 16:00 | 16 March 2021 17:00 | 0 | 1645 | 10h | 01.14.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1647 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 March 2021 8:00 | 17 March 2021 13:00 | 0 | 1646 | 5h | 01.14.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1648 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1647,1641 | 0h | 01.14.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1649 |  | Auto Scheduled | הקמת אתר אחסון סאפ למלאי המגיע מהחזרות במצ"מ | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.14.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1650 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1651 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.14.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1652 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1653 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1654 |  | Auto Scheduled | יישום ופיתוח סאפ | 1.13 days | 09 March 2021 8:00 | 09 March 2021 17:00 | 1 |  | 0h | 01.14.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1655 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 March 2021 8:00 | 14 March 2021 15:00 | 0 | 1654 | 25h | 01.14.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1656 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 March 2021 15:00 | 15 March 2021 16:00 | 0 | 1655 | 10h | 01.14.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1657 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 March 2021 16:00 | 16 March 2021 17:00 | 0 | 1656 | 10h | 01.14.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1658 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 March 2021 8:00 | 17 March 2021 13:00 | 0 | 1657 | 5h | 01.14.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1659 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1658,1652 | 0h | 01.14.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1660 |  | Auto Scheduled | הגדרת מחסנים למחסנים מיוחדים. כולל מבנה פיסי מלא. כולל אסטרטגיות אחסון וליקוט ועוד. | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.56999999999999995 |  | 70h | 01.14.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1661 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1662 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.56999999999999995 |  | 70h | 01.14.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1663 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1664 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1665 |  | Auto Scheduled | יישום ופיתוח סאפ | 25.75 days | 25 March 2021 8:00 | 05 May 2021 17:00 | 0.67000000000000004 |  | 0h | 01.14.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1666 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 May 2021 8:00 | 10 May 2021 15:00 | 0 | 1665 | 25h | 01.14.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1667 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 May 2021 15:00 | 11 May 2021 16:00 | 0 | 1666 | 10h | 01.14.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1668 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 May 2021 16:00 | 12 May 2021 17:00 | 0 | 1667 | 10h | 01.14.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1669 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 May 2021 8:00 | 13 May 2021 13:00 | 0 | 1668 | 5h | 01.14.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1670 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1669,1663 | 0h | 01.14.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1671 |  | Auto Scheduled | הגדרת מחסנים רזים למחסנים מיוחדים. | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.46999999999999997 |  | 70h | 01.14.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1672 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1673 |  | Auto Scheduled | LifeCycle Tasks | 173.13 days | 10 January 2021 8:00 | 05 September 2021 8:00 | 0.46999999999999997 |  | 70h | 01.14.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1674 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1675 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1676 |  | Auto Scheduled | יישום ופיתוח סאפ | 9 days | 19 April 2021 8:00 | 28 April 2021 17:00 | 0.64000000000000001 |  | 0h | 01.14.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1677 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 April 2021 8:00 | 03 May 2021 15:00 | 0 | 1676 | 25h | 01.14.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1678 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 May 2021 15:00 | 04 May 2021 16:00 | 0 | 1677 | 10h | 01.14.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1679 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 May 2021 16:00 | 05 May 2021 17:00 | 0 | 1678 | 10h | 01.14.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1680 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 May 2021 8:00 | 06 May 2021 13:00 | 0 | 1679 | 5h | 01.14.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1681 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1680,1674 | 0h | 01.14.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1682 |  | Auto Scheduled | פיתוח תוכניות הסבות מלאים | 194 days | 10 January 2021 8:00 | 17 October 2021 13:00 | 0.19 |  | 70h | 01.14.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1683 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1684 |  | Auto Scheduled | LifeCycle Tasks | 194 days | 10 January 2021 8:00 | 17 October 2021 13:00 | 0.19 |  | 70h | 01.14.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1685 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.14.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1686 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 January 2021 8:00 | 12 January 2021 10:00 | 1 | 1572 | 20h | 01.14.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1687 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 04 October 2021 8:00 | 07 October 2021 17:00 | 0 |  | 0h | 01.14.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1688 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 October 2021 8:00 | 12 October 2021 15:00 | 0 | 1687 | 25h | 01.14.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1689 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 October 2021 15:00 | 13 October 2021 16:00 | 0 | 1688 | 10h | 01.14.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1690 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 October 2021 16:00 | 14 October 2021 17:00 | 0 | 1689 | 10h | 01.14.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1691 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 October 2021 8:00 | 17 October 2021 13:00 | 0 | 1690 | 5h | 01.14.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1692 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 October 2021 13:00 | 17 October 2021 13:00 | 0 | 1691,1685 | 0h | 01.14.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1693 |  | Auto Scheduled | 01.15: כושרים | 425.75 days | 17 August 2020 8:00 | 08 March 2022 13:00 | 0.5 |  | 774h | 01.15 | חתום | מוריה | hd | עינת | nan | BP | NA | As Soon As Possible | 3
1694 |  | Auto Scheduled | 01.15: כושרים.BP | 110.38 days | 17 August 2020 8:00 | 31 December 2020 9:00 | 1 |  | 144h | 01.15.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1695 |  | Auto Scheduled | 01.15: כושרים | 110.38 days | 17 August 2020 8:00 | 31 December 2020 9:00 | 1 |  | 144h | 01.15.BP.01 | חתום | מוריה | parent | עינת | nan | BP | NA | As Soon As Possible | 5
1696 |  | Auto Scheduled | Sub Tasks | 97 days | 17 August 2020 8:00 | 15 December 2020 10:00 | 1 |  | 104h | 01.15.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1697 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 17 August 2020 8:00 | 18 August 2020 10:00 | 1 |  | 11h | 01.15.BP.01.01.20 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | Must Start On | 7
1698 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.38 days | 19 August 2020 8:00 | 20 August 2020 10:00 | 1 |  | 11h | 01.15.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1699 |  | Auto Scheduled | אישור אבי | 1.13 days | 02 September 2020 8:00 | 02 September 2020 17:00 | 1 | 1698 | 9h | 01.15.BP.01.01.22 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1700 |  | Auto Scheduled | אישור מפקדת | 2 days | 14 September 2020 8:00 | 15 September 2020 15:00 | 1 | 1699 | 16h | 01.15.BP.01.01.23 | בוצע | עינת | MoM | עינת | nan | BP | NA | As Soon As Possible | 7
1701 |  | Auto Scheduled | אישור מקל"ר | 1 day | 05 October 2020 8:00 | 05 October 2020 16:00 | 1 | 1700 | 8h | 01.15.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1702 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 14 October 2020 8:00 | 14 October 2020 10:00 | 1 | 1701 | 2h | 01.15.BP.01.01.25 | בוצע | סיגל | MoM | עינת | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
1703 |  | Auto Scheduled | אישור חטלו"ג | 2.13 days | 15 October 2020 8:00 | 18 October 2020 16:00 | 1 | 1702 | 17h | 01.15.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
1704 |  | Auto Scheduled | אישור ניר בשן | 3.5 days | 08 November 2020 8:00 | 11 November 2020 9:00 | 1 | 1703 | 28h | 01.15.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1705 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 15 December 2020 8:00 | 15 December 2020 10:00 | 1 | 1704 | 2h | 01.15.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1706 |  | Auto Scheduled | LifeCycle Tasks | 35 days | 18 November 2020 8:00 | 31 December 2020 9:00 | 1 |  | 40h | 01.15.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1707 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 16 December 2020 8:00 | 16 December 2020 17:00 | 1 | 1705 | 0h | 01.15.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1708 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 01.15.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1709 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 1708 | 10h | 01.15.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1710 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 1709 | 5h | 01.15.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1711 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 1710 | 10h | 01.15.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1712 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 1711 | 10h | 01.15.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1713 |  | Auto Scheduled | בחתימה | 0 days | 16 December 2020 8:00 | 16 December 2020 8:00 | 1 | 1712,1707 | 0h | 01.15.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1714 |  | Auto Scheduled | חתום | 0 days | 16 December 2020 8:00 | 16 December 2020 8:00 | 1 | 1713 | 0h | 01.15.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1715 |  | Auto Scheduled | 01.15: כושרים.INT | 327.88 days | 16 December 2020 8:00 | 08 March 2022 13:00 | 8.0000000000000002E-2 |  | 280h | 01.15.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1716 |  | Auto Scheduled | מערכת הסאפ תבצע שחרור משריון ושינוי לכושר הרלוונטי ע"ב שדר הביצוע ממערכת הזכיין | 293 days | 16 December 2020 8:00 | 24 January 2022 13:00 | 0.12 |  | 70h | 01.15.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1717 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1718 |  | Auto Scheduled | LifeCycle Tasks | 293 days | 16 December 2020 8:00 | 24 January 2022 13:00 | 0.12 |  | 70h | 01.15.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1719 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1720 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1721 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 02 January 2022 8:00 | 16 January 2022 17:00 | 0 |  | 0h | 01.15.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1722 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 January 2022 8:00 | 19 January 2022 15:00 | 0 | 1721 | 25h | 01.15.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1723 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 January 2022 15:00 | 20 January 2022 16:00 | 0 | 1722 | 10h | 01.15.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1724 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 January 2022 16:00 | 23 January 2022 17:00 | 0 | 1723 | 10h | 01.15.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1725 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 January 2022 8:00 | 24 January 2022 13:00 | 0 | 1724 | 5h | 01.15.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1726 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 January 2022 13:00 | 24 January 2022 13:00 | 0 | 1725,1719 | 0h | 01.15.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1727 |  | Auto Scheduled | מערכת סאפ תאפשר העברת ממשקים ל זכיין עבור שינוי כושר | 313.25 days | 16 December 2020 8:00 | 17 February 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.15.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1728 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1729 |  | Auto Scheduled | LifeCycle Tasks | 313.25 days | 16 December 2020 8:00 | 17 February 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.15.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1730 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1731 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1732 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 25.88 days | 10 January 2022 8:00 | 09 February 2022 17:00 | 0 |  | 0h | 01.15.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1733 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 February 2022 8:00 | 14 February 2022 15:00 | 0 | 1732 | 25h | 01.15.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1734 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 February 2022 15:00 | 15 February 2022 16:00 | 0 | 1733 | 10h | 01.15.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1735 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 February 2022 16:00 | 16 February 2022 17:00 | 0 | 1734 | 10h | 01.15.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1736 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 February 2022 8:00 | 17 February 2022 13:00 | 0 | 1735 | 5h | 01.15.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1737 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 17 February 2022 13:00 | 17 February 2022 13:00 | 0 | 1736,1730 | 0h | 01.15.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1738 |  | Auto Scheduled | מערכת זכיין תאפשר העברת ממשקים ל סאפ עבור שינוי כושר | 321.13 days | 16 December 2020 8:00 | 28 February 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.15.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1739 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1740 |  | Auto Scheduled | LifeCycle Tasks | 321.13 days | 16 December 2020 8:00 | 28 February 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.15.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1741 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1742 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1743 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 25.88 days | 19 January 2022 8:00 | 20 February 2022 17:00 | 0 |  | 0h | 01.15.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1744 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 February 2022 8:00 | 23 February 2022 15:00 | 0 | 1743 | 25h | 01.15.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1745 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 February 2022 15:00 | 24 February 2022 16:00 | 0 | 1744 | 10h | 01.15.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1746 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 February 2022 16:00 | 27 February 2022 17:00 | 0 | 1745 | 10h | 01.15.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1747 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 February 2022 8:00 | 28 February 2022 13:00 | 0 | 1746 | 5h | 01.15.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1748 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 28 February 2022 13:00 | 28 February 2022 13:00 | 0 | 1747,1741 | 0h | 01.15.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1749 |  | Auto Scheduled | מערכת סאפ תשנה את המלאי לכושר הרלוונטי כפי שהתקבל מה זכיין | 327.88 days | 16 December 2020 8:00 | 08 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.15.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1750 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1751 |  | Auto Scheduled | LifeCycle Tasks | 327.88 days | 16 December 2020 8:00 | 08 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 01.15.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1752 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1753 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1754 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 24.75 days | 30 January 2022 8:00 | 28 February 2022 17:00 | 0 |  | 0h | 01.15.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1755 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 March 2022 8:00 | 03 March 2022 15:00 | 0 | 1754 | 25h | 01.15.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1756 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 March 2022 15:00 | 06 March 2022 16:00 | 0 | 1755 | 10h | 01.15.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1757 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 March 2022 16:00 | 07 March 2022 17:00 | 0 | 1756 | 10h | 01.15.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1758 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 08 March 2022 8:00 | 08 March 2022 13:00 | 0 | 1757 | 5h | 01.15.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1759 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 08 March 2022 13:00 | 08 March 2022 13:00 | 0 | 1758,1752 | 0h | 01.15.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1760 |  | Auto Scheduled | 01.15: כושרים.SAP | 318.88 days | 16 December 2020 8:00 | 24 February 2022 13:00 | 0.69999999999999996 |  | 350h | 01.15.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1761 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי אובייקט הרשאה עבור המרות טכניות בין כושרים | 242.38 days | 16 December 2020 8:00 | 22 November 2021 13:00 | 0.16 |  | 70h | 01.15.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1762 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1763 |  | Auto Scheduled | LifeCycle Tasks | 242.38 days | 16 December 2020 8:00 | 22 November 2021 13:00 | 0.16 |  | 70h | 01.15.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1764 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1765 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1766 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 07 November 2021 8:00 | 14 November 2021 17:00 | 0 |  | 0h | 01.15.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1767 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 15 November 2021 8:00 | 17 November 2021 15:00 | 0 | 1766 | 25h | 01.15.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1768 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 November 2021 15:00 | 18 November 2021 16:00 | 0 | 1767 | 10h | 01.15.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1769 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 November 2021 16:00 | 21 November 2021 17:00 | 0 | 1768 | 10h | 01.15.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1770 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 22 November 2021 8:00 | 22 November 2021 13:00 | 0 | 1769 | 5h | 01.15.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1771 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 22 November 2021 13:00 | 22 November 2021 13:00 | 0 | 1770,1764 | 0h | 01.15.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1772 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי אובייקט הרשאות עבור שימוש בטבלת בי אר אף לפי משקים | 192.25 days | 16 December 2020 8:00 | 05 September 2021 8:00 | 0.58999999999999997 |  | 70h | 01.15.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1773 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1774 |  | Auto Scheduled | LifeCycle Tasks | 192.25 days | 16 December 2020 8:00 | 05 September 2021 8:00 | 0.58999999999999997 |  | 70h | 01.15.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1775 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1776 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1777 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 18 July 2021 8:00 | 11 August 2021 17:00 | 0.71999999999999997 |  | 0h | 01.15.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1778 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 August 2021 8:00 | 16 August 2021 15:00 | 0 | 1777 | 25h | 01.15.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1779 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 16 August 2021 15:00 | 17 August 2021 16:00 | 0 | 1778 | 10h | 01.15.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1780 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 August 2021 16:00 | 18 August 2021 17:00 | 0 | 1779 | 10h | 01.15.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1781 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 August 2021 8:00 | 19 August 2021 13:00 | 0 | 1780 | 5h | 01.15.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1782 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1781,1775 | 0h | 01.15.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1783 |  | Auto Scheduled | מימוש כושרים אחוד במערכת סאפ יתבצע עפ"י עמ"ט הכושרים עבור מחסנים מיוחדים ועבור מחסנים בתפעול מערכת זכיין א"א, הרשאות ועוד. | 205.25 days | 16 December 2020 8:00 | 06 October 2021 13:00 | 0.84999999999999998 |  | 70h | 01.15.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1784 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1785 |  | Auto Scheduled | LifeCycle Tasks | 205.25 days | 16 December 2020 8:00 | 06 October 2021 13:00 | 0.84999999999999998 |  | 70h | 01.15.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1786 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1787 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1788 |  | Auto Scheduled | יישום ופיתוח סאפ | 118.13 days | 05 April 2021 8:00 | 19 September 2021 17:00 | 0.89000000000000001 |  | 0h | 01.15.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1789 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 September 2021 8:00 | 03 October 2021 15:00 | 0 | 1788 | 25h | 01.15.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1790 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 October 2021 15:00 | 04 October 2021 16:00 | 0 | 1789 | 10h | 01.15.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1791 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 October 2021 16:00 | 05 October 2021 17:00 | 0 | 1790 | 10h | 01.15.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1792 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 October 2021 8:00 | 06 October 2021 13:00 | 0 | 1791 | 5h | 01.15.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1793 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 October 2021 13:00 | 06 October 2021 13:00 | 0 | 1792,1786 | 0h | 01.15.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1794 |  | Auto Scheduled | ביצוע הסבות לכושרים המתאימים | 318.88 days | 16 December 2020 8:00 | 24 February 2022 13:00 | 0.14999999999999999 |  | 70h | 01.15.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1795 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1796 |  | Auto Scheduled | LifeCycle Tasks | 318.88 days | 16 December 2020 8:00 | 24 February 2022 13:00 | 0.14999999999999999 |  | 70h | 01.15.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1797 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1798 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1799 |  | Auto Scheduled | יישום ופיתוח סאפ | 7.88 days | 08 February 2022 8:00 | 16 February 2022 17:00 | 0 |  | 0h | 01.15.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1800 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 February 2022 8:00 | 21 February 2022 15:00 | 0 | 1799 | 25h | 01.15.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1801 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 February 2022 15:00 | 22 February 2022 16:00 | 0 | 1800 | 10h | 01.15.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1802 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 February 2022 16:00 | 23 February 2022 17:00 | 0 | 1801 | 10h | 01.15.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1803 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 February 2022 8:00 | 24 February 2022 13:00 | 0 | 1802 | 5h | 01.15.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1804 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 February 2022 13:00 | 24 February 2022 13:00 | 0 | 1803,1797 | 0h | 01.15.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1805 |  | Auto Scheduled | יש להקים טבלת חוקה בבי אר אף שתייצג את עמ"ט הכושרים בכל תהליך עסקי. | 192.25 days | 16 December 2020 8:00 | 05 September 2021 8:00 | 0.73999999999999999 |  | 70h | 01.15.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1806 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1807 |  | Auto Scheduled | LifeCycle Tasks | 192.25 days | 16 December 2020 8:00 | 05 September 2021 8:00 | 0.73999999999999999 |  | 70h | 01.15.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1808 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.15.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1809 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 16 December 2020 8:00 | 20 December 2020 10:00 | 1 | 1705 | 20h | 01.15.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1810 |  | Auto Scheduled | יישום ופיתוח סאפ | 24.75 days | 25 April 2021 8:00 | 03 June 2021 17:00 | 0.90000000000000002 |  | 0h | 01.15.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
1811 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 June 2021 8:00 | 08 June 2021 15:00 | 0 | 1810 | 25h | 01.15.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1812 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 June 2021 15:00 | 09 June 2021 16:00 | 0 | 1811 | 10h | 01.15.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1813 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 June 2021 16:00 | 10 June 2021 17:00 | 0 | 1812 | 10h | 01.15.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1814 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 June 2021 8:00 | 13 June 2021 13:00 | 0 | 1813 | 5h | 01.15.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1815 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 1814,1808 | 0h | 01.15.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1816 |  | Auto Scheduled | 01.16: המרות טכניות | 468.5 days | 02 August 2020 8:00 | 14 April 2022 13:00 | 0.14999999999999999 |  | 1,386h | 01.16 | חתום | מוריה | hd | מורן | nan | BP | NA | As Soon As Possible | 3
1817 |  | Auto Scheduled | 01.16: המרות טכניות.BP | 122.75 days | 02 August 2020 8:00 | 31 December 2020 9:00 | 1 |  | 126h | 01.16.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1818 |  | Auto Scheduled | 01.16: המרות טכניות | 122.75 days | 02 August 2020 8:00 | 31 December 2020 9:00 | 1 |  | 126h | 01.16.BP.01 | חתום | מוריה | parent | מורן | nan | BP | NA | As Soon As Possible | 5
1819 |  | Auto Scheduled | Sub Tasks | 103.75 days | 02 August 2020 8:00 | 08 December 2020 10:00 | 1 |  | 86h | 01.16.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1820 |  | Auto Scheduled | 23/09: הערות שרון ותקווה | 0.13 days | 02 August 2020 8:00 | 02 August 2020 9:00 | 1 |  | 1h | 01.16.BP.01.01.01 | בוצע | מוריה | MoM | מאור | שרון רחמים | BP | NA | Must Start On | 7
1821 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 19 August 2020 8:00 | 20 August 2020 10:00 | 1 |  | 11h | 01.16.BP.01.01.20 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1822 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.38 days | 08 September 2020 8:00 | 09 September 2020 10:00 | 1 |  | 11h | 01.16.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
1823 |  | Auto Scheduled | אישור אבי | 0.88 days | 22 September 2020 8:00 | 22 September 2020 15:00 | 1 | 1822 | 7h | 01.16.BP.01.01.22 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1824 |  | Auto Scheduled | אישור מקל"ר | 1.5 days | 30 September 2020 8:00 | 01 October 2020 11:00 | 1 | 1823 | 12h | 01.16.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1825 |  | Auto Scheduled | אישור המנהלת | 1.5 days | 15 October 2020 8:00 | 18 October 2020 11:00 | 1 | 1824 | 12h | 01.16.BP.01.01.24 | בוצע | סיגל | MoM | מאור | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1826 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 01 November 2020 8:00 | 01 November 2020 10:00 | 1 | 1825 | 2h | 01.16.BP.01.01.25 | בוצע | מאור | MoM | מאור | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1827 |  | Auto Scheduled | אישור חטלו"ג | 0.63 days | 02 November 2020 8:00 | 02 November 2020 13:00 | 1 | 1826 | 5h | 01.16.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1828 |  | Auto Scheduled | אישור ניר בשן | 2.88 days | 08 November 2020 8:00 | 10 November 2020 13:00 | 1 | 1827 | 23h | 01.16.BP.01.01.27 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1829 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 08 December 2020 8:00 | 08 December 2020 10:00 | 1 | 1828 | 2h | 01.16.BP.01.01.28 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1830 |  | Auto Scheduled | LifeCycle Tasks | 35 days | 18 November 2020 8:00 | 31 December 2020 9:00 | 1 |  | 40h | 01.16.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1831 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 09 December 2020 8:00 | 09 December 2020 17:00 | 1 | 1829 | 0h | 01.16.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1832 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 01.16.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1833 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 1832 | 10h | 01.16.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1834 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 1833 | 5h | 01.16.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1835 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 1834 | 10h | 01.16.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1836 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 1835 | 10h | 01.16.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1837 |  | Auto Scheduled | בחתימה | 0 days | 09 December 2020 8:00 | 09 December 2020 8:00 | 1 | 1836,1831 | 0h | 01.16.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1838 |  | Auto Scheduled | חתום | 0 days | 09 December 2020 8:00 | 09 December 2020 8:00 | 1 | 1837 | 0h | 01.16.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
1839 |  | Auto Scheduled | 01.16: המרות טכניות.INT | 363.88 days | 09 December 2020 8:00 | 14 April 2022 13:00 | 5.9999999999999998E-2 |  | 280h | 01.16.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1840 |  | Auto Scheduled | מערכת זכיין תשלח שדר לסאפ עם הנתונים המסומנים להמרה לטובת תהליך המרה | 352.63 days | 09 December 2020 8:00 | 31 March 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.16.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1841 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1842 |  | Auto Scheduled | LifeCycle Tasks | 352.63 days | 09 December 2020 8:00 | 31 March 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.16.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1843 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1844 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1845 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 33.75 days | 10 February 2022 8:00 | 23 March 2022 17:00 | 0 |  | 0h | 01.16.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1846 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 March 2022 8:00 | 28 March 2022 15:00 | 0 | 1845 | 25h | 01.16.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1847 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 March 2022 15:00 | 29 March 2022 16:00 | 0 | 1846 | 10h | 01.16.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1848 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 March 2022 16:00 | 30 March 2022 17:00 | 0 | 1847 | 10h | 01.16.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1849 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 March 2022 8:00 | 31 March 2022 13:00 | 0 | 1848 | 5h | 01.16.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1850 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 31 March 2022 13:00 | 31 March 2022 13:00 | 0 | 1849,1843 | 0h | 01.16.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1851 |  | Auto Scheduled | מערכת זכיין תשלח שדר על קבלת הפריטים למלאי אל מול אספקת צפי הפנימי | 335.75 days | 09 December 2020 8:00 | 10 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.16.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1852 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1853 |  | Auto Scheduled | LifeCycle Tasks | 335.75 days | 09 December 2020 8:00 | 10 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.16.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1854 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1855 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1856 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 39.38 days | 13 January 2022 8:00 | 02 March 2022 17:00 | 0 |  | 0h | 01.16.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1857 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 March 2022 8:00 | 07 March 2022 15:00 | 0 | 1856 | 25h | 01.16.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1858 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 March 2022 15:00 | 08 March 2022 16:00 | 0 | 1857 | 10h | 01.16.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1859 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 March 2022 16:00 | 09 March 2022 17:00 | 0 | 1858 | 10h | 01.16.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1860 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 March 2022 8:00 | 10 March 2022 13:00 | 0 | 1859 | 5h | 01.16.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1861 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 March 2022 13:00 | 10 March 2022 13:00 | 0 | 1860,1854 | 0h | 01.16.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1862 |  | Auto Scheduled | מערכת סאפ תשלח שדר למערכת הזכיין עם נתוני אספקת צפי פנימי | 325.63 days | 09 December 2020 8:00 | 27 February 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.16.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1863 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1864 |  | Auto Scheduled | LifeCycle Tasks | 325.63 days | 09 December 2020 8:00 | 27 February 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.16.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1865 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1866 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1867 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 39.38 days | 02 January 2022 8:00 | 17 February 2022 17:00 | 0 |  | 0h | 01.16.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1868 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 February 2022 8:00 | 22 February 2022 15:00 | 0 | 1867 | 25h | 01.16.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1869 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 February 2022 15:00 | 23 February 2022 16:00 | 0 | 1868 | 10h | 01.16.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1870 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 February 2022 16:00 | 24 February 2022 17:00 | 0 | 1869 | 10h | 01.16.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1871 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 February 2022 8:00 | 27 February 2022 13:00 | 0 | 1870 | 5h | 01.16.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1872 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 27 February 2022 13:00 | 27 February 2022 13:00 | 0 | 1871,1865 | 0h | 01.16.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1873 |  | Auto Scheduled | מערכת זכיין תשלח שדר עדכון של הסטאטוסים למערכת הסאפ | 363.88 days | 09 December 2020 8:00 | 14 April 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.16.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
1874 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1875 |  | Auto Scheduled | LifeCycle Tasks | 363.88 days | 09 December 2020 8:00 | 14 April 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 01.16.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1876 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1877 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1878 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 33.75 days | 24 February 2022 8:00 | 06 April 2022 17:00 | 0 |  | 0h | 01.16.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
1879 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 April 2022 8:00 | 11 April 2022 15:00 | 0 | 1878 | 25h | 01.16.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1880 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 April 2022 15:00 | 12 April 2022 16:00 | 0 | 1879 | 10h | 01.16.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1881 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 April 2022 16:00 | 13 April 2022 17:00 | 0 | 1880 | 10h | 01.16.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1882 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 April 2022 8:00 | 14 April 2022 13:00 | 0 | 1881 | 5h | 01.16.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1883 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 14 April 2022 13:00 | 14 April 2022 13:00 | 0 | 1882,1876 | 0h | 01.16.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
1884 |  | Auto Scheduled | 01.16: המרות טכניות.SAP | 347 days | 09 December 2020 8:00 | 24 March 2022 13:00 | 0.17000000000000001 |  | 980h | 01.16.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
1885 |  | Auto Scheduled | מערכת סאפ תסגור את הזמנת הצפי הפנימי לאחר קבלת הפריטים למלאי | 347 days | 09 December 2020 8:00 | 24 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.16.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1886 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1887 |  | Auto Scheduled | LifeCycle Tasks | 347 days | 09 December 2020 8:00 | 24 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 01.16.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1888 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1889 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1890 |  | Auto Scheduled | יישום ופיתוח סאפ | 39.38 days | 27 January 2022 8:00 | 16 March 2022 17:00 | 0 |  | 0h | 01.16.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1891 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 March 2022 8:00 | 21 March 2022 15:00 | 0 | 1890 | 25h | 01.16.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1892 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 March 2022 15:00 | 22 March 2022 16:00 | 0 | 1891 | 10h | 01.16.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1893 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 March 2022 16:00 | 23 March 2022 17:00 | 0 | 1892 | 10h | 01.16.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1894 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 March 2022 8:00 | 24 March 2022 13:00 | 0 | 1893 | 5h | 01.16.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1895 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 March 2022 13:00 | 24 March 2022 13:00 | 0 | 1894,1888 | 0h | 01.16.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1896 |  | Auto Scheduled | מערכת סאפ תאפשר קישור פתיחת הזמנת צפי פנימי עם הזמנת הרכש המקורית | 251.38 days | 09 December 2020 8:00 | 25 November 2021 13:00 | 0.16 |  | 70h | 01.16.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1897 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1898 |  | Auto Scheduled | LifeCycle Tasks | 251.38 days | 09 December 2020 8:00 | 25 November 2021 13:00 | 0.16 |  | 70h | 01.16.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1899 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1900 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1901 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 10 November 2021 8:00 | 17 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1902 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 November 2021 8:00 | 22 November 2021 15:00 | 0 | 1901 | 25h | 01.16.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1903 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 November 2021 15:00 | 23 November 2021 16:00 | 0 | 1902 | 10h | 01.16.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1904 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 November 2021 16:00 | 24 November 2021 17:00 | 0 | 1903 | 10h | 01.16.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1905 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 November 2021 8:00 | 25 November 2021 13:00 | 0 | 1904 | 5h | 01.16.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1906 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 November 2021 13:00 | 25 November 2021 13:00 | 0 | 1905,1899 | 0h | 01.16.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1907 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת הזמנת צפי פנימי עם המק"טים שהגיעו בפועל | 250.25 days | 09 December 2020 8:00 | 24 November 2021 13:00 | 0.16 |  | 70h | 01.16.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1908 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1909 |  | Auto Scheduled | LifeCycle Tasks | 250.25 days | 09 December 2020 8:00 | 24 November 2021 13:00 | 0.16 |  | 70h | 01.16.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1910 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1911 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1912 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 09 November 2021 8:00 | 16 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1913 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 November 2021 8:00 | 21 November 2021 15:00 | 0 | 1912 | 25h | 01.16.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1914 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 November 2021 15:00 | 22 November 2021 16:00 | 0 | 1913 | 10h | 01.16.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1915 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 November 2021 16:00 | 23 November 2021 17:00 | 0 | 1914 | 10h | 01.16.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1916 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 November 2021 8:00 | 24 November 2021 13:00 | 0 | 1915 | 5h | 01.16.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1917 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 November 2021 13:00 | 24 November 2021 13:00 | 0 | 1916,1910 | 0h | 01.16.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1918 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת הזמנת רכש עם מק"ט רכש שצפוי להגיע | 249.13 days | 09 December 2020 8:00 | 23 November 2021 13:00 | 0.16 |  | 70h | 01.16.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1919 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1920 |  | Auto Scheduled | LifeCycle Tasks | 249.13 days | 09 December 2020 8:00 | 23 November 2021 13:00 | 0.16 |  | 70h | 01.16.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1921 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1922 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1923 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 08 November 2021 8:00 | 15 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1924 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 November 2021 8:00 | 18 November 2021 15:00 | 0 | 1923 | 25h | 01.16.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1925 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 November 2021 15:00 | 21 November 2021 16:00 | 0 | 1924 | 10h | 01.16.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1926 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 November 2021 16:00 | 22 November 2021 17:00 | 0 | 1925 | 10h | 01.16.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1927 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 November 2021 8:00 | 23 November 2021 13:00 | 0 | 1926 | 5h | 01.16.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1928 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 23 November 2021 13:00 | 23 November 2021 13:00 | 0 | 1927,1921 | 0h | 01.16.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1929 |  | Auto Scheduled | מערכת סאפ לא תפתח פק"ע, לא תבצע תנועות מלאי ולא תשלח שדרים במידה ובדיקת החוקה אינה עוברת תקינה | 243.5 days | 09 December 2020 8:00 | 16 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1930 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1931 |  | Auto Scheduled | LifeCycle Tasks | 243.5 days | 09 December 2020 8:00 | 16 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1932 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1933 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1934 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 04 November 2021 8:00 | 08 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1935 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 November 2021 8:00 | 11 November 2021 15:00 | 0 | 1934 | 25h | 01.16.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1936 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 November 2021 15:00 | 14 November 2021 16:00 | 0 | 1935 | 10h | 01.16.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1937 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 November 2021 16:00 | 15 November 2021 17:00 | 0 | 1936 | 10h | 01.16.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1938 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 November 2021 8:00 | 16 November 2021 13:00 | 0 | 1937 | 5h | 01.16.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1939 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 16 November 2021 13:00 | 16 November 2021 13:00 | 0 | 1938,1932 | 0h | 01.16.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1940 |  | Auto Scheduled | מערכת סאפ תקדים את בדיקת כלל החוקות לשלב של טרם פתיחת הפק"ע חוקות במסך זי אמ הייצ' 1 ומיגו | 241.25 days | 09 December 2020 8:00 | 14 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1941 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1942 |  | Auto Scheduled | LifeCycle Tasks | 241.25 days | 09 December 2020 8:00 | 14 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1943 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1944 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1945 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 02 November 2021 8:00 | 04 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1946 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 November 2021 8:00 | 09 November 2021 15:00 | 0 | 1945 | 25h | 01.16.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1947 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 November 2021 15:00 | 10 November 2021 16:00 | 0 | 1946 | 10h | 01.16.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1948 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 November 2021 16:00 | 11 November 2021 17:00 | 0 | 1947 | 10h | 01.16.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1949 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 November 2021 8:00 | 14 November 2021 13:00 | 0 | 1948 | 5h | 01.16.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1950 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 14 November 2021 13:00 | 14 November 2021 13:00 | 0 | 1949,1943 | 0h | 01.16.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1951 |  | Auto Scheduled | מערכת סאפ לא תבצע תנועות מלאי באופן אוטומטי לאחר בדיקת חוקות תקינות כאשר ההמרה מיועדת לביצוע במחסן שמנוהל זכיין | 241.25 days | 09 December 2020 8:00 | 14 November 2021 13:00 | 8.9999999999999997E-2 |  | 70h | 01.16.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1952 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1953 |  | Auto Scheduled | LifeCycle Tasks | 241.25 days | 09 December 2020 8:00 | 14 November 2021 13:00 | 8.9999999999999997E-2 |  | 70h | 01.16.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1954 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1955 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1956 |  | Auto Scheduled | יישום ופיתוח סאפ | 18 days | 14 October 2021 8:00 | 04 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1957 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 November 2021 8:00 | 09 November 2021 15:00 | 0 | 1956 | 25h | 01.16.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1958 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 November 2021 15:00 | 10 November 2021 16:00 | 0 | 1957 | 10h | 01.16.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1959 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 November 2021 16:00 | 11 November 2021 17:00 | 0 | 1958 | 10h | 01.16.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1960 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 November 2021 8:00 | 14 November 2021 13:00 | 0 | 1959 | 5h | 01.16.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1961 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 14 November 2021 13:00 | 14 November 2021 13:00 | 0 | 1960,1954 | 0h | 01.16.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1962 |  | Auto Scheduled | מערכת סאפ תאפשר בדיקת החוקות להמרה בין מק"טים | 225.5 days | 09 December 2020 8:00 | 25 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1963 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1964 |  | Auto Scheduled | LifeCycle Tasks | 225.5 days | 09 December 2020 8:00 | 25 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1965 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1966 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1967 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 13 October 2021 8:00 | 17 October 2021 17:00 | 0 |  | 0h | 01.16.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1968 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 October 2021 8:00 | 20 October 2021 15:00 | 0 | 1967 | 25h | 01.16.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1969 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 October 2021 15:00 | 21 October 2021 16:00 | 0 | 1968 | 10h | 01.16.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1970 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 October 2021 16:00 | 24 October 2021 17:00 | 0 | 1969 | 10h | 01.16.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1971 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 October 2021 8:00 | 25 October 2021 13:00 | 0 | 1970 | 5h | 01.16.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1972 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 October 2021 13:00 | 25 October 2021 13:00 | 0 | 1971,1965 | 0h | 01.16.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1973 |  | Auto Scheduled | מערכת סאפ תאפשר הזנת מק"ט נוכחי ומק"ט חדש ע"ב טרנזקציות זי אמ הייצ' 1,2 | 224.38 days | 09 December 2020 8:00 | 24 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1974 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1975 |  | Auto Scheduled | LifeCycle Tasks | 224.38 days | 09 December 2020 8:00 | 24 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1976 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1977 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1978 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 12 October 2021 8:00 | 14 October 2021 17:00 | 0 |  | 0h | 01.16.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1979 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 October 2021 8:00 | 19 October 2021 15:00 | 0 | 1978 | 25h | 01.16.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1980 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 October 2021 15:00 | 20 October 2021 16:00 | 0 | 1979 | 10h | 01.16.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1981 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 October 2021 16:00 | 21 October 2021 17:00 | 0 | 1980 | 10h | 01.16.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1982 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 October 2021 8:00 | 24 October 2021 13:00 | 0 | 1981 | 5h | 01.16.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1983 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 October 2021 13:00 | 24 October 2021 13:00 | 0 | 1982,1976 | 0h | 01.16.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1984 |  | Auto Scheduled | מערכת סאפ תאפשר המשך תהליך עבודה להמרות טכניות עבור מחסנים מיוחדים | 223.25 days | 09 December 2020 8:00 | 21 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1985 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1986 |  | Auto Scheduled | LifeCycle Tasks | 223.25 days | 09 December 2020 8:00 | 21 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1987 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1988 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1989 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 11 October 2021 8:00 | 13 October 2021 17:00 | 0 |  | 0h | 01.16.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
1990 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 October 2021 8:00 | 18 October 2021 15:00 | 0 | 1989 | 25h | 01.16.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1991 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 October 2021 15:00 | 19 October 2021 16:00 | 0 | 1990 | 10h | 01.16.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1992 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 October 2021 16:00 | 20 October 2021 17:00 | 0 | 1991 | 10h | 01.16.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1993 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 21 October 2021 8:00 | 21 October 2021 13:00 | 0 | 1992 | 5h | 01.16.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1994 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 21 October 2021 13:00 | 21 October 2021 13:00 | 0 | 1993,1987 | 0h | 01.16.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1995 |  | Auto Scheduled | מערכת סאפ תאפשר עבודה תהליך המרות טכניות במבנה ארגוני הקיים והמבנה הארגוני החדש | 222.13 days | 09 December 2020 8:00 | 20 October 2021 13:00 | 0.25 |  | 70h | 01.16.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
1996 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
1997 |  | Auto Scheduled | LifeCycle Tasks | 222.13 days | 09 December 2020 8:00 | 20 October 2021 13:00 | 0.25 |  | 70h | 01.16.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
1998 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
1999 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2000 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 05 October 2021 8:00 | 12 October 2021 17:00 | 0.20000000000000001 |  | 0h | 01.16.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2001 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 2000 | 25h | 01.16.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2002 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 2001 | 10h | 01.16.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2003 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 2002 | 10h | 01.16.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2004 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 2003 | 5h | 01.16.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2005 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 2004,1998 | 0h | 01.16.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2006 |  | Auto Scheduled | מערכת סאפ תרחיב את החוקה הקיימת עבור מבנה ארגוני חדש | 222.13 days | 09 December 2020 8:00 | 20 October 2021 13:00 | 0.17000000000000001 |  | 70h | 01.16.SAP.12 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2007 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2008 |  | Auto Scheduled | LifeCycle Tasks | 222.13 days | 09 December 2020 8:00 | 20 October 2021 13:00 | 0.17000000000000001 |  | 70h | 01.16.SAP.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2009 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.12.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2010 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.12.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2011 |  | Auto Scheduled | יישום ופיתוח סאפ | 19.13 days | 02 September 2021 8:00 | 12 October 2021 17:00 | 0.12 |  | 0h | 01.16.SAP.12.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2012 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 2011 | 25h | 01.16.SAP.12.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2013 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 2012 | 10h | 01.16.SAP.12.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2014 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 2013 | 10h | 01.16.SAP.12.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2015 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 2014 | 5h | 01.16.SAP.12.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2016 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 2015,2009 | 0h | 01.16.SAP.12.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2017 |  | Auto Scheduled | תשתית החוקה המתבצעת בעת ההמרה תעבור לשלב מוקדם יותר בתהליך. | 228.88 days | 09 December 2020 8:00 | 28 October 2021 13:00 | 0.25 |  | 70h | 01.16.SAP.13 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2018 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.13.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2019 |  | Auto Scheduled | LifeCycle Tasks | 228.88 days | 09 December 2020 8:00 | 28 October 2021 13:00 | 0.25 |  | 70h | 01.16.SAP.13.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2020 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.13.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2021 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.13.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2022 |  | Auto Scheduled | יישום ופיתוח סאפ | 36 days | 22 August 2021 8:00 | 20 October 2021 17:00 | 0.23999999999999999 |  | 0h | 01.16.SAP.13.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2023 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 October 2021 8:00 | 25 October 2021 15:00 | 0 | 2022 | 25h | 01.16.SAP.13.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2024 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 October 2021 15:00 | 26 October 2021 16:00 | 0 | 2023 | 10h | 01.16.SAP.13.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2025 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 October 2021 16:00 | 27 October 2021 17:00 | 0 | 2024 | 10h | 01.16.SAP.13.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2026 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 October 2021 8:00 | 28 October 2021 13:00 | 0 | 2025 | 5h | 01.16.SAP.13.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2027 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 October 2021 13:00 | 28 October 2021 13:00 | 0 | 2026,2020 | 0h | 01.16.SAP.13.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2028 |  | Auto Scheduled | מערכת סאפ תציג הודעת שגיאה עם סיבה שבגללה נפלה בדיקת החוקה | 242.38 days | 09 December 2020 8:00 | 15 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.14 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2029 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.14.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2030 |  | Auto Scheduled | LifeCycle Tasks | 242.38 days | 09 December 2020 8:00 | 15 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.16.SAP.14.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2031 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.16.SAP.14.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2032 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 09 December 2020 8:00 | 13 December 2020 10:00 | 1 | 1829 | 20h | 01.16.SAP.14.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2033 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 03 November 2021 8:00 | 07 November 2021 17:00 | 0 |  | 0h | 01.16.SAP.14.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2034 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 November 2021 8:00 | 10 November 2021 15:00 | 0 | 2033 | 25h | 01.16.SAP.14.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2035 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 November 2021 15:00 | 11 November 2021 16:00 | 0 | 2034 | 10h | 01.16.SAP.14.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2036 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 November 2021 16:00 | 14 November 2021 17:00 | 0 | 2035 | 10h | 01.16.SAP.14.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2037 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 November 2021 8:00 | 15 November 2021 13:00 | 0 | 2036 | 5h | 01.16.SAP.14.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2038 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 15 November 2021 13:00 | 15 November 2021 13:00 | 0 | 2037,2031 | 0h | 01.16.SAP.14.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2039 |  | Auto Scheduled | 01.17: סדרות | 429.13 days | 16 August 2020 8:00 | 10 March 2022 13:00 | 0.28000000000000003 |  | 1,389h | 01.17 | חתום | מוריה | hd | עינת | nan | BP | NA | As Soon As Possible | 3
2040 |  | Auto Scheduled | 01.17: סדרות.BP | 93.38 days | 16 August 2020 8:00 | 08 December 2020 17:00 | 1 |  | 129h | 01.17.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2041 |  | Auto Scheduled | 01.17: סדרות | 93.38 days | 16 August 2020 8:00 | 08 December 2020 17:00 | 1 |  | 129h | 01.17.BP.01 | חתום | מוריה | parent | עינת | nan | BP | NA | As Soon As Possible | 5
2042 |  | Auto Scheduled | Sub Tasks | 92.38 days | 16 August 2020 8:00 | 08 December 2020 9:00 | 1 |  | 89h | 01.17.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2043 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 16 August 2020 8:00 | 17 August 2020 10:00 | 1 |  | 11h | 01.17.BP.01.01.20 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | Must Start On | 7
2044 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.38 days | 01 September 2020 8:00 | 02 September 2020 10:00 | 1 |  | 11h | 01.17.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2045 |  | Auto Scheduled | אישור אבי | 0.75 days | 15 September 2020 8:00 | 15 September 2020 14:00 | 1 | 2044 | 6h | 01.17.BP.01.01.22 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2046 |  | Auto Scheduled | אישור מקל"ר | 2 days | 22 September 2020 8:00 | 23 September 2020 15:00 | 1 | 2045 | 16h | 01.17.BP.01.01.23 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2047 |  | Auto Scheduled | אישור מפקדת | 0.38 days | 13 October 2020 8:00 | 13 October 2020 11:00 | 1 | 2046 | 3h | 01.17.BP.01.01.24 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2048 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 15 October 2020 8:00 | 15 October 2020 10:00 | 1 | 2047 | 2h | 01.17.BP.01.01.25 | בוצע | סיגל | MoM | עינת | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
2049 |  | Auto Scheduled | אישור חטלו"ג | 2 days | 18 October 2020 8:00 | 19 October 2020 15:00 | 1 | 2048 | 16h | 01.17.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
2050 |  | Auto Scheduled | אישור ניר בשן | 2.88 days | 08 November 2020 8:00 | 10 November 2020 13:00 | 1 | 2049 | 23h | 01.17.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2051 |  | Auto Scheduled | אישור שגיב שרביט | 0.13 days | 08 December 2020 8:00 | 08 December 2020 9:00 | 1 | 2050 | 1h | 01.17.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2052 |  | Auto Scheduled | LifeCycle Tasks | 38.25 days | 22 October 2020 8:00 | 08 December 2020 17:00 | 1 |  | 40h | 01.17.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2053 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 08 December 2020 8:00 | 08 December 2020 17:00 | 1 | 2051 | 0h | 01.17.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2054 |  | Auto Scheduled | טרם החל | 0.63 days | 22 October 2020 8:00 | 22 October 2020 13:00 | 1 |  | 5h | 01.17.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2055 |  | Auto Scheduled | בעבודה | 1.25 days | 29 October 2020 8:00 | 01 November 2020 9:00 | 1 | 2054 | 10h | 01.17.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2056 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 12 November 2020 8:00 | 12 November 2020 13:00 | 1 | 2055 | 5h | 01.17.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2057 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 19 November 2020 8:00 | 22 November 2020 9:00 | 1 | 2056 | 10h | 01.17.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2058 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 03 December 2020 8:00 | 06 December 2020 9:00 | 1 | 2057 | 10h | 01.17.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2059 |  | Auto Scheduled | בחתימה | 0 days | 08 December 2020 8:00 | 08 December 2020 8:00 | 1 | 2058,2053 | 0h | 01.17.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2060 |  | Auto Scheduled | חתום | 0 days | 08 December 2020 8:00 | 08 December 2020 8:00 | 1 | 2059 | 0h | 01.17.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2061 |  | Auto Scheduled | 01.17: סדרות.INT | 336.88 days | 08 December 2020 8:00 | 10 March 2022 13:00 | 0.23000000000000001 |  | 140h | 01.17.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2062 |  | Auto Scheduled | מערכת הסאפ תפיץ נתוני סדרה לזכיין , לשלושת המרחבים עבור פתיחת סדרות,שינוי מאפיינים,סטאטוס סדרות | 315.5 days | 08 December 2020 8:00 | 13 February 2022 13:00 | 0.37 |  | 70h | 01.17.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2063 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2064 |  | Auto Scheduled | LifeCycle Tasks | 315.5 days | 08 December 2020 8:00 | 13 February 2022 13:00 | 0.37 |  | 70h | 01.17.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2065 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2066 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2067 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 28.13 days | 02 January 2022 8:00 | 03 February 2022 17:00 | 0.39000000000000001 |  | 0h | 01.17.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
2068 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 February 2022 8:00 | 08 February 2022 15:00 | 0 | 2067 | 25h | 01.17.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2069 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 February 2022 15:00 | 09 February 2022 16:00 | 0 | 2068 | 10h | 01.17.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2070 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 February 2022 16:00 | 10 February 2022 17:00 | 0 | 2069 | 10h | 01.17.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2071 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 February 2022 8:00 | 13 February 2022 13:00 | 0 | 2070 | 5h | 01.17.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2072 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 13 February 2022 13:00 | 13 February 2022 13:00 | 0 | 2071,2065 | 0h | 01.17.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2073 |  | Auto Scheduled | מערכת הזכיין תאפשר לפתוח סדרות ושינוי מאפייני סדרה , מערכת זכיין תשלח בממשק לסאפ את השינוי שבוצע מערכת סאפ תעדכן את יתר המרחיבם ע"ב דרישה מספר 94 | 336.88 days | 08 December 2020 8:00 | 10 March 2022 13:00 | 0.14000000000000001 |  | 70h | 01.17.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2074 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2075 |  | Auto Scheduled | LifeCycle Tasks | 336.88 days | 08 December 2020 8:00 | 10 March 2022 13:00 | 0.14000000000000001 |  | 70h | 01.17.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2076 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2077 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2078 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 49.5 days | 02 January 2022 8:00 | 02 March 2022 17:00 | 0.11 |  | 0h | 01.17.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
2079 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 March 2022 8:00 | 07 March 2022 15:00 | 0 | 2078 | 25h | 01.17.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2080 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 March 2022 15:00 | 08 March 2022 16:00 | 0 | 2079 | 10h | 01.17.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2081 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 March 2022 16:00 | 09 March 2022 17:00 | 0 | 2080 | 10h | 01.17.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2082 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 March 2022 8:00 | 10 March 2022 13:00 | 0 | 2081 | 5h | 01.17.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2083 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 March 2022 13:00 | 10 March 2022 13:00 | 0 | 2082,2076 | 0h | 01.17.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2084 |  | Auto Scheduled | 01.17: סדרות.SAP | 257 days | 08 December 2020 8:00 | 01 December 2021 13:00 | 0.26000000000000001 |  | 1,120h | 01.17.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2085 |  | Auto Scheduled | מערכת סאפ תקבע טווח מספרים לקודי סדרה שונים בין מרחבים | 215.38 days | 08 December 2020 8:00 | 11 October 2021 13:00 | 8.0000000000000002E-2 |  | 70h | 01.17.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2086 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2087 |  | Auto Scheduled | LifeCycle Tasks | 215.38 days | 08 December 2020 8:00 | 11 October 2021 13:00 | 8.0000000000000002E-2 |  | 70h | 01.17.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2088 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2089 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2090 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 22 August 2021 8:00 | 03 October 2021 17:00 | 0 |  | 0h | 01.17.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2091 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 October 2021 8:00 | 06 October 2021 15:00 | 0 | 2090 | 25h | 01.17.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2092 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 October 2021 15:00 | 07 October 2021 16:00 | 0 | 2091 | 10h | 01.17.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2093 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 October 2021 16:00 | 10 October 2021 17:00 | 0 | 2092 | 10h | 01.17.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2094 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 October 2021 8:00 | 11 October 2021 13:00 | 0 | 2093 | 5h | 01.17.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2095 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 11 October 2021 13:00 | 11 October 2021 13:00 | 0 | 2094,2088 | 0h | 01.17.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2096 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת סדרה ע"ב מסך מיגו עבור סדרות במחסנים מנוהלי סאפ | 212 days | 08 December 2020 8:00 | 06 October 2021 13:00 | 0.39000000000000001 |  | 70h | 01.17.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2097 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2098 |  | Auto Scheduled | LifeCycle Tasks | 212 days | 08 December 2020 8:00 | 06 October 2021 13:00 | 0.39000000000000001 |  | 70h | 01.17.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2099 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2100 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2101 |  | Auto Scheduled | יישום ופיתוח סאפ | 34.88 days | 01 August 2021 8:00 | 19 September 2021 17:00 | 0.41999999999999998 |  | 0h | 01.17.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2102 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 September 2021 8:00 | 03 October 2021 15:00 | 0 | 2101 | 25h | 01.17.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2103 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 October 2021 15:00 | 04 October 2021 16:00 | 0 | 2102 | 10h | 01.17.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2104 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 October 2021 16:00 | 05 October 2021 17:00 | 0 | 2103 | 10h | 01.17.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2105 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 October 2021 8:00 | 06 October 2021 13:00 | 0 | 2104 | 5h | 01.17.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2106 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 October 2021 13:00 | 06 October 2021 13:00 | 0 | 2105,2099 | 0h | 01.17.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2107 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת סדרה ע"ב מסך VL32N עבור סדרות במחסנים מנוהלי סאפ סדרות מזון | 227.75 days | 08 December 2020 8:00 | 26 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.17.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2108 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2109 |  | Auto Scheduled | LifeCycle Tasks | 227.75 days | 08 December 2020 8:00 | 26 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.17.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2110 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2111 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2112 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 14 October 2021 8:00 | 18 October 2021 17:00 | 0 |  | 0h | 01.17.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2113 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 October 2021 8:00 | 21 October 2021 15:00 | 0 | 2112 | 25h | 01.17.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2114 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 October 2021 15:00 | 24 October 2021 16:00 | 0 | 2113 | 10h | 01.17.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2115 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 October 2021 16:00 | 25 October 2021 17:00 | 0 | 2114 | 10h | 01.17.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2116 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 26 October 2021 8:00 | 26 October 2021 13:00 | 0 | 2115 | 5h | 01.17.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2117 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 26 October 2021 13:00 | 26 October 2021 13:00 | 0 | 2116,2110 | 0h | 01.17.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2118 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת סדרה ע"ב מסך אמ אס סי אחד אן או דרך מרק"ט על בסיס נתונים שנשלחו | 240.13 days | 08 December 2020 8:00 | 10 November 2021 13:00 | 0.11 |  | 70h | 01.17.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2119 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2120 |  | Auto Scheduled | LifeCycle Tasks | 240.13 days | 08 December 2020 8:00 | 10 November 2021 13:00 | 0.11 |  | 70h | 01.17.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2121 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2122 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2123 |  | Auto Scheduled | יישום ופיתוח סאפ | 14.63 days | 17 October 2021 8:00 | 02 November 2021 17:00 | 0 |  | 0h | 01.17.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2124 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 November 2021 8:00 | 07 November 2021 15:00 | 0 | 2123 | 25h | 01.17.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2125 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 November 2021 15:00 | 08 November 2021 16:00 | 0 | 2124 | 10h | 01.17.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2126 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 November 2021 16:00 | 09 November 2021 17:00 | 0 | 2125 | 10h | 01.17.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2127 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 November 2021 8:00 | 10 November 2021 13:00 | 0 | 2126 | 5h | 01.17.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2128 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 November 2021 13:00 | 10 November 2021 13:00 | 0 | 2127,2121 | 0h | 01.17.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2129 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת סדרה במסגרת פתיחת פק"ע ע"ב מסך זי סי או אפס אחד | 245.75 days | 08 December 2020 8:00 | 17 November 2021 13:00 | 0.11 |  | 70h | 01.17.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2130 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2131 |  | Auto Scheduled | LifeCycle Tasks | 245.75 days | 08 December 2020 8:00 | 17 November 2021 13:00 | 0.11 |  | 70h | 01.17.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2132 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2133 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2134 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 25 October 2021 8:00 | 09 November 2021 17:00 | 0 |  | 0h | 01.17.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2135 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 November 2021 8:00 | 14 November 2021 15:00 | 0 | 2134 | 25h | 01.17.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2136 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 November 2021 15:00 | 15 November 2021 16:00 | 0 | 2135 | 10h | 01.17.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2137 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 November 2021 16:00 | 16 November 2021 17:00 | 0 | 2136 | 10h | 01.17.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2138 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 November 2021 8:00 | 17 November 2021 13:00 | 0 | 2137 | 5h | 01.17.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2139 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 November 2021 13:00 | 17 November 2021 13:00 | 0 | 2138,2132 | 0h | 01.17.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2140 |  | Auto Scheduled | מערכת הסאפ תאפשר פתיחת סדרה בתהליך הערכות | 250.25 days | 08 December 2020 8:00 | 23 November 2021 13:00 | 0.22 |  | 70h | 01.17.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2141 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2142 |  | Auto Scheduled | LifeCycle Tasks | 250.25 days | 08 December 2020 8:00 | 23 November 2021 13:00 | 0.22 |  | 70h | 01.17.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2143 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2144 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2145 |  | Auto Scheduled | יישום ופיתוח סאפ | 7.88 days | 07 November 2021 8:00 | 15 November 2021 17:00 | 0.14000000000000001 |  | 0h | 01.17.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2146 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 November 2021 8:00 | 18 November 2021 15:00 | 0 | 2145 | 25h | 01.17.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2147 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 November 2021 15:00 | 21 November 2021 16:00 | 0 | 2146 | 10h | 01.17.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2148 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 November 2021 16:00 | 22 November 2021 17:00 | 0 | 2147 | 10h | 01.17.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2149 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 November 2021 8:00 | 23 November 2021 13:00 | 0 | 2148 | 5h | 01.17.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2150 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 23 November 2021 13:00 | 23 November 2021 13:00 | 0 | 2149,2143 | 0h | 01.17.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2151 |  | Auto Scheduled | מערכת סאפ נדרשות לתת מענה לדוחות בפריטי דלק בחלוקה לחציון, טווח תאריכים במספר שנים. | 228.88 days | 08 December 2020 8:00 | 27 October 2021 13:00 | 0.68999999999999995 |  | 70h | 01.17.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2152 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2153 |  | Auto Scheduled | LifeCycle Tasks | 228.88 days | 08 December 2020 8:00 | 27 October 2021 13:00 | 0.68999999999999995 |  | 70h | 01.17.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2154 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2155 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2156 |  | Auto Scheduled | יישום ופיתוח סאפ | 11.25 days | 06 October 2021 8:00 | 19 October 2021 17:00 | 1 |  | 0h | 01.17.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2157 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 October 2021 8:00 | 24 October 2021 15:00 | 0 | 2156 | 25h | 01.17.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2158 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 October 2021 15:00 | 25 October 2021 16:00 | 0 | 2157 | 10h | 01.17.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2159 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 October 2021 16:00 | 26 October 2021 17:00 | 0 | 2158 | 10h | 01.17.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2160 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 October 2021 8:00 | 27 October 2021 13:00 | 0 | 2159 | 5h | 01.17.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2161 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 27 October 2021 13:00 | 27 October 2021 13:00 | 0 | 2160,2154 | 0h | 01.17.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2162 |  | Auto Scheduled | מערכת סאפ תאפשר לשנות מאפייני סדרות , | 252.5 days | 08 December 2020 8:00 | 25 November 2021 13:00 | 0.19 |  | 70h | 01.17.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2163 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2164 |  | Auto Scheduled | LifeCycle Tasks | 252.5 days | 08 December 2020 8:00 | 25 November 2021 13:00 | 0.19 |  | 70h | 01.17.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2165 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2166 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2167 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 14 November 2021 8:00 | 17 November 2021 17:00 | 0 |  | 0h | 01.17.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2168 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 November 2021 8:00 | 22 November 2021 15:00 | 0 | 2167 | 25h | 01.17.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2169 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 November 2021 15:00 | 23 November 2021 16:00 | 0 | 2168 | 10h | 01.17.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2170 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 November 2021 16:00 | 24 November 2021 17:00 | 0 | 2169 | 10h | 01.17.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2171 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 November 2021 8:00 | 25 November 2021 13:00 | 0 | 2170 | 5h | 01.17.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2172 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 November 2021 13:00 | 25 November 2021 13:00 | 0 | 2171,2165 | 0h | 01.17.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2173 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי סטטוס סדרה באמצעות הגו'ב הליילי בחינת מאפייני פג"ת | 221 days | 08 December 2020 8:00 | 18 October 2021 13:00 | 0.39000000000000001 |  | 70h | 01.17.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2174 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2175 |  | Auto Scheduled | LifeCycle Tasks | 221 days | 08 December 2020 8:00 | 18 October 2021 13:00 | 0.39000000000000001 |  | 70h | 01.17.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2176 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2177 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2178 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 05 October 2021 8:00 | 10 October 2021 17:00 | 0.59999999999999998 |  | 0h | 01.17.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2179 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 October 2021 8:00 | 13 October 2021 15:00 | 0 | 2178 | 25h | 01.17.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2180 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 October 2021 15:00 | 14 October 2021 16:00 | 0 | 2179 | 10h | 01.17.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2181 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 October 2021 16:00 | 17 October 2021 17:00 | 0 | 2180 | 10h | 01.17.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2182 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 October 2021 8:00 | 18 October 2021 13:00 | 0 | 2181 | 5h | 01.17.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2183 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 18 October 2021 13:00 | 18 October 2021 13:00 | 0 | 2182,2176 | 0h | 01.17.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2184 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי פג"ת לסדרה לפי שינוי במאפייני החומר באמצעות הגו'ב הליילי בחינת מאפייני פג"ת | 222.13 days | 08 December 2020 8:00 | 19 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.17.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2185 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2186 |  | Auto Scheduled | LifeCycle Tasks | 222.13 days | 08 December 2020 8:00 | 19 October 2021 13:00 | 0.23000000000000001 |  | 70h | 01.17.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2187 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2188 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2189 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 06 October 2021 8:00 | 11 October 2021 17:00 | 0.13 |  | 0h | 01.17.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2190 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 October 2021 8:00 | 14 October 2021 15:00 | 0 | 2189 | 25h | 01.17.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2191 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 October 2021 15:00 | 17 October 2021 16:00 | 0 | 2190 | 10h | 01.17.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2192 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 October 2021 16:00 | 18 October 2021 17:00 | 0 | 2191 | 10h | 01.17.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2193 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 October 2021 8:00 | 19 October 2021 13:00 | 0 | 2192 | 5h | 01.17.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2194 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 October 2021 13:00 | 19 October 2021 13:00 | 0 | 2193,2187 | 0h | 01.17.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2195 |  | Auto Scheduled | מערכת סאפ תמשיך לאפשר הזנת מספר סדרה באופן ידני | 199 days | 08 December 2020 8:00 | 05 September 2021 8:00 | 0.56999999999999995 |  | 70h | 01.17.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2196 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2197 |  | Auto Scheduled | LifeCycle Tasks | 199 days | 08 December 2020 8:00 | 05 September 2021 8:00 | 0.56999999999999995 |  | 70h | 01.17.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2198 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2199 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2200 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 21 July 2021 8:00 | 27 July 2021 17:00 | 1 |  | 0h | 01.17.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2201 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 28 July 2021 8:00 | 01 August 2021 15:00 | 0 | 2200 | 25h | 01.17.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2202 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 01 August 2021 15:00 | 02 August 2021 16:00 | 0 | 2201 | 10h | 01.17.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2203 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 02 August 2021 16:00 | 03 August 2021 17:00 | 0 | 2202 | 10h | 01.17.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2204 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 04 August 2021 8:00 | 04 August 2021 13:00 | 0 | 2203 | 5h | 01.17.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2205 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 2204,2198 | 0h | 01.17.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2206 |  | Auto Scheduled | מערכת סאפ תאפשר לפתוח סדרה בתהליך חיוב עצמי, במחסנים מיוחדים מנוהלי סאפ וניהול צבאי בלבד. | 250.25 days | 08 December 2020 8:00 | 23 November 2021 13:00 | 0.23000000000000001 |  | 70h | 01.17.SAP.12 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2207 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2208 |  | Auto Scheduled | LifeCycle Tasks | 250.25 days | 08 December 2020 8:00 | 23 November 2021 13:00 | 0.23000000000000001 |  | 70h | 01.17.SAP.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2209 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.12.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2210 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.12.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2211 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 14 November 2021 8:00 | 15 November 2021 17:00 | 0 |  | 0h | 01.17.SAP.12.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2212 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 November 2021 8:00 | 18 November 2021 15:00 | 0 | 2211 | 25h | 01.17.SAP.12.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2213 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 November 2021 15:00 | 21 November 2021 16:00 | 0 | 2212 | 10h | 01.17.SAP.12.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2214 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 November 2021 16:00 | 22 November 2021 17:00 | 0 | 2213 | 10h | 01.17.SAP.12.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2215 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 November 2021 8:00 | 23 November 2021 13:00 | 0 | 2214 | 5h | 01.17.SAP.12.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2216 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 23 November 2021 13:00 | 23 November 2021 13:00 | 0 | 2215,2209 | 0h | 01.17.SAP.12.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2217 |  | Auto Scheduled | מערכת סאפ תאפשר לפתוח סדרות עם נומרטור פנימי ומאפיינים רלוונטים כגון תהליך ייצור, פג"ת, ספק, גודל יחידה,חלקים באריזה,כשל"פ ע"ב מסך אמ אס סי אחד אן | 257 days | 08 December 2020 8:00 | 01 December 2021 13:00 | 0.13 |  | 70h | 01.17.SAP.13 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2218 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.13.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2219 |  | Auto Scheduled | LifeCycle Tasks | 257 days | 08 December 2020 8:00 | 01 December 2021 13:00 | 0.13 |  | 70h | 01.17.SAP.13.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2220 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.13.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2221 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.13.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2222 |  | Auto Scheduled | יישום ופיתוח סאפ | 48.38 days | 13 September 2021 8:00 | 23 November 2021 17:00 | 0.10000000000000001 |  | 0h | 01.17.SAP.13.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2223 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 November 2021 8:00 | 28 November 2021 15:00 | 0 | 2222 | 25h | 01.17.SAP.13.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2224 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 November 2021 15:00 | 29 November 2021 16:00 | 0 | 2223 | 10h | 01.17.SAP.13.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2225 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 November 2021 16:00 | 30 November 2021 17:00 | 0 | 2224 | 10h | 01.17.SAP.13.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2226 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 December 2021 8:00 | 01 December 2021 13:00 | 0 | 2225 | 5h | 01.17.SAP.13.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2227 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 01 December 2021 13:00 | 01 December 2021 13:00 | 0 | 2226,2220 | 0h | 01.17.SAP.13.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2228 |  | Auto Scheduled | מערכת סאפ תאפשר לפתוח סדרה בתהליך המרות נדרש כי מלאי הסדרה לא תתאפשר לניפוק כל עוד לא בוצע המרה במערכת זכיין | 251.38 days | 08 December 2020 8:00 | 24 November 2021 13:00 | 0.17000000000000001 |  | 70h | 01.17.SAP.14 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2229 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.14.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2230 |  | Auto Scheduled | LifeCycle Tasks | 251.38 days | 08 December 2020 8:00 | 24 November 2021 13:00 | 0.17000000000000001 |  | 70h | 01.17.SAP.14.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2231 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.14.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2232 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.14.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2233 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 10 November 2021 8:00 | 16 November 2021 17:00 | 0 |  | 0h | 01.17.SAP.14.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2234 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 November 2021 8:00 | 21 November 2021 15:00 | 0 | 2233 | 25h | 01.17.SAP.14.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2235 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 November 2021 15:00 | 22 November 2021 16:00 | 0 | 2234 | 10h | 01.17.SAP.14.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2236 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 November 2021 16:00 | 23 November 2021 17:00 | 0 | 2235 | 10h | 01.17.SAP.14.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2237 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 November 2021 8:00 | 24 November 2021 13:00 | 0 | 2236 | 5h | 01.17.SAP.14.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2238 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 November 2021 13:00 | 24 November 2021 13:00 | 0 | 2237,2231 | 0h | 01.17.SAP.14.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2239 |  | Auto Scheduled | מערכת סאפ תאפשר גזירת שדה פג"ת מנתוני החומר | 199 days | 08 December 2020 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.17.SAP.15 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2240 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.15.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2241 |  | Auto Scheduled | LifeCycle Tasks | 199 days | 08 December 2020 8:00 | 05 September 2021 8:00 | 0.37 |  | 70h | 01.17.SAP.15.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2242 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.15.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2243 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.15.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2244 |  | Auto Scheduled | יישום ופיתוח סאפ | 1.13 days | 20 July 2021 8:00 | 20 July 2021 17:00 | 1 |  | 0h | 01.17.SAP.15.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2245 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 July 2021 8:00 | 25 July 2021 15:00 | 0 | 2244 | 25h | 01.17.SAP.15.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2246 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 July 2021 15:00 | 26 July 2021 16:00 | 0 | 2245 | 10h | 01.17.SAP.15.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2247 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 July 2021 16:00 | 27 July 2021 17:00 | 0 | 2246 | 10h | 01.17.SAP.15.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2248 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 July 2021 8:00 | 28 July 2021 13:00 | 0 | 2247 | 5h | 01.17.SAP.15.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2249 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 2248,2242 | 0h | 01.17.SAP.15.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2250 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת סדרות ומספור קוד סדרה גם כאשר לא מנהלים אצוות יצרן | 217.63 days | 08 December 2020 8:00 | 13 October 2021 13:00 | 0.47999999999999998 |  | 70h | 01.17.SAP.16 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2251 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.16.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2252 |  | Auto Scheduled | LifeCycle Tasks | 217.63 days | 08 December 2020 8:00 | 13 October 2021 13:00 | 0.47999999999999998 |  | 70h | 01.17.SAP.16.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2253 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.17.SAP.16.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2254 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 08 December 2020 8:00 | 10 December 2020 10:00 | 1 | 2051 | 20h | 01.17.SAP.16.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2255 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 03 October 2021 8:00 | 05 October 2021 17:00 | 1 |  | 0h | 01.17.SAP.16.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2256 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 October 2021 8:00 | 10 October 2021 15:00 | 0 | 2255 | 25h | 01.17.SAP.16.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2257 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 October 2021 15:00 | 11 October 2021 16:00 | 0 | 2256 | 10h | 01.17.SAP.16.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2258 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 October 2021 16:00 | 12 October 2021 17:00 | 0 | 2257 | 10h | 01.17.SAP.16.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2259 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 October 2021 8:00 | 13 October 2021 13:00 | 0 | 2258 | 5h | 01.17.SAP.16.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2260 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 13 October 2021 13:00 | 13 October 2021 13:00 | 0 | 2259,2253 | 0h | 01.17.SAP.16.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2261 |  | Auto Scheduled | 01.18: בימ"לים | 327.88 days | 20 August 2020 8:00 | 10 November 2021 13:00 | 0.26000000000000001 |  | 1,244h | 01.18 | חתום | מוריה | hd | מורן | nan | BP | NA | As Soon As Possible | 3
2262 |  | Auto Scheduled | 01.18: בימ"לים.BP | 110.25 days | 20 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 124h | 01.18.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2263 |  | Auto Scheduled | 01.18: בימ"לים | 110.25 days | 20 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 124h | 01.18.BP.01 | חתום | מוריה | parent | מורן | nan | BP | NA | As Soon As Possible | 5
2264 |  | Auto Scheduled | Sub Tasks | 84.63 days | 20 September 2020 8:00 | 03 January 2021 10:00 | 1 |  | 84h | 01.18.BP.01.01 |  | מוריה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2265 |  | Auto Scheduled | כתיבת מסמך | 5.63 days | 20 September 2020 8:00 | 24 September 2020 17:00 | 1 |  | 45h | 01.18.BP.01.01.20 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | Must Start On | 7
2266 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.13 days | 20 November 2020 8:00 | 22 November 2020 17:00 | 1 | 2265 | 9h | 01.18.BP.01.01.21 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
2267 |  | Auto Scheduled | אישור אבי | 0.88 days | 02 December 2020 8:00 | 02 December 2020 15:00 | 1 | 2266 | 7h | 01.18.BP.01.01.22 | בוצע | אבי | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
2268 |  | Auto Scheduled | אישור המנהלת | 0.38 days | 10 December 2020 8:00 | 10 December 2020 11:00 | 1 | 2267 | 3h | 01.18.BP.01.01.23 | בוצע | אבי | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
2269 |  | Auto Scheduled | אישור מקל"ר | 0.5 days | 14 December 2020 8:00 | 14 December 2020 12:00 | 1 | 2268 | 4h | 01.18.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2270 |  | Auto Scheduled | אישור מפקדת | 0.63 days | 17 December 2020 8:00 | 17 December 2020 13:00 | 1 | 2269 | 5h | 01.18.BP.01.01.25 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
2271 |  | Auto Scheduled | אישור ניר בשן | 1 day | 23 December 2020 8:00 | 23 December 2020 16:00 | 1 | 2270 | 8h | 01.18.BP.01.01.26 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
2272 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 03 January 2021 8:00 | 03 January 2021 9:00 | 1 | 2271 | 1h | 01.18.BP.01.01.27 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2273 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 2272 | 2h | 01.18.BP.01.01.28 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
2274 |  | Auto Scheduled | LifeCycle Tasks | 110.25 days | 20 August 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 01.18.BP.01.02 |  | מוריה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2275 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 2273 | 0h | 01.18.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2276 |  | Auto Scheduled | טרם החל | 0.63 days | 20 August 2020 8:00 | 20 August 2020 13:00 | 1 |  | 5h | 01.18.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2277 |  | Auto Scheduled | בעבודה | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 2276 | 10h | 01.18.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2278 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 10 September 2020 8:00 | 10 September 2020 13:00 | 1 | 2277 | 5h | 01.18.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2279 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 2278 | 10h | 01.18.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2280 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 October 2020 8:00 | 04 October 2020 9:00 | 1 | 2279 | 10h | 01.18.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2281 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2280,2275 | 0h | 01.18.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2282 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2281 | 0h | 01.18.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2283 |  | Auto Scheduled | 01.18: בימ"לים.INT | 218.75 days | 04 January 2021 8:00 | 10 November 2021 13:00 | 0.20999999999999999 |  | 490h | 01.18.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2284 |  | Auto Scheduled | מערכת סאפ וזכיין יאפשרו תעדוף ניפוקים בעדיפות גבוהה של פריטים הנמצאים במחסני הבימ"ל למחסני זכיין בכדי לאפשר ניפוק מהיר לדרג הנפרש בשע"ח | 218.75 days | 04 January 2021 8:00 | 10 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2285 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2286 |  | Auto Scheduled | LifeCycle Tasks | 218.75 days | 04 January 2021 8:00 | 10 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2287 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2288 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2289 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 31 October 2021 8:00 | 02 November 2021 17:00 | 0 |  | 0h | 01.18.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2290 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 November 2021 8:00 | 07 November 2021 15:00 | 0 | 2289 | 25h | 01.18.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2291 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 November 2021 15:00 | 08 November 2021 16:00 | 0 | 2290 | 10h | 01.18.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2292 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 November 2021 16:00 | 09 November 2021 17:00 | 0 | 2291 | 10h | 01.18.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2293 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 November 2021 8:00 | 10 November 2021 13:00 | 0 | 2292 | 5h | 01.18.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2294 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 November 2021 13:00 | 10 November 2021 13:00 | 0 | 2293,2287 | 0h | 01.18.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2295 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס לבימ"ל מנוהל זכיין | 198.5 days | 04 January 2021 8:00 | 17 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2296 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2297 |  | Auto Scheduled | LifeCycle Tasks | 198.5 days | 04 January 2021 8:00 | 17 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2298 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2299 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2300 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 05 October 2021 8:00 | 07 October 2021 17:00 | 0 |  | 0h | 01.18.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2301 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 October 2021 8:00 | 12 October 2021 15:00 | 0 | 2300 | 25h | 01.18.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2302 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 October 2021 15:00 | 13 October 2021 16:00 | 0 | 2301 | 10h | 01.18.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2303 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 October 2021 16:00 | 14 October 2021 17:00 | 0 | 2302 | 10h | 01.18.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2304 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 October 2021 8:00 | 17 October 2021 13:00 | 0 | 2303 | 5h | 01.18.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2305 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 17 October 2021 13:00 | 17 October 2021 13:00 | 0 | 2304,2298 | 0h | 01.18.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2306 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס לחלון קבלה בבימ"ל מנוהל זכיין | 201.88 days | 04 January 2021 8:00 | 20 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2307 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2308 |  | Auto Scheduled | LifeCycle Tasks | 201.88 days | 04 January 2021 8:00 | 20 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2309 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2310 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2311 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 10 October 2021 8:00 | 12 October 2021 17:00 | 0 |  | 0h | 01.18.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2312 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 October 2021 8:00 | 17 October 2021 15:00 | 0 | 2311 | 25h | 01.18.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2313 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 October 2021 15:00 | 18 October 2021 16:00 | 0 | 2312 | 10h | 01.18.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2314 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 October 2021 16:00 | 19 October 2021 17:00 | 0 | 2313 | 10h | 01.18.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2315 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 October 2021 8:00 | 20 October 2021 13:00 | 0 | 2314 | 5h | 01.18.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2316 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 20 October 2021 13:00 | 20 October 2021 13:00 | 0 | 2315,2309 | 0h | 01.18.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2317 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן מנוהל זכיין במרה"ס לבימ"ל מנוהל סאפ באתר 0010 | 199.63 days | 04 January 2021 8:00 | 18 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2318 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2319 |  | Auto Scheduled | LifeCycle Tasks | 199.63 days | 04 January 2021 8:00 | 18 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2320 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2321 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2322 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 06 October 2021 8:00 | 10 October 2021 17:00 | 0 |  | 0h | 01.18.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2323 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 October 2021 8:00 | 13 October 2021 15:00 | 0 | 2322 | 25h | 01.18.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2324 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 October 2021 15:00 | 14 October 2021 16:00 | 0 | 2323 | 10h | 01.18.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2325 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 October 2021 16:00 | 17 October 2021 17:00 | 0 | 2324 | 10h | 01.18.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2326 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 October 2021 8:00 | 18 October 2021 13:00 | 0 | 2325 | 5h | 01.18.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2327 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 18 October 2021 13:00 | 18 October 2021 13:00 | 0 | 2326,2320 | 0h | 01.18.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2328 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן מנוהל זכיין במרה"ס לבימ"ל מנוהל סאפ באתר מרה"ס | 203 days | 04 January 2021 8:00 | 21 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2329 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2330 |  | Auto Scheduled | LifeCycle Tasks | 203 days | 04 January 2021 8:00 | 21 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2331 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2332 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2333 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 11 October 2021 8:00 | 13 October 2021 17:00 | 0 |  | 0h | 01.18.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2334 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 October 2021 8:00 | 18 October 2021 15:00 | 0 | 2333 | 25h | 01.18.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2335 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 October 2021 15:00 | 19 October 2021 16:00 | 0 | 2334 | 10h | 01.18.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2336 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 October 2021 16:00 | 20 October 2021 17:00 | 0 | 2335 | 10h | 01.18.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2337 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 21 October 2021 8:00 | 21 October 2021 13:00 | 0 | 2336 | 5h | 01.18.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2338 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 21 October 2021 13:00 | 21 October 2021 13:00 | 0 | 2337,2331 | 0h | 01.18.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2339 |  | Auto Scheduled | מערכת זכיין תאפשר ניפוק פריטים " גמורים" ממחסן גמורים בבימ"ל אתר מרה"ס מנוהל זכיין למחסן מיוחד מנוהל סאפ באתר מרה"ס | 206.38 days | 04 January 2021 8:00 | 26 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2340 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2341 |  | Auto Scheduled | LifeCycle Tasks | 206.38 days | 04 January 2021 8:00 | 26 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2342 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2343 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2344 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 14 October 2021 8:00 | 18 October 2021 17:00 | 0 |  | 0h | 01.18.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2345 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 October 2021 8:00 | 21 October 2021 15:00 | 0 | 2344 | 25h | 01.18.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2346 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 October 2021 15:00 | 24 October 2021 16:00 | 0 | 2345 | 10h | 01.18.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2347 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 October 2021 16:00 | 25 October 2021 17:00 | 0 | 2346 | 10h | 01.18.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2348 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 26 October 2021 8:00 | 26 October 2021 13:00 | 0 | 2347 | 5h | 01.18.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2349 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 26 October 2021 13:00 | 26 October 2021 13:00 | 0 | 2348,2342 | 0h | 01.18.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2350 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים " גמורים" ממחסן גמורים בבימ"ל אתר מרה"ס למחסן מנוהל זכיין באתר מרה"ס | 207.5 days | 04 January 2021 8:00 | 27 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2351 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2352 |  | Auto Scheduled | LifeCycle Tasks | 207.5 days | 04 January 2021 8:00 | 27 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.INT.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2353 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.INT.07.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2354 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.INT.07.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2355 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 3.38 days | 17 October 2021 8:00 | 19 October 2021 17:00 | 0 |  | 0h | 01.18.INT.07.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2356 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 October 2021 8:00 | 24 October 2021 15:00 | 0 | 2355 | 25h | 01.18.INT.07.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2357 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 October 2021 15:00 | 25 October 2021 16:00 | 0 | 2356 | 10h | 01.18.INT.07.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2358 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 October 2021 16:00 | 26 October 2021 17:00 | 0 | 2357 | 10h | 01.18.INT.07.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2359 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 October 2021 8:00 | 27 October 2021 13:00 | 0 | 2358 | 5h | 01.18.INT.07.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2360 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 27 October 2021 13:00 | 27 October 2021 13:00 | 0 | 2359,2353 | 0h | 01.18.INT.07.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2361 |  | Auto Scheduled | 01.18: בימ"לים.SAP | 217.63 days | 04 January 2021 8:00 | 09 November 2021 13:00 | 0.19 |  | 630h | 01.18.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2362 |  | Auto Scheduled | מערכת סאפ תאפשר השמדה עבור פריטים מנוהלים בבימ"לים | 217.63 days | 04 January 2021 8:00 | 09 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2363 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2364 |  | Auto Scheduled | LifeCycle Tasks | 217.63 days | 04 January 2021 8:00 | 09 November 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2365 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2366 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2367 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 28 October 2021 8:00 | 01 November 2021 17:00 | 0 |  | 0h | 01.18.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2368 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 November 2021 8:00 | 04 November 2021 15:00 | 0 | 2367 | 25h | 01.18.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2369 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 04 November 2021 15:00 | 07 November 2021 16:00 | 0 | 2368 | 10h | 01.18.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2370 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 November 2021 16:00 | 08 November 2021 17:00 | 0 | 2369 | 10h | 01.18.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2371 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 November 2021 8:00 | 09 November 2021 13:00 | 0 | 2370 | 5h | 01.18.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2372 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 09 November 2021 13:00 | 09 November 2021 13:00 | 0 | 2371,2365 | 0h | 01.18.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2373 |  | Auto Scheduled | מערכת סאפ נדרשת לתמוך את שינוי מבנה ארגוני של איחוד מחלקות לבימ"ל מכני אחוד | 196.25 days | 04 January 2021 8:00 | 13 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2374 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2375 |  | Auto Scheduled | LifeCycle Tasks | 196.25 days | 04 January 2021 8:00 | 13 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2376 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2377 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2378 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 03 October 2021 8:00 | 05 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2379 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 06 October 2021 8:00 | 10 October 2021 15:00 | 0 | 2378 | 25h | 01.18.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2380 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 October 2021 15:00 | 11 October 2021 16:00 | 0 | 2379 | 10h | 01.18.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2381 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 October 2021 16:00 | 12 October 2021 17:00 | 0 | 2380 | 10h | 01.18.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2382 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 October 2021 8:00 | 13 October 2021 13:00 | 0 | 2381 | 5h | 01.18.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2383 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 13 October 2021 13:00 | 13 October 2021 13:00 | 0 | 2382,2376 | 0h | 01.18.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2384 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס למחסן ח"ח,טכני בבימ"ל מנוהל סאפ באתר 0010 | 197.38 days | 04 January 2021 8:00 | 14 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2385 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2386 |  | Auto Scheduled | LifeCycle Tasks | 197.38 days | 04 January 2021 8:00 | 14 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2387 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2388 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2389 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 04 October 2021 8:00 | 06 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2390 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 October 2021 8:00 | 11 October 2021 15:00 | 0 | 2389 | 25h | 01.18.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2391 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 October 2021 15:00 | 12 October 2021 16:00 | 0 | 2390 | 10h | 01.18.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2392 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 October 2021 16:00 | 13 October 2021 17:00 | 0 | 2391 | 10h | 01.18.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2393 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 October 2021 8:00 | 14 October 2021 13:00 | 0 | 2392 | 5h | 01.18.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2394 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 14 October 2021 13:00 | 14 October 2021 13:00 | 0 | 2393,2387 | 0h | 01.18.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2395 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס לחלון קבלה בבימ"ל מנוהל סאפ באתר מרה"ס | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2396 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2397 |  | Auto Scheduled | LifeCycle Tasks | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2398 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2399 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2400 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 07 October 2021 8:00 | 11 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2401 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 October 2021 8:00 | 14 October 2021 15:00 | 0 | 2400 | 25h | 01.18.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2402 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 October 2021 15:00 | 17 October 2021 16:00 | 0 | 2401 | 10h | 01.18.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2403 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 October 2021 16:00 | 18 October 2021 17:00 | 0 | 2402 | 10h | 01.18.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2404 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 October 2021 8:00 | 19 October 2021 13:00 | 0 | 2403 | 5h | 01.18.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2405 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 October 2021 13:00 | 19 October 2021 13:00 | 0 | 2404,2398 | 0h | 01.18.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2406 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק ח"ח,טכני פנים בימ"ל ממחסן ח"ח,טכני אתר 0010 לחלון קבלה בבימ"ל אתר מרה"ס | 204.13 days | 04 January 2021 8:00 | 24 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2407 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2408 |  | Auto Scheduled | LifeCycle Tasks | 204.13 days | 04 January 2021 8:00 | 24 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2409 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2410 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2411 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 12 October 2021 8:00 | 14 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2412 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 October 2021 8:00 | 19 October 2021 15:00 | 0 | 2411 | 25h | 01.18.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2413 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 October 2021 15:00 | 20 October 2021 16:00 | 0 | 2412 | 10h | 01.18.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2414 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 October 2021 16:00 | 21 October 2021 17:00 | 0 | 2413 | 10h | 01.18.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2415 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 October 2021 8:00 | 24 October 2021 13:00 | 0 | 2414 | 5h | 01.18.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2416 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 24 October 2021 13:00 | 24 October 2021 13:00 | 0 | 2415,2409 | 0h | 01.18.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2417 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים " גמורים" ממחסן גמורים בבימ"ל אתר מרה"ס למחסן מיוחד מנוהל סאפ באתר מרה"ס | 205.25 days | 04 January 2021 8:00 | 25 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2418 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2419 |  | Auto Scheduled | LifeCycle Tasks | 205.25 days | 04 January 2021 8:00 | 25 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2420 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2421 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2422 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 13 October 2021 8:00 | 17 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2423 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 October 2021 8:00 | 20 October 2021 15:00 | 0 | 2422 | 25h | 01.18.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2424 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 October 2021 15:00 | 21 October 2021 16:00 | 0 | 2423 | 10h | 01.18.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2425 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 October 2021 16:00 | 24 October 2021 17:00 | 0 | 2424 | 10h | 01.18.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2426 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 October 2021 8:00 | 25 October 2021 13:00 | 0 | 2425 | 5h | 01.18.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2427 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 October 2021 13:00 | 25 October 2021 13:00 | 0 | 2426,2420 | 0h | 01.18.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2428 |  | Auto Scheduled | מערכת סאפ תאפשר ניפוק פריטים ממחסן גמורים בבימ"ל מנוהל סאפ באתר מרה"ס לאתר 0010 | 208.63 days | 04 January 2021 8:00 | 28 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2429 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2430 |  | Auto Scheduled | LifeCycle Tasks | 208.63 days | 04 January 2021 8:00 | 28 October 2021 13:00 | 0.20999999999999999 |  | 70h | 01.18.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2431 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2432 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2433 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 18 October 2021 8:00 | 20 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2434 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 October 2021 8:00 | 25 October 2021 15:00 | 0 | 2433 | 25h | 01.18.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2435 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 October 2021 15:00 | 26 October 2021 16:00 | 0 | 2434 | 10h | 01.18.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2436 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 October 2021 16:00 | 27 October 2021 17:00 | 0 | 2435 | 10h | 01.18.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2437 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 October 2021 8:00 | 28 October 2021 13:00 | 0 | 2436 | 5h | 01.18.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2438 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 October 2021 13:00 | 28 October 2021 13:00 | 0 | 2437,2431 | 0h | 01.18.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2439 |  | Auto Scheduled | מערכת סאפ תאפשר חיוב עצמי ממציאת פריט,חיוב עצמי על אפסניה מייצור | 217.63 days | 04 January 2021 8:00 | 09 November 2021 13:00 | 0.16 |  | 70h | 01.18.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2440 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2441 |  | Auto Scheduled | LifeCycle Tasks | 217.63 days | 04 January 2021 8:00 | 09 November 2021 13:00 | 0.16 |  | 70h | 01.18.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2442 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2443 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2444 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 25 October 2021 8:00 | 01 November 2021 17:00 | 0 |  | 0h | 01.18.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2445 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 November 2021 8:00 | 04 November 2021 15:00 | 0 | 2444 | 25h | 01.18.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2446 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 04 November 2021 15:00 | 07 November 2021 16:00 | 0 | 2445 | 10h | 01.18.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2447 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 November 2021 16:00 | 08 November 2021 17:00 | 0 | 2446 | 10h | 01.18.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2448 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 November 2021 8:00 | 09 November 2021 13:00 | 0 | 2447 | 5h | 01.18.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2449 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 09 November 2021 13:00 | 09 November 2021 13:00 | 0 | 2448,2442 | 0h | 01.18.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2450 |  | Auto Scheduled | מערכת סאפ תאפשר צריכה,צריכה במשימה | 213.13 days | 04 January 2021 8:00 | 03 November 2021 13:00 | 0.16 |  | 70h | 01.18.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2451 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2452 |  | Auto Scheduled | LifeCycle Tasks | 213.13 days | 04 January 2021 8:00 | 03 November 2021 13:00 | 0.16 |  | 70h | 01.18.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2453 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 01.18.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2454 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2273 | 20h | 01.18.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2455 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 19 October 2021 8:00 | 26 October 2021 17:00 | 0 |  | 0h | 01.18.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2456 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 27 October 2021 8:00 | 31 October 2021 15:00 | 0 | 2455 | 25h | 01.18.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2457 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 31 October 2021 15:00 | 01 November 2021 16:00 | 0 | 2456 | 10h | 01.18.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2458 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 November 2021 16:00 | 02 November 2021 17:00 | 0 | 2457 | 10h | 01.18.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2459 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 November 2021 8:00 | 03 November 2021 13:00 | 0 | 2458 | 5h | 01.18.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2460 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 November 2021 13:00 | 03 November 2021 13:00 | 0 | 2459,2453 | 0h | 01.18.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2461 |  | Auto Scheduled | 02: שרשרת אספקה | 533.75 days | 06 July 2020 8:00 | 08 June 2022 13:00 | 0.32000000000000001 |  | 8,124h | 02 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
2462 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת | 329 days | 21 July 2020 8:00 | 12 October 2021 13:00 | 0.81000000000000005 |  | 350h | 02.01 | חתום | אבי פרישמן | hd | פריאל | nan | BP | NA | As Soon As Possible | 3
2463 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת.BP | 154.13 days | 21 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 140h | 02.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2464 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת | 154.13 days | 21 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 140h | 02.01.BP.01 | חתום | אבי פרישמן | parent | פריאל | nan | BP | NA | As Soon As Possible | 5
2465 |  | Auto Scheduled | Sub Tasks | 136.38 days | 10 August 2020 8:00 | 26 January 2021 10:00 | 1 |  | 100h | 02.01.BP.01.01 |  | אבי פרישמן | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2466 |  | Auto Scheduled | 1. באחריות אמל"ח בשיתוף פעולה עם המשתמשים, לרכז את כלל המסמכים, מסכים ותהליכים העלולים להפגע כתוצאה מהשינויים (כדוגמת הקישור בין לקוח למיכליות ברמת ארגון מכירות דלק) לצורך ביצוע ההתאמות על ידנו. | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.01.BP.01.01.10 | בוצע | פריאל | MoM | פריאל | מאיה | BP | NA | Must Start On | 7
2467 |  | Auto Scheduled | 2. יש לבדוק האם משק הדלקים שינוהל SAP בלבד יכלל באתר וארגון מכירות מרהס. באחריות אמלח למול אבי | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.01.BP.01.01.11 | בוצע | אבי | MoM | פריאל | מאיה | BP | NA | As Soon As Possible | 7
2468 |  | Auto Scheduled | כתיבת מסמך | 3.25 days | 24 September 2020 8:00 | 28 September 2020 16:00 | 1 |  | 26h | 02.01.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2469 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.5 days | 29 October 2020 8:00 | 29 October 2020 12:00 | 1 | 2468 | 4h | 02.01.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2470 |  | Auto Scheduled | אישור מקל"ר | 1.75 days | 03 November 2020 8:00 | 04 November 2020 13:00 | 1 | 2469 | 14h | 02.01.BP.01.01.32 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2471 |  | Auto Scheduled | אישור אבי | 3.88 days | 22 November 2020 8:00 | 25 November 2020 12:00 | 1 | 2470 | 31h | 02.01.BP.01.01.33 | בוצע | אבי | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2472 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 2471 | 2h | 02.01.BP.01.01.34 | בוצע | סיגל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2473 |  | Auto Scheduled | אישור מפקדת | 1.88 days | 04 January 2021 8:00 | 05 January 2021 14:00 | 1 | 2472 | 15h | 02.01.BP.01.01.35 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2474 |  | Auto Scheduled | אישור חטלו"ג | 0.25 days | 24 January 2021 8:00 | 24 January 2021 10:00 | 1 | 2473 | 2h | 02.01.BP.01.01.36 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2475 |  | Auto Scheduled | אישור ניר בשן | 0.25 days | 25 January 2021 8:00 | 25 January 2021 10:00 | 1 | 2474 | 2h | 02.01.BP.01.01.37 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2476 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 26 January 2021 8:00 | 26 January 2021 10:00 | 1 | 2475 | 2h | 02.01.BP.01.01.38 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2477 |  | Auto Scheduled | LifeCycle Tasks | 154.13 days | 21 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 40h | 02.01.BP.01.02 |  | אבי פרישמן | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2478 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 27 January 2021 8:00 | 27 January 2021 17:00 | 1 | 2476 | 0h | 02.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2479 |  | Auto Scheduled | טרם החל | 0.63 days | 21 July 2020 8:00 | 21 July 2020 13:00 | 1 |  | 5h | 02.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2480 |  | Auto Scheduled | בעבודה | 1.25 days | 28 July 2020 8:00 | 29 July 2020 9:00 | 1 | 2479 | 10h | 02.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2481 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 11 August 2020 8:00 | 11 August 2020 13:00 | 1 | 2480 | 5h | 02.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2482 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 18 August 2020 8:00 | 19 August 2020 9:00 | 1 | 2481 | 10h | 02.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2483 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 September 2020 8:00 | 02 September 2020 9:00 | 1 | 2482 | 10h | 02.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2484 |  | Auto Scheduled | בחתימה | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 2483,2478 | 0h | 02.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2485 |  | Auto Scheduled | חתום | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 2484 | 0h | 02.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2486 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת.SAP | 176 days | 27 January 2021 8:00 | 12 October 2021 13:00 | 0.79000000000000004 |  | 210h | 02.01.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2487 |  | Auto Scheduled | מערכת ה-סאפ תכלול חוקות בדרישה בהתאם למבנה הארגוני החדש של המרה"ס | 165.88 days | 27 January 2021 8:00 | 29 September 2021 13:00 | 0.87 |  | 70h | 02.01.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2488 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.01.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2489 |  | Auto Scheduled | LifeCycle Tasks | 165.88 days | 27 January 2021 8:00 | 29 September 2021 13:00 | 0.87 |  | 70h | 02.01.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2490 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.01.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2491 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2476 | 20h | 02.01.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2492 |  | Auto Scheduled | יישום ופיתוח סאפ | 95.63 days | 28 April 2021 8:00 | 05 September 2021 17:00 | 0.92000000000000004 |  | 0h | 02.01.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2493 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 September 2021 8:00 | 13 September 2021 15:00 | 0 | 2492 | 25h | 02.01.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2494 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 September 2021 15:00 | 14 September 2021 16:00 | 0 | 2493 | 10h | 02.01.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2495 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 September 2021 16:00 | 19 September 2021 17:00 | 0 | 2494 | 10h | 02.01.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2496 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 September 2021 8:00 | 29 September 2021 13:00 | 0 | 2495 | 5h | 02.01.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2497 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 September 2021 13:00 | 29 September 2021 13:00 | 0 | 2496,2490 | 0h | 02.01.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2498 |  | Auto Scheduled | מערכת ה-סאפ תאפשר אישור ידני,אוטומטי לדרישה מותאם למבנה הארגוני החדש של המרה"ס | 173.75 days | 27 January 2021 8:00 | 10 October 2021 13:00 | 0.81000000000000005 |  | 70h | 02.01.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2499 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.01.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2500 |  | Auto Scheduled | LifeCycle Tasks | 173.75 days | 27 January 2021 8:00 | 10 October 2021 13:00 | 0.81000000000000005 |  | 70h | 02.01.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2501 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.01.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2502 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2476 | 20h | 02.01.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2503 |  | Auto Scheduled | יישום ופיתוח סאפ | 39.38 days | 28 July 2021 8:00 | 30 September 2021 17:00 | 0.93000000000000005 |  | 0h | 02.01.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2504 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 October 2021 8:00 | 05 October 2021 15:00 | 0 | 2503 | 25h | 02.01.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2505 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 October 2021 15:00 | 06 October 2021 16:00 | 0 | 2504 | 10h | 02.01.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2506 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 October 2021 16:00 | 07 October 2021 17:00 | 0 | 2505 | 10h | 02.01.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2507 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 October 2021 8:00 | 10 October 2021 13:00 | 0 | 2506 | 5h | 02.01.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2508 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 October 2021 13:00 | 10 October 2021 13:00 | 0 | 2507,2501 | 0h | 02.01.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2509 |  | Auto Scheduled | מערכת ה-סאפ תתמוך באפשרות של פתיחת דרישה, למולה תאפשר פתיחת הזמנה בצורה אוטומטית ו,או באישור ידני. | 176 days | 27 January 2021 8:00 | 12 October 2021 13:00 | 0.16 |  | 70h | 02.01.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2510 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.01.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2511 |  | Auto Scheduled | LifeCycle Tasks | 176 days | 27 January 2021 8:00 | 12 October 2021 13:00 | 0.16 |  | 70h | 02.01.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2512 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.01.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2513 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2476 | 20h | 02.01.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2514 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 14 September 2021 8:00 | 04 October 2021 17:00 | 0 |  | 0h | 02.01.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2515 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 October 2021 8:00 | 07 October 2021 15:00 | 0 | 2514 | 25h | 02.01.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2516 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 October 2021 15:00 | 10 October 2021 16:00 | 0 | 2515 | 10h | 02.01.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2517 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 October 2021 16:00 | 11 October 2021 17:00 | 0 | 2516 | 10h | 02.01.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2518 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 October 2021 8:00 | 12 October 2021 13:00 | 0 | 2517 | 5h | 02.01.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2519 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 12 October 2021 13:00 | 12 October 2021 13:00 | 0 | 2518,2512 | 0h | 02.01.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2520 |  | Auto Scheduled | 02.02: אספקה ליחידות | 510.13 days | 06 July 2020 8:00 | 10 May 2022 13:00 | 0.14000000000000001 |  | 2,032h | 02.02 | חתום | פריאל ישי | hd | פריאל | nan | BP | NA | As Soon As Possible | 3
2521 |  | Auto Scheduled | 02.02: אספקה ליחידות.BP | 166.5 days | 06 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 282h | 02.02.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2522 |  | Auto Scheduled | 02.02: אספקה ליחידות | 166.5 days | 06 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 282h | 02.02.BP.01 | חתום | פריאל ישי | parent | פריאל | nan | BP | NA | As Soon As Possible | 5
2523 |  | Auto Scheduled | Sub Tasks | 164.5 days | 06 July 2020 8:00 | 26 January 2021 10:00 | 1 |  | 242h | 02.02.BP.01.01 |  | פריאל ישי | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2524 |  | Auto Scheduled | הפער המרכזי הוא נושא ניהול המצ"מ – האם ינוהל באתר אחסון נפרד מבחינת מערכת ה-SAP או לא. לאחר סגירת הנושא במבנה הארגוני נוכל לסכם את ה-BP. | 2.63 days | 13 July 2020 8:00 | 15 July 2020 11:00 | 1 |  | 21h | 02.02.BP.01.01.10 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | Must Start On | 7
2525 |  | Auto Scheduled | (הסבר – את רוב הפעולות הקשורות החזרה החלטנו שנדרש לבצע בSAP אבל אם לא יהיה אתר אחסון נפרד המצ"מ יאבד שליטה במלאי ולכן אולי נצטרך לעדכן את הBP) | 2.75 days | 12 July 2020 8:00 | 14 July 2020 12:00 | 1 |  | 22h | 02.02.BP.01.01.11 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
2526 |  | Auto Scheduled | מבחינת יישום שרשרת לא משנה באיזו מערכת המצ"מ יעבוד, למשתמשים זה משנה כי אם לא יהיה להם אתר אחסון נפרד בSAP הם לא יוכלו לבצע את הפעולות בSAP כמו שקבעו (חוששים לאבד שליטה במלאי). | 2.88 days | 09 July 2020 8:00 | 13 July 2020 13:00 | 1 |  | 23h | 02.02.BP.01.01.12 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
2527 |  | Auto Scheduled | אבי מכיר את הסוגייה וסוגיות נוספות שבעייתיות בנושא המצ"ב, שגם מלאי העלו. מה הסטאטוס? | 3 days | 08 July 2020 8:00 | 12 July 2020 14:00 | 1 |  | 24h | 02.02.BP.01.01.13 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
2528 |  | Auto Scheduled | המיפוי (/BP) של כל התהליך נשלח לאישור ב19.05. ממתין לאישור אמל"ח. | 3.13 days | 07 July 2020 8:00 | 09 July 2020 15:00 | 1 |  | 25h | 02.02.BP.01.01.14 | בוצע |  | MoM |  | מאיה | BP | NA | As Soon As Possible | 7
2529 |  | Auto Scheduled | כמו כן, נשלח לאישור BP אספקה ללא סימוכין - מה הסטאטוס? | 3.25 days | 06 July 2020 8:00 | 08 July 2020 16:00 | 1 |  | 26h | 02.02.BP.01.01.15 | בוצע |  | MoM |  | מאיה | BP | NA | As Soon As Possible | 7
2530 |  | Auto Scheduled | כתיבת מסמך | 0.5 days | 21 September 2020 8:00 | 21 September 2020 12:00 | 1 |  | 4h | 02.02.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2531 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 3.13 days | 24 September 2020 8:00 | 28 September 2020 15:00 | 1 | 2530 | 25h | 02.02.BP.01.01.31 | בוצע | פריאל | MoM |  | nan | BP | NA | As Soon As Possible | 7
2532 |  | Auto Scheduled | אישור מקל"ר | 2 days | 28 October 2020 8:00 | 29 October 2020 15:00 | 1 | 2531 | 16h | 02.02.BP.01.01.32 | בוצע |  | MoM |  | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
2533 |  | Auto Scheduled | אישור אבי | 4.25 days | 18 November 2020 8:00 | 23 November 2020 15:00 | 1 | 2532 | 34h | 02.02.BP.01.01.33 | בוצע | אבי | MoM | פריאל | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
2534 |  | Auto Scheduled | אישור מפקדת | 1.88 days | 04 January 2021 8:00 | 05 January 2021 14:00 | 1 | 2533 | 15h | 02.02.BP.01.01.34 | בוצע |  | MoM | פריאל | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
2535 |  | Auto Scheduled | אישור חטלו"ג | 0.25 days | 24 January 2021 8:00 | 24 January 2021 10:00 | 1 | 2534 | 2h | 02.02.BP.01.01.35 | בוצע |  | MoM |  | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
2536 |  | Auto Scheduled | אישור ניר בשן | 0.25 days | 25 January 2021 8:00 | 25 January 2021 10:00 | 1 | 2535 | 2h | 02.02.BP.01.01.36 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2537 |  | Auto Scheduled | אישור המנהלת | 0.13 days | 26 January 2021 8:00 | 26 January 2021 9:00 | 1 | 2536 | 1h | 02.02.BP.01.01.37 | בוצע | סיגל | MoM | פריאל | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
2538 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 26 January 2021 8:00 | 26 January 2021 10:00 | 1 | 2537 | 2h | 02.02.BP.01.01.38 | בוצע |  | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
2539 |  | Auto Scheduled | LifeCycle Tasks | 159.75 days | 14 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 40h | 02.02.BP.01.02 |  | פריאל ישי | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2540 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 27 January 2021 8:00 | 27 January 2021 17:00 | 1 | 2538 | 0h | 02.02.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2541 |  | Auto Scheduled | טרם החל | 0.63 days | 14 July 2020 8:00 | 14 July 2020 13:00 | 1 |  | 5h | 02.02.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2542 |  | Auto Scheduled | בעבודה | 1.25 days | 21 July 2020 8:00 | 22 July 2020 9:00 | 1 | 2541 | 10h | 02.02.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2543 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 04 August 2020 8:00 | 04 August 2020 13:00 | 1 | 2542 | 5h | 02.02.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2544 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 11 August 2020 8:00 | 12 August 2020 9:00 | 1 | 2543 | 10h | 02.02.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2545 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 25 August 2020 8:00 | 26 August 2020 9:00 | 1 | 2544 | 10h | 02.02.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2546 |  | Auto Scheduled | בחתימה | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 2545,2540 | 0h | 02.02.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2547 |  | Auto Scheduled | חתום | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 2546 | 0h | 02.02.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2548 |  | Auto Scheduled | 02.02: אספקה ליחידות.INT | 344.75 days | 27 January 2021 8:00 | 10 May 2022 13:00 | 8.0000000000000002E-2 |  | 910h | 02.02.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2549 |  | Auto Scheduled | מערכת ה-סאפ תשלח הזמנות למערכת ה-זכיין לטובת ליקוט, אריזה והפצה ליחידה. | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2550 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2551 |  | Auto Scheduled | LifeCycle Tasks | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2552 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2553 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2554 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 19.13 days | 02 January 2022 8:00 | 24 January 2022 17:00 | 0 |  | 0h | 02.02.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2555 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 January 2022 8:00 | 27 January 2022 15:00 | 0 | 2554 | 25h | 02.02.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2556 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 January 2022 15:00 | 30 January 2022 16:00 | 0 | 2555 | 10h | 02.02.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2557 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 January 2022 16:00 | 31 January 2022 17:00 | 0 | 2556 | 10h | 02.02.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2558 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 February 2022 8:00 | 01 February 2022 13:00 | 0 | 2557 | 5h | 02.02.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2559 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 01 February 2022 13:00 | 01 February 2022 13:00 | 0 | 2558,2552 | 0h | 02.02.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2560 |  | Auto Scheduled | הזמנת הניפוק המעודכנת תעבור בממשק למרחב המנפק הרלוונטי | 338 days | 27 January 2021 8:00 | 02 May 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 02.02.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2561 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2562 |  | Auto Scheduled | LifeCycle Tasks | 338 days | 27 January 2021 8:00 | 02 May 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 02.02.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2563 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2564 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2565 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 25.88 days | 23 March 2022 8:00 | 24 April 2022 17:00 | 0 |  | 0h | 02.02.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2566 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 April 2022 8:00 | 27 April 2022 15:00 | 0 | 2565 | 25h | 02.02.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2567 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 April 2022 15:00 | 28 April 2022 16:00 | 0 | 2566 | 10h | 02.02.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2568 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 April 2022 16:00 | 01 May 2022 17:00 | 0 | 2567 | 10h | 02.02.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2569 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 May 2022 8:00 | 02 May 2022 13:00 | 0 | 2568 | 5h | 02.02.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2570 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 02 May 2022 13:00 | 02 May 2022 13:00 | 0 | 2569,2563 | 0h | 02.02.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2571 |  | Auto Scheduled | מערכת ה- זכיין תשלח בממשק אוטומטי למערכת ה-סאפ את אספקות ה- זכיין או כל ישות מקבילה כולל נתוני התכולה המתוכננים ומועד אספקה מתוכנן.--הנתונים יכללו, מספר הזמנה כולל שורה, לקוח, משאית, פריטים, כמויות, אמצעי אריזה,ניטול, נתוני מסלול וכו'. | 298.63 days | 27 January 2021 8:00 | 14 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2572 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2573 |  | Auto Scheduled | LifeCycle Tasks | 298.63 days | 27 January 2021 8:00 | 14 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2574 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2575 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2576 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 46.13 days | 09 January 2022 8:00 | 06 March 2022 17:00 | 0 |  | 0h | 02.02.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2577 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 March 2022 8:00 | 09 March 2022 15:00 | 0 | 2576 | 25h | 02.02.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2578 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 March 2022 15:00 | 10 March 2022 16:00 | 0 | 2577 | 10h | 02.02.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2579 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 March 2022 16:00 | 13 March 2022 17:00 | 0 | 2578 | 10h | 02.02.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2580 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 March 2022 8:00 | 14 March 2022 13:00 | 0 | 2579 | 5h | 02.02.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2581 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 14 March 2022 13:00 | 14 March 2022 13:00 | 0 | 2580,2574 | 0h | 02.02.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2582 |  | Auto Scheduled | מערכת ה זכיין תתמוך בשליחת סטטוסים,חיוויים שישלחו אונליין למערכת ה סאפ, ומערכת הסאפ תאפשר קבלת עדכון סטטוס בהתאם לסטטוס האספקה הקיים במערכת הזכיין לשלבים הבאים: "בליקוט", "לוקט", "הועבר למחסן הפצה", "הועמס למשאית", "מוכן להפצה ישירות מהמחסן", "יצא למשלו | 306.5 days | 27 January 2021 8:00 | 23 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2583 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2584 |  | Auto Scheduled | LifeCycle Tasks | 306.5 days | 27 January 2021 8:00 | 23 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2585 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2586 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2587 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 37.13 days | 30 January 2022 8:00 | 15 March 2022 17:00 | 0 |  | 0h | 02.02.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2588 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 March 2022 8:00 | 20 March 2022 15:00 | 0 | 2587 | 25h | 02.02.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2589 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 March 2022 15:00 | 21 March 2022 16:00 | 0 | 2588 | 10h | 02.02.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2590 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 March 2022 16:00 | 22 March 2022 17:00 | 0 | 2589 | 10h | 02.02.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2591 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 March 2022 8:00 | 23 March 2022 13:00 | 0 | 2590 | 5h | 02.02.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2592 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 23 March 2022 13:00 | 23 March 2022 13:00 | 0 | 2591,2585 | 0h | 02.02.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2593 |  | Auto Scheduled | מערכת ה סאפ תשלח שדר עדכון נתוני האספקה,משלוח למסופון פי או די רק לאחר העמסה בפועל על המשאית. | 306.5 days | 27 January 2021 8:00 | 23 March 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 02.02.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2594 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2595 |  | Auto Scheduled | LifeCycle Tasks | 306.5 days | 27 January 2021 8:00 | 23 March 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 02.02.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2596 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2597 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2598 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 31.5 days | 06 February 2022 8:00 | 15 March 2022 17:00 | 0 |  | 0h | 02.02.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2599 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 March 2022 8:00 | 20 March 2022 15:00 | 0 | 2598 | 25h | 02.02.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2600 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 March 2022 15:00 | 21 March 2022 16:00 | 0 | 2599 | 10h | 02.02.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2601 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 March 2022 16:00 | 22 March 2022 17:00 | 0 | 2600 | 10h | 02.02.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2602 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 March 2022 8:00 | 23 March 2022 13:00 | 0 | 2601 | 5h | 02.02.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2603 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 23 March 2022 13:00 | 23 March 2022 13:00 | 0 | 2602,2596 | 0h | 02.02.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2604 |  | Auto Scheduled | מערכת ה-זכיין תשדר את סטטוס האספקה ואת תנועות הניפוק למערכת ה-סאפ | 303.13 days | 27 January 2021 8:00 | 20 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.02.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2605 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2606 |  | Auto Scheduled | LifeCycle Tasks | 303.13 days | 27 January 2021 8:00 | 20 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.02.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2607 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2608 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2609 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 16.88 days | 20 February 2022 8:00 | 10 March 2022 17:00 | 0 |  | 0h | 02.02.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2610 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 March 2022 8:00 | 15 March 2022 15:00 | 0 | 2609 | 25h | 02.02.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2611 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 15 March 2022 15:00 | 16 March 2022 16:00 | 0 | 2610 | 10h | 02.02.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2612 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 March 2022 16:00 | 17 March 2022 17:00 | 0 | 2611 | 10h | 02.02.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2613 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 March 2022 8:00 | 20 March 2022 13:00 | 0 | 2612 | 5h | 02.02.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2614 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 20 March 2022 13:00 | 20 March 2022 13:00 | 0 | 2613,2607 | 0h | 02.02.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2615 |  | Auto Scheduled | הנתיב שיוזן בהזמנה יהיה פיקטיבי ובעת יצירת האספקה במערכת ה סאפ יתקבלו נתוני המסלול ממערכת הטי אמ אס ויוזנו לאספקה שתיווצר במערכת הסאפ. | 305.38 days | 27 January 2021 8:00 | 22 March 2022 13:00 | 0.11 |  | 70h | 02.02.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2616 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2617 |  | Auto Scheduled | LifeCycle Tasks | 305.38 days | 27 January 2021 8:00 | 22 March 2022 13:00 | 0.11 |  | 70h | 02.02.INT.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2618 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.07.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2619 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.07.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2620 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 13.5 days | 27 February 2022 8:00 | 14 March 2022 17:00 | 0 |  | 0h | 02.02.INT.07.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2621 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 15 March 2022 8:00 | 17 March 2022 15:00 | 0 | 2620 | 25h | 02.02.INT.07.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2622 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 March 2022 15:00 | 20 March 2022 16:00 | 0 | 2621 | 10h | 02.02.INT.07.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2623 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 20 March 2022 16:00 | 21 March 2022 17:00 | 0 | 2622 | 10h | 02.02.INT.07.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2624 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 22 March 2022 8:00 | 22 March 2022 13:00 | 0 | 2623 | 5h | 02.02.INT.07.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2625 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 22 March 2022 13:00 | 22 March 2022 13:00 | 0 | 2624,2618 | 0h | 02.02.INT.07.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2626 |  | Auto Scheduled | מערכת ה- זכיין תשלח שדרים למערכת ה- סאפ לשיקוף המשלוחים שייפתחו לצורך הפצת האספקות ליחידות | 309.88 days | 27 January 2021 8:00 | 28 March 2022 13:00 | 0.14000000000000001 |  | 70h | 02.02.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2627 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2628 |  | Auto Scheduled | LifeCycle Tasks | 309.88 days | 27 January 2021 8:00 | 28 March 2022 13:00 | 0.14000000000000001 |  | 70h | 02.02.INT.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2629 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.08.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2630 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.08.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2631 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 9 days | 09 March 2022 8:00 | 20 March 2022 17:00 | 0 |  | 0h | 02.02.INT.08.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2632 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 March 2022 8:00 | 23 March 2022 15:00 | 0 | 2631 | 25h | 02.02.INT.08.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2633 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 March 2022 15:00 | 24 March 2022 16:00 | 0 | 2632 | 10h | 02.02.INT.08.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2634 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 March 2022 16:00 | 27 March 2022 17:00 | 0 | 2633 | 10h | 02.02.INT.08.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2635 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 March 2022 8:00 | 28 March 2022 13:00 | 0 | 2634 | 5h | 02.02.INT.08.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2636 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 28 March 2022 13:00 | 28 March 2022 13:00 | 0 | 2635,2629 | 0h | 02.02.INT.08.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2637 |  | Auto Scheduled | מערכת ה – זכיין תשלח שדר למערכת הסאפ לצורך קישור אריזות לאספקה ולשימוש המידע ב – פי או די | 320 days | 27 January 2021 8:00 | 10 April 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2638 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2639 |  | Auto Scheduled | LifeCycle Tasks | 320 days | 27 January 2021 8:00 | 10 April 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.INT.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2640 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.09.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2641 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.09.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2642 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 18 days | 10 March 2022 8:00 | 31 March 2022 17:00 | 0 |  | 0h | 02.02.INT.09.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2643 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 April 2022 8:00 | 05 April 2022 15:00 | 0 | 2642 | 25h | 02.02.INT.09.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2644 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 April 2022 15:00 | 06 April 2022 16:00 | 0 | 2643 | 10h | 02.02.INT.09.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2645 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 April 2022 16:00 | 07 April 2022 17:00 | 0 | 2644 | 10h | 02.02.INT.09.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2646 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 April 2022 8:00 | 10 April 2022 13:00 | 0 | 2645 | 5h | 02.02.INT.09.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2647 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 April 2022 13:00 | 10 April 2022 13:00 | 0 | 2646,2640 | 0h | 02.02.INT.09.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2648 |  | Auto Scheduled | מערכת הפי או די תתמוך בשליחת סטטוס "קבלת משלוח" למערכת הסאפ | 322.25 days | 27 January 2021 8:00 | 12 April 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.INT.10 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2649 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2650 |  | Auto Scheduled | LifeCycle Tasks | 322.25 days | 27 January 2021 8:00 | 12 April 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.INT.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2651 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.10.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2652 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.10.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2653 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 19.13 days | 13 March 2022 8:00 | 04 April 2022 17:00 | 0 |  | 0h | 02.02.INT.10.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2654 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 April 2022 8:00 | 07 April 2022 15:00 | 0 | 2653 | 25h | 02.02.INT.10.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2655 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 April 2022 15:00 | 10 April 2022 16:00 | 0 | 2654 | 10h | 02.02.INT.10.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2656 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 April 2022 16:00 | 11 April 2022 17:00 | 0 | 2655 | 10h | 02.02.INT.10.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2657 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 April 2022 8:00 | 12 April 2022 13:00 | 0 | 2656 | 5h | 02.02.INT.10.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2658 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 12 April 2022 13:00 | 12 April 2022 13:00 | 0 | 2657,2651 | 0h | 02.02.INT.10.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2659 |  | Auto Scheduled | מערכת הזכיין תשלח שדר למערכת הסאפ לצורך יצירת משלוח מהמרחב המקבל ליחידה. | 327.88 days | 27 January 2021 8:00 | 19 April 2022 13:00 | 0.16 |  | 70h | 02.02.INT.11 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2660 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2661 |  | Auto Scheduled | LifeCycle Tasks | 327.88 days | 27 January 2021 8:00 | 19 April 2022 13:00 | 0.16 |  | 70h | 02.02.INT.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2662 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.11.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2663 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.11.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2664 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 04 April 2022 8:00 | 11 April 2022 17:00 | 0 |  | 0h | 02.02.INT.11.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2665 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 April 2022 8:00 | 14 April 2022 15:00 | 0 | 2664 | 25h | 02.02.INT.11.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2666 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 April 2022 15:00 | 17 April 2022 16:00 | 0 | 2665 | 10h | 02.02.INT.11.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2667 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 April 2022 16:00 | 18 April 2022 17:00 | 0 | 2666 | 10h | 02.02.INT.11.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2668 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 April 2022 8:00 | 19 April 2022 13:00 | 0 | 2667 | 5h | 02.02.INT.11.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2669 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 19 April 2022 13:00 | 19 April 2022 13:00 | 0 | 2668,2662 | 0h | 02.02.INT.11.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2670 |  | Auto Scheduled | מערכת הסאפ תאפשר לשלוח הזמנות למערכת הזכיין ללא בדיקת זמינות פריטים במשק המזון בלבד לטובת תכנון הפצה | 344.75 days | 27 January 2021 8:00 | 10 May 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 02.02.INT.12 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2671 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2672 |  | Auto Scheduled | LifeCycle Tasks | 344.75 days | 27 January 2021 8:00 | 10 May 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 02.02.INT.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2673 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.12.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2674 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.12.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2675 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 21.38 days | 06 April 2022 8:00 | 02 May 2022 17:00 | 0 |  | 0h | 02.02.INT.12.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2676 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 May 2022 8:00 | 05 May 2022 15:00 | 0 | 2675 | 25h | 02.02.INT.12.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2677 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 May 2022 15:00 | 08 May 2022 16:00 | 0 | 2676 | 10h | 02.02.INT.12.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2678 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 May 2022 16:00 | 09 May 2022 17:00 | 0 | 2677 | 10h | 02.02.INT.12.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2679 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 May 2022 8:00 | 10 May 2022 13:00 | 0 | 2678 | 5h | 02.02.INT.12.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2680 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 May 2022 13:00 | 10 May 2022 13:00 | 0 | 2679,2673 | 0h | 02.02.INT.12.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2681 |  | Auto Scheduled | במקרים שנשלחים למערכת ה-זכיין הזמנות ללא ציון מספר הסדרה, יש לוודא בחירת הסדרה ע"י מערכת ה- זכיין בהתאם למאפייני הפריט פיפו, ליפו וכד ועדכון הסדרה במערכות הסאפ – יבוצע באספקה לאחר ליקוט המלאי במערכת הזכיין. | 257 days | 27 January 2021 8:00 | 20 January 2022 13:00 | 0.17000000000000001 |  | 70h | 02.02.INT.13 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2682 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.13.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2683 |  | Auto Scheduled | LifeCycle Tasks | 257 days | 27 January 2021 8:00 | 20 January 2022 13:00 | 0.17000000000000001 |  | 70h | 02.02.INT.13.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2684 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.INT.13.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2685 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.INT.13.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2686 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 5.63 days | 06 January 2022 8:00 | 12 January 2022 17:00 | 0 |  | 0h | 02.02.INT.13.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2687 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 January 2022 8:00 | 17 January 2022 15:00 | 0 | 2686 | 25h | 02.02.INT.13.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2688 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 January 2022 15:00 | 18 January 2022 16:00 | 0 | 2687 | 10h | 02.02.INT.13.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2689 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 January 2022 16:00 | 19 January 2022 17:00 | 0 | 2688 | 10h | 02.02.INT.13.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2690 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 January 2022 8:00 | 20 January 2022 13:00 | 0 | 2689 | 5h | 02.02.INT.13.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2691 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 20 January 2022 13:00 | 20 January 2022 13:00 | 0 | 2690,2684 | 0h | 02.02.INT.13.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2692 |  | Auto Scheduled | 02.02: אספקה ליחידות.SAP | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 0.10000000000000001 |  | 840h | 02.02.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2693 |  | Auto Scheduled | מערכת ה סאפ תתמוך בהפקת טפסי שילוח | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.02.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2694 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2695 |  | Auto Scheduled | LifeCycle Tasks | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.02.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2696 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2697 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2698 |  | Auto Scheduled | יישום ופיתוח סאפ | 15.75 days | 05 January 2022 8:00 | 24 January 2022 17:00 | 0 |  | 0h | 02.02.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2699 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 January 2022 8:00 | 27 January 2022 15:00 | 0 | 2698 | 25h | 02.02.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2700 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 January 2022 15:00 | 30 January 2022 16:00 | 0 | 2699 | 10h | 02.02.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2701 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 January 2022 16:00 | 31 January 2022 17:00 | 0 | 2700 | 10h | 02.02.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2702 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 February 2022 8:00 | 01 February 2022 13:00 | 0 | 2701 | 5h | 02.02.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2703 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 01 February 2022 13:00 | 01 February 2022 13:00 | 0 | 2702,2696 | 0h | 02.02.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2704 |  | Auto Scheduled | מערכת ה-סאפ תאפשר פתיחת אספקה כנגד הזמנת אס טי או ולמול האספקות הסופיות המתקבלות ממערכת הזכיין. | 262.63 days | 27 January 2021 8:00 | 27 January 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2705 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2706 |  | Auto Scheduled | LifeCycle Tasks | 262.63 days | 27 January 2021 8:00 | 27 January 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2707 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2708 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2709 |  | Auto Scheduled | יישום ופיתוח סאפ | 43.88 days | 28 November 2021 8:00 | 19 January 2022 17:00 | 0 |  | 0h | 02.02.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2710 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 January 2022 8:00 | 24 January 2022 15:00 | 0 | 2709 | 25h | 02.02.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2711 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 January 2022 15:00 | 25 January 2022 16:00 | 0 | 2710 | 10h | 02.02.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2712 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 January 2022 16:00 | 26 January 2022 17:00 | 0 | 2711 | 10h | 02.02.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2713 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 January 2022 8:00 | 27 January 2022 13:00 | 0 | 2712 | 5h | 02.02.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2714 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 27 January 2022 13:00 | 27 January 2022 13:00 | 0 | 2713,2707 | 0h | 02.02.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2715 |  | Auto Scheduled | תינתן אפשרות לשליטה בהזמנות שישלחו לזכיין ע"י בעלי תפקידים שיוגדרו לכך | 236.75 days | 27 January 2021 8:00 | 27 December 2021 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2716 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2717 |  | Auto Scheduled | LifeCycle Tasks | 236.75 days | 27 January 2021 8:00 | 27 December 2021 13:00 | 5.0000000000000003E-2 |  | 70h | 02.02.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2718 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2719 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2720 |  | Auto Scheduled | יישום ופיתוח סאפ | 38.25 days | 02 November 2021 8:00 | 19 December 2021 17:00 | 0 |  | 0h | 02.02.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2721 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 December 2021 8:00 | 22 December 2021 15:00 | 0 | 2720 | 25h | 02.02.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2722 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 December 2021 15:00 | 23 December 2021 16:00 | 0 | 2721 | 10h | 02.02.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2723 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 December 2021 16:00 | 26 December 2021 17:00 | 0 | 2722 | 10h | 02.02.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2724 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 December 2021 8:00 | 27 December 2021 13:00 | 0 | 2723 | 5h | 02.02.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2725 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 27 December 2021 13:00 | 27 December 2021 13:00 | 0 | 2724,2718 | 0h | 02.02.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2726 |  | Auto Scheduled | ההזמנה תנופק מהמרחב המנפק הראשון למרחב המנפק השני למחסן ההפצה. | 189.5 days | 27 January 2021 8:00 | 28 October 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2727 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2728 |  | Auto Scheduled | LifeCycle Tasks | 189.5 days | 27 January 2021 8:00 | 28 October 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2729 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2730 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2731 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 13 October 2021 8:00 | 20 October 2021 17:00 | 0 |  | 0h | 02.02.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2732 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 October 2021 8:00 | 25 October 2021 15:00 | 0 | 2731 | 25h | 02.02.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2733 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 October 2021 15:00 | 26 October 2021 16:00 | 0 | 2732 | 10h | 02.02.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2734 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 October 2021 16:00 | 27 October 2021 17:00 | 0 | 2733 | 10h | 02.02.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2735 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 October 2021 8:00 | 28 October 2021 13:00 | 0 | 2734 | 5h | 02.02.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2736 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 October 2021 13:00 | 28 October 2021 13:00 | 0 | 2735,2729 | 0h | 02.02.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2737 |  | Auto Scheduled | מערכת הסאפ תתמוך ביצירת משלוח על סמך האספקה המקורית. | 205.25 days | 27 January 2021 8:00 | 17 November 2021 13:00 | 0.10000000000000001 |  | 70h | 02.02.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2738 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2739 |  | Auto Scheduled | LifeCycle Tasks | 205.25 days | 27 January 2021 8:00 | 17 November 2021 13:00 | 0.10000000000000001 |  | 70h | 02.02.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2740 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2741 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2742 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 20 October 2021 8:00 | 09 November 2021 17:00 | 0 |  | 0h | 02.02.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2743 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 November 2021 8:00 | 14 November 2021 15:00 | 0 | 2742 | 25h | 02.02.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2744 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 November 2021 15:00 | 15 November 2021 16:00 | 0 | 2743 | 10h | 02.02.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2745 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 November 2021 16:00 | 16 November 2021 17:00 | 0 | 2744 | 10h | 02.02.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2746 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 November 2021 8:00 | 17 November 2021 13:00 | 0 | 2745 | 5h | 02.02.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2747 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 17 November 2021 13:00 | 17 November 2021 13:00 | 0 | 2746,2740 | 0h | 02.02.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2748 |  | Auto Scheduled | מערכת הסאפ תאפשר לציין בטופס השילוח כי נדרש להוביל את המשלוח למחסן ההפצה במרכז המקבל ולא ישירות ליחידה. | 196.25 days | 27 January 2021 8:00 | 07 November 2021 13:00 | 0.13 |  | 70h | 02.02.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2749 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2750 |  | Auto Scheduled | LifeCycle Tasks | 196.25 days | 27 January 2021 8:00 | 07 November 2021 13:00 | 0.13 |  | 70h | 02.02.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2751 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2752 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2753 |  | Auto Scheduled | יישום ופיתוח סאפ | 11.25 days | 17 October 2021 8:00 | 28 October 2021 17:00 | 0 |  | 0h | 02.02.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2754 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 31 October 2021 8:00 | 02 November 2021 15:00 | 0 | 2753 | 25h | 02.02.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2755 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 02 November 2021 15:00 | 03 November 2021 16:00 | 0 | 2754 | 10h | 02.02.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2756 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 November 2021 16:00 | 04 November 2021 17:00 | 0 | 2755 | 10h | 02.02.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2757 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 November 2021 8:00 | 07 November 2021 13:00 | 0 | 2756 | 5h | 02.02.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2758 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 07 November 2021 13:00 | 07 November 2021 13:00 | 0 | 2757,2751 | 0h | 02.02.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2759 |  | Auto Scheduled | מערכת הסאפ תאפשר שינוי אתר אחסון מקבל ליחידה שלא מקושרת אליה במערכת. | 187.25 days | 27 January 2021 8:00 | 26 October 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2760 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2761 |  | Auto Scheduled | LifeCycle Tasks | 187.25 days | 27 January 2021 8:00 | 26 October 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2762 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2763 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2764 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 11 October 2021 8:00 | 18 October 2021 17:00 | 0 |  | 0h | 02.02.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2765 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 October 2021 8:00 | 21 October 2021 15:00 | 0 | 2764 | 25h | 02.02.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2766 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 October 2021 15:00 | 24 October 2021 16:00 | 0 | 2765 | 10h | 02.02.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2767 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 October 2021 16:00 | 25 October 2021 17:00 | 0 | 2766 | 10h | 02.02.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2768 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 26 October 2021 8:00 | 26 October 2021 13:00 | 0 | 2767 | 5h | 02.02.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2769 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 26 October 2021 13:00 | 26 October 2021 13:00 | 0 | 2768,2762 | 0h | 02.02.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2770 |  | Auto Scheduled | נדרש להוסיף,לוודא בעת יצירת דרישה לניפוק לגורם חוץ קיום שדה חובה למילוי מספר הספק המקבל | 263.75 days | 27 January 2021 8:00 | 30 January 2022 13:00 | 0.16 |  | 70h | 02.02.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2771 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2772 |  | Auto Scheduled | LifeCycle Tasks | 263.75 days | 27 January 2021 8:00 | 30 January 2022 13:00 | 0.16 |  | 70h | 02.02.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2773 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2774 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2775 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 13 January 2022 8:00 | 20 January 2022 17:00 | 0 |  | 0h | 02.02.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2776 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 January 2022 8:00 | 25 January 2022 15:00 | 0 | 2775 | 25h | 02.02.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2777 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 January 2022 15:00 | 26 January 2022 16:00 | 0 | 2776 | 10h | 02.02.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2778 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 January 2022 16:00 | 27 January 2022 17:00 | 0 | 2777 | 10h | 02.02.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2779 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 January 2022 8:00 | 30 January 2022 13:00 | 0 | 2778 | 5h | 02.02.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2780 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 30 January 2022 13:00 | 30 January 2022 13:00 | 0 | 2779,2773 | 0h | 02.02.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2781 |  | Auto Scheduled | ניפוק מהמרחב השני ליחידה | 203 days | 27 January 2021 8:00 | 15 November 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2782 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2783 |  | Auto Scheduled | LifeCycle Tasks | 203 days | 27 January 2021 8:00 | 15 November 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2784 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2785 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2786 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 31 October 2021 8:00 | 07 November 2021 17:00 | 0 |  | 0h | 02.02.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2787 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 November 2021 8:00 | 10 November 2021 15:00 | 0 | 2786 | 25h | 02.02.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2788 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 November 2021 15:00 | 11 November 2021 16:00 | 0 | 2787 | 10h | 02.02.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2789 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 11 November 2021 16:00 | 14 November 2021 17:00 | 0 | 2788 | 10h | 02.02.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2790 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 November 2021 8:00 | 15 November 2021 13:00 | 0 | 2789 | 5h | 02.02.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2791 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 15 November 2021 13:00 | 15 November 2021 13:00 | 0 | 2790,2784 | 0h | 02.02.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2792 |  | Auto Scheduled | מערכת הסאפ תאפשר פיצול אספקות במרחבים שטרם מובצעו בשלב המבצוע ההדרגתי על ידי נקודות המשלוח החדשות והישנות. | 183.88 days | 27 January 2021 8:00 | 21 October 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2793 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2794 |  | Auto Scheduled | LifeCycle Tasks | 183.88 days | 27 January 2021 8:00 | 21 October 2021 13:00 | 0.16 |  | 70h | 02.02.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2795 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2796 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2797 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 06 October 2021 8:00 | 13 October 2021 17:00 | 0 |  | 0h | 02.02.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2798 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 October 2021 8:00 | 18 October 2021 15:00 | 0 | 2797 | 25h | 02.02.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2799 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 October 2021 15:00 | 19 October 2021 16:00 | 0 | 2798 | 10h | 02.02.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2800 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 October 2021 16:00 | 20 October 2021 17:00 | 0 | 2799 | 10h | 02.02.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2801 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 21 October 2021 8:00 | 21 October 2021 13:00 | 0 | 2800 | 5h | 02.02.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2802 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 21 October 2021 13:00 | 21 October 2021 13:00 | 0 | 2801,2795 | 0h | 02.02.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2803 |  | Auto Scheduled | מערכת ה – סאפ תתמוך ביצירת סטאטוסים,חיוויים ברמת כותרת, לדוגמה: "הגיע ליחידה" ו"נופק" . | 189.5 days | 27 January 2021 8:00 | 28 October 2021 13:00 | 0.10000000000000001 |  | 70h | 02.02.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2804 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2805 |  | Auto Scheduled | LifeCycle Tasks | 189.5 days | 27 January 2021 8:00 | 28 October 2021 13:00 | 0.10000000000000001 |  | 70h | 02.02.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2806 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2807 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2808 |  | Auto Scheduled | יישום ופיתוח סאפ | 15.75 days | 03 October 2021 8:00 | 20 October 2021 17:00 | 0 |  | 0h | 02.02.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2809 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 October 2021 8:00 | 25 October 2021 15:00 | 0 | 2808 | 25h | 02.02.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2810 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 October 2021 15:00 | 26 October 2021 16:00 | 0 | 2809 | 10h | 02.02.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2811 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 October 2021 16:00 | 27 October 2021 17:00 | 0 | 2810 | 10h | 02.02.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2812 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 October 2021 8:00 | 28 October 2021 13:00 | 0 | 2811 | 5h | 02.02.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2813 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 October 2021 13:00 | 28 October 2021 13:00 | 0 | 2812,2806 | 0h | 02.02.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2814 |  | Auto Scheduled | תינתן אפשרות לשינוי אתר אחסון מנפק בשלבי הדרישה וההזמנה מה שיאפשר שליטה בבחירת גורם מנפק – צבאי או זכיין. | 232.25 days | 27 January 2021 8:00 | 21 December 2021 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.SAP.12 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2815 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.12.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2816 |  | Auto Scheduled | LifeCycle Tasks | 232.25 days | 27 January 2021 8:00 | 21 December 2021 13:00 | 8.9999999999999997E-2 |  | 70h | 02.02.SAP.12.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2817 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.02.SAP.12.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2818 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 2538 | 20h | 02.02.SAP.12.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2819 |  | Auto Scheduled | יישום ופיתוח סאפ | 19.13 days | 21 November 2021 8:00 | 13 December 2021 17:00 | 0 |  | 0h | 02.02.SAP.12.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
2820 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 December 2021 8:00 | 16 December 2021 15:00 | 0 | 2819 | 25h | 02.02.SAP.12.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2821 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 16 December 2021 15:00 | 19 December 2021 16:00 | 0 | 2820 | 10h | 02.02.SAP.12.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2822 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 December 2021 16:00 | 20 December 2021 17:00 | 0 | 2821 | 10h | 02.02.SAP.12.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2823 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 21 December 2021 8:00 | 21 December 2021 13:00 | 0 | 2822 | 5h | 02.02.SAP.12.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2824 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 21 December 2021 13:00 | 21 December 2021 13:00 | 0 | 2823,2817 | 0h | 02.02.SAP.12.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2825 |  | Auto Scheduled | 02.04: ויסות פנים ובין מרחבים | 131.63 days | 26 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 152h | 02.04 | חתום | אבי פרישמן | hd | מוריה | nan | BP | NA | As Soon As Possible | 3
2826 |  | Auto Scheduled | 02.04: ויסות פנים ובין מרחבים.BP | 131.63 days | 26 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 152h | 02.04.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2827 |  | Auto Scheduled | 02.04: ויסות פנים ובין מרחבים | 131.63 days | 26 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 152h | 02.04.BP.01 | חתום | אבי פרישמן | parent | מוריה | nan | BP | NA | As Soon As Possible | 5
2828 |  | Auto Scheduled | Sub Tasks | 129.63 days | 26 July 2020 8:00 | 03 January 2021 10:00 | 1 |  | 112h | 02.04.BP.01.01 |  | אבי פרישמן | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2829 |  | Auto Scheduled | תגובות שונות | 0.63 days | 26 July 2020 8:00 | 26 July 2020 13:00 | 1 |  | 5h | 02.04.BP.01.01.10 | בוצע | ואל | MoM | ואל | תקווה רובינצ'יק | BP | NA | Must Start On | 7
2830 |  | Auto Scheduled | כתיבת מסמך | 0.75 days | 18 August 2020 8:00 | 18 August 2020 14:00 | 1 |  | 6h | 02.04.BP.01.01.30 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2831 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 2.88 days | 25 August 2020 8:00 | 27 August 2020 13:00 | 1 | 2830 | 23h | 02.04.BP.01.01.31 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2832 |  | Auto Scheduled | אישור מקל"ר | 1.75 days | 25 September 2020 8:00 | 28 September 2020 13:00 | 1 | 2831 | 14h | 02.04.BP.01.01.32 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
2833 |  | Auto Scheduled | אישור אבי | 2.38 days | 14 October 2020 8:00 | 18 October 2020 9:00 | 1 | 2832 | 19h | 02.04.BP.01.01.33 | בוצע | אבי | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
2834 |  | Auto Scheduled | אישור המנהלת | 0.38 days | 09 November 2020 8:00 | 09 November 2020 11:00 | 1 | 2833 | 3h | 02.04.BP.01.01.34 | בוצע | סיגל | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
2835 |  | Auto Scheduled | אישור מפקדת | 0.38 days | 11 November 2020 8:00 | 11 November 2020 11:00 | 1 | 2834 | 3h | 02.04.BP.01.01.35 | בוצע | מוריה | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
2836 |  | Auto Scheduled | אישור חטלו"ג | 0.63 days | 15 November 2020 8:00 | 15 November 2020 13:00 | 1 | 2835 | 5h | 02.04.BP.01.01.36 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
2837 |  | Auto Scheduled | אישור ניר בשן | 4 days | 19 November 2020 8:00 | 24 November 2020 13:00 | 1 | 2836 | 32h | 02.04.BP.01.01.37 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2838 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 2837 | 2h | 02.04.BP.01.01.38 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2839 |  | Auto Scheduled | LifeCycle Tasks | 38.25 days | 18 November 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 02.04.BP.01.02 |  | אבי פרישמן | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2840 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 2838 | 0h | 02.04.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2841 |  | Auto Scheduled | טרם החל | 0.63 days | 18 November 2020 8:00 | 18 November 2020 13:00 | 1 |  | 5h | 02.04.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2842 |  | Auto Scheduled | בעבודה | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 2841 | 10h | 02.04.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2843 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2020 8:00 | 09 December 2020 13:00 | 1 | 2842 | 5h | 02.04.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2844 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 2843 | 10h | 02.04.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2845 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 December 2020 8:00 | 31 December 2020 9:00 | 1 | 2844 | 10h | 02.04.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2846 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2845,2840 | 0h | 02.04.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2847 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2846 | 0h | 02.04.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2848 |  | Auto Scheduled | 02.06: החזרות מיחידות | 465.13 days | 08 July 2020 8:00 | 17 March 2022 13:00 | 0.37 |  | 538h | 02.06 | חתום | אבי פרישמן | hd | רועי | nan | BP | NA | As Soon As Possible | 3
2849 |  | Auto Scheduled | 02.06: החזרות מיחידות.BP | 145.13 days | 08 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 118h | 02.06.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2850 |  | Auto Scheduled | 02.06: החזרות מיחידות | 145.13 days | 08 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 118h | 02.06.BP.01 | חתום | אבי פרישמן | parent | רועי | nan | BP | NA | As Soon As Possible | 5
2851 |  | Auto Scheduled | Sub Tasks | 76.75 days | 29 September 2020 8:00 | 03 January 2021 10:00 | 1 |  | 78h | 02.06.BP.01.01 |  | אבי פרישמן | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2852 |  | Auto Scheduled | כתיבת מסמך | 2.63 days | 29 September 2020 8:00 | 01 October 2020 11:00 | 1 |  | 21h | 02.06.BP.01.01.30 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | Must Start On | 7
2853 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.88 days | 27 October 2020 8:00 | 27 October 2020 15:00 | 1 | 2852 | 7h | 02.06.BP.01.01.31 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2854 |  | Auto Scheduled | אישור המנהלת | 2 days | 04 November 2020 8:00 | 05 November 2020 15:00 | 1 | 2853 | 16h | 02.06.BP.01.01.32 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2855 |  | Auto Scheduled | אישור מפקדת | 0.5 days | 25 November 2020 8:00 | 25 November 2020 12:00 | 1 | 2854 | 4h | 02.06.BP.01.01.33 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2856 |  | Auto Scheduled | אישור אבי | 0.88 days | 30 November 2020 8:00 | 30 November 2020 15:00 | 1 | 2855 | 7h | 02.06.BP.01.01.34 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2857 |  | Auto Scheduled | אישור מקל"ר | 0.13 days | 08 December 2020 8:00 | 08 December 2020 9:00 | 1 | 2856 | 1h | 02.06.BP.01.01.35 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2858 |  | Auto Scheduled | אישור חטלו"ג | 2.13 days | 08 December 2020 8:00 | 09 December 2020 16:00 | 1 | 2857 | 17h | 02.06.BP.01.01.36 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
2859 |  | Auto Scheduled | אישור ניר בשן | 0.38 days | 30 December 2020 8:00 | 30 December 2020 11:00 | 1 | 2858 | 3h | 02.06.BP.01.01.37 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2860 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 2859 | 2h | 02.06.BP.01.01.38 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2861 |  | Auto Scheduled | LifeCycle Tasks | 145.13 days | 08 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 02.06.BP.01.02 |  | אבי פרישמן | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2862 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 2860 | 0h | 02.06.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2863 |  | Auto Scheduled | טרם החל | 0.63 days | 08 July 2020 8:00 | 08 July 2020 13:00 | 1 |  | 5h | 02.06.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2864 |  | Auto Scheduled | בעבודה | 1.25 days | 15 July 2020 8:00 | 16 July 2020 9:00 | 1 | 2863 | 10h | 02.06.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2865 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 29 July 2020 8:00 | 29 July 2020 13:00 | 1 | 2864 | 5h | 02.06.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2866 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 August 2020 8:00 | 06 August 2020 9:00 | 1 | 2865 | 10h | 02.06.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2867 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 19 August 2020 8:00 | 20 August 2020 9:00 | 1 | 2866 | 10h | 02.06.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2868 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2867,2862 | 0h | 02.06.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2869 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2868 | 0h | 02.06.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2870 |  | Auto Scheduled | 02.06: החזרות מיחידות.INT | 321.13 days | 04 January 2021 8:00 | 17 March 2022 13:00 | 5.9999999999999998E-2 |  | 140h | 02.06.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2871 |  | Auto Scheduled | מערכת ה-סאפ תאפשר לבצע העברה של המלאי למערכת ה- זכיין לטובת ניהול אחסנת הפריטים. תתאפשר ההעברה לכל מחסן מנוהל זכיין. בצורה פשוטה ללא כל שלבי שרשרת האספקה. | 321.13 days | 04 January 2021 8:00 | 17 March 2022 13:00 | 4.0000000000000001E-2 |  | 70h | 02.06.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2872 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2873 |  | Auto Scheduled | LifeCycle Tasks | 321.13 days | 04 January 2021 8:00 | 17 March 2022 13:00 | 4.0000000000000001E-2 |  | 70h | 02.06.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2874 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2875 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2860 | 20h | 02.06.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2876 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 55.13 days | 02 January 2022 8:00 | 09 March 2022 17:00 | 0 |  | 0h | 02.06.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2877 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 March 2022 8:00 | 14 March 2022 15:00 | 0 | 2876 | 25h | 02.06.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2878 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 March 2022 15:00 | 15 March 2022 16:00 | 0 | 2877 | 10h | 02.06.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2879 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 March 2022 16:00 | 16 March 2022 17:00 | 0 | 2878 | 10h | 02.06.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2880 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 March 2022 8:00 | 17 March 2022 13:00 | 0 | 2879 | 5h | 02.06.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2881 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 17 March 2022 13:00 | 17 March 2022 13:00 | 0 | 2880,2874 | 0h | 02.06.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2882 |  | Auto Scheduled | מערכת ה-סאפ תשדר למערכת ה-זכיין את הזמנת ההחזרה | 309.88 days | 04 January 2021 8:00 | 03 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.06.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2883 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2884 |  | Auto Scheduled | LifeCycle Tasks | 309.88 days | 04 January 2021 8:00 | 03 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.06.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2885 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2886 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2860 | 20h | 02.06.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2887 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 16.88 days | 03 February 2022 8:00 | 23 February 2022 17:00 | 0 |  | 0h | 02.06.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2888 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 February 2022 8:00 | 28 February 2022 15:00 | 0 | 2887 | 25h | 02.06.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2889 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 February 2022 15:00 | 01 March 2022 16:00 | 0 | 2888 | 10h | 02.06.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2890 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 March 2022 16:00 | 02 March 2022 17:00 | 0 | 2889 | 10h | 02.06.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2891 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 March 2022 8:00 | 03 March 2022 13:00 | 0 | 2890 | 5h | 02.06.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2892 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 03 March 2022 13:00 | 03 March 2022 13:00 | 0 | 2891,2885 | 0h | 02.06.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2893 |  | Auto Scheduled | 02.06: החזרות מיחידות.SAP | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.64000000000000001 |  | 280h | 02.06.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2894 |  | Auto Scheduled | מערכת סאפ תאפשר לסמן החזרה בדחיפה או במשיכה | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.65000000000000002 |  | 70h | 02.06.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2895 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2896 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.65000000000000002 |  | 70h | 02.06.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2897 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2898 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2860 | 20h | 02.06.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2899 |  | Auto Scheduled | יישום ופיתוח סאפ | 9 days | 11 July 2021 8:00 | 20 July 2021 17:00 | 1 |  | 0h | 02.06.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2900 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 July 2021 8:00 | 25 July 2021 15:00 | 0 | 2899 | 25h | 02.06.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2901 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 July 2021 15:00 | 26 July 2021 16:00 | 0 | 2900 | 10h | 02.06.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2902 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 July 2021 16:00 | 27 July 2021 17:00 | 0 | 2901 | 10h | 02.06.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2903 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 July 2021 8:00 | 28 July 2021 13:00 | 0 | 2902 | 5h | 02.06.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2904 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 2903,2897 | 0h | 02.06.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2905 |  | Auto Scheduled | מערכת סאפ תאפשר לנהל חוקת החזרות למרה"ס על פי טבלת בי אר אף | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.53000000000000003 |  | 70h | 02.06.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2906 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2907 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.53000000000000003 |  | 70h | 02.06.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2908 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2909 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2860 | 20h | 02.06.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2910 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 01 June 2021 8:00 | 06 June 2021 17:00 | 1 |  | 0h | 02.06.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2911 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 June 2021 8:00 | 09 June 2021 15:00 | 0 | 2910 | 25h | 02.06.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2912 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 June 2021 15:00 | 10 June 2021 16:00 | 0 | 2911 | 10h | 02.06.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2913 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 June 2021 16:00 | 13 June 2021 17:00 | 0 | 2912 | 10h | 02.06.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2914 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 June 2021 8:00 | 14 June 2021 13:00 | 0 | 2913 | 5h | 02.06.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2915 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 2914,2908 | 0h | 02.06.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2916 |  | Auto Scheduled | מערכת סאפ תאפשר לפתוח דרישת החזרה למרה"ס | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.76000000000000001 |  | 70h | 02.06.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2917 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2918 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.76000000000000001 |  | 70h | 02.06.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2919 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2920 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2860 | 20h | 02.06.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2921 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 02 May 2021 8:00 | 01 June 2021 17:00 | 1 |  | 0h | 02.06.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2922 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 June 2021 8:00 | 06 June 2021 15:00 | 0 | 2921 | 25h | 02.06.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2923 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 June 2021 15:00 | 07 June 2021 16:00 | 0 | 2922 | 10h | 02.06.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2924 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 June 2021 16:00 | 08 June 2021 17:00 | 0 | 2923 | 10h | 02.06.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2925 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 June 2021 8:00 | 09 June 2021 13:00 | 0 | 2924 | 5h | 02.06.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2926 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 2925,2919 | 0h | 02.06.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2927 |  | Auto Scheduled | נדרש להוסיף בעת יצירת דרישת ההחזרה מגורם חוץ שדה חובה למילוי מספר הספק המקבל | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.47999999999999998 |  | 70h | 02.06.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
2928 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2929 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.47999999999999998 |  | 70h | 02.06.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2930 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.06.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2931 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2860 | 20h | 02.06.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2932 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 13 May 2021 8:00 | 26 May 2021 17:00 | 1 |  | 0h | 02.06.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
2933 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 30 May 2021 8:00 | 01 June 2021 15:00 | 0 | 2932 | 25h | 02.06.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2934 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 01 June 2021 15:00 | 02 June 2021 16:00 | 0 | 2933 | 10h | 02.06.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2935 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 02 June 2021 16:00 | 03 June 2021 17:00 | 0 | 2934 | 10h | 02.06.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2936 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 June 2021 8:00 | 06 June 2021 13:00 | 0 | 2935 | 5h | 02.06.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2937 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 2936,2930 | 0h | 02.06.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
2938 |  | Auto Scheduled | 02.08: מכירות | 441.5 days | 19 July 2020 8:00 | 27 February 2022 13:00 | 0.16 |  | 1,114h | 02.08 | חתום | תהילה | hd | רועי | nan | BP | NA | As Soon As Possible | 3
2939 |  | Auto Scheduled | 02.08: מכירות.BP | 137.25 days | 19 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 134h | 02.08.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2940 |  | Auto Scheduled | 02.08: מכירות | 137.25 days | 19 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 134h | 02.08.BP.01 | חתום | תהילה | parent | רועי | nan | BP | NA | As Soon As Possible | 5
2941 |  | Auto Scheduled | Sub Tasks | 117.25 days | 10 August 2020 8:00 | 03 January 2021 10:00 | 1 |  | 94h | 02.08.BP.01.01 |  | תהילה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2942 |  | Auto Scheduled | ע"פ תהילה יצחק, עדיין התהליך האושי לא סגור ולכן כרגע מקפיאים את ההתקדמות. יש לספק לו"ז | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.08.BP.01.01.10 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | Must Start On | 7
2943 |  | Auto Scheduled | ע"פ מסמכי המרכז קיים מחסן מכירות אחד בדרום. ע"פ המשתמשים נדרש מתחם מכירות בכל מרחב | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.08.BP.01.01.11 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
2944 |  | Auto Scheduled | תהילה: -BP מחולק לשלושה תתי תהליכים שונים. השבוע סוכם עקרונית עם אבי על מבנה הארגוני של מתחמי המכירות בנוסף נסגרו מספר סוגיות אושיות משמעותיות. ועכשיו ניתן לזמן את הדיונים הבאים בנושא. יתואם שבוע הבא גם למול משהב"ט. | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.08.BP.01.01.12 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
2945 |  | Auto Scheduled | מה עלה מהדיונים? | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.08.BP.01.01.13 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
2946 |  | Auto Scheduled | כתיבת מסמך | 5.75 days | 13 September 2020 8:00 | 20 September 2020 9:00 | 1 |  | 46h | 02.08.BP.01.01.30 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2947 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.13 days | 15 November 2020 8:00 | 15 November 2020 17:00 | 1 | 2946 | 9h | 02.08.BP.01.01.31 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2948 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 25 November 2020 8:00 | 25 November 2020 12:00 | 1 | 2947 | 4h | 02.08.BP.01.01.32 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2949 |  | Auto Scheduled | אישור מקל"ר | 0.88 days | 30 November 2020 8:00 | 30 November 2020 15:00 | 1 | 2948 | 7h | 02.08.BP.01.01.33 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2950 |  | Auto Scheduled | אישור מפקדת | 1.25 days | 08 December 2020 8:00 | 09 December 2020 9:00 | 1 | 2949 | 10h | 02.08.BP.01.01.34 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2951 |  | Auto Scheduled | אישור אבי | 0.5 days | 21 December 2020 8:00 | 21 December 2020 12:00 | 1 | 2950 | 4h | 02.08.BP.01.01.35 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2952 |  | Auto Scheduled | אישור חטלו"ג | 0.63 days | 24 December 2020 8:00 | 24 December 2020 13:00 | 1 | 2951 | 5h | 02.08.BP.01.01.36 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2953 |  | Auto Scheduled | אישור ניר בשן | 0.38 days | 30 December 2020 8:00 | 30 December 2020 11:00 | 1 | 2952 | 3h | 02.08.BP.01.01.37 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2954 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 2953 | 2h | 02.08.BP.01.01.38 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
2955 |  | Auto Scheduled | LifeCycle Tasks | 137.25 days | 19 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 02.08.BP.01.02 |  | תהילה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2956 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 2954 | 0h | 02.08.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2957 |  | Auto Scheduled | טרם החל | 0.63 days | 19 July 2020 8:00 | 19 July 2020 13:00 | 1 |  | 5h | 02.08.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2958 |  | Auto Scheduled | בעבודה | 1.25 days | 26 July 2020 8:00 | 27 July 2020 9:00 | 1 | 2957 | 10h | 02.08.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2959 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 8:00 | 09 August 2020 13:00 | 1 | 2958 | 5h | 02.08.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2960 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 August 2020 8:00 | 17 August 2020 9:00 | 1 | 2959 | 10h | 02.08.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2961 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 August 2020 8:00 | 31 August 2020 9:00 | 1 | 2960 | 10h | 02.08.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2962 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2961,2956 | 0h | 02.08.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2963 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 2962 | 0h | 02.08.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
2964 |  | Auto Scheduled | 02.08: מכירות.INT | 305.38 days | 04 January 2021 8:00 | 27 February 2022 13:00 | 0.12 |  | 420h | 02.08.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
2965 |  | Auto Scheduled | מערכת סאפ תאפשר לשדר למערכת זכיין את האספקה | 281.75 days | 04 January 2021 8:00 | 27 January 2022 13:00 | 0.10000000000000001 |  | 70h | 02.08.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2966 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2967 |  | Auto Scheduled | LifeCycle Tasks | 281.75 days | 04 January 2021 8:00 | 27 January 2022 13:00 | 0.10000000000000001 |  | 70h | 02.08.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2968 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2969 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2970 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 02 January 2022 8:00 | 19 January 2022 17:00 | 0 |  | 0h | 02.08.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2971 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 January 2022 8:00 | 24 January 2022 15:00 | 0 | 2970 | 25h | 02.08.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2972 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 January 2022 15:00 | 25 January 2022 16:00 | 0 | 2971 | 10h | 02.08.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2973 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 January 2022 16:00 | 26 January 2022 17:00 | 0 | 2972 | 10h | 02.08.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2974 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 January 2022 8:00 | 27 January 2022 13:00 | 0 | 2973 | 5h | 02.08.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2975 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 27 January 2022 13:00 | 27 January 2022 13:00 | 0 | 2974,2968 | 0h | 02.08.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2976 |  | Auto Scheduled | מערכת זכיין תאפשר עדכון מערכת סאפ על כך שהאספקה נופקה | 281.75 days | 04 January 2021 8:00 | 27 January 2022 13:00 | 0.13 |  | 70h | 02.08.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2977 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2978 |  | Auto Scheduled | LifeCycle Tasks | 281.75 days | 04 January 2021 8:00 | 27 January 2022 13:00 | 0.13 |  | 70h | 02.08.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2979 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2980 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2981 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 10.13 days | 09 January 2022 8:00 | 19 January 2022 17:00 | 0 |  | 0h | 02.08.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2982 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 January 2022 8:00 | 24 January 2022 15:00 | 0 | 2981 | 25h | 02.08.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2983 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 January 2022 15:00 | 25 January 2022 16:00 | 0 | 2982 | 10h | 02.08.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2984 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 January 2022 16:00 | 26 January 2022 17:00 | 0 | 2983 | 10h | 02.08.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2985 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 January 2022 8:00 | 27 January 2022 13:00 | 0 | 2984 | 5h | 02.08.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2986 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 27 January 2022 13:00 | 27 January 2022 13:00 | 0 | 2985,2979 | 0h | 02.08.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2987 |  | Auto Scheduled | מערכת סאפ תאפשר לשדר למערכת זכיין את האספקה | 291.88 days | 04 January 2021 8:00 | 09 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.08.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2988 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
2989 |  | Auto Scheduled | LifeCycle Tasks | 291.88 days | 04 January 2021 8:00 | 09 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.08.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
2990 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2991 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2992 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 13 January 2022 8:00 | 01 February 2022 17:00 | 0 |  | 0h | 02.08.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
2993 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 February 2022 8:00 | 06 February 2022 15:00 | 0 | 2992 | 25h | 02.08.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2994 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 February 2022 15:00 | 07 February 2022 16:00 | 0 | 2993 | 10h | 02.08.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2995 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 February 2022 16:00 | 08 February 2022 17:00 | 0 | 2994 | 10h | 02.08.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2996 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 February 2022 8:00 | 09 February 2022 13:00 | 0 | 2995 | 5h | 02.08.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2997 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 09 February 2022 13:00 | 09 February 2022 13:00 | 0 | 2996,2990 | 0h | 02.08.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
2998 |  | Auto Scheduled | מערכת סאפ תאפשר בדיקת מלאי בשיקוף ממערכת זכיין | 293 days | 04 January 2021 8:00 | 10 February 2022 13:00 | 0.19 |  | 70h | 02.08.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
2999 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3000 |  | Auto Scheduled | LifeCycle Tasks | 293 days | 04 January 2021 8:00 | 10 February 2022 13:00 | 0.19 |  | 70h | 02.08.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3001 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3002 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3003 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 4.5 days | 30 January 2022 8:00 | 02 February 2022 17:00 | 0 |  | 0h | 02.08.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3004 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 February 2022 8:00 | 07 February 2022 15:00 | 0 | 3003 | 25h | 02.08.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3005 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 February 2022 15:00 | 08 February 2022 16:00 | 0 | 3004 | 10h | 02.08.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3006 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 February 2022 16:00 | 09 February 2022 17:00 | 0 | 3005 | 10h | 02.08.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3007 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 February 2022 8:00 | 10 February 2022 13:00 | 0 | 3006 | 5h | 02.08.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3008 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 February 2022 13:00 | 10 February 2022 13:00 | 0 | 3007,3001 | 0h | 02.08.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3009 |  | Auto Scheduled | מערכת סאפ תאפשר לשדר למערכת זכיין את האספקה | 305.38 days | 04 January 2021 8:00 | 27 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.08.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3010 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3011 |  | Auto Scheduled | LifeCycle Tasks | 305.38 days | 04 January 2021 8:00 | 27 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.08.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3012 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3013 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3014 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 31 January 2022 8:00 | 17 February 2022 17:00 | 0 |  | 0h | 02.08.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3015 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 February 2022 8:00 | 22 February 2022 15:00 | 0 | 3014 | 25h | 02.08.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3016 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 February 2022 15:00 | 23 February 2022 16:00 | 0 | 3015 | 10h | 02.08.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3017 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 February 2022 16:00 | 24 February 2022 17:00 | 0 | 3016 | 10h | 02.08.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3018 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 February 2022 8:00 | 27 February 2022 13:00 | 0 | 3017 | 5h | 02.08.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3019 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 27 February 2022 13:00 | 27 February 2022 13:00 | 0 | 3018,3012 | 0h | 02.08.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3020 |  | Auto Scheduled | מערכת זכיין תאפשר עדכון מערכת סאפ על כך שהאספקה נופקה | 295.25 days | 04 January 2021 8:00 | 14 February 2022 13:00 | 0.12 |  | 70h | 02.08.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3021 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3022 |  | Auto Scheduled | LifeCycle Tasks | 295.25 days | 04 January 2021 8:00 | 14 February 2022 13:00 | 0.12 |  | 70h | 02.08.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3023 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3024 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3025 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 12.38 days | 23 January 2022 8:00 | 06 February 2022 17:00 | 0 |  | 0h | 02.08.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3026 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 February 2022 8:00 | 09 February 2022 15:00 | 0 | 3025 | 25h | 02.08.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3027 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 February 2022 15:00 | 10 February 2022 16:00 | 0 | 3026 | 10h | 02.08.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3028 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 February 2022 16:00 | 13 February 2022 17:00 | 0 | 3027 | 10h | 02.08.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3029 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 February 2022 8:00 | 14 February 2022 13:00 | 0 | 3028 | 5h | 02.08.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3030 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 14 February 2022 13:00 | 14 February 2022 13:00 | 0 | 3029,3023 | 0h | 02.08.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3031 |  | Auto Scheduled | 02.08: מכירות.SAP | 264.88 days | 04 January 2021 8:00 | 06 January 2022 13:00 | 0.10000000000000001 |  | 560h | 02.08.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3032 |  | Auto Scheduled | מערכת סאפ תאפשר לפתוח בל"מ על סמך בל"מ ממשהב"ט | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.11 |  | 70h | 02.08.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3033 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3034 |  | Auto Scheduled | LifeCycle Tasks | 200.75 days | 04 January 2021 8:00 | 19 October 2021 13:00 | 0.11 |  | 70h | 02.08.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3035 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3036 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3037 |  | Auto Scheduled | יישום ופיתוח סאפ | 14.63 days | 12 September 2021 8:00 | 11 October 2021 17:00 | 0 |  | 0h | 02.08.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3038 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 October 2021 8:00 | 14 October 2021 15:00 | 0 | 3037 | 25h | 02.08.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3039 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 October 2021 15:00 | 17 October 2021 16:00 | 0 | 3038 | 10h | 02.08.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3040 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 October 2021 16:00 | 18 October 2021 17:00 | 0 | 3039 | 10h | 02.08.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3041 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 October 2021 8:00 | 19 October 2021 13:00 | 0 | 3040 | 5h | 02.08.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3042 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 October 2021 13:00 | 19 October 2021 13:00 | 0 | 3041,3035 | 0h | 02.08.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3043 |  | Auto Scheduled | מערכת סאפ תאפשר שינוי סטאטוס הבל"מ | 205.25 days | 04 January 2021 8:00 | 25 October 2021 13:00 | 0.11 |  | 70h | 02.08.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3044 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3045 |  | Auto Scheduled | LifeCycle Tasks | 205.25 days | 04 January 2021 8:00 | 25 October 2021 13:00 | 0.11 |  | 70h | 02.08.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3046 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3047 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3048 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 30 September 2021 8:00 | 17 October 2021 17:00 | 0 |  | 0h | 02.08.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3049 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 October 2021 8:00 | 20 October 2021 15:00 | 0 | 3048 | 25h | 02.08.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3050 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 October 2021 15:00 | 21 October 2021 16:00 | 0 | 3049 | 10h | 02.08.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3051 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 October 2021 16:00 | 24 October 2021 17:00 | 0 | 3050 | 10h | 02.08.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3052 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 October 2021 8:00 | 25 October 2021 13:00 | 0 | 3051 | 5h | 02.08.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3053 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 25 October 2021 13:00 | 25 October 2021 13:00 | 0 | 3052,3046 | 0h | 02.08.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3054 |  | Auto Scheduled | מערכת סאפ תאפשר עדכון אתר ואתר אחסון | 232.25 days | 04 January 2021 8:00 | 28 November 2021 13:00 | 8.0000000000000002E-2 |  | 70h | 02.08.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3055 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3056 |  | Auto Scheduled | LifeCycle Tasks | 232.25 days | 04 January 2021 8:00 | 28 November 2021 13:00 | 8.0000000000000002E-2 |  | 70h | 02.08.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3057 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3058 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3059 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 25 October 2021 8:00 | 18 November 2021 17:00 | 0 |  | 0h | 02.08.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3060 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 November 2021 8:00 | 23 November 2021 15:00 | 0 | 3059 | 25h | 02.08.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3061 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 November 2021 15:00 | 24 November 2021 16:00 | 0 | 3060 | 10h | 02.08.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3062 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 November 2021 16:00 | 25 November 2021 17:00 | 0 | 3061 | 10h | 02.08.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3063 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 November 2021 8:00 | 28 November 2021 13:00 | 0 | 3062 | 5h | 02.08.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3064 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 November 2021 13:00 | 28 November 2021 13:00 | 0 | 3063,3057 | 0h | 02.08.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3065 |  | Auto Scheduled | מערכת סאפ תאפשר ליצור הזמנת מכירה מסוג זי או אר לאחר אישור הבל"מ במערכת | 236.75 days | 04 January 2021 8:00 | 02 December 2021 13:00 | 0.11 |  | 70h | 02.08.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3066 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3067 |  | Auto Scheduled | LifeCycle Tasks | 236.75 days | 04 January 2021 8:00 | 02 December 2021 13:00 | 0.11 |  | 70h | 02.08.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3068 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3069 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3070 |  | Auto Scheduled | יישום ופיתוח סאפ | 14.63 days | 08 November 2021 8:00 | 24 November 2021 17:00 | 0 |  | 0h | 02.08.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3071 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 November 2021 8:00 | 29 November 2021 15:00 | 0 | 3070 | 25h | 02.08.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3072 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 November 2021 15:00 | 30 November 2021 16:00 | 0 | 3071 | 10h | 02.08.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3073 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 November 2021 16:00 | 01 December 2021 17:00 | 0 | 3072 | 10h | 02.08.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3074 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 December 2021 8:00 | 02 December 2021 13:00 | 0 | 3073 | 5h | 02.08.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3075 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 02 December 2021 13:00 | 02 December 2021 13:00 | 0 | 3074,3068 | 0h | 02.08.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3076 |  | Auto Scheduled | מערכת סאפ תאפשר ניהול נתוני לקוח לצורך תיאום אספקה | 255.88 days | 04 January 2021 8:00 | 27 December 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 02.08.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3077 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3078 |  | Auto Scheduled | LifeCycle Tasks | 255.88 days | 04 January 2021 8:00 | 27 December 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 02.08.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3079 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3080 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3081 |  | Auto Scheduled | יישום ופיתוח סאפ | 28.13 days | 15 November 2021 8:00 | 19 December 2021 17:00 | 0 |  | 0h | 02.08.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3082 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 December 2021 8:00 | 22 December 2021 15:00 | 0 | 3081 | 25h | 02.08.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3083 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 December 2021 15:00 | 23 December 2021 16:00 | 0 | 3082 | 10h | 02.08.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3084 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 December 2021 16:00 | 26 December 2021 17:00 | 0 | 3083 | 10h | 02.08.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3085 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 December 2021 8:00 | 27 December 2021 13:00 | 0 | 3084 | 5h | 02.08.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3086 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 27 December 2021 13:00 | 27 December 2021 13:00 | 0 | 3085,3079 | 0h | 02.08.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3087 |  | Auto Scheduled | מערכת סאפ תאפשר פתיחת לוט על סמך מלאי | 258.13 days | 04 January 2021 8:00 | 29 December 2021 13:00 | 0.12 |  | 70h | 02.08.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3088 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3089 |  | Auto Scheduled | LifeCycle Tasks | 258.13 days | 04 January 2021 8:00 | 29 December 2021 13:00 | 0.12 |  | 70h | 02.08.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3090 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3091 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3092 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 07 December 2021 8:00 | 21 December 2021 17:00 | 0 |  | 0h | 02.08.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3093 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 December 2021 8:00 | 26 December 2021 15:00 | 0 | 3092 | 25h | 02.08.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3094 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 December 2021 15:00 | 27 December 2021 16:00 | 0 | 3093 | 10h | 02.08.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3095 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 December 2021 16:00 | 28 December 2021 17:00 | 0 | 3094 | 10h | 02.08.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3096 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 December 2021 8:00 | 29 December 2021 13:00 | 0 | 3095 | 5h | 02.08.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3097 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 December 2021 13:00 | 29 December 2021 13:00 | 0 | 3096,3090 | 0h | 02.08.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3098 |  | Auto Scheduled | מערכת סאפ תאפשר ניהול נתוני לקוח לצורך תיאום אספקה | 264.88 days | 04 January 2021 8:00 | 06 January 2022 13:00 | 0.11 |  | 70h | 02.08.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3099 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3100 |  | Auto Scheduled | LifeCycle Tasks | 264.88 days | 04 January 2021 8:00 | 06 January 2022 13:00 | 0.11 |  | 70h | 02.08.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3101 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3102 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3103 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 14 December 2021 8:00 | 29 December 2021 17:00 | 0 |  | 0h | 02.08.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3104 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 30 December 2021 8:00 | 03 January 2022 15:00 | 0 | 3103 | 25h | 02.08.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3105 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 January 2022 15:00 | 04 January 2022 16:00 | 0 | 3104 | 10h | 02.08.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3106 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 January 2022 16:00 | 05 January 2022 17:00 | 0 | 3105 | 10h | 02.08.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3107 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 January 2022 8:00 | 06 January 2022 13:00 | 0 | 3106 | 5h | 02.08.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3108 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 January 2022 13:00 | 06 January 2022 13:00 | 0 | 3107,3101 | 0h | 02.08.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3109 |  | Auto Scheduled | מערכת סאפ תאפשר בדיקת מלאי בשיקוף ממערכת זכיין | 261.5 days | 04 January 2021 8:00 | 03 January 2022 13:00 | 0.19 |  | 70h | 02.08.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3110 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3111 |  | Auto Scheduled | LifeCycle Tasks | 261.5 days | 04 January 2021 8:00 | 03 January 2022 13:00 | 0.19 |  | 70h | 02.08.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3112 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.08.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3113 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 2954 | 20h | 02.08.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3114 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 21 December 2021 8:00 | 26 December 2021 17:00 | 0 |  | 0h | 02.08.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3115 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 27 December 2021 8:00 | 29 December 2021 15:00 | 0 | 3114 | 25h | 02.08.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3116 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 December 2021 15:00 | 30 December 2021 16:00 | 0 | 3115 | 10h | 02.08.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3117 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 December 2021 16:00 | 02 January 2022 17:00 | 0 | 3116 | 10h | 02.08.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3118 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 January 2022 8:00 | 03 January 2022 13:00 | 0 | 3117 | 5h | 02.08.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3119 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 January 2022 13:00 | 03 January 2022 13:00 | 0 | 3118,3112 | 0h | 02.08.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3120 |  | Auto Scheduled | 02.11: החלפות | 420.13 days | 08 July 2020 8:00 | 20 January 2022 13:00 | 0.54000000000000004 |  | 614h | 02.11 | חתום | רמ"ח תו"ב | hd | רועי | nan | BP | NA | As Soon As Possible | 3
3121 |  | Auto Scheduled | 02.11: החלפות.BP | 145.13 days | 08 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 124h | 02.11.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3122 |  | Auto Scheduled | 02.11: החלפות | 145.13 days | 08 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 124h | 02.11.BP.01 | חתום | רמ"ח תו"ב | parent | רועי | nan | BP | NA | As Soon As Possible | 5
3123 |  | Auto Scheduled | Sub Tasks | 117.25 days | 10 August 2020 8:00 | 03 January 2021 10:00 | 1 |  | 84h | 02.11.BP.01.01 |  | רמ"ח תו"ב | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3124 |  | Auto Scheduled | ממתינים להחלטות או"שיות ברמת חטלוג ומנהלת המרהס שלפיה תגזר תפיסת הפתרון. נפתח כמה פעמים ע"י משתמשים - מה הסטאטוס? | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.11.BP.01.01.10 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | Must Start On | 7
3125 |  | Auto Scheduled | כתיבת מסמך | 3.25 days | 22 September 2020 8:00 | 24 September 2020 16:00 | 1 |  | 26h | 02.11.BP.01.01.30 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3126 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.75 days | 27 October 2020 8:00 | 28 October 2020 13:00 | 1 | 3125 | 14h | 02.11.BP.01.01.31 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3127 |  | Auto Scheduled | אישור המנהלת | 1 day | 15 November 2020 8:00 | 15 November 2020 16:00 | 1 | 3126 | 8h | 02.11.BP.01.01.32 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3128 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 24 November 2020 8:00 | 24 November 2020 10:00 | 1 | 3127 | 2h | 02.11.BP.01.01.33 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3129 |  | Auto Scheduled | אישור אבי | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 3128 | 10h | 02.11.BP.01.01.34 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3130 |  | Auto Scheduled | אישור מקל"ר | 0.13 days | 08 December 2020 8:00 | 08 December 2020 9:00 | 1 | 3129 | 1h | 02.11.BP.01.01.35 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3131 |  | Auto Scheduled | אישור חטלו"ג | 2.13 days | 08 December 2020 8:00 | 09 December 2020 16:00 | 1 | 3130 | 17h | 02.11.BP.01.01.36 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3132 |  | Auto Scheduled | אישור ניר בשן | 0.38 days | 30 December 2020 8:00 | 30 December 2020 11:00 | 1 | 3131 | 3h | 02.11.BP.01.01.37 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3133 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 3132 | 2h | 02.11.BP.01.01.38 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3134 |  | Auto Scheduled | LifeCycle Tasks | 145.13 days | 08 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 02.11.BP.01.02 |  | רמ"ח תו"ב | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3135 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 3133 | 0h | 02.11.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3136 |  | Auto Scheduled | טרם החל | 0.63 days | 08 July 2020 8:00 | 08 July 2020 13:00 | 1 |  | 5h | 02.11.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3137 |  | Auto Scheduled | בעבודה | 1.25 days | 15 July 2020 8:00 | 16 July 2020 9:00 | 1 | 3136 | 10h | 02.11.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3138 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 29 July 2020 8:00 | 29 July 2020 13:00 | 1 | 3137 | 5h | 02.11.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3139 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 August 2020 8:00 | 06 August 2020 9:00 | 1 | 3138 | 10h | 02.11.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3140 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 19 August 2020 8:00 | 20 August 2020 9:00 | 1 | 3139 | 10h | 02.11.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3141 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 3140,3135 | 0h | 02.11.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3142 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 3141 | 0h | 02.11.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3143 |  | Auto Scheduled | 02.11: החלפות.INT | 276.13 days | 04 January 2021 8:00 | 20 January 2022 13:00 | 0.17000000000000001 |  | 210h | 02.11.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3144 |  | Auto Scheduled | מערכת ה-זכיין תאפשר לשדר את האספקה,אספקות למערכת ה-טי אמ אס | 276.13 days | 04 January 2021 8:00 | 20 January 2022 13:00 | 0.16 |  | 70h | 02.11.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3145 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3146 |  | Auto Scheduled | LifeCycle Tasks | 276.13 days | 04 January 2021 8:00 | 20 January 2022 13:00 | 0.16 |  | 70h | 02.11.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3147 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3148 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3149 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 05 January 2022 8:00 | 12 January 2022 17:00 | 0 |  | 0h | 02.11.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3150 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 January 2022 8:00 | 17 January 2022 15:00 | 0 | 3149 | 25h | 02.11.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3151 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 January 2022 15:00 | 18 January 2022 16:00 | 0 | 3150 | 10h | 02.11.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3152 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 January 2022 16:00 | 19 January 2022 17:00 | 0 | 3151 | 10h | 02.11.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3153 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 January 2022 8:00 | 20 January 2022 13:00 | 0 | 3152 | 5h | 02.11.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3154 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 20 January 2022 13:00 | 20 January 2022 13:00 | 0 | 3153,3147 | 0h | 02.11.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3155 |  | Auto Scheduled | מערכת ה-סאפ תאפשר לשדר את האספקה,אספקות למערכת ה-זכיין עם יעדי התספקות המתאימים | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.16 |  | 70h | 02.11.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3156 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3157 |  | Auto Scheduled | LifeCycle Tasks | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.16 |  | 70h | 02.11.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3158 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3159 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3160 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 03 January 2022 8:00 | 10 January 2022 17:00 | 0 |  | 0h | 02.11.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3161 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 January 2022 8:00 | 13 January 2022 15:00 | 0 | 3160 | 25h | 02.11.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3162 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 January 2022 15:00 | 16 January 2022 16:00 | 0 | 3161 | 10h | 02.11.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3163 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 January 2022 16:00 | 17 January 2022 17:00 | 0 | 3162 | 10h | 02.11.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3164 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 January 2022 8:00 | 18 January 2022 13:00 | 0 | 3163 | 5h | 02.11.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3165 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 18 January 2022 13:00 | 18 January 2022 13:00 | 0 | 3164,3158 | 0h | 02.11.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3166 |  | Auto Scheduled | מערכת ה-סאפ תאפשר לפתוח אספקה כנגד אספקה שנפתחה ב-זכיין | 271.63 days | 04 January 2021 8:00 | 16 January 2022 13:00 | 0.17000000000000001 |  | 70h | 02.11.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3167 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3168 |  | Auto Scheduled | LifeCycle Tasks | 271.63 days | 04 January 2021 8:00 | 16 January 2022 13:00 | 0.17000000000000001 |  | 70h | 02.11.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3169 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3170 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3171 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 5.63 days | 02 January 2022 8:00 | 06 January 2022 17:00 | 0 |  | 0h | 02.11.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3172 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 January 2022 8:00 | 11 January 2022 15:00 | 0 | 3171 | 25h | 02.11.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3173 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 January 2022 15:00 | 12 January 2022 16:00 | 0 | 3172 | 10h | 02.11.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3174 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 January 2022 16:00 | 13 January 2022 17:00 | 0 | 3173 | 10h | 02.11.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3175 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 January 2022 8:00 | 16 January 2022 13:00 | 0 | 3174 | 5h | 02.11.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3176 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 16 January 2022 13:00 | 16 January 2022 13:00 | 0 | 3175,3169 | 0h | 02.11.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3177 |  | Auto Scheduled | 02.11: החלפות.SAP | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.66000000000000003 |  | 280h | 02.11.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3178 |  | Auto Scheduled | מערכת סאפ תאפשר לבצע את הקליטה למלאי עם סיבת תנועה "הוחלף" ו"לא הוחלף" בתנועת הקבלה 101 | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.65000000000000002 |  | 70h | 02.11.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3179 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3180 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.65000000000000002 |  | 70h | 02.11.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3181 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3182 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3183 |  | Auto Scheduled | יישום ופיתוח סאפ | 9 days | 03 August 2021 8:00 | 12 August 2021 17:00 | 1 |  | 0h | 02.11.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3184 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 15 August 2021 8:00 | 17 August 2021 15:00 | 0 | 3183 | 25h | 02.11.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3185 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 17 August 2021 15:00 | 18 August 2021 16:00 | 0 | 3184 | 10h | 02.11.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3186 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 August 2021 16:00 | 19 August 2021 17:00 | 0 | 3185 | 10h | 02.11.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3187 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 22 August 2021 8:00 | 22 August 2021 13:00 | 0 | 3186 | 5h | 02.11.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3188 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3187,3181 | 0h | 02.11.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3189 |  | Auto Scheduled | מערכת הסאפ תאפשר לבצע קליטה של הזמנת ניפוק ההחלפה למלאי לאתר אחסון מיוחד המשוייך למרה"ס ב-סאפ שאינו מקושר ל-זכיין | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.71999999999999997 |  | 70h | 02.11.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3190 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3191 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.71999999999999997 |  | 70h | 02.11.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3192 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3193 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3194 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 26 July 2021 8:00 | 10 August 2021 17:00 | 1 |  | 0h | 02.11.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3195 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 August 2021 8:00 | 15 August 2021 15:00 | 0 | 3194 | 25h | 02.11.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3196 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 15 August 2021 15:00 | 16 August 2021 16:00 | 0 | 3195 | 10h | 02.11.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3197 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 August 2021 16:00 | 17 August 2021 17:00 | 0 | 3196 | 10h | 02.11.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3198 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 August 2021 8:00 | 18 August 2021 13:00 | 0 | 3197 | 5h | 02.11.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3199 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3198,3192 | 0h | 02.11.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3200 |  | Auto Scheduled | מערכת סאפ תאפשר לנהל חוקת ניפוק למרה"ס על פי טבלת החלטה | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.23000000000000001 |  | 70h | 02.11.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3201 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3202 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.23000000000000001 |  | 70h | 02.11.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3203 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3204 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3205 |  | Auto Scheduled | יישום ופיתוח סאפ | 2.25 days | 22 August 2021 8:00 | 23 August 2021 17:00 | 0 |  | 0h | 02.11.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3206 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 August 2021 8:00 | 26 August 2021 15:00 | 0 | 3205 | 25h | 02.11.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3207 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 August 2021 15:00 | 29 August 2021 16:00 | 0 | 3206 | 10h | 02.11.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3208 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 August 2021 16:00 | 30 August 2021 17:00 | 0 | 3207 | 10h | 02.11.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3209 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 August 2021 8:00 | 31 August 2021 13:00 | 0 | 3208 | 5h | 02.11.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3210 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3209,3203 | 0h | 02.11.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3211 |  | Auto Scheduled | מערכת סאפ תאפשר לפתוח דרישת ניפוק ZN01 מהמרה"ס מסוג החלפה | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.79000000000000004 |  | 70h | 02.11.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3212 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3213 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.79000000000000004 |  | 70h | 02.11.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3214 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.11.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3215 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3133 | 20h | 02.11.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3216 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 04 July 2021 8:00 | 28 July 2021 17:00 | 1 |  | 0h | 02.11.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3217 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 July 2021 8:00 | 02 August 2021 15:00 | 0 | 3216 | 25h | 02.11.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3218 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 02 August 2021 15:00 | 03 August 2021 16:00 | 0 | 3217 | 10h | 02.11.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3219 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 August 2021 16:00 | 04 August 2021 17:00 | 0 | 3218 | 10h | 02.11.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3220 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 05 August 2021 8:00 | 05 August 2021 13:00 | 0 | 3219 | 5h | 02.11.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3221 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3220,3214 | 0h | 02.11.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3222 |  | Auto Scheduled | 02.12: תיקונים | 530.38 days | 09 July 2020 8:00 | 08 June 2022 13:00 | 0.14999999999999999 |  | 1,395h | 02.12 | חתום | פריאל ישי | hd | פריאל | nan | BP | NA | As Soon As Possible | 3
3223 |  | Auto Scheduled | 02.12: תיקונים.BP | 174.38 days | 09 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 135h | 02.12.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3224 |  | Auto Scheduled | 02.12: תיקונים | 174.38 days | 09 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 135h | 02.12.BP.01 | חתום | פריאל ישי | parent | פריאל | nan | BP | NA | As Soon As Possible | 5
3225 |  | Auto Scheduled | Sub Tasks | 147.63 days | 10 August 2020 8:00 | 09 February 2021 10:00 | 1 |  | 95h | 02.12.BP.01.01 |  | פריאל ישי | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3226 |  | Auto Scheduled | גדי מתנגד להפצת המסמך (סיכום דיון) עד שתתקיים ישיבה נוספת איתם - מה הסטאטוס? | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.12.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | Must Start On | 7
3227 |  | Auto Scheduled | כתיבת מסמך | 2 days | 14 October 2020 8:00 | 15 October 2020 15:00 | 1 |  | 16h | 02.12.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3228 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 3.25 days | 04 November 2020 8:00 | 08 November 2020 16:00 | 1 | 3227 | 26h | 02.12.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3229 |  | Auto Scheduled | אישור מקל"ר | 1.5 days | 09 December 2020 8:00 | 10 December 2020 11:00 | 1 | 3228 | 12h | 02.12.BP.01.01.32 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3230 |  | Auto Scheduled | אישור אבי | 1 day | 24 December 2020 8:00 | 24 December 2020 16:00 | 1 | 3229 | 8h | 02.12.BP.01.01.33 | בוצע | אבי | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3231 |  | Auto Scheduled | אישור מפקדת | 1.88 days | 04 January 2021 8:00 | 05 January 2021 14:00 | 1 | 3230 | 15h | 02.12.BP.01.01.34 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3232 |  | Auto Scheduled | אישור חטלו"ג | 0.25 days | 24 January 2021 8:00 | 24 January 2021 10:00 | 1 | 3231 | 2h | 02.12.BP.01.01.35 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3233 |  | Auto Scheduled | אישור שגיב שרביט | 0.38 days | 25 January 2021 8:00 | 25 January 2021 11:00 | 1 | 3232 | 3h | 02.12.BP.01.01.36 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3234 |  | Auto Scheduled | אישור ניר בשן | 1.25 days | 27 January 2021 8:00 | 28 January 2021 9:00 | 1 | 3233 | 10h | 02.12.BP.01.01.37 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3235 |  | Auto Scheduled | אישור המנהלת | 0.25 days | 09 February 2021 8:00 | 09 February 2021 10:00 | 1 | 3234 | 2h | 02.12.BP.01.01.38 | בוצע | סיגל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3236 |  | Auto Scheduled | LifeCycle Tasks | 174.38 days | 09 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 40h | 02.12.BP.01.02 |  | פריאל ישי | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3237 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 10 February 2021 8:00 | 10 February 2021 17:00 | 1 | 3235 | 0h | 02.12.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3238 |  | Auto Scheduled | טרם החל | 0.63 days | 09 July 2020 8:00 | 09 July 2020 13:00 | 1 |  | 5h | 02.12.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3239 |  | Auto Scheduled | בעבודה | 1.25 days | 16 July 2020 8:00 | 19 July 2020 9:00 | 1 | 3238 | 10h | 02.12.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3240 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 30 July 2020 8:00 | 30 July 2020 13:00 | 1 | 3239 | 5h | 02.12.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3241 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 06 August 2020 8:00 | 09 August 2020 9:00 | 1 | 3240 | 10h | 02.12.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3242 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 20 August 2020 8:00 | 23 August 2020 9:00 | 1 | 3241 | 10h | 02.12.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3243 |  | Auto Scheduled | בחתימה | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 3242,3237 | 0h | 02.12.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3244 |  | Auto Scheduled | חתום | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 3243 | 0h | 02.12.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3245 |  | Auto Scheduled | 02.12: תיקונים.INT | 298.63 days | 27 January 2021 8:00 | 14 March 2022 13:00 | 0.11 |  | 490h | 02.12.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3246 |  | Auto Scheduled | מערכת הסאפ תתמוך בהעברת הזמנת החוב זי25אמ לזכיין לטובת תכנון הפצת הפריט מהמצ"מ ליחידה | 298.63 days | 27 January 2021 8:00 | 14 March 2022 13:00 | 0.11 |  | 70h | 02.12.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3247 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3248 |  | Auto Scheduled | LifeCycle Tasks | 298.63 days | 27 January 2021 8:00 | 14 March 2022 13:00 | 0.11 |  | 70h | 02.12.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3249 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3250 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3251 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 14.63 days | 16 February 2022 8:00 | 06 March 2022 17:00 | 0 |  | 0h | 02.12.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3252 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 07 March 2022 8:00 | 09 March 2022 15:00 | 0 | 3251 | 25h | 02.12.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3253 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 March 2022 15:00 | 10 March 2022 16:00 | 0 | 3252 | 10h | 02.12.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3254 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 March 2022 16:00 | 13 March 2022 17:00 | 0 | 3253 | 10h | 02.12.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3255 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 March 2022 8:00 | 14 March 2022 13:00 | 0 | 3254 | 5h | 02.12.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3256 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 14 March 2022 13:00 | 14 March 2022 13:00 | 0 | 3255,3249 | 0h | 02.12.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3257 |  | Auto Scheduled | מערכת ה- זכיין תשלח בממשק אוטומטי למערכת ה-סאפ את השדר לשינוע כולל נתוני התכולה המתוכננים ומועד אספקה מתוכנן. נתונים אלו יעדכנו את האספקה במערכת הסאפ. הנתונים יכללו, מספר הזמנה כולל שורה, לקוח, משאית, פריטים, כמויות, אמצעי אריזה, נתוני מסלול וכו'. | 295.25 days | 27 January 2021 8:00 | 09 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3258 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3259 |  | Auto Scheduled | LifeCycle Tasks | 295.25 days | 27 January 2021 8:00 | 09 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3260 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3261 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3262 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 10 February 2022 8:00 | 01 March 2022 17:00 | 0 |  | 0h | 02.12.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3263 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 March 2022 8:00 | 06 March 2022 15:00 | 0 | 3262 | 25h | 02.12.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3264 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 March 2022 15:00 | 07 March 2022 16:00 | 0 | 3263 | 10h | 02.12.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3265 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 March 2022 16:00 | 08 March 2022 17:00 | 0 | 3264 | 10h | 02.12.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3266 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 09 March 2022 8:00 | 09 March 2022 13:00 | 0 | 3265 | 5h | 02.12.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3267 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 09 March 2022 13:00 | 09 March 2022 13:00 | 0 | 3266,3260 | 0h | 02.12.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3268 |  | Auto Scheduled | מערכת הסאפ תשלח שדר למערכת הזכיין לטובת תכנון שינוע מטען מהמצ"מ לבימ"ל ולהיפך ללא קבלה למלאי באמצעות מערכת הויי אמ אס. | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3269 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3270 |  | Auto Scheduled | LifeCycle Tasks | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3271 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3272 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3273 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 02 February 2022 8:00 | 21 February 2022 17:00 | 0 |  | 0h | 02.12.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3274 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 February 2022 8:00 | 24 February 2022 15:00 | 0 | 3273 | 25h | 02.12.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3275 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 February 2022 15:00 | 27 February 2022 16:00 | 0 | 3274 | 10h | 02.12.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3276 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 February 2022 16:00 | 28 February 2022 17:00 | 0 | 3275 | 10h | 02.12.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3277 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 March 2022 8:00 | 01 March 2022 13:00 | 0 | 3276 | 5h | 02.12.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3278 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 01 March 2022 13:00 | 01 March 2022 13:00 | 0 | 3277,3271 | 0h | 02.12.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3279 |  | Auto Scheduled | מערכת ה סאפ תאפשר שליחת שדר למסופון הפי או די הכולל את הפריטים הנדרשים לאיסוף מהיחידה. | 278.38 days | 27 January 2021 8:00 | 16 February 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 02.12.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3280 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3281 |  | Auto Scheduled | LifeCycle Tasks | 278.38 days | 27 January 2021 8:00 | 16 February 2022 13:00 | 8.0000000000000002E-2 |  | 70h | 02.12.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3282 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3283 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3284 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 23.63 days | 11 January 2022 8:00 | 08 February 2022 17:00 | 0 |  | 0h | 02.12.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3285 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 February 2022 8:00 | 13 February 2022 15:00 | 0 | 3284 | 25h | 02.12.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3286 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 February 2022 15:00 | 14 February 2022 16:00 | 0 | 3285 | 10h | 02.12.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3287 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 February 2022 16:00 | 15 February 2022 17:00 | 0 | 3286 | 10h | 02.12.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3288 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 February 2022 8:00 | 16 February 2022 13:00 | 0 | 3287 | 5h | 02.12.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3289 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 16 February 2022 13:00 | 16 February 2022 13:00 | 0 | 3288,3282 | 0h | 02.12.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3290 |  | Auto Scheduled | מערכת הזכיין תאפשר עדכון מערכת הסאפ בנתוני האיסוף. | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3291 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3292 |  | Auto Scheduled | LifeCycle Tasks | 266 days | 27 January 2021 8:00 | 01 February 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.INT.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3293 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.05.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3294 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.05.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3295 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 05 January 2022 8:00 | 24 January 2022 17:00 | 0 |  | 0h | 02.12.INT.05.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3296 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 January 2022 8:00 | 27 January 2022 15:00 | 0 | 3295 | 25h | 02.12.INT.05.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3297 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 January 2022 15:00 | 30 January 2022 16:00 | 0 | 3296 | 10h | 02.12.INT.05.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3298 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 January 2022 16:00 | 31 January 2022 17:00 | 0 | 3297 | 10h | 02.12.INT.05.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3299 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 February 2022 8:00 | 01 February 2022 13:00 | 0 | 3298 | 5h | 02.12.INT.05.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3300 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 01 February 2022 13:00 | 01 February 2022 13:00 | 0 | 3299,3293 | 0h | 02.12.INT.05.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3301 |  | Auto Scheduled | מערכת הסאפ תאפשר שליחת הזמנות החזרה למערכת הזכיין לטובת תכנון איסוף פריטים מהיחידה. | 261.5 days | 27 January 2021 8:00 | 26 January 2022 13:00 | 0.11 |  | 70h | 02.12.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3302 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3303 |  | Auto Scheduled | LifeCycle Tasks | 261.5 days | 27 January 2021 8:00 | 26 January 2022 13:00 | 0.11 |  | 70h | 02.12.INT.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3304 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.06.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3305 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.06.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3306 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 14.63 days | 02 January 2022 8:00 | 18 January 2022 17:00 | 0 |  | 0h | 02.12.INT.06.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3307 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 January 2022 8:00 | 23 January 2022 15:00 | 0 | 3306 | 25h | 02.12.INT.06.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3308 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 January 2022 15:00 | 24 January 2022 16:00 | 0 | 3307 | 10h | 02.12.INT.06.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3309 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 January 2022 16:00 | 25 January 2022 17:00 | 0 | 3308 | 10h | 02.12.INT.06.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3310 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 26 January 2022 8:00 | 26 January 2022 13:00 | 0 | 3309 | 5h | 02.12.INT.06.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3311 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 26 January 2022 13:00 | 26 January 2022 13:00 | 0 | 3310,3304 | 0h | 02.12.INT.06.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3312 |  | Auto Scheduled | מערכת הסאפ תתמוך בהעברת הזמנת החוב זי25אמ לזכיין לטובת תכנון הפצת הפריט מהבימ"ל ליחידה | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 0.19 |  | 70h | 02.12.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3313 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3314 |  | Auto Scheduled | LifeCycle Tasks | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 0.19 |  | 70h | 02.12.INT.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3315 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.INT.07.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3316 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.INT.07.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3317 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 4.5 days | 16 February 2022 8:00 | 21 February 2022 17:00 | 0 |  | 0h | 02.12.INT.07.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3318 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 February 2022 8:00 | 24 February 2022 15:00 | 0 | 3317 | 25h | 02.12.INT.07.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3319 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 February 2022 15:00 | 27 February 2022 16:00 | 0 | 3318 | 10h | 02.12.INT.07.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3320 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 February 2022 16:00 | 28 February 2022 17:00 | 0 | 3319 | 10h | 02.12.INT.07.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3321 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 March 2022 8:00 | 01 March 2022 13:00 | 0 | 3320 | 5h | 02.12.INT.07.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3322 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 01 March 2022 13:00 | 01 March 2022 13:00 | 0 | 3321,3315 | 0h | 02.12.INT.07.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3323 |  | Auto Scheduled | 02.12: תיקונים.SAP | 368.38 days | 27 January 2021 8:00 | 08 June 2022 13:00 | 0.12 |  | 770h | 02.12.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3324 |  | Auto Scheduled | מערכת הסאפ תאפשר ביצוע קבלת פריטים בבימ"ל. | 293 days | 27 January 2021 8:00 | 07 March 2022 13:00 | 0.25 |  | 70h | 02.12.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3325 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3326 |  | Auto Scheduled | LifeCycle Tasks | 293 days | 27 January 2021 8:00 | 07 March 2022 13:00 | 0.25 |  | 70h | 02.12.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3327 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3328 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3329 |  | Auto Scheduled | יישום ופיתוח סאפ | 1.13 days | 27 February 2022 8:00 | 27 February 2022 17:00 | 0 |  | 0h | 02.12.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3330 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 28 February 2022 8:00 | 02 March 2022 15:00 | 0 | 3329 | 25h | 02.12.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3331 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 02 March 2022 15:00 | 03 March 2022 16:00 | 0 | 3330 | 10h | 02.12.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3332 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 March 2022 16:00 | 06 March 2022 17:00 | 0 | 3331 | 10h | 02.12.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3333 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 07 March 2022 8:00 | 07 March 2022 13:00 | 0 | 3332 | 5h | 02.12.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3334 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 07 March 2022 13:00 | 07 March 2022 13:00 | 0 | 3333,3327 | 0h | 02.12.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3335 |  | Auto Scheduled | מערכת הסאפ תתמוך בשליחת מייל אוטומטי ליחידה עם הפריטים הפסולים ומספר ההזמנה. | 322.25 days | 27 January 2021 8:00 | 12 April 2022 13:00 | 0.12 |  | 70h | 02.12.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3336 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3337 |  | Auto Scheduled | LifeCycle Tasks | 322.25 days | 27 January 2021 8:00 | 12 April 2022 13:00 | 0.12 |  | 70h | 02.12.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3338 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3339 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3340 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 21 March 2022 8:00 | 04 April 2022 17:00 | 0 |  | 0h | 02.12.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3341 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 April 2022 8:00 | 07 April 2022 15:00 | 0 | 3340 | 25h | 02.12.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3342 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 April 2022 15:00 | 10 April 2022 16:00 | 0 | 3341 | 10h | 02.12.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3343 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 April 2022 16:00 | 11 April 2022 17:00 | 0 | 3342 | 10h | 02.12.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3344 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 April 2022 8:00 | 12 April 2022 13:00 | 0 | 3343 | 5h | 02.12.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3345 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 12 April 2022 13:00 | 12 April 2022 13:00 | 0 | 3344,3338 | 0h | 02.12.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3346 |  | Auto Scheduled | מערכת הסאפ תאפשר העברת כושר לפריט שעבר תיקון | 326.75 days | 27 January 2021 8:00 | 18 April 2022 13:00 | 0.12 |  | 70h | 02.12.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3347 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3348 |  | Auto Scheduled | LifeCycle Tasks | 326.75 days | 27 January 2021 8:00 | 18 April 2022 13:00 | 0.12 |  | 70h | 02.12.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3349 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3350 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3351 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 27 March 2022 8:00 | 10 April 2022 17:00 | 0 |  | 0h | 02.12.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3352 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 April 2022 8:00 | 13 April 2022 15:00 | 0 | 3351 | 25h | 02.12.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3353 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 April 2022 15:00 | 14 April 2022 16:00 | 0 | 3352 | 10h | 02.12.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3354 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 April 2022 16:00 | 17 April 2022 17:00 | 0 | 3353 | 10h | 02.12.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3355 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 April 2022 8:00 | 18 April 2022 13:00 | 0 | 3354 | 5h | 02.12.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3356 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 18 April 2022 13:00 | 18 April 2022 13:00 | 0 | 3355,3349 | 0h | 02.12.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3357 |  | Auto Scheduled | יש לפתח במערכת הסאפ מסך תפעולי באמצעותו יהיה ניתן לעקוב עבור כל הזמנת החזרה מסוג תיקונים אחר סטטוס הפריט, באמצעות המסמכים הזמנות ותנועות המקושרים להחזרה ואחר מספר הימים בתיקון. בנוסף יתאפשר באמצעותו ליצור מסמכי חומר לצורך הפסילה, הויסות מהמצמ לבימל ולהפך | 342.5 days | 27 January 2021 8:00 | 08 May 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3358 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3359 |  | Auto Scheduled | LifeCycle Tasks | 342.5 days | 27 January 2021 8:00 | 08 May 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3360 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3361 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3362 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 10 April 2022 8:00 | 28 April 2022 17:00 | 0 |  | 0h | 02.12.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3363 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 May 2022 8:00 | 03 May 2022 15:00 | 0 | 3362 | 25h | 02.12.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3364 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 03 May 2022 15:00 | 04 May 2022 16:00 | 0 | 3363 | 10h | 02.12.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3365 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 04 May 2022 16:00 | 05 May 2022 17:00 | 0 | 3364 | 10h | 02.12.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3366 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 08 May 2022 8:00 | 08 May 2022 13:00 | 0 | 3365 | 5h | 02.12.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3367 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 08 May 2022 13:00 | 08 May 2022 13:00 | 0 | 3366,3360 | 0h | 02.12.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3368 |  | Auto Scheduled | מערכת ה-סאפ תתמוך באפשרות של פתיחת דרישה, ולמולה תאפשר פתיחת הזמנה בצורה אוטומטית ו,או באישור ידני. | 368.38 days | 27 January 2021 8:00 | 08 June 2022 13:00 | 0.11 |  | 70h | 02.12.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3369 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3370 |  | Auto Scheduled | LifeCycle Tasks | 368.38 days | 27 January 2021 8:00 | 08 June 2022 13:00 | 0.11 |  | 70h | 02.12.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3371 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3372 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3373 |  | Auto Scheduled | יישום ופיתוח סאפ | 14.63 days | 15 May 2022 8:00 | 31 May 2022 17:00 | 0 |  | 0h | 02.12.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3374 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 June 2022 8:00 | 05 June 2022 15:00 | 0 | 3373 | 25h | 02.12.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3375 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 June 2022 15:00 | 06 June 2022 16:00 | 0 | 3374 | 10h | 02.12.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3376 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 June 2022 16:00 | 07 June 2022 17:00 | 0 | 3375 | 10h | 02.12.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3377 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 08 June 2022 8:00 | 08 June 2022 13:00 | 0 | 3376 | 5h | 02.12.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3378 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 08 June 2022 13:00 | 08 June 2022 13:00 | 0 | 3377,3371 | 0h | 02.12.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3379 |  | Auto Scheduled | מערכת הסאפ תאפשר יצירת הזמנת חוב בעת קבלת המלאי במצ"מ עם סימוכין להזמנת ההחזרה. | 303.13 days | 27 January 2021 8:00 | 20 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3380 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3381 |  | Auto Scheduled | LifeCycle Tasks | 303.13 days | 27 January 2021 8:00 | 20 March 2022 13:00 | 0.10000000000000001 |  | 70h | 02.12.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3382 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3383 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3384 |  | Auto Scheduled | יישום ופיתוח סאפ | 15.75 days | 21 February 2022 8:00 | 10 March 2022 17:00 | 0 |  | 0h | 02.12.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3385 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 March 2022 8:00 | 15 March 2022 15:00 | 0 | 3384 | 25h | 02.12.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3386 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 15 March 2022 15:00 | 16 March 2022 16:00 | 0 | 3385 | 10h | 02.12.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3387 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 March 2022 16:00 | 17 March 2022 17:00 | 0 | 3386 | 10h | 02.12.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3388 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 20 March 2022 8:00 | 20 March 2022 13:00 | 0 | 3387 | 5h | 02.12.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3389 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 20 March 2022 13:00 | 20 March 2022 13:00 | 0 | 3388,3382 | 0h | 02.12.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3390 |  | Auto Scheduled | יש לגבש דמ"צים לדוחות בקרה אחר תהליך התיקונים | 354.88 days | 27 January 2021 8:00 | 23 May 2022 13:00 | 0.12 |  | 70h | 02.12.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3391 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3392 |  | Auto Scheduled | LifeCycle Tasks | 354.88 days | 27 January 2021 8:00 | 23 May 2022 13:00 | 0.12 |  | 70h | 02.12.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3393 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3394 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3395 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 01 May 2022 8:00 | 15 May 2022 17:00 | 0 |  | 0h | 02.12.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3396 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 May 2022 8:00 | 18 May 2022 15:00 | 0 | 3395 | 25h | 02.12.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3397 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 May 2022 15:00 | 19 May 2022 16:00 | 0 | 3396 | 10h | 02.12.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3398 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 May 2022 16:00 | 22 May 2022 17:00 | 0 | 3397 | 10h | 02.12.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3399 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 May 2022 8:00 | 23 May 2022 13:00 | 0 | 3398 | 5h | 02.12.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3400 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 23 May 2022 13:00 | 23 May 2022 13:00 | 0 | 3399,3393 | 0h | 02.12.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3401 |  | Auto Scheduled | מערכת הסאפ תאפשר ביצוע קבלת מלאי למצ"מ תיקונים סאפי. | 322.25 days | 27 January 2021 8:00 | 12 April 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 02.12.SAP.08 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3402 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.08.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3403 |  | Auto Scheduled | LifeCycle Tasks | 322.25 days | 27 January 2021 8:00 | 12 April 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 02.12.SAP.08.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3404 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.08.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3405 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.08.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3406 |  | Auto Scheduled | יישום ופיתוח סאפ | 24.75 days | 06 March 2022 8:00 | 04 April 2022 17:00 | 0 |  | 0h | 02.12.SAP.08.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3407 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 April 2022 8:00 | 07 April 2022 15:00 | 0 | 3406 | 25h | 02.12.SAP.08.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3408 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 April 2022 15:00 | 10 April 2022 16:00 | 0 | 3407 | 10h | 02.12.SAP.08.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3409 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 April 2022 16:00 | 11 April 2022 17:00 | 0 | 3408 | 10h | 02.12.SAP.08.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3410 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 April 2022 8:00 | 12 April 2022 13:00 | 0 | 3409 | 5h | 02.12.SAP.08.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3411 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 12 April 2022 13:00 | 12 April 2022 13:00 | 0 | 3410,3404 | 0h | 02.12.SAP.08.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3412 |  | Auto Scheduled | מערכת הסאפ תאפשר לבצע תהליך זיכוי יחידה, העברת כושר לפריט וסגירת הזמנת חוב זי25אמ. | 311 days | 27 January 2021 8:00 | 29 March 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.12.SAP.09 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3413 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.09.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3414 |  | Auto Scheduled | LifeCycle Tasks | 311 days | 27 January 2021 8:00 | 29 March 2022 13:00 | 8.9999999999999997E-2 |  | 70h | 02.12.SAP.09.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3415 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.09.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3416 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.09.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3417 |  | Auto Scheduled | יישום ופיתוח סאפ | 19.13 days | 27 February 2022 8:00 | 21 March 2022 17:00 | 0 |  | 0h | 02.12.SAP.09.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3418 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 March 2022 8:00 | 24 March 2022 15:00 | 0 | 3417 | 25h | 02.12.SAP.09.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3419 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 March 2022 15:00 | 27 March 2022 16:00 | 0 | 3418 | 10h | 02.12.SAP.09.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3420 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 March 2022 16:00 | 28 March 2022 17:00 | 0 | 3419 | 10h | 02.12.SAP.09.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3421 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 March 2022 8:00 | 29 March 2022 13:00 | 0 | 3420 | 5h | 02.12.SAP.09.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3422 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 29 March 2022 13:00 | 29 March 2022 13:00 | 0 | 3421,3415 | 0h | 02.12.SAP.09.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3423 |  | Auto Scheduled | מערכת ה-סאפ תכלול חוקות בדרישה בהתאם למבנה הארגוני החדש של המרה"ס | 289.63 days | 27 January 2021 8:00 | 02 March 2022 13:00 | 0.19 |  | 70h | 02.12.SAP.10 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3424 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.10.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3425 |  | Auto Scheduled | LifeCycle Tasks | 289.63 days | 27 January 2021 8:00 | 02 March 2022 13:00 | 0.19 |  | 70h | 02.12.SAP.10.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3426 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.10.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3427 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.10.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3428 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 17 February 2022 8:00 | 22 February 2022 17:00 | 0 |  | 0h | 02.12.SAP.10.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3429 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 February 2022 8:00 | 27 February 2022 15:00 | 0 | 3428 | 25h | 02.12.SAP.10.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3430 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 February 2022 15:00 | 28 February 2022 16:00 | 0 | 3429 | 10h | 02.12.SAP.10.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3431 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 February 2022 16:00 | 01 March 2022 17:00 | 0 | 3430 | 10h | 02.12.SAP.10.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3432 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 March 2022 8:00 | 02 March 2022 13:00 | 0 | 3431 | 5h | 02.12.SAP.10.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3433 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 02 March 2022 13:00 | 02 March 2022 13:00 | 0 | 3432,3426 | 0h | 02.12.SAP.10.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3434 |  | Auto Scheduled | מערכת ה-סאפ תאפשר אישור ידני,אוטומטי לדרישה מותאם למבנה הארגוני החדש של המרה"ס | 290.75 days | 27 January 2021 8:00 | 03 March 2022 13:00 | 0.19 |  | 70h | 02.12.SAP.11 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3435 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.11.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3436 |  | Auto Scheduled | LifeCycle Tasks | 290.75 days | 27 January 2021 8:00 | 03 March 2022 13:00 | 0.19 |  | 70h | 02.12.SAP.11.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3437 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.12.SAP.11.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3438 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3233 | 20h | 02.12.SAP.11.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3439 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 20 February 2022 8:00 | 23 February 2022 17:00 | 0 |  | 0h | 02.12.SAP.11.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3440 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 February 2022 8:00 | 28 February 2022 15:00 | 0 | 3439 | 25h | 02.12.SAP.11.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3441 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 February 2022 15:00 | 01 March 2022 16:00 | 0 | 3440 | 10h | 02.12.SAP.11.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3442 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 March 2022 16:00 | 02 March 2022 17:00 | 0 | 3441 | 10h | 02.12.SAP.11.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3443 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 March 2022 8:00 | 03 March 2022 13:00 | 0 | 3442 | 5h | 02.12.SAP.11.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3444 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 March 2022 13:00 | 03 March 2022 13:00 | 0 | 3443,3437 | 0h | 02.12.SAP.11.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3445 |  | Auto Scheduled | 02.13: השאלות | 421.25 days | 12 July 2020 8:00 | 25 January 2022 13:00 | 0.65000000000000002 |  | 759h | 02.13 | חתום | אבי פרישמן | hd | רועי | nan | BP | NA | As Soon As Possible | 3
3446 |  | Auto Scheduled | 02.13: השאלות.BP | 142.88 days | 12 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 129h | 02.13.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3447 |  | Auto Scheduled | 02.13: השאלות | 142.88 days | 12 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 129h | 02.13.BP.01 | חתום | אבי פרישמן | parent | רועי | nan | BP | NA | As Soon As Possible | 5
3448 |  | Auto Scheduled | Sub Tasks | 89.13 days | 14 September 2020 8:00 | 03 January 2021 10:00 | 1 |  | 89h | 02.13.BP.01.01 |  | אבי פרישמן | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3449 |  | Auto Scheduled | כתיבת מסמך | 1.13 days | 14 September 2020 8:00 | 14 September 2020 17:00 | 1 |  | 9h | 02.13.BP.01.01.80 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | Must Start On | 7
3450 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 3 days | 24 September 2020 8:00 | 28 September 2020 14:00 | 1 | 3449 | 24h | 02.13.BP.01.01.81 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3451 |  | Auto Scheduled | אישור מקל"ר | 1.25 days | 27 October 2020 8:00 | 28 October 2020 9:00 | 1 | 3450 | 10h | 02.13.BP.01.01.82 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3452 |  | Auto Scheduled | אישור המנהלת | 0.38 days | 09 November 2020 8:00 | 09 November 2020 11:00 | 1 | 3451 | 3h | 02.13.BP.01.01.83 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3453 |  | Auto Scheduled | אישור מפקדת | 1.38 days | 11 November 2020 8:00 | 12 November 2020 10:00 | 1 | 3452 | 11h | 02.13.BP.01.01.84 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3454 |  | Auto Scheduled | אישור אבי | 1.25 days | 25 November 2020 8:00 | 26 November 2020 9:00 | 1 | 3453 | 10h | 02.13.BP.01.01.85 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3455 |  | Auto Scheduled | אישור חטלו"ג | 2.13 days | 08 December 2020 8:00 | 09 December 2020 16:00 | 1 | 3454 | 17h | 02.13.BP.01.01.86 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3456 |  | Auto Scheduled | אישור ניר בשן | 0.38 days | 30 December 2020 8:00 | 30 December 2020 11:00 | 1 | 3455 | 3h | 02.13.BP.01.01.87 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3457 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 03 January 2021 8:00 | 03 January 2021 10:00 | 1 | 3456 | 2h | 02.13.BP.01.01.88 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3458 |  | Auto Scheduled | LifeCycle Tasks | 142.88 days | 12 July 2020 8:00 | 04 January 2021 17:00 | 1 |  | 40h | 02.13.BP.01.02 |  | אבי פרישמן | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3459 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 04 January 2021 8:00 | 04 January 2021 17:00 | 1 | 3457 | 0h | 02.13.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3460 |  | Auto Scheduled | טרם החל | 0.63 days | 12 July 2020 8:00 | 12 July 2020 13:00 | 1 |  | 5h | 02.13.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3461 |  | Auto Scheduled | בעבודה | 1.25 days | 19 July 2020 8:00 | 20 July 2020 9:00 | 1 | 3460 | 10h | 02.13.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3462 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 02 August 2020 8:00 | 02 August 2020 13:00 | 1 | 3461 | 5h | 02.13.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3463 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 09 August 2020 8:00 | 10 August 2020 9:00 | 1 | 3462 | 10h | 02.13.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3464 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 23 August 2020 8:00 | 24 August 2020 9:00 | 1 | 3463 | 10h | 02.13.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3465 |  | Auto Scheduled | בחתימה | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 3464,3459 | 0h | 02.13.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3466 |  | Auto Scheduled | חתום | 0 days | 04 January 2021 8:00 | 04 January 2021 8:00 | 1 | 3465 | 0h | 02.13.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3467 |  | Auto Scheduled | 02.13: השאלות.INT | 279.5 days | 04 January 2021 8:00 | 25 January 2022 13:00 | 0.14999999999999999 |  | 140h | 02.13.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3468 |  | Auto Scheduled | מערכת זכיין תאפשר לעדכן את סטטוס ניפוק האספקה ועדכון המלאים במערכת סאפ | 279.5 days | 04 January 2021 8:00 | 25 January 2022 13:00 | 0.14000000000000001 |  | 70h | 02.13.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3469 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3470 |  | Auto Scheduled | LifeCycle Tasks | 279.5 days | 04 January 2021 8:00 | 25 January 2022 13:00 | 0.14000000000000001 |  | 70h | 02.13.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3471 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3472 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3473 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 9 days | 06 January 2022 8:00 | 17 January 2022 17:00 | 0 |  | 0h | 02.13.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3474 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 18 January 2022 8:00 | 20 January 2022 15:00 | 0 | 3473 | 25h | 02.13.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3475 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 January 2022 15:00 | 23 January 2022 16:00 | 0 | 3474 | 10h | 02.13.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3476 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 January 2022 16:00 | 24 January 2022 17:00 | 0 | 3475 | 10h | 02.13.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3477 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 25 January 2022 8:00 | 25 January 2022 13:00 | 0 | 3476 | 5h | 02.13.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3478 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 25 January 2022 13:00 | 25 January 2022 13:00 | 0 | 3477,3471 | 0h | 02.13.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3479 |  | Auto Scheduled | מערכת סאפ תעביר את נתוני האספקות שנפתחו למערכת ה-זכיין עבור היחידה הדורשת | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.14999999999999999 |  | 70h | 02.13.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3480 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3481 |  | Auto Scheduled | LifeCycle Tasks | 273.88 days | 04 January 2021 8:00 | 18 January 2022 13:00 | 0.14999999999999999 |  | 70h | 02.13.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3482 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3483 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3484 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 7.88 days | 02 January 2022 8:00 | 10 January 2022 17:00 | 0 |  | 0h | 02.13.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3485 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 January 2022 8:00 | 13 January 2022 15:00 | 0 | 3484 | 25h | 02.13.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3486 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 January 2022 15:00 | 16 January 2022 16:00 | 0 | 3485 | 10h | 02.13.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3487 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 January 2022 16:00 | 17 January 2022 17:00 | 0 | 3486 | 10h | 02.13.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3488 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 January 2022 8:00 | 18 January 2022 13:00 | 0 | 3487 | 5h | 02.13.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3489 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 18 January 2022 13:00 | 18 January 2022 13:00 | 0 | 3488,3482 | 0h | 02.13.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3490 |  | Auto Scheduled | 02.13: השאלות.SAP | 194 days | 04 January 2021 8:00 | 11 October 2021 13:00 | 0.69999999999999996 |  | 490h | 02.13.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3491 |  | Auto Scheduled | מערכת הסאפ תאפשר לבצע הארכת תוקף השאלה מסך זי אל אי אן די | 188.38 days | 04 January 2021 8:00 | 04 October 2021 13:00 | 0.19 |  | 70h | 02.13.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3492 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3493 |  | Auto Scheduled | LifeCycle Tasks | 188.38 days | 04 January 2021 8:00 | 04 October 2021 13:00 | 0.19 |  | 70h | 02.13.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3494 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3495 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3496 |  | Auto Scheduled | יישום ופיתוח סאפ | 4.5 days | 05 September 2021 8:00 | 13 September 2021 17:00 | 0 |  | 0h | 02.13.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3497 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 September 2021 8:00 | 29 September 2021 15:00 | 0 | 3496 | 25h | 02.13.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3498 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 September 2021 15:00 | 30 September 2021 16:00 | 0 | 3497 | 10h | 02.13.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3499 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 September 2021 16:00 | 03 October 2021 17:00 | 0 | 3498 | 10h | 02.13.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3500 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 04 October 2021 8:00 | 04 October 2021 13:00 | 0 | 3499 | 5h | 02.13.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3501 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 04 October 2021 13:00 | 04 October 2021 13:00 | 0 | 3500,3494 | 0h | 02.13.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3502 |  | Auto Scheduled | נדרש להוסיף בעת יצירת הדרישה לניפוק השאלה לגורם חוץ שדה חובה למילוי מספר הספק המקבל | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.79000000000000004 |  | 70h | 02.13.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3503 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3504 |  | Auto Scheduled | LifeCycle Tasks | 177.63 days | 04 January 2021 8:00 | 05 September 2021 8:00 | 0.79000000000000004 |  | 70h | 02.13.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3505 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3506 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3507 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 27 June 2021 8:00 | 21 July 2021 17:00 | 1 |  | 0h | 02.13.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3508 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 July 2021 8:00 | 26 July 2021 15:00 | 0 | 3507 | 25h | 02.13.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3509 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 July 2021 15:00 | 27 July 2021 16:00 | 0 | 3508 | 10h | 02.13.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3510 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 July 2021 16:00 | 28 July 2021 17:00 | 0 | 3509 | 10h | 02.13.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3511 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 29 July 2021 8:00 | 29 July 2021 13:00 | 0 | 3510 | 5h | 02.13.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3512 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3511,3505 | 0h | 02.13.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3513 |  | Auto Scheduled | במעמד החזרה של פריט מגורם חיצוני, קיזוז השאלה על סמך הצלבה של פרטי הפריט בנוסף להצלבה של מספר ספק. | 181.63 days | 04 January 2021 8:00 | 13 September 2021 13:00 | 0.79000000000000004 |  | 70h | 02.13.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3514 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3515 |  | Auto Scheduled | LifeCycle Tasks | 181.63 days | 04 January 2021 8:00 | 13 September 2021 13:00 | 0.79000000000000004 |  | 70h | 02.13.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3516 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3517 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3518 |  | Auto Scheduled | יישום ופיתוח סאפ | 37.13 days | 18 July 2021 8:00 | 31 August 2021 17:00 | 0.91000000000000003 |  | 0h | 02.13.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3519 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 01 September 2021 8:00 | 05 September 2021 15:00 | 0 | 3518 | 25h | 02.13.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3520 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 September 2021 15:00 | 09 September 2021 16:00 | 0 | 3519 | 10h | 02.13.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3521 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 September 2021 16:00 | 12 September 2021 17:00 | 0 | 3520 | 10h | 02.13.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3522 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 13 September 2021 8:00 | 13 September 2021 13:00 | 0 | 3521 | 5h | 02.13.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3523 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 13 September 2021 13:00 | 13 September 2021 13:00 | 0 | 3522,3516 | 0h | 02.13.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3524 |  | Auto Scheduled | אפשרות הזנה של מספר תיק השאלה שדה מספרי משהב"ט בהזמנת ההשאלה לגורם חיצוני סימולי חוץ. | 183.88 days | 04 January 2021 8:00 | 19 September 2021 13:00 | 0.46000000000000002 |  | 70h | 02.13.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3525 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3526 |  | Auto Scheduled | LifeCycle Tasks | 183.88 days | 04 January 2021 8:00 | 19 September 2021 13:00 | 0.46000000000000002 |  | 70h | 02.13.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3527 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3528 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3529 |  | Auto Scheduled | יישום ופיתוח סאפ | 7.88 days | 25 August 2021 8:00 | 02 September 2021 17:00 | 0.65000000000000002 |  | 0h | 02.13.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3530 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 September 2021 8:00 | 12 September 2021 15:00 | 0 | 3529 | 25h | 02.13.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3531 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 September 2021 15:00 | 13 September 2021 16:00 | 0 | 3530 | 10h | 02.13.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3532 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 September 2021 16:00 | 14 September 2021 17:00 | 0 | 3531 | 10h | 02.13.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3533 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 September 2021 8:00 | 19 September 2021 13:00 | 0 | 3532 | 5h | 02.13.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3534 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 19 September 2021 13:00 | 19 September 2021 13:00 | 0 | 3533,3527 | 0h | 02.13.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3535 |  | Auto Scheduled | מערכת סאפ תאפשר לאשר,לדחות להקטין כמות של השאלה ליחידה | 186.13 days | 04 January 2021 8:00 | 30 September 2021 13:00 | 0.14999999999999999 |  | 70h | 02.13.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3536 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3537 |  | Auto Scheduled | LifeCycle Tasks | 186.13 days | 04 January 2021 8:00 | 30 September 2021 13:00 | 0.14999999999999999 |  | 70h | 02.13.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3538 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3539 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3540 |  | Auto Scheduled | יישום ופיתוח סאפ | 7.88 days | 29 August 2021 8:00 | 09 September 2021 17:00 | 0 |  | 0h | 02.13.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3541 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 September 2021 8:00 | 14 September 2021 15:00 | 0 | 3540 | 25h | 02.13.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3542 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 September 2021 15:00 | 19 September 2021 16:00 | 0 | 3541 | 10h | 02.13.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3543 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 September 2021 16:00 | 29 September 2021 17:00 | 0 | 3542 | 10h | 02.13.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3544 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 September 2021 8:00 | 30 September 2021 13:00 | 0 | 3543 | 5h | 02.13.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3545 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 30 September 2021 13:00 | 30 September 2021 13:00 | 0 | 3544,3538 | 0h | 02.13.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3546 |  | Auto Scheduled | מערכת ה-סאפ תאפשר לבצע קיזוז וסגירת הזמנת החזרת השאלה זי25 על סמך מימוש החזרה מסוג הזמנה זי23באופן אוטומטי | 194 days | 04 January 2021 8:00 | 11 October 2021 13:00 | 0.82999999999999996 |  | 70h | 02.13.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3547 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3548 |  | Auto Scheduled | LifeCycle Tasks | 194 days | 04 January 2021 8:00 | 11 October 2021 13:00 | 0.82999999999999996 |  | 70h | 02.13.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3549 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3550 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3551 |  | Auto Scheduled | יישום ופיתוח סאפ | 111.38 days | 20 April 2021 8:00 | 03 October 2021 17:00 | 0.87 |  | 0h | 02.13.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3552 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 October 2021 8:00 | 06 October 2021 15:00 | 0 | 3551 | 25h | 02.13.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3553 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 06 October 2021 15:00 | 07 October 2021 16:00 | 0 | 3552 | 10h | 02.13.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3554 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 07 October 2021 16:00 | 10 October 2021 17:00 | 0 | 3553 | 10h | 02.13.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3555 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 October 2021 8:00 | 11 October 2021 13:00 | 0 | 3554 | 5h | 02.13.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3556 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 11 October 2021 13:00 | 11 October 2021 13:00 | 0 | 3555,3549 | 0h | 02.13.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3557 |  | Auto Scheduled | אפשרות של צ' להופיע בשתי הזמנות שונות במקביל במקרה שלנו זי23 ו-זי25. | 178.25 days | 04 January 2021 8:00 | 05 September 2021 13:00 | 0.47999999999999998 |  | 70h | 02.13.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3558 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3559 |  | Auto Scheduled | LifeCycle Tasks | 178.25 days | 04 January 2021 8:00 | 05 September 2021 13:00 | 0.47999999999999998 |  | 70h | 02.13.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3560 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.13.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3561 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 04 January 2021 8:00 | 06 January 2021 10:00 | 1 | 3457 | 20h | 02.13.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3562 |  | Auto Scheduled | יישום ופיתוח סאפ | 3.38 days | 24 August 2021 8:00 | 26 August 2021 17:00 | 1 |  | 0h | 02.13.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3563 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 August 2021 8:00 | 31 August 2021 15:00 | 0 | 3562 | 25h | 02.13.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3564 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 31 August 2021 15:00 | 01 September 2021 16:00 | 0 | 3563 | 10h | 02.13.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3565 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 September 2021 16:00 | 02 September 2021 17:00 | 0 | 3564 | 10h | 02.13.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3566 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 0 | 3565 | 5h | 02.13.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3567 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 13:00 | 05 September 2021 13:00 | 0 | 3566,3560 | 0h | 02.13.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3568 |  | Auto Scheduled | 02.18: טיפול בהפרשים | 173.25 days | 12 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 162h | 02.18 | חתום | פריאל ישי | hd | פריאל | nan | BP | NA | As Soon As Possible | 3
3569 |  | Auto Scheduled | 02.18: טיפול בהפרשים.BP | 173.25 days | 12 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 162h | 02.18.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3570 |  | Auto Scheduled | 02.18: טיפול בהפרשים | 173.25 days | 12 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 162h | 02.18.BP.01 | חתום | פריאל ישי | parent | פריאל | nan | BP | NA | As Soon As Possible | 5
3571 |  | Auto Scheduled | Sub Tasks | 147.63 days | 10 August 2020 8:00 | 09 February 2021 10:00 | 1 |  | 122h | 02.18.BP.01.01 |  | פריאל ישי | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3572 |  | Auto Scheduled | אמלח נדרש לאשר מול חטלו"ג שהניפוק יהיה בשלב יציאת המשאית למחסן ההפצה. | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.18.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | Must Start On | 7
3573 |  | Auto Scheduled | היה דיון ב-2.8. עד הדיון, פריאל בודק האם קשור לעוד מקומות ואיך משפיע. מה הסטאטוס? | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.18.BP.01.01.11 | בוצע |  | MoM |  | מאיה | BP | NA | As Soon As Possible | 7
3574 |  | Auto Scheduled | כתיבת מסמך | 2 days | 08 September 2020 8:00 | 09 September 2020 15:00 | 1 |  | 16h | 02.18.BP.01.01.30 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3575 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 2.75 days | 29 September 2020 8:00 | 01 October 2020 12:00 | 1 | 3574 | 22h | 02.18.BP.01.01.31 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3576 |  | Auto Scheduled | אישור מקל"ר | 5.25 days | 28 October 2020 8:00 | 03 November 2020 14:00 | 1 | 3575 | 42h | 02.18.BP.01.01.32 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3577 |  | Auto Scheduled | אישור אבי | 1 day | 24 December 2020 8:00 | 24 December 2020 16:00 | 1 | 3576 | 8h | 02.18.BP.01.01.33 | בוצע | אבי | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3578 |  | Auto Scheduled | אישור המנהלת | 3.25 days | 04 January 2021 8:00 | 06 January 2021 16:00 | 1 | 3577 | 26h | 02.18.BP.01.01.34 | בוצע | סיגל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3579 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 08 February 2021 8:00 | 08 February 2021 10:00 | 1 | 3578 | 2h | 02.18.BP.01.01.35 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3580 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 09 February 2021 8:00 | 09 February 2021 9:00 | 1 | 3579 | 1h | 02.18.BP.01.01.36 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3581 |  | Auto Scheduled | אישור ניר בשן | 0.13 days | 09 February 2021 8:00 | 09 February 2021 9:00 | 1 | 3580 | 1h | 02.18.BP.01.01.37 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3582 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 09 February 2021 8:00 | 09 February 2021 10:00 | 1 | 3581 | 2h | 02.18.BP.01.01.38 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
3583 |  | Auto Scheduled | LifeCycle Tasks | 173.25 days | 12 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 40h | 02.18.BP.01.02 |  | פריאל ישי | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3584 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 10 February 2021 8:00 | 10 February 2021 17:00 | 1 | 3582 | 0h | 02.18.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3585 |  | Auto Scheduled | טרם החל | 0.63 days | 12 July 2020 8:00 | 12 July 2020 13:00 | 1 |  | 5h | 02.18.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3586 |  | Auto Scheduled | בעבודה | 1.25 days | 19 July 2020 8:00 | 20 July 2020 9:00 | 1 | 3585 | 10h | 02.18.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3587 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 02 August 2020 8:00 | 02 August 2020 13:00 | 1 | 3586 | 5h | 02.18.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3588 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 09 August 2020 8:00 | 10 August 2020 9:00 | 1 | 3587 | 10h | 02.18.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3589 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 23 August 2020 8:00 | 24 August 2020 9:00 | 1 | 3588 | 10h | 02.18.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3590 |  | Auto Scheduled | בחתימה | 0 days | 10 February 2021 8:00 | 10 February 2021 8:00 | 1 | 3589,3584 | 0h | 02.18.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3591 |  | Auto Scheduled | חתום | 0 days | 10 February 2021 8:00 | 10 February 2021 8:00 | 1 | 3590 | 0h | 02.18.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3592 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות | 187.88 days | 09 July 2020 8:00 | 28 February 2021 17:00 | 1 |  | 169h | 02.21 | חתום |  | hd | מאור | nan | BP | NA | As Soon As Possible | 3
3593 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות.BP | 187.88 days | 09 July 2020 8:00 | 28 February 2021 17:00 | 1 |  | 169h | 02.21.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3594 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות | 187.88 days | 09 July 2020 8:00 | 28 February 2021 17:00 | 1 |  | 169h | 02.21.BP.01 | חתום |  | parent | מאור | nan | BP | NA | As Soon As Possible | 5
3595 |  | Auto Scheduled | Sub Tasks | 104.25 days | 10 September 2020 8:00 | 18 January 2021 14:00 | 1 |  | 129h | 02.21.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3596 |  | Auto Scheduled | כתיבת מסמך | 6.38 days | 10 September 2020 8:00 | 17 September 2020 14:00 | 1 |  | 51h | 02.21.BP.01.01.30 | בוצע | מאור | MoM | מאור | תע = שרשרת | BP | NA | Must Start On | 7
3597 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.63 days | 19 November 2020 8:00 | 19 November 2020 13:00 | 1 | 3596 | 5h | 02.21.BP.01.01.31 | בוצע | מאור | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3598 |  | Auto Scheduled | אישור המנהלת | 0.38 days | 25 November 2020 8:00 | 25 November 2020 11:00 | 1 | 3597 | 3h | 02.21.BP.01.01.32 | בוצע | סיגל | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3599 |  | Auto Scheduled | אישור מקל"ר | 1.13 days | 29 November 2020 8:00 | 29 November 2020 17:00 | 1 | 3598 | 9h | 02.21.BP.01.01.33 | בוצע | מאור | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3600 |  | Auto Scheduled | אישור אבי | 0.25 days | 09 December 2020 8:00 | 09 December 2020 10:00 | 1 | 3599 | 2h | 02.21.BP.01.01.34 | בוצע | אבי | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3601 |  | Auto Scheduled | אישור מפקדת | 1.88 days | 12 December 2020 8:00 | 14 December 2020 14:00 | 1 | 3600 | 15h | 02.21.BP.01.01.35 | בוצע | מאור | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3602 |  | Auto Scheduled | אישור חטלו"ג | 1.25 days | 31 December 2020 8:00 | 03 January 2021 9:00 | 1 | 3601 | 10h | 02.21.BP.01.01.36 | בוצע | מאור | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3603 |  | Auto Scheduled | אישור ניר בשן | 0.13 days | 13 January 2021 8:00 | 13 January 2021 9:00 | 1 | 3602 | 1h | 02.21.BP.01.01.37 | בוצע | מאור | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3604 |  | Auto Scheduled | אישור שגיב שרביט | 4.13 days | 13 January 2021 8:00 | 18 January 2021 14:00 | 1 | 3603 | 33h | 02.21.BP.01.01.38 | בוצע | מאור | MoM | מאור | nan | BP | NA | As Soon As Possible | 7
3605 |  | Auto Scheduled | LifeCycle Tasks | 187.88 days | 09 July 2020 8:00 | 28 February 2021 17:00 | 1 |  | 40h | 02.21.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3606 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 28 February 2021 8:00 | 28 February 2021 17:00 | 1 | 3604 | 0h | 02.21.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3607 |  | Auto Scheduled | טרם החל | 0.63 days | 09 July 2020 8:00 | 09 July 2020 13:00 | 1 |  | 5h | 02.21.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3608 |  | Auto Scheduled | בעבודה | 1.25 days | 16 July 2020 8:00 | 19 July 2020 9:00 | 1 | 3607 | 10h | 02.21.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3609 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 30 July 2020 8:00 | 30 July 2020 13:00 | 1 | 3608 | 5h | 02.21.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3610 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 06 August 2020 8:00 | 09 August 2020 9:00 | 1 | 3609 | 10h | 02.21.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3611 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 20 August 2020 8:00 | 23 August 2020 9:00 | 1 | 3610 | 10h | 02.21.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3612 |  | Auto Scheduled | בחתימה | 0 days | 28 February 2021 8:00 | 28 February 2021 8:00 | 1 | 3611,3606 | 0h | 02.21.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3613 |  | Auto Scheduled | חתום | 0 days | 28 February 2021 8:00 | 28 February 2021 8:00 | 1 | 3612 | 0h | 02.21.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3614 |  | Auto Scheduled | 02.23: MRP | 407.75 days | 21 July 2020 8:00 | 18 January 2022 13:00 | 0.17000000000000001 |  | 355h | 02.23 | חתום | מאיה | hd | פריאל | nan | BP | NA | As Soon As Possible | 3
3615 |  | Auto Scheduled | 02.23: MRP.BP | 165.38 days | 21 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 145h | 02.23.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3616 |  | Auto Scheduled | 02.23: MRP | 165.38 days | 21 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 145h | 02.23.BP.01 | חתום | מאיה | parent | פריאל | nan | BP | NA | As Soon As Possible | 5
3617 |  | Auto Scheduled | Sub Tasks | 146.63 days | 10 August 2020 8:00 | 08 February 2021 11:00 | 1 |  | 105h | 02.23.BP.01.01 |  | מאיה | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3618 |  | Auto Scheduled | היום יש ביזור פנימי במרכזים בצורה ידנית (חוץ מחנויות מכר) האם יש שינוי ממה שקורה היום?--אמל"ח נדרש לעדכן האם נדרש התהליך בעידן במרה"ס | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.23.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | Must Start On | 7
3619 |  | Auto Scheduled | כתיבת מסמך | 3.13 days | 30 September 2020 8:00 | 04 October 2020 15:00 | 1 |  | 25h | 02.23.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3620 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 4.75 days | 03 November 2020 8:00 | 09 November 2020 10:00 | 1 | 3619 | 38h | 02.23.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3621 |  | Auto Scheduled | אישור אבי | 1 day | 24 December 2020 8:00 | 24 December 2020 16:00 | 1 | 3620 | 8h | 02.23.BP.01.01.32 | בוצע | אבי | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3622 |  | Auto Scheduled | אישור חטלו"ג | 1.88 days | 04 January 2021 8:00 | 05 January 2021 14:00 | 1 | 3621 | 15h | 02.23.BP.01.01.33 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3623 |  | Auto Scheduled | אישור מקל"ר | 0.5 days | 24 January 2021 8:00 | 24 January 2021 12:00 | 1 | 3622 | 4h | 02.23.BP.01.01.34 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3624 |  | Auto Scheduled | אישור המנהלת | 1.13 days | 27 January 2021 8:00 | 27 January 2021 17:00 | 1 | 3623 | 9h | 02.23.BP.01.01.35 | בוצע | סיגל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3625 |  | Auto Scheduled | אישור מפקדת | 0.13 days | 08 February 2021 8:00 | 08 February 2021 9:00 | 1 | 3624 | 1h | 02.23.BP.01.01.36 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3626 |  | Auto Scheduled | אישור ניר בשן | 0.13 days | 08 February 2021 8:00 | 08 February 2021 9:00 | 1 | 3625 | 1h | 02.23.BP.01.01.37 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3627 |  | Auto Scheduled | אישור שגיב שרביט | 0.38 days | 08 February 2021 8:00 | 08 February 2021 11:00 | 1 | 3626 | 3h | 02.23.BP.01.01.38 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3628 |  | Auto Scheduled | LifeCycle Tasks | 165.38 days | 21 July 2020 8:00 | 10 February 2021 17:00 | 1 |  | 40h | 02.23.BP.01.02 |  | מאיה | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3629 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 10 February 2021 8:00 | 10 February 2021 17:00 | 1 | 3627 | 0h | 02.23.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3630 |  | Auto Scheduled | טרם החל | 0.63 days | 21 July 2020 8:00 | 21 July 2020 13:00 | 1 |  | 5h | 02.23.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3631 |  | Auto Scheduled | בעבודה | 1.25 days | 28 July 2020 8:00 | 29 July 2020 9:00 | 1 | 3630 | 10h | 02.23.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3632 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 11 August 2020 8:00 | 11 August 2020 13:00 | 1 | 3631 | 5h | 02.23.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3633 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 18 August 2020 8:00 | 19 August 2020 9:00 | 1 | 3632 | 10h | 02.23.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3634 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 01 September 2020 8:00 | 02 September 2020 9:00 | 1 | 3633 | 10h | 02.23.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3635 |  | Auto Scheduled | בחתימה | 0 days | 10 February 2021 8:00 | 10 February 2021 8:00 | 1 | 3634,3629 | 0h | 02.23.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3636 |  | Auto Scheduled | חתום | 0 days | 10 February 2021 8:00 | 10 February 2021 8:00 | 1 | 3635 | 0h | 02.23.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3637 |  | Auto Scheduled | 02.23: MRP.SAP | 243.5 days | 10 February 2021 8:00 | 18 January 2022 13:00 | 5.9999999999999998E-2 |  | 210h | 02.23.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3638 |  | Auto Scheduled | נדרש לבצע במערכת הסאפ שינויים בהתאם לשינוי במבנה הארגוני גורם מנפק\מקבל. | 201.88 days | 10 February 2021 8:00 | 28 November 2021 13:00 | 5.0000000000000003E-2 |  | 70h | 02.23.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3639 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.23.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3640 |  | Auto Scheduled | LifeCycle Tasks | 201.88 days | 10 February 2021 8:00 | 28 November 2021 13:00 | 5.0000000000000003E-2 |  | 70h | 02.23.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3641 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.23.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3642 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 February 2021 8:00 | 14 February 2021 10:00 | 1 | 3627 | 20h | 02.23.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3643 |  | Auto Scheduled | יישום ופיתוח סאפ | 81 days | 26 July 2021 8:00 | 18 November 2021 17:00 | 0.02 |  | 0h | 02.23.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3644 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 November 2021 8:00 | 23 November 2021 15:00 | 0 | 3643 | 25h | 02.23.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3645 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 23 November 2021 15:00 | 24 November 2021 16:00 | 0 | 3644 | 10h | 02.23.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3646 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 24 November 2021 16:00 | 25 November 2021 17:00 | 0 | 3645 | 10h | 02.23.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3647 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 November 2021 8:00 | 28 November 2021 13:00 | 0 | 3646 | 5h | 02.23.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3648 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 November 2021 13:00 | 28 November 2021 13:00 | 0 | 3647,3641 | 0h | 02.23.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3649 |  | Auto Scheduled | מערכת הסאפ תתמוך ביצירת המלצות לייצור כנגזרת מריצות אמ אר פי. | 208.63 days | 10 February 2021 8:00 | 06 December 2021 13:00 | 0.14999999999999999 |  | 70h | 02.23.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3650 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.23.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3651 |  | Auto Scheduled | LifeCycle Tasks | 208.63 days | 10 February 2021 8:00 | 06 December 2021 13:00 | 0.14999999999999999 |  | 70h | 02.23.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3652 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.23.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3653 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 February 2021 8:00 | 14 February 2021 10:00 | 1 | 3627 | 20h | 02.23.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3654 |  | Auto Scheduled | יישום ופיתוח סאפ | 7.88 days | 18 November 2021 8:00 | 28 November 2021 17:00 | 0 |  | 0h | 02.23.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3655 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 29 November 2021 8:00 | 01 December 2021 15:00 | 0 | 3654 | 25h | 02.23.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3656 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 01 December 2021 15:00 | 02 December 2021 16:00 | 0 | 3655 | 10h | 02.23.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3657 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 02 December 2021 16:00 | 05 December 2021 17:00 | 0 | 3656 | 10h | 02.23.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3658 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 06 December 2021 8:00 | 06 December 2021 13:00 | 0 | 3657 | 5h | 02.23.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3659 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 06 December 2021 13:00 | 06 December 2021 13:00 | 0 | 3658,3652 | 0h | 02.23.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3660 |  | Auto Scheduled | מערכת הסאפ תתמוך בהקמת אזורי אמ אר פי חדשים | 243.5 days | 10 February 2021 8:00 | 18 January 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 02.23.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3661 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.23.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3662 |  | Auto Scheduled | LifeCycle Tasks | 243.5 days | 10 February 2021 8:00 | 18 January 2022 13:00 | 5.9999999999999998E-2 |  | 70h | 02.23.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3663 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.23.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3664 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 10 February 2021 8:00 | 14 February 2021 10:00 | 1 | 3627 | 20h | 02.23.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3665 |  | Auto Scheduled | יישום ופיתוח סאפ | 36 days | 28 November 2021 8:00 | 10 January 2022 17:00 | 0 |  | 0h | 02.23.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3666 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 January 2022 8:00 | 13 January 2022 15:00 | 0 | 3665 | 25h | 02.23.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3667 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 January 2022 15:00 | 16 January 2022 16:00 | 0 | 3666 | 10h | 02.23.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3668 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 January 2022 16:00 | 17 January 2022 17:00 | 0 | 3667 | 10h | 02.23.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3669 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 January 2022 8:00 | 18 January 2022 13:00 | 0 | 3668 | 5h | 02.23.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3670 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 18 January 2022 13:00 | 18 January 2022 13:00 | 0 | 3669,3663 | 0h | 02.23.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3671 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין | 443.75 days | 19 July 2020 8:00 | 01 March 2022 13:00 | 0.39000000000000001 |  | 484h | 02.24 | חתום | פריאל ישי | hd | פריאל | nan | BP | NA | As Soon As Possible | 3
3672 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.BP | 156.38 days | 19 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 134h | 02.24.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3673 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין | 156.38 days | 19 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 134h | 02.24.BP.01 | חתום | פריאל ישי | parent | פריאל | nan | BP | NA | As Soon As Possible | 5
3674 |  | Auto Scheduled | Sub Tasks | 136.38 days | 10 August 2020 8:00 | 26 January 2021 10:00 | 1 |  | 94h | 02.24.BP.01.01 |  | פריאל ישי | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3675 |  | Auto Scheduled | 3. יש לקבוע את החוקות על פיהם נאחד/נפצל אספקות ע"פ נהלים/פקודות/או"ש. באחריות אמלח למול משתמשים | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.24.BP.01.01.12 | בוצע | פריאל | MoM | פריאל | מאיה | BP | NA | Must Start On | 7
3676 |  | Auto Scheduled | 4. יש לקבוע את החוקות על פיהם יקבע וקטור הניפוק ע"פ נהלים/פקודות/או"ש. באחריות אמלח למול משתמשים | 0.13 days | 10 August 2020 8:00 | 10 August 2020 9:00 | 1 |  | 1h | 02.24.BP.01.01.13 | בוצע | פריאל | MoM | פריאל | מאיה | BP | NA | As Soon As Possible | 7
3677 |  | Auto Scheduled | כתיבת מסמך | 2.88 days | 04 October 2020 8:00 | 06 October 2020 13:00 | 1 |  | 23h | 02.24.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3678 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 2.63 days | 03 November 2020 8:00 | 05 November 2020 11:00 | 1 | 3677 | 21h | 02.24.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3679 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 01 December 2020 8:00 | 01 December 2020 12:00 | 1 | 3678 | 4h | 02.24.BP.01.01.32 | בוצע | סיגל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3680 |  | Auto Scheduled | אישור מקל"ר | 1.88 days | 06 December 2020 8:00 | 07 December 2020 14:00 | 1 | 3679 | 15h | 02.24.BP.01.01.33 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3681 |  | Auto Scheduled | אישור אבי | 1 day | 24 December 2020 8:00 | 24 December 2020 16:00 | 1 | 3680 | 8h | 02.24.BP.01.01.34 | בוצע | אבי | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3682 |  | Auto Scheduled | אישור מפקדת | 1.88 days | 04 January 2021 8:00 | 05 January 2021 14:00 | 1 | 3681 | 15h | 02.24.BP.01.01.35 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3683 |  | Auto Scheduled | אישור ניר בשן | 0.38 days | 24 January 2021 8:00 | 24 January 2021 11:00 | 1 | 3682 | 3h | 02.24.BP.01.01.36 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3684 |  | Auto Scheduled | אישור חטלו"ג | 0.13 days | 26 January 2021 8:00 | 26 January 2021 9:00 | 1 | 3683 | 1h | 02.24.BP.01.01.37 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3685 |  | Auto Scheduled | אישור שגיב שרביט | 0.25 days | 26 January 2021 8:00 | 26 January 2021 10:00 | 1 | 3684 | 2h | 02.24.BP.01.01.38 | בוצע | פריאל | MoM | פריאל | nan | BP | NA | As Soon As Possible | 7
3686 |  | Auto Scheduled | LifeCycle Tasks | 156.38 days | 19 July 2020 8:00 | 27 January 2021 17:00 | 1 |  | 40h | 02.24.BP.01.02 |  | פריאל ישי | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3687 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 27 January 2021 8:00 | 27 January 2021 17:00 | 1 | 3685 | 0h | 02.24.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3688 |  | Auto Scheduled | טרם החל | 0.63 days | 19 July 2020 8:00 | 19 July 2020 13:00 | 1 |  | 5h | 02.24.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3689 |  | Auto Scheduled | בעבודה | 1.25 days | 26 July 2020 8:00 | 27 July 2020 9:00 | 1 | 3688 | 10h | 02.24.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3690 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 8:00 | 09 August 2020 13:00 | 1 | 3689 | 5h | 02.24.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3691 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 16 August 2020 8:00 | 17 August 2020 9:00 | 1 | 3690 | 10h | 02.24.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3692 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 30 August 2020 8:00 | 31 August 2020 9:00 | 1 | 3691 | 10h | 02.24.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3693 |  | Auto Scheduled | בחתימה | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 3692,3687 | 0h | 02.24.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3694 |  | Auto Scheduled | חתום | 0 days | 27 January 2021 8:00 | 27 January 2021 8:00 | 1 | 3693 | 0h | 02.24.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3695 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.INT | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 5.9999999999999998E-2 |  | 140h | 02.24.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3696 |  | Auto Scheduled | מערכת הזכיין תאפשר קבלת שדר עדכון לאספקה ממערכת הסאפ לטובת עדכון ביצוע תהליכים שהוגדרו לעיל. | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 02.24.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3697 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3698 |  | Auto Scheduled | LifeCycle Tasks | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 02.24.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3699 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3700 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3685 | 20h | 02.24.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3701 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 29.25 days | 17 January 2022 8:00 | 21 February 2022 17:00 | 0 |  | 0h | 02.24.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3702 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 February 2022 8:00 | 24 February 2022 15:00 | 0 | 3701 | 25h | 02.24.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3703 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 February 2022 15:00 | 27 February 2022 16:00 | 0 | 3702 | 10h | 02.24.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3704 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 February 2022 16:00 | 28 February 2022 17:00 | 0 | 3703 | 10h | 02.24.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3705 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 March 2022 8:00 | 01 March 2022 13:00 | 0 | 3704 | 5h | 02.24.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3706 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 01 March 2022 13:00 | 01 March 2022 13:00 | 0 | 3705,3699 | 0h | 02.24.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3707 |  | Auto Scheduled | מערכת הסאפ תאפשר שליחת אספקה ללא סימוכין למערכת הזכיין של הזכיין רק לאחר אישורה לא אוטומטי. | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.24.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3708 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3709 |  | Auto Scheduled | LifeCycle Tasks | 288.5 days | 27 January 2021 8:00 | 01 March 2022 13:00 | 5.0000000000000003E-2 |  | 70h | 02.24.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3710 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3711 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3685 | 20h | 02.24.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3712 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 41.63 days | 02 January 2022 8:00 | 21 February 2022 17:00 | 0 |  | 0h | 02.24.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3713 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 22 February 2022 8:00 | 24 February 2022 15:00 | 0 | 3712 | 25h | 02.24.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3714 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 February 2022 15:00 | 27 February 2022 16:00 | 0 | 3713 | 10h | 02.24.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3715 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 27 February 2022 16:00 | 28 February 2022 17:00 | 0 | 3714 | 10h | 02.24.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3716 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 01 March 2022 8:00 | 01 March 2022 13:00 | 0 | 3715 | 5h | 02.24.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3717 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 01 March 2022 13:00 | 01 March 2022 13:00 | 0 | 3716,3710 | 0h | 02.24.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3718 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.SAP | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.68999999999999995 |  | 210h | 02.24.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3719 |  | Auto Scheduled | מערכת הסאפ תאפשר לעלות לאישור אספקות עם סיבה הדורשת אישור על פי הטבלה לעיל. יוגדר בטבלת בי אר אף | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.78000000000000003 |  | 70h | 02.24.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3720 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3721 |  | Auto Scheduled | LifeCycle Tasks | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.78000000000000003 |  | 70h | 02.24.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3722 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3723 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3685 | 20h | 02.24.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3724 |  | Auto Scheduled | יישום ופיתוח סאפ | 20.25 days | 11 May 2021 8:00 | 15 June 2021 17:00 | 1 |  | 0h | 02.24.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3725 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 June 2021 8:00 | 20 June 2021 15:00 | 0 | 3724 | 25h | 02.24.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3726 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 20 June 2021 15:00 | 21 June 2021 16:00 | 0 | 3725 | 10h | 02.24.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3727 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 June 2021 16:00 | 22 June 2021 17:00 | 0 | 3726 | 10h | 02.24.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3728 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 June 2021 8:00 | 23 June 2021 13:00 | 0 | 3727 | 5h | 02.24.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3729 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3728,3722 | 0h | 02.24.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3730 |  | Auto Scheduled | מערכת הסאפ תאפשר ליצור אספקה ללא סימוכין עם סיבה רלוונטית ושדה "אישור שליחת אספקה" . | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.62 |  | 70h | 02.24.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3731 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3732 |  | Auto Scheduled | LifeCycle Tasks | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.62 |  | 70h | 02.24.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3733 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3734 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3685 | 20h | 02.24.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3735 |  | Auto Scheduled | יישום ופיתוח סאפ | 7.88 days | 02 May 2021 8:00 | 10 May 2021 17:00 | 1 |  | 0h | 02.24.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3736 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 May 2021 8:00 | 13 May 2021 15:00 | 0 | 3735 | 25h | 02.24.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3737 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 May 2021 15:00 | 18 May 2021 16:00 | 0 | 3736 | 10h | 02.24.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3738 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 18 May 2021 16:00 | 19 May 2021 17:00 | 0 | 3737 | 10h | 02.24.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3739 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 May 2021 8:00 | 30 May 2021 13:00 | 0 | 3738 | 5h | 02.24.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3740 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3739,3733 | 0h | 02.24.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3741 |  | Auto Scheduled | מערכת הסאפ תאפשר צפייה בדוח אספקות ללא סימוכין בסטאטוס טרם אושר במסך זי די אי איי אן או מסך שיוחלט בשלב הריל אמת ושינוי סטאטוס באספקה ל "אושר" | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.59999999999999998 |  | 70h | 02.24.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3742 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3743 |  | Auto Scheduled | LifeCycle Tasks | 158.5 days | 27 January 2021 8:00 | 05 September 2021 8:00 | 0.59999999999999998 |  | 70h | 02.24.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3744 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 02.24.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3745 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 27 January 2021 8:00 | 31 January 2021 10:00 | 1 | 3685 | 20h | 02.24.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3746 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 15 June 2021 8:00 | 22 June 2021 17:00 | 1 |  | 0h | 02.24.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3747 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 23 June 2021 8:00 | 27 June 2021 15:00 | 0 | 3746 | 25h | 02.24.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3748 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 27 June 2021 15:00 | 28 June 2021 16:00 | 0 | 3747 | 10h | 02.24.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3749 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 28 June 2021 16:00 | 29 June 2021 17:00 | 0 | 3748 | 10h | 02.24.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3750 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 30 June 2021 8:00 | 30 June 2021 13:00 | 0 | 3749 | 5h | 02.24.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3751 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3750,3744 | 0h | 02.24.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3752 |  | Auto Scheduled | 03: אחזקה | 609.13 days | 08 December 2019 8:00 | 10 February 2022 13:00 | 0.17000000000000001 |  | 890h | 03 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
3753 |  | Auto Scheduled | 03.01: שכר עידוד | 493.75 days | 08 December 2019 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 03.01 | בעבודה | איהאב | hd | איהאב | nan | BP | NA | As Soon As Possible | 3
3754 |  | Auto Scheduled | 03.01: שכר עידוד.BP | 493.75 days | 08 December 2019 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 03.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3755 |  | Auto Scheduled | 03.01: שכר עידוד | 493.75 days | 08 December 2019 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 03.01.BP.01 | בעבודה | איהאב | parent | איהאב | nan | BP | NA | As Soon As Possible | 5
3756 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.01.BP.01.01 |  | איהאב | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3757 |  | Auto Scheduled | LifeCycle Tasks | 493.75 days | 08 December 2019 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 03.01.BP.01.02 |  | איהאב | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3758 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3759 |  | Auto Scheduled | טרם החל | 0.63 days | 08 December 2019 8:00 | 08 December 2019 13:00 | 1 |  | 5h | 03.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3760 |  | Auto Scheduled | בעבודה | 1.25 days | 08 December 2019 13:00 | 09 December 2019 14:00 | 0 | 3759 | 10h | 03.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3761 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 December 2019 14:00 | 10 December 2019 10:00 | 0 | 3760 | 5h | 03.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3762 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 December 2019 10:00 | 11 December 2019 11:00 | 0 | 3761 | 10h | 03.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3763 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 December 2019 11:00 | 12 December 2019 12:00 | 0 | 3762 | 10h | 03.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3764 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3763,3758 | 0h | 03.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3765 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3764 | 0h | 03.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3766 |  | Auto Scheduled | 03.02: בחינה קבלה מרכש | 176.13 days | 01 June 2021 8:00 | 23 January 2022 13:00 | 0.16 |  | 460h | 03.02 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
3767 |  | Auto Scheduled | 03.02: בחינה קבלה מרכש.BP | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 03.02.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3768 |  | Auto Scheduled | 03.02: בחינה קבלה מרכש | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 03.02.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
3769 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3770 |  | Auto Scheduled | LifeCycle Tasks | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 03.02.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3771 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3772 |  | Auto Scheduled | טרם החל | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 |  | 5h | 03.02.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3773 |  | Auto Scheduled | בעבודה | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 3772 | 10h | 03.02.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3774 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 | 3773 | 5h | 03.02.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3775 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 3774 | 10h | 03.02.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3776 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 3775 | 10h | 03.02.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3777 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 3776,3771 | 0h | 03.02.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3778 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 3777 | 0h | 03.02.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3779 |  | Auto Scheduled | 03.02: בחינה קבלה מרכש.INT | 99.63 days | 05 September 2021 8:00 | 23 January 2022 13:00 | 0.14999999999999999 |  | 140h | 03.02.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3780 |  | Auto Scheduled | מערכת סאפ תעביר למערכת זכיין את נתוני הבחינה | 95.13 days | 05 September 2021 8:00 | 17 January 2022 13:00 | 0.16 |  | 70h | 03.02.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3781 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3782 |  | Auto Scheduled | LifeCycle Tasks | 95.13 days | 05 September 2021 8:00 | 17 January 2022 13:00 | 0.16 |  | 70h | 03.02.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3783 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3784 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.02.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3785 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 6.75 days | 02 January 2022 8:00 | 09 January 2022 17:00 | 0 |  | 0h | 03.02.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3786 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 January 2022 8:00 | 12 January 2022 15:00 | 0 | 3785 | 25h | 03.02.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3787 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 12 January 2022 15:00 | 13 January 2022 16:00 | 0 | 3786 | 10h | 03.02.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3788 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 January 2022 16:00 | 16 January 2022 17:00 | 0 | 3787 | 10h | 03.02.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3789 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 January 2022 8:00 | 17 January 2022 13:00 | 0 | 3788 | 5h | 03.02.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3790 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 17 January 2022 13:00 | 17 January 2022 13:00 | 0 | 3789,3783 | 0h | 03.02.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3791 |  | Auto Scheduled | מערכת זכיין תעביר למערכת סאפ את סטאטוס המלאים שטרם עברו בחינה לאחר קבלה, מלאים שאוחסנו למרות שלא עברו בחינה זו | 99.63 days | 05 September 2021 8:00 | 23 January 2022 13:00 | 0.13 |  | 70h | 03.02.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3792 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3793 |  | Auto Scheduled | LifeCycle Tasks | 99.63 days | 05 September 2021 8:00 | 23 January 2022 13:00 | 0.13 |  | 70h | 03.02.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3794 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3795 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.02.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3796 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 10.13 days | 03 January 2022 8:00 | 13 January 2022 17:00 | 0 |  | 0h | 03.02.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3797 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 January 2022 8:00 | 18 January 2022 15:00 | 0 | 3796 | 25h | 03.02.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3798 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 January 2022 15:00 | 19 January 2022 16:00 | 0 | 3797 | 10h | 03.02.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3799 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 19 January 2022 16:00 | 20 January 2022 17:00 | 0 | 3798 | 10h | 03.02.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3800 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 January 2022 8:00 | 23 January 2022 13:00 | 0 | 3799 | 5h | 03.02.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3801 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 23 January 2022 13:00 | 23 January 2022 13:00 | 0 | 3800,3794 | 0h | 03.02.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3802 |  | Auto Scheduled | 03.02: בחינה קבלה מרכש.SAP | 79 days | 01 June 2021 8:00 | 12 September 2021 10:00 | 0.12 |  | 280h | 03.02.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3803 |  | Auto Scheduled | מערכת סאפ נדרשת לתת מענה לדיווח תהליך הבחינות. | 79 days | 01 June 2021 8:00 | 12 September 2021 10:00 | 0.17000000000000001 |  | 70h | 03.02.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3804 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3805 |  | Auto Scheduled | LifeCycle Tasks | 79 days | 01 June 2021 8:00 | 12 September 2021 10:00 | 0.17000000000000001 |  | 70h | 03.02.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3806 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3807 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.02.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3808 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 01 June 2021 8:00 | 07 June 2021 17:00 | 0 |  | 0h | 03.02.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3809 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 08 June 2021 8:00 | 10 June 2021 15:00 | 0 | 3808 | 25h | 03.02.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3810 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 10 June 2021 15:00 | 13 June 2021 16:00 | 0 | 3809 | 10h | 03.02.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3811 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 13 June 2021 16:00 | 14 June 2021 17:00 | 0 | 3810 | 10h | 03.02.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3812 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 15 June 2021 8:00 | 15 June 2021 13:00 | 0 | 3811 | 5h | 03.02.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3813 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3812,3806 | 0h | 03.02.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3814 |  | Auto Scheduled | מערכת סאפ תאפשר לסמן מלאים שטרם עברו בחינה לאחר קבלה , מלאים שאוחסנו למרות שלא עברו בחינה זו | 77.88 days | 02 June 2021 8:00 | 12 September 2021 10:00 | 0.17000000000000001 |  | 70h | 03.02.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3815 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3816 |  | Auto Scheduled | LifeCycle Tasks | 77.88 days | 02 June 2021 8:00 | 12 September 2021 10:00 | 0.17000000000000001 |  | 70h | 03.02.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3817 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3818 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.02.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3819 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 02 June 2021 8:00 | 08 June 2021 17:00 | 0 |  | 0h | 03.02.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3820 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 June 2021 8:00 | 13 June 2021 15:00 | 0 | 3819 | 25h | 03.02.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3821 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 13 June 2021 15:00 | 14 June 2021 16:00 | 0 | 3820 | 10h | 03.02.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3822 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 14 June 2021 16:00 | 15 June 2021 17:00 | 0 | 3821 | 10h | 03.02.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3823 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 June 2021 8:00 | 16 June 2021 13:00 | 0 | 3822 | 5h | 03.02.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3824 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3823,3817 | 0h | 03.02.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3825 |  | Auto Scheduled | מערכת סאפ תאפשר לקבל החלטות שימוש מתאימות למלאי שטרם עבר בחינה לאחר קבלה | 76.75 days | 03 June 2021 8:00 | 12 September 2021 10:00 | 0.17000000000000001 |  | 70h | 03.02.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3826 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3827 |  | Auto Scheduled | LifeCycle Tasks | 76.75 days | 03 June 2021 8:00 | 12 September 2021 10:00 | 0.17000000000000001 |  | 70h | 03.02.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3828 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3829 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.02.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3830 |  | Auto Scheduled | יישום ופיתוח סאפ | 5.63 days | 03 June 2021 8:00 | 09 June 2021 17:00 | 0 |  | 0h | 03.02.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3831 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 10 June 2021 8:00 | 14 June 2021 15:00 | 0 | 3830 | 25h | 03.02.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3832 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 14 June 2021 15:00 | 15 June 2021 16:00 | 0 | 3831 | 10h | 03.02.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3833 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 15 June 2021 16:00 | 16 June 2021 17:00 | 0 | 3832 | 10h | 03.02.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3834 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 17 June 2021 8:00 | 17 June 2021 13:00 | 0 | 3833 | 5h | 03.02.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3835 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3834,3828 | 0h | 03.02.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3836 |  | Auto Scheduled | מערכת סאפ תאפשר באספקה נכנסת להציג אינ' לצורך לביצוע בחינה,סטאטוס הבחינה עבור פריט שתתקבל בממשק ממע' תב"ל או מע' חלופית שתפותח לצורך מתן מענה. | 41.88 days | 18 July 2021 8:00 | 12 September 2021 10:00 | 5.9999999999999998E-2 |  | 70h | 03.02.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3837 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3838 |  | Auto Scheduled | LifeCycle Tasks | 41.88 days | 18 July 2021 8:00 | 12 September 2021 10:00 | 5.9999999999999998E-2 |  | 70h | 03.02.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3839 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.02.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3840 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.02.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3841 |  | Auto Scheduled | יישום ופיתוח סאפ | 30.38 days | 18 July 2021 8:00 | 23 August 2021 17:00 | 0 |  | 0h | 03.02.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3842 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 August 2021 8:00 | 26 August 2021 15:00 | 0 | 3841 | 25h | 03.02.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3843 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 26 August 2021 15:00 | 29 August 2021 16:00 | 0 | 3842 | 10h | 03.02.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3844 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 August 2021 16:00 | 30 August 2021 17:00 | 0 | 3843 | 10h | 03.02.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3845 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 31 August 2021 8:00 | 31 August 2021 13:00 | 0 | 3844 | 5h | 03.02.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3846 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3845,3839 | 0h | 03.02.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3847 |  | Auto Scheduled | 03.03: אחזקה MasterData | 117.63 days | 01 September 2021 8:00 | 10 February 2022 13:00 | 0.17000000000000001 |  | 390h | 03.03 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
3848 |  | Auto Scheduled | 03.03: אחזקה MasterData.BP | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 03.03.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3849 |  | Auto Scheduled | 03.03: אחזקה MasterData | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 03.03.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
3850 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3851 |  | Auto Scheduled | LifeCycle Tasks | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 03.03.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3852 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3853 |  | Auto Scheduled | טרם החל | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 |  | 5h | 03.03.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3854 |  | Auto Scheduled | בעבודה | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 3853 | 10h | 03.03.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3855 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 | 3854 | 5h | 03.03.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3856 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 3855 | 10h | 03.03.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3857 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 3856 | 10h | 03.03.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3858 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 3857,3852 | 0h | 03.03.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3859 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 3858 | 0h | 03.03.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3860 |  | Auto Scheduled | 03.03: אחזקה MasterData.INT | 115.38 days | 05 September 2021 8:00 | 10 February 2022 13:00 | 0.12 |  | 280h | 03.03.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3861 |  | Auto Scheduled | מערכת סאפ תשלח חיווי האם האספקה עם הצ',מסדים שנוספו תקינים | 115.38 days | 05 September 2021 8:00 | 10 February 2022 13:00 | 0.10000000000000001 |  | 70h | 03.03.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3862 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3863 |  | Auto Scheduled | LifeCycle Tasks | 115.38 days | 05 September 2021 8:00 | 10 February 2022 13:00 | 0.10000000000000001 |  | 70h | 03.03.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3864 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3865 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.03.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3866 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 16 January 2022 8:00 | 02 February 2022 17:00 | 0 |  | 0h | 03.03.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3867 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 February 2022 8:00 | 07 February 2022 15:00 | 0 | 3866 | 25h | 03.03.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3868 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 February 2022 15:00 | 08 February 2022 16:00 | 0 | 3867 | 10h | 03.03.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3869 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 08 February 2022 16:00 | 09 February 2022 17:00 | 0 | 3868 | 10h | 03.03.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3870 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 February 2022 8:00 | 10 February 2022 13:00 | 0 | 3869 | 5h | 03.03.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3871 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 10 February 2022 13:00 | 10 February 2022 13:00 | 0 | 3870,3864 | 0h | 03.03.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3872 |  | Auto Scheduled | מערכות זכיין וסאפ יאפשרו העברת שדרים ע"ב אספקה נכנסת כולל הפרטים שיוזנו במערכת סאפ. | 94 days | 05 September 2021 8:00 | 16 January 2022 13:00 | 0.17000000000000001 |  | 70h | 03.03.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3873 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3874 |  | Auto Scheduled | LifeCycle Tasks | 94 days | 05 September 2021 8:00 | 16 January 2022 13:00 | 0.17000000000000001 |  | 70h | 03.03.INT.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3875 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.02.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3876 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.03.INT.02.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3877 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 5.63 days | 02 January 2022 8:00 | 06 January 2022 17:00 | 0 |  | 0h | 03.03.INT.02.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3878 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 09 January 2022 8:00 | 11 January 2022 15:00 | 0 | 3877 | 25h | 03.03.INT.02.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3879 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 11 January 2022 15:00 | 12 January 2022 16:00 | 0 | 3878 | 10h | 03.03.INT.02.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3880 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 January 2022 16:00 | 13 January 2022 17:00 | 0 | 3879 | 10h | 03.03.INT.02.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3881 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 16 January 2022 8:00 | 16 January 2022 13:00 | 0 | 3880 | 5h | 03.03.INT.02.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3882 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 16 January 2022 13:00 | 16 January 2022 13:00 | 0 | 3881,3875 | 0h | 03.03.INT.02.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3883 |  | Auto Scheduled | מערכות זכיין וסאפ יאפשרו העברת שדרים לקליטת צ',מס"דים לאחר שינוי הסטאטוס מבירור כך שהמלאי בסאפ יעודכן. | 104.13 days | 05 September 2021 8:00 | 27 January 2022 13:00 | 0.10000000000000001 |  | 70h | 03.03.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3884 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3885 |  | Auto Scheduled | LifeCycle Tasks | 104.13 days | 05 September 2021 8:00 | 27 January 2022 13:00 | 0.10000000000000001 |  | 70h | 03.03.INT.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3886 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.03.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3887 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.03.INT.03.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3888 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 15.75 days | 02 January 2022 8:00 | 19 January 2022 17:00 | 0 |  | 0h | 03.03.INT.03.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3889 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 January 2022 8:00 | 24 January 2022 15:00 | 0 | 3888 | 25h | 03.03.INT.03.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3890 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 24 January 2022 15:00 | 25 January 2022 16:00 | 0 | 3889 | 10h | 03.03.INT.03.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3891 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 25 January 2022 16:00 | 26 January 2022 17:00 | 0 | 3890 | 10h | 03.03.INT.03.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3892 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 January 2022 8:00 | 27 January 2022 13:00 | 0 | 3891 | 5h | 03.03.INT.03.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3893 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 27 January 2022 13:00 | 27 January 2022 13:00 | 0 | 3892,3886 | 0h | 03.03.INT.03.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3894 |  | Auto Scheduled | מערכת זכיין תשלח שדר לעדכון אספקה נכנסת בסאפ | 108.63 days | 05 September 2021 8:00 | 02 February 2022 13:00 | 0.11 |  | 70h | 03.03.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3895 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3896 |  | Auto Scheduled | LifeCycle Tasks | 108.63 days | 05 September 2021 8:00 | 02 February 2022 13:00 | 0.11 |  | 70h | 03.03.INT.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3897 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.INT.04.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3898 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.03.INT.04.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3899 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 14.63 days | 09 January 2022 8:00 | 25 January 2022 17:00 | 0 |  | 0h | 03.03.INT.04.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
3900 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 26 January 2022 8:00 | 30 January 2022 15:00 | 0 | 3899 | 25h | 03.03.INT.04.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3901 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 30 January 2022 15:00 | 31 January 2022 16:00 | 0 | 3900 | 10h | 03.03.INT.04.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3902 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 31 January 2022 16:00 | 01 February 2022 17:00 | 0 | 3901 | 10h | 03.03.INT.04.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3903 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 February 2022 8:00 | 02 February 2022 13:00 | 0 | 3902 | 5h | 03.03.INT.04.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3904 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 02 February 2022 13:00 | 02 February 2022 13:00 | 0 | 3903,3897 | 0h | 03.03.INT.04.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3905 |  | Auto Scheduled | 03.03: אחזקה MasterData.SAP | 7.38 days | 01 September 2021 8:00 | 14 September 2021 13:00 | 0.25 |  | 70h | 03.03.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3906 |  | Auto Scheduled | מערכת סאפ תאפשר הזנת הצ' או מס"ד בשלב האספקה הנכנסת. | 7.38 days | 01 September 2021 8:00 | 14 September 2021 13:00 | 0.25 |  | 70h | 03.03.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3907 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3908 |  | Auto Scheduled | LifeCycle Tasks | 7.38 days | 01 September 2021 8:00 | 14 September 2021 13:00 | 0.25 |  | 70h | 03.03.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3909 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 03.03.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3910 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 03.03.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3911 |  | Auto Scheduled | יישום ופיתוח סאפ | 1.13 days | 01 September 2021 8:00 | 01 September 2021 17:00 | 0 |  | 0h | 03.03.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3912 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 02 September 2021 8:00 | 09 September 2021 15:00 | 0 | 3911 | 25h | 03.03.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3913 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 September 2021 15:00 | 12 September 2021 16:00 | 0 | 3912 | 10h | 03.03.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3914 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 12 September 2021 16:00 | 13 September 2021 17:00 | 0 | 3913 | 10h | 03.03.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3915 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 14 September 2021 8:00 | 14 September 2021 13:00 | 0 | 3914 | 5h | 03.03.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3916 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 14 September 2021 13:00 | 14 September 2021 13:00 | 0 | 3915,3909 | 0h | 03.03.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3917 |  | Auto Scheduled | 04: תקציב ורכש | 374 days | 16 July 2020 8:00 | 02 December 2021 13:00 | 0.37 |  | 1,310h | 04 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
3918 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש | 367.25 days | 16 July 2020 8:00 | 24 November 2021 13:00 | 0.39000000000000001 |  | 670h | 04.01 | חתום |  | hd | תהילה | nan | BP | NA | As Soon As Possible | 3
3919 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש.BP | 275.5 days | 16 July 2020 8:00 | 15 July 2021 17:00 | 1 |  | 110h | 04.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3920 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש | 275.5 days | 16 July 2020 8:00 | 15 July 2021 17:00 | 1 |  | 110h | 04.01.BP.01 | חתום |  | parent | תהילה | nan | BP | NA | As Soon As Possible | 5
3921 |  | Auto Scheduled | Sub Tasks | 43.13 days | 18 April 2021 8:00 | 21 June 2021 11:00 | 1 |  | 70h | 04.01.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3922 |  | Auto Scheduled | כתיבת מסמך | 2.5 days | 18 April 2021 8:00 | 20 April 2021 10:00 | 1 |  | 20h | 04.01.BP.01.01.20 | בוצע |  | MoM |  | nan | BP | NA | Must Start On | 7
3923 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.38 days | 15 May 2021 8:00 | 18 May 2021 11:00 | 1 | 3922 | 3h | 04.01.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3924 |  | Auto Scheduled | אישור אבי | 0.5 days | 18 May 2021 8:00 | 18 May 2021 12:00 | 1 | 3923 | 4h | 04.01.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3925 |  | Auto Scheduled | אישור המנהלת | 0.63 days | 23 May 2021 8:00 | 30 May 2021 13:00 | 1 | 3924 | 5h | 04.01.BP.01.01.23 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3926 |  | Auto Scheduled | אישור מקל"ר | 0.5 days | 28 May 2021 8:00 | 30 May 2021 12:00 | 1 | 3925 | 4h | 04.01.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3927 |  | Auto Scheduled | אישור מפקדת | 0.5 days | 02 June 2021 8:00 | 02 June 2021 12:00 | 1 | 3926 | 4h | 04.01.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3928 |  | Auto Scheduled | אישור חטלו"ג | 0.5 days | 07 June 2021 8:00 | 07 June 2021 12:00 | 1 | 3927 | 4h | 04.01.BP.01.01.26 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3929 |  | Auto Scheduled | אישור ניר בשן | 0.63 days | 12 June 2021 8:00 | 13 June 2021 13:00 | 1 | 3928 | 5h | 04.01.BP.01.01.27 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3930 |  | Auto Scheduled | אישור שגיב שרביט | 2.63 days | 17 June 2021 8:00 | 21 June 2021 11:00 | 1 | 3929 | 21h | 04.01.BP.01.01.28 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
3931 |  | Auto Scheduled | LifeCycle Tasks | 275.5 days | 16 July 2020 8:00 | 15 July 2021 17:00 | 1 |  | 40h | 04.01.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3932 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 15 July 2021 8:00 | 15 July 2021 17:00 | 1 | 3930 | 0h | 04.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3933 |  | Auto Scheduled | טרם החל | 0.63 days | 16 July 2020 8:00 | 16 July 2020 13:00 | 1 |  | 5h | 04.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3934 |  | Auto Scheduled | בעבודה | 1.25 days | 23 July 2020 8:00 | 26 July 2020 9:00 | 1 | 3933 | 10h | 04.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3935 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 | 3934 | 5h | 04.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3936 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 13 August 2020 8:00 | 16 August 2020 9:00 | 1 | 3935 | 10h | 04.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3937 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 3936 | 10h | 04.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3938 |  | Auto Scheduled | בחתימה | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 3937,3932 | 0h | 04.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3939 |  | Auto Scheduled | חתום | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 3938 | 0h | 04.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
3940 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש.INT | 92.88 days | 15 July 2021 8:00 | 24 November 2021 13:00 | 0.14999999999999999 |  | 70h | 04.01.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3941 |  | Auto Scheduled | שינויים בממשקי דרישות והזמנות בהתאם לטבלת קשר בין גוף דורש לארגון רכש אתר וקבוצת רכש | 92.88 days | 15 July 2021 8:00 | 24 November 2021 13:00 | 0.14999999999999999 |  | 70h | 04.01.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
3942 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3943 |  | Auto Scheduled | LifeCycle Tasks | 92.88 days | 15 July 2021 8:00 | 24 November 2021 13:00 | 0.14999999999999999 |  | 70h | 04.01.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3944 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3945 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3946 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 14.63 days | 31 October 2021 8:00 | 16 November 2021 17:00 | 7.0000000000000007E-2 |  | 0h | 04.01.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | As Soon As Possible | 7
3947 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 17 November 2021 8:00 | 21 November 2021 15:00 | 0 | 3946 | 25h | 04.01.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3948 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 21 November 2021 15:00 | 22 November 2021 16:00 | 0 | 3947 | 10h | 04.01.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3949 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 22 November 2021 16:00 | 23 November 2021 17:00 | 0 | 3948 | 10h | 04.01.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3950 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 24 November 2021 8:00 | 24 November 2021 13:00 | 0 | 3949 | 5h | 04.01.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3951 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 24 November 2021 13:00 | 24 November 2021 13:00 | 0 | 3950,3944 | 0h | 04.01.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
3952 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש.SAP | 95.13 days | 30 June 2021 8:00 | 11 November 2021 13:00 | 0.38 |  | 490h | 04.01.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
3953 |  | Auto Scheduled | שיוך תקציב לחברה 9888-קודי חברה מסויימים משתנים לקוד חברה 9888 | 82.75 days | 15 July 2021 8:00 | 11 November 2021 13:00 | 8.0000000000000002E-2 |  | 70h | 04.01.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3954 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3955 |  | Auto Scheduled | LifeCycle Tasks | 82.75 days | 15 July 2021 8:00 | 11 November 2021 13:00 | 8.0000000000000002E-2 |  | 70h | 04.01.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3956 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3957 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3958 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 10 October 2021 8:00 | 03 November 2021 17:00 | 0 |  | 0h | 04.01.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
3959 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 04 November 2021 8:00 | 08 November 2021 15:00 | 0 | 3958 | 25h | 04.01.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3960 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 08 November 2021 15:00 | 09 November 2021 16:00 | 0 | 3959 | 10h | 04.01.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3961 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 09 November 2021 16:00 | 10 November 2021 17:00 | 0 | 3960 | 10h | 04.01.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3962 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 11 November 2021 8:00 | 11 November 2021 13:00 | 0 | 3961 | 5h | 04.01.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3963 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 11 November 2021 13:00 | 11 November 2021 13:00 | 0 | 3962,3956 | 0h | 04.01.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3964 |  | Auto Scheduled | מבנה ארגוני -הקמת ארגוני רכש בהתאם למבנה המפורט | 52.88 days | 30 June 2021 8:00 | 05 September 2021 8:00 | 0.84999999999999998 |  | 70h | 04.01.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3965 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3966 |  | Auto Scheduled | LifeCycle Tasks | 52.88 days | 30 June 2021 8:00 | 05 September 2021 8:00 | 0.84999999999999998 |  | 70h | 04.01.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3967 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3968 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3969 |  | Auto Scheduled | יישום ופיתוח סאפ | 33.75 days | 30 June 2021 8:00 | 10 August 2021 17:00 | 1 |  | 0h | 04.01.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3970 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 11 August 2021 8:00 | 15 August 2021 15:00 | 0 | 3969 | 25h | 04.01.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3971 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 15 August 2021 15:00 | 16 August 2021 16:00 | 0 | 3970 | 10h | 04.01.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3972 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 16 August 2021 16:00 | 17 August 2021 17:00 | 0 | 3971 | 10h | 04.01.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3973 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 18 August 2021 8:00 | 18 August 2021 13:00 | 0 | 3972 | 5h | 04.01.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3974 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3973,3967 | 0h | 04.01.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3975 |  | Auto Scheduled | מבנה ארגוני - שיוך אתרים לארגוני רכש חדשים | 52.88 days | 30 June 2021 8:00 | 05 September 2021 8:00 | 0.79000000000000004 |  | 70h | 04.01.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3976 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3977 |  | Auto Scheduled | LifeCycle Tasks | 52.88 days | 30 June 2021 8:00 | 05 September 2021 8:00 | 0.79000000000000004 |  | 70h | 04.01.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3978 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3979 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3980 |  | Auto Scheduled | יישום ופיתוח סאפ | 21.38 days | 30 June 2021 8:00 | 26 July 2021 17:00 | 1 |  | 0h | 04.01.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3981 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 27 July 2021 8:00 | 29 July 2021 15:00 | 0 | 3980 | 25h | 04.01.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3982 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 July 2021 15:00 | 01 August 2021 16:00 | 0 | 3981 | 10h | 04.01.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3983 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 August 2021 16:00 | 02 August 2021 17:00 | 0 | 3982 | 10h | 04.01.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3984 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 August 2021 8:00 | 03 August 2021 13:00 | 0 | 3983 | 5h | 04.01.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3985 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 3984,3978 | 0h | 04.01.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3986 |  | Auto Scheduled | הרחבת הטבלה הקיימת, הקמת טבלה חדשה- טבלה שתקשר בין גוף דורש ל ארגון רכש, אתר וקבוצת רכש | 55.75 days | 08 July 2021 8:00 | 03 October 2021 13:00 | 0.20000000000000001 |  | 70h | 04.01.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3987 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3988 |  | Auto Scheduled | LifeCycle Tasks | 55.75 days | 08 July 2021 8:00 | 03 October 2021 13:00 | 0.20000000000000001 |  | 70h | 04.01.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
3989 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3990 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3991 |  | Auto Scheduled | יישום ופיתוח סאפ | 49.5 days | 08 July 2021 8:00 | 12 September 2021 17:00 | 0.17999999999999999 |  | 0h | 04.01.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
3992 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 13 September 2021 8:00 | 19 September 2021 15:00 | 0 | 3991 | 25h | 04.01.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3993 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 19 September 2021 15:00 | 29 September 2021 16:00 | 0 | 3992 | 10h | 04.01.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3994 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 29 September 2021 16:00 | 30 September 2021 17:00 | 0 | 3993 | 10h | 04.01.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3995 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 October 2021 8:00 | 03 October 2021 13:00 | 0 | 3994 | 5h | 04.01.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3996 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 October 2021 13:00 | 03 October 2021 13:00 | 0 | 3995,3989 | 0h | 04.01.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
3997 |  | Auto Scheduled | הזמנות רכש - הסבת הזמנות , הסכמים של מרה"ס דרום חסימת הקמת דרישות , הזמנות למבנה אירגוני ישן . שמירת קשר בין הזמנת מקור מנה"ר והזמנת צפי פנימי 92זי הייצ'. | 52.38 days | 15 July 2021 8:00 | 05 October 2021 13:00 | 0.16 |  | 70h | 04.01.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
3998 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
3999 |  | Auto Scheduled | LifeCycle Tasks | 52.38 days | 15 July 2021 8:00 | 05 October 2021 13:00 | 0.16 |  | 70h | 04.01.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4000 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4001 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4002 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 02 September 2021 8:00 | 14 September 2021 17:00 | 0 |  | 0h | 04.01.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
4003 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 19 September 2021 8:00 | 30 September 2021 15:00 | 0 | 4002 | 25h | 04.01.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4004 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 30 September 2021 15:00 | 03 October 2021 16:00 | 0 | 4003 | 10h | 04.01.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4005 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 03 October 2021 16:00 | 04 October 2021 17:00 | 0 | 4004 | 10h | 04.01.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4006 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 05 October 2021 8:00 | 05 October 2021 13:00 | 0 | 4005 | 5h | 04.01.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4007 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 October 2021 13:00 | 05 October 2021 13:00 | 0 | 4006,4000 | 0h | 04.01.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4008 |  | Auto Scheduled | הזמנות רכש - הזמנות בשלב הביניים ותאריך קבלה צפוי אחרי מבצוע -– יצירת בדיקה ושינוי מבנה ארגוני למבנה חדש | 55.75 days | 15 July 2021 8:00 | 10 October 2021 13:00 | 0.38 |  | 70h | 04.01.SAP.06 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4009 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.06.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4010 |  | Auto Scheduled | LifeCycle Tasks | 55.75 days | 15 July 2021 8:00 | 10 October 2021 13:00 | 0.38 |  | 70h | 04.01.SAP.06.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4011 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.06.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4012 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.06.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4013 |  | Auto Scheduled | יישום ופיתוח סאפ | 34.88 days | 03 August 2021 8:00 | 30 September 2021 17:00 | 0.40000000000000002 |  | 0h | 04.01.SAP.06.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
4014 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 03 October 2021 8:00 | 05 October 2021 15:00 | 0 | 4013 | 25h | 04.01.SAP.06.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4015 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 05 October 2021 15:00 | 06 October 2021 16:00 | 0 | 4014 | 10h | 04.01.SAP.06.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4016 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 06 October 2021 16:00 | 07 October 2021 17:00 | 0 | 4015 | 10h | 04.01.SAP.06.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4017 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 10 October 2021 8:00 | 10 October 2021 13:00 | 0 | 4016 | 5h | 04.01.SAP.06.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4018 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 10 October 2021 13:00 | 10 October 2021 13:00 | 0 | 4017,4011 | 0h | 04.01.SAP.06.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4019 |  | Auto Scheduled | שיוך תקציב לחברה 9888-קודי חברה מסויימים משתנים לקוד חברה 9888 - שיוך כלל מרכזי הקרנות של המרכזים לקוד חברה 9888. הסבות | 76 days | 15 July 2021 8:00 | 03 November 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 04.01.SAP.07 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4020 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.07.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4021 |  | Auto Scheduled | LifeCycle Tasks | 76 days | 15 July 2021 8:00 | 03 November 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 04.01.SAP.07.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4022 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.01.SAP.07.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4023 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 3930 | 20h | 04.01.SAP.07.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4024 |  | Auto Scheduled | יישום ופיתוח סאפ | 24.75 days | 14 September 2021 8:00 | 26 October 2021 17:00 | 0 |  | 0h | 04.01.SAP.07.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
4025 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 27 October 2021 8:00 | 31 October 2021 15:00 | 0 | 4024 | 25h | 04.01.SAP.07.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4026 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 31 October 2021 15:00 | 01 November 2021 16:00 | 0 | 4025 | 10h | 04.01.SAP.07.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4027 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 November 2021 16:00 | 02 November 2021 17:00 | 0 | 4026 | 10h | 04.01.SAP.07.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4028 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 November 2021 8:00 | 03 November 2021 13:00 | 0 | 4027 | 5h | 04.01.SAP.07.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4029 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 03 November 2021 13:00 | 03 November 2021 13:00 | 0 | 4028,4022 | 0h | 04.01.SAP.07.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4030 |  | Auto Scheduled | 04.02: סבב אישורים | 363.88 days | 16 July 2020 8:00 | 21 November 2021 13:00 | 0.47999999999999998 |  | 210h | 04.02 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4031 |  | Auto Scheduled | 04.02: סבב אישורים.BP | 314.88 days | 16 July 2020 8:00 | 05 September 2021 8:00 | 0.13 |  | 70h | 04.02.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4032 |  | Auto Scheduled | 04.02: סבב אישורים | 314.88 days | 16 July 2020 8:00 | 05 September 2021 8:00 | 0.13 |  | 70h | 04.02.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4033 |  | Auto Scheduled | Sub Tasks | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 04.02.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4034 |  | Auto Scheduled | כתיבת מסמך | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 04.02.BP.01.01.20 | טרם החל |  | MoM |  | nan | BP | NA | Must Start On | 7
4035 |  | Auto Scheduled | LifeCycle Tasks | 314.88 days | 16 July 2020 8:00 | 05 September 2021 8:00 | 0.98999999999999999 |  | 40h | 04.02.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4036 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4034 | 0h | 04.02.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4037 |  | Auto Scheduled | טרם החל | 0.63 days | 16 July 2020 8:00 | 16 July 2020 13:00 | 1 |  | 5h | 04.02.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4038 |  | Auto Scheduled | בעבודה | 1.25 days | 23 July 2020 8:00 | 26 July 2020 9:00 | 1 | 4037 | 10h | 04.02.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4039 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 | 4038 | 5h | 04.02.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4040 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 13 August 2020 8:00 | 16 August 2020 9:00 | 1 | 4039 | 10h | 04.02.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4041 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 27 August 2020 8:00 | 30 August 2020 9:00 | 1 | 4040 | 10h | 04.02.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4042 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4041,4036 | 0h | 04.02.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4043 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4042 | 0h | 04.02.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4044 |  | Auto Scheduled | 04.02: סבב אישורים.SAP | 100.75 days | 01 July 2021 8:00 | 21 November 2021 13:00 | 0.68999999999999995 |  | 140h | 04.02.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4045 |  | Auto Scheduled | סבב אישורים | 49 days | 05 September 2021 8:00 | 21 November 2021 13:00 | 0.5 |  | 70h | 04.02.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4046 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.02.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4047 |  | Auto Scheduled | LifeCycle Tasks | 49 days | 05 September 2021 8:00 | 21 November 2021 13:00 | 0.5 |  | 70h | 04.02.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4048 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.02.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4049 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.02.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4050 |  | Auto Scheduled | יישום ופיתוח סאפ | 16.88 days | 24 October 2021 8:00 | 11 November 2021 17:00 | 0.60999999999999999 |  | 0h | 04.02.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
4051 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 November 2021 8:00 | 16 November 2021 15:00 | 0 | 4050 | 25h | 04.02.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4052 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 16 November 2021 15:00 | 17 November 2021 16:00 | 0 | 4051 | 10h | 04.02.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4053 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 November 2021 16:00 | 18 November 2021 17:00 | 0 | 4052 | 10h | 04.02.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4054 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 21 November 2021 8:00 | 21 November 2021 13:00 | 0 | 4053 | 5h | 04.02.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4055 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 21 November 2021 13:00 | 21 November 2021 13:00 | 0 | 4054,4048 | 0h | 04.02.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4056 |  | Auto Scheduled | מבנה ארגוני | 54.25 days | 01 July 2021 8:00 | 12 September 2021 10:00 | 0.82999999999999996 |  | 70h | 04.02.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4057 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.02.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4058 |  | Auto Scheduled | LifeCycle Tasks | 54.25 days | 01 July 2021 8:00 | 12 September 2021 10:00 | 0.82999999999999996 |  | 70h | 04.02.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4059 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.02.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4060 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.02.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4061 |  | Auto Scheduled | יישום ופיתוח סאפ | 28.13 days | 01 July 2021 8:00 | 04 August 2021 17:00 | 1 |  | 0h | 04.02.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
4062 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 August 2021 8:00 | 09 August 2021 15:00 | 0 | 4061 | 25h | 04.02.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4063 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 09 August 2021 15:00 | 10 August 2021 16:00 | 0 | 4062 | 10h | 04.02.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4064 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 August 2021 16:00 | 11 August 2021 17:00 | 0 | 4063 | 10h | 04.02.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4065 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 August 2021 8:00 | 12 August 2021 13:00 | 0 | 4064 | 5h | 04.02.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4066 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 4065,4059 | 0h | 04.02.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4067 |  | Auto Scheduled | 04.03: הזמנה פנימית | 67 days | 25 August 2021 8:00 | 02 December 2021 13:00 | 0.17999999999999999 |  | 390h | 04.03 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4068 |  | Auto Scheduled | 04.03: הזמנה פנימית.BP | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.03.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4069 |  | Auto Scheduled | 04.03: הזמנה פנימית | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.03.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4070 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4071 |  | Auto Scheduled | LifeCycle Tasks | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.03.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4072 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4073 |  | Auto Scheduled | טרם החל | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 |  | 5h | 04.03.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4074 |  | Auto Scheduled | בעבודה | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4073 | 10h | 04.03.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4075 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 | 4074 | 5h | 04.03.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4076 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4075 | 10h | 04.03.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4077 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4076 | 10h | 04.03.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4078 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4077,4072 | 0h | 04.03.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4079 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4078 | 0h | 04.03.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4080 |  | Auto Scheduled | 04.03: הזמנה פנימית.SAP | 67 days | 25 August 2021 8:00 | 02 December 2021 13:00 | 0.14000000000000001 |  | 350h | 04.03.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4081 |  | Auto Scheduled | הזמנה פנימית זי הייצ' 92 -הוספת שדה הזמנת מקור | 49 days | 05 September 2021 8:00 | 21 November 2021 13:00 | 0.27000000000000002 |  | 70h | 04.03.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4082 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4083 |  | Auto Scheduled | LifeCycle Tasks | 49 days | 05 September 2021 8:00 | 21 November 2021 13:00 | 0.27000000000000002 |  | 70h | 04.03.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4084 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4085 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.03.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4086 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 04 November 2021 8:00 | 11 November 2021 17:00 | 0.25 |  | 0h | 04.03.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
4087 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 November 2021 8:00 | 16 November 2021 15:00 | 0 | 4086 | 25h | 04.03.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4088 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 16 November 2021 15:00 | 17 November 2021 16:00 | 0 | 4087 | 10h | 04.03.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4089 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 November 2021 16:00 | 18 November 2021 17:00 | 0 | 4088 | 10h | 04.03.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4090 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 21 November 2021 8:00 | 21 November 2021 13:00 | 0 | 4089 | 5h | 04.03.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4091 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 21 November 2021 13:00 | 21 November 2021 13:00 | 0 | 4090,4084 | 0h | 04.03.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4092 |  | Auto Scheduled | הזמנה פנימית זי הייצ' 92 -בדיקה שהזמנת מקור קיימת במערכת | 51.25 days | 05 September 2021 8:00 | 23 November 2021 13:00 | 0.27000000000000002 |  | 70h | 04.03.SAP.02 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4093 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.02.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4094 |  | Auto Scheduled | LifeCycle Tasks | 51.25 days | 05 September 2021 8:00 | 23 November 2021 13:00 | 0.27000000000000002 |  | 70h | 04.03.SAP.02.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4095 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.02.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4096 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.03.SAP.02.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4097 |  | Auto Scheduled | יישום ופיתוח סאפ | 6.75 days | 08 November 2021 8:00 | 15 November 2021 17:00 | 0.25 |  | 0h | 04.03.SAP.02.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
4098 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 16 November 2021 8:00 | 18 November 2021 15:00 | 0 | 4097 | 25h | 04.03.SAP.02.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4099 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 18 November 2021 15:00 | 21 November 2021 16:00 | 0 | 4098 | 10h | 04.03.SAP.02.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4100 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 21 November 2021 16:00 | 22 November 2021 17:00 | 0 | 4099 | 10h | 04.03.SAP.02.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4101 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 23 November 2021 8:00 | 23 November 2021 13:00 | 0 | 4100 | 5h | 04.03.SAP.02.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4102 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 23 November 2021 13:00 | 23 November 2021 13:00 | 0 | 4101,4095 | 0h | 04.03.SAP.02.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4103 |  | Auto Scheduled | הזמנה פנימית זי הייצ' 92 -"אספקה הושלמה" בהזמנה פנימית - פיתוח תהליך סגירת שורה בהזמנת מקורמתוך מיגו או בעדכון ידני בזהמנה | 59.13 days | 05 September 2021 8:00 | 02 December 2021 13:00 | 0.11 |  | 70h | 04.03.SAP.03 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4104 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.03.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4105 |  | Auto Scheduled | LifeCycle Tasks | 59.13 days | 05 September 2021 8:00 | 02 December 2021 13:00 | 0.11 |  | 70h | 04.03.SAP.03.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4106 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.03.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4107 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.03.SAP.03.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4108 |  | Auto Scheduled | יישום ופיתוח סאפ | 13.5 days | 09 November 2021 8:00 | 24 November 2021 17:00 | 0 |  | 0h | 04.03.SAP.03.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
4109 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 25 November 2021 8:00 | 29 November 2021 15:00 | 0 | 4108 | 25h | 04.03.SAP.03.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4110 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 November 2021 15:00 | 30 November 2021 16:00 | 0 | 4109 | 10h | 04.03.SAP.03.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4111 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 November 2021 16:00 | 01 December 2021 17:00 | 0 | 4110 | 10h | 04.03.SAP.03.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4112 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 02 December 2021 8:00 | 02 December 2021 13:00 | 0 | 4111 | 5h | 04.03.SAP.03.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4113 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 02 December 2021 13:00 | 02 December 2021 13:00 | 0 | 4112,4106 | 0h | 04.03.SAP.03.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4114 |  | Auto Scheduled | זי אמ איי הייצ' איי אן - קבלת נתונים נוספים ממשהבט- הוספת הנתונים לממשק יוצא של משהבט | 18.63 days | 25 August 2021 8:00 | 04 October 2021 13:00 | 0.12 |  | 70h | 04.03.SAP.04 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4115 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.04.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4116 |  | Auto Scheduled | LifeCycle Tasks | 18.63 days | 25 August 2021 8:00 | 04 October 2021 13:00 | 0.12 |  | 70h | 04.03.SAP.04.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4117 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.04.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4118 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.03.SAP.04.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4119 |  | Auto Scheduled | יישום ופיתוח סאפ | 12.38 days | 25 August 2021 8:00 | 13 September 2021 17:00 | 0 |  | 0h | 04.03.SAP.04.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
4120 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 14 September 2021 8:00 | 29 September 2021 15:00 | 0 | 4119 | 25h | 04.03.SAP.04.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4121 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 29 September 2021 15:00 | 30 September 2021 16:00 | 0 | 4120 | 10h | 04.03.SAP.04.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4122 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 30 September 2021 16:00 | 03 October 2021 17:00 | 0 | 4121 | 10h | 04.03.SAP.04.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4123 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 04 October 2021 8:00 | 04 October 2021 13:00 | 0 | 4122 | 5h | 04.03.SAP.04.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4124 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 04 October 2021 13:00 | 04 October 2021 13:00 | 0 | 4123,4117 | 0h | 04.03.SAP.04.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4125 |  | Auto Scheduled | זי אמ איי הייצ' איי אן - יצירת אספקות ומשלוחים אוטומטית מטרנזקציה חדשה | 35.5 days | 30 August 2021 8:00 | 28 October 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 04.03.SAP.05 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4126 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.05.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4127 |  | Auto Scheduled | LifeCycle Tasks | 35.5 days | 30 August 2021 8:00 | 28 October 2021 13:00 | 7.0000000000000007E-2 |  | 70h | 04.03.SAP.05.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4128 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.03.SAP.05.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4129 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 04.03.SAP.05.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4130 |  | Auto Scheduled | יישום ופיתוח סאפ | 29.25 days | 30 August 2021 8:00 | 20 October 2021 17:00 | 0 |  | 0h | 04.03.SAP.05.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
4131 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 21 October 2021 8:00 | 25 October 2021 15:00 | 0 | 4130 | 25h | 04.03.SAP.05.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4132 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 25 October 2021 15:00 | 26 October 2021 16:00 | 0 | 4131 | 10h | 04.03.SAP.05.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4133 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 26 October 2021 16:00 | 27 October 2021 17:00 | 0 | 4132 | 10h | 04.03.SAP.05.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4134 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 28 October 2021 8:00 | 28 October 2021 13:00 | 0 | 4133 | 5h | 04.03.SAP.05.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4135 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 28 October 2021 13:00 | 28 October 2021 13:00 | 0 | 4134,4128 | 0h | 04.03.SAP.05.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4136 |  | Auto Scheduled | 04.04: רכש חו"ל | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.04 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4137 |  | Auto Scheduled | 04.04: רכש חו"ל.BP | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.04.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4138 |  | Auto Scheduled | 04.04: רכש חו"ל | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.04.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4139 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.04.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4140 |  | Auto Scheduled | LifeCycle Tasks | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 04.04.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4141 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 04.04.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4142 |  | Auto Scheduled | טרם החל | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 |  | 5h | 04.04.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4143 |  | Auto Scheduled | בעבודה | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4142 | 10h | 04.04.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4144 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 | 4143 | 5h | 04.04.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4145 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4144 | 10h | 04.04.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4146 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4145 | 10h | 04.04.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4147 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4146,4141 | 0h | 04.04.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4148 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4147 | 0h | 04.04.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4149 |  | Auto Scheduled | 06: קטלוג | 315.5 days | 06 August 2020 8:00 | 12 October 2021 13:00 | 0.60999999999999999 |  | 424h | 06 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
4150 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג | 243.5 days | 04 November 2020 8:00 | 12 October 2021 13:00 | 0.39000000000000001 |  | 236h | 06.01 | חתום |  | hd | קטיה | nan | BP | NA | As Soon As Possible | 3
4151 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג.BP | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 96h | 06.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4152 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 96h | 06.01.BP.01 | חתום |  | parent | קטיה | nan | BP | NA | As Soon As Possible | 5
4153 |  | Auto Scheduled | Sub Tasks | 36.25 days | 09 May 2021 8:00 | 04 July 2021 10:00 | 1 |  | 56h | 06.01.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4154 |  | Auto Scheduled | כתיבת מסמך | 0.63 days | 09 May 2021 8:00 | 09 May 2021 13:00 | 1 |  | 5h | 06.01.BP.01.01.20 | בוצע |  | MoM |  | nan | BP | NA | Must Start On | 7
4155 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.63 days | 15 May 2021 8:00 | 18 May 2021 13:00 | 1 | 4154 | 5h | 06.01.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4156 |  | Auto Scheduled | אישור אבי | 0.5 days | 20 May 2021 8:00 | 30 May 2021 12:00 | 1 | 4155 | 4h | 06.01.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4157 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 25 May 2021 8:00 | 30 May 2021 12:00 | 1 | 4156 | 4h | 06.01.BP.01.01.23 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4158 |  | Auto Scheduled | אישור מפקדת | 0.63 days | 30 May 2021 8:00 | 30 May 2021 13:00 | 1 | 4157 | 5h | 06.01.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4159 |  | Auto Scheduled | אישור חטלו"ג | 0.5 days | 04 June 2021 8:00 | 06 June 2021 12:00 | 1 | 4158 | 4h | 06.01.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4160 |  | Auto Scheduled | אישור מקל"ר | 0.5 days | 09 June 2021 8:00 | 09 June 2021 12:00 | 1 | 4159 | 4h | 06.01.BP.01.01.26 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4161 |  | Auto Scheduled | אישור ניר בשן | 1.75 days | 14 June 2021 8:00 | 15 June 2021 13:00 | 1 | 4160 | 14h | 06.01.BP.01.01.27 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4162 |  | Auto Scheduled | אישור שגיב שרביט | 1.38 days | 01 July 2021 8:00 | 04 July 2021 10:00 | 1 | 4161 | 11h | 06.01.BP.01.01.28 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4163 |  | Auto Scheduled | LifeCycle Tasks | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 40h | 06.01.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4164 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 15 July 2021 8:00 | 15 July 2021 17:00 | 1 | 4162 | 0h | 06.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4165 |  | Auto Scheduled | טרם החל | 0.63 days | 04 November 2020 8:00 | 04 November 2020 13:00 | 1 |  | 5h | 06.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4166 |  | Auto Scheduled | בעבודה | 1.25 days | 11 November 2020 8:00 | 12 November 2020 9:00 | 1 | 4165 | 10h | 06.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4167 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 25 November 2020 8:00 | 25 November 2020 13:00 | 1 | 4166 | 5h | 06.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4168 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 02 December 2020 8:00 | 03 December 2020 9:00 | 1 | 4167 | 10h | 06.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4169 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 4168 | 10h | 06.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4170 |  | Auto Scheduled | בחתימה | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 4169,4164 | 0h | 06.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4171 |  | Auto Scheduled | חתום | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 4170 | 0h | 06.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4172 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג.INT | 58 days | 15 July 2021 8:00 | 12 October 2021 13:00 | 0.17000000000000001 |  | 70h | 06.01.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4173 |  | Auto Scheduled | מערכת סאפ תעביר למערכת זכיין את האינד' לפריט דרוש בחינה בקטלוג,דרוש בחינה לאחר קבלה דרך הנתונים הקטלוגיים | 58 days | 15 July 2021 8:00 | 12 October 2021 13:00 | 0.17000000000000001 |  | 70h | 06.01.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
4174 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 06.01.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4175 |  | Auto Scheduled | LifeCycle Tasks | 58 days | 15 July 2021 8:00 | 12 October 2021 13:00 | 0.17000000000000001 |  | 70h | 06.01.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4176 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 06.01.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4177 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 4162 | 20h | 06.01.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4178 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 5.63 days | 19 September 2021 8:00 | 04 October 2021 17:00 | 0 |  | 0h | 06.01.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
4179 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 05 October 2021 8:00 | 07 October 2021 15:00 | 0 | 4178 | 25h | 06.01.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4180 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 07 October 2021 15:00 | 10 October 2021 16:00 | 0 | 4179 | 10h | 06.01.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4181 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 10 October 2021 16:00 | 11 October 2021 17:00 | 0 | 4180 | 10h | 06.01.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4182 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 12 October 2021 8:00 | 12 October 2021 13:00 | 0 | 4181 | 5h | 06.01.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4183 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 12 October 2021 13:00 | 12 October 2021 13:00 | 0 | 4182,4176 | 0h | 06.01.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4184 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג.SAP | 40.5 days | 15 July 2021 8:00 | 05 September 2021 8:00 | 0.13 |  | 70h | 06.01.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4185 |  | Auto Scheduled | מערכת סאפ תאפשר מתן אינדיקציה לפריט דרוש בחינה בקטלוג | 40.5 days | 15 July 2021 8:00 | 05 September 2021 8:00 | 0.13 |  | 70h | 06.01.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4186 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 06.01.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4187 |  | Auto Scheduled | LifeCycle Tasks | 40.5 days | 15 July 2021 8:00 | 05 September 2021 8:00 | 0.13 |  | 70h | 06.01.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4188 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 06.01.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4189 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 15 July 2021 8:00 | 19 July 2021 10:00 | 1 | 4162 | 20h | 06.01.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4190 |  | Auto Scheduled | יישום ופיתוח סאפ | 10.13 days | 01 August 2021 8:00 | 11 August 2021 17:00 | 0 |  | 0h | 06.01.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | Must Start On | 7
4191 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 12 August 2021 8:00 | 16 August 2021 15:00 | 0 | 4190 | 25h | 06.01.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4192 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 16 August 2021 15:00 | 17 August 2021 16:00 | 0 | 4191 | 10h | 06.01.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4193 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 17 August 2021 16:00 | 18 August 2021 17:00 | 0 | 4192 | 10h | 06.01.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4194 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 19 August 2021 8:00 | 19 August 2021 13:00 | 0 | 4193 | 5h | 06.01.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4195 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 4194,4188 | 0h | 06.01.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4196 |  | Auto Scheduled | 06.02: ממשק נתוני קטלוג לזכיין | 258.63 days | 06 August 2020 8:00 | 15 July 2021 17:00 | 1 |  | 94h | 06.02 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4197 |  | Auto Scheduled | 06.02: ממשק נתוני קטלוג לזכיין.BP | 258.63 days | 06 August 2020 8:00 | 15 July 2021 17:00 | 1 |  | 94h | 06.02.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4198 |  | Auto Scheduled | 06.02: ממשק נתוני קטלוג לזכיין | 258.63 days | 06 August 2020 8:00 | 15 July 2021 17:00 | 1 |  | 94h | 06.02.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4199 |  | Auto Scheduled | Sub Tasks | 34 days | 11 May 2021 8:00 | 04 July 2021 10:00 | 1 |  | 54h | 06.02.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4200 |  | Auto Scheduled | כתיבת מסמך | 0.38 days | 11 May 2021 8:00 | 11 May 2021 11:00 | 1 |  | 3h | 06.02.BP.01.01.20 | בוצע |  | MoM |  | nan | BP | NA | Must Start On | 7
4201 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.63 days | 15 May 2021 8:00 | 18 May 2021 13:00 | 1 | 4200 | 5h | 06.02.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4202 |  | Auto Scheduled | אישור אבי | 0.5 days | 20 May 2021 8:00 | 30 May 2021 12:00 | 1 | 4201 | 4h | 06.02.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4203 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 25 May 2021 8:00 | 30 May 2021 12:00 | 1 | 4202 | 4h | 06.02.BP.01.01.23 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4204 |  | Auto Scheduled | אישור מפקדת | 0.63 days | 30 May 2021 8:00 | 30 May 2021 13:00 | 1 | 4203 | 5h | 06.02.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4205 |  | Auto Scheduled | אישור חטלו"ג | 0.5 days | 04 June 2021 8:00 | 06 June 2021 12:00 | 1 | 4204 | 4h | 06.02.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4206 |  | Auto Scheduled | אישור מקל"ר | 0.5 days | 09 June 2021 8:00 | 09 June 2021 12:00 | 1 | 4205 | 4h | 06.02.BP.01.01.26 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4207 |  | Auto Scheduled | אישור ניר בשן | 1.75 days | 14 June 2021 8:00 | 15 June 2021 13:00 | 1 | 4206 | 14h | 06.02.BP.01.01.27 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4208 |  | Auto Scheduled | אישור שגיב שרביט | 1.38 days | 01 July 2021 8:00 | 04 July 2021 10:00 | 1 | 4207 | 11h | 06.02.BP.01.01.28 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4209 |  | Auto Scheduled | LifeCycle Tasks | 258.63 days | 06 August 2020 8:00 | 15 July 2021 17:00 | 1 |  | 40h | 06.02.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4210 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 15 July 2021 8:00 | 15 July 2021 17:00 | 1 | 4208 | 0h | 06.02.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4211 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 06.02.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4212 |  | Auto Scheduled | בעבודה | 1.25 days | 13 August 2020 8:00 | 16 August 2020 9:00 | 1 | 4211 | 10h | 06.02.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4213 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 27 August 2020 8:00 | 27 August 2020 13:00 | 1 | 4212 | 5h | 06.02.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4214 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 03 September 2020 8:00 | 06 September 2020 9:00 | 1 | 4213 | 10h | 06.02.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4215 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 17 September 2020 8:00 | 20 September 2020 9:00 | 1 | 4214 | 10h | 06.02.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4216 |  | Auto Scheduled | בחתימה | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 4215,4210 | 0h | 06.02.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4217 |  | Auto Scheduled | חתום | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 4216 | 0h | 06.02.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4218 |  | Auto Scheduled | 06.03: שינויים במערכות הקטלוג | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 94h | 06.03 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4219 |  | Auto Scheduled | 06.03: שינויים במערכות הקטלוג.BP | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 94h | 06.03.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4220 |  | Auto Scheduled | 06.03: שינויים במערכות הקטלוג | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 94h | 06.03.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4221 |  | Auto Scheduled | Sub Tasks | 34 days | 11 May 2021 8:00 | 04 July 2021 10:00 | 1 |  | 54h | 06.03.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4222 |  | Auto Scheduled | כתיבת מסמך | 0.38 days | 11 May 2021 8:00 | 11 May 2021 11:00 | 1 |  | 3h | 06.03.BP.01.01.20 | בוצע |  | MoM |  | nan | BP | NA | Must Start On | 7
4223 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.63 days | 15 May 2021 8:00 | 18 May 2021 13:00 | 1 | 4222 | 5h | 06.03.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4224 |  | Auto Scheduled | אישור אבי | 0.5 days | 20 May 2021 8:00 | 30 May 2021 12:00 | 1 | 4223 | 4h | 06.03.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4225 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 25 May 2021 8:00 | 30 May 2021 12:00 | 1 | 4224 | 4h | 06.03.BP.01.01.23 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4226 |  | Auto Scheduled | אישור מפקדת | 0.63 days | 30 May 2021 8:00 | 30 May 2021 13:00 | 1 | 4225 | 5h | 06.03.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4227 |  | Auto Scheduled | אישור חטלו"ג | 0.5 days | 04 June 2021 8:00 | 06 June 2021 12:00 | 1 | 4226 | 4h | 06.03.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4228 |  | Auto Scheduled | אישור מקל"ר | 0.5 days | 09 June 2021 8:00 | 09 June 2021 12:00 | 1 | 4227 | 4h | 06.03.BP.01.01.26 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4229 |  | Auto Scheduled | אישור ניר בשן | 1.75 days | 14 June 2021 8:00 | 15 June 2021 13:00 | 1 | 4228 | 14h | 06.03.BP.01.01.27 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4230 |  | Auto Scheduled | אישור שגיב שרביט | 1.38 days | 01 July 2021 8:00 | 04 July 2021 10:00 | 1 | 4229 | 11h | 06.03.BP.01.01.28 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4231 |  | Auto Scheduled | LifeCycle Tasks | 186.63 days | 04 November 2020 8:00 | 15 July 2021 17:00 | 1 |  | 40h | 06.03.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4232 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 15 July 2021 8:00 | 15 July 2021 17:00 | 1 | 4230 | 0h | 06.03.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4233 |  | Auto Scheduled | טרם החל | 0.63 days | 04 November 2020 8:00 | 04 November 2020 13:00 | 1 |  | 5h | 06.03.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4234 |  | Auto Scheduled | בעבודה | 1.25 days | 11 November 2020 8:00 | 12 November 2020 9:00 | 1 | 4233 | 10h | 06.03.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4235 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 25 November 2020 8:00 | 25 November 2020 13:00 | 1 | 4234 | 5h | 06.03.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4236 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 02 December 2020 8:00 | 03 December 2020 9:00 | 1 | 4235 | 10h | 06.03.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4237 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 4236 | 10h | 06.03.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4238 |  | Auto Scheduled | בחתימה | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 4237,4232 | 0h | 06.03.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4239 |  | Auto Scheduled | חתום | 0 days | 15 July 2021 8:00 | 15 July 2021 8:00 | 1 | 4238 | 0h | 06.03.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4240 |  | Auto Scheduled | 07: הובלה | 60.75 days | 04 November 2020 8:00 | 18 January 2021 17:00 | 1 |  | 84h | 07 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
4241 |  | Auto Scheduled | 07.01: הפצה | 60.75 days | 04 November 2020 8:00 | 18 January 2021 17:00 | 1 |  | 84h | 07.01 | חתום |  | hd | יורם | nan | BP | NA | As Soon As Possible | 3
4242 |  | Auto Scheduled | 07.01: הפצה.BP | 60.75 days | 04 November 2020 8:00 | 18 January 2021 17:00 | 1 |  | 84h | 07.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4243 |  | Auto Scheduled | 07.01: הפצה | 60.75 days | 04 November 2020 8:00 | 18 January 2021 17:00 | 1 |  | 84h | 07.01.BP.01 | חתום |  | parent | יורם | nan | BP | NA | As Soon As Possible | 5
4244 |  | Auto Scheduled | Sub Tasks | 28.63 days | 29 November 2020 8:00 | 03 January 2021 12:00 | 1 |  | 44h | 07.01.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4245 |  | Auto Scheduled | כתיבת מסמך | 1.38 days | 29 November 2020 8:00 | 30 November 2020 10:00 | 1 |  | 11h | 07.01.BP.01.01.20 | בוצע |  | MoM |  | nan | BP | NA | Must Start On | 7
4246 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 0.63 days | 13 December 2020 8:00 | 13 December 2020 13:00 | 1 | 4245 | 5h | 07.01.BP.01.01.21 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4247 |  | Auto Scheduled | אישור אבי | 0.13 days | 17 December 2020 8:00 | 17 December 2020 9:00 | 1 | 4246 | 1h | 07.01.BP.01.01.22 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4248 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 18 December 2020 8:00 | 20 December 2020 12:00 | 1 | 4247 | 4h | 07.01.BP.01.01.23 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4249 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 23 December 2020 8:00 | 23 December 2020 10:00 | 1 | 4248 | 2h | 07.01.BP.01.01.24 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4250 |  | Auto Scheduled | אישור חטלו"ג | 0.38 days | 24 December 2020 8:00 | 24 December 2020 11:00 | 1 | 4249 | 3h | 07.01.BP.01.01.25 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4251 |  | Auto Scheduled | אישור מקל"ר | 0.13 days | 28 December 2020 8:00 | 28 December 2020 9:00 | 1 | 4250 | 1h | 07.01.BP.01.01.26 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4252 |  | Auto Scheduled | אישור ניר בשן | 0.5 days | 28 December 2020 8:00 | 28 December 2020 12:00 | 1 | 4251 | 4h | 07.01.BP.01.01.27 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4253 |  | Auto Scheduled | אישור שגיב שרביט | 1.63 days | 31 December 2020 8:00 | 03 January 2021 12:00 | 1 | 4252 | 13h | 07.01.BP.01.01.28 | בוצע |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4254 |  | Auto Scheduled | LifeCycle Tasks | 60.75 days | 04 November 2020 8:00 | 18 January 2021 17:00 | 1 |  | 40h | 07.01.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4255 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1.13 days | 18 January 2021 8:00 | 18 January 2021 17:00 | 1 | 4253 | 0h | 07.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4256 |  | Auto Scheduled | טרם החל | 0.63 days | 04 November 2020 8:00 | 04 November 2020 13:00 | 1 |  | 5h | 07.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4257 |  | Auto Scheduled | בעבודה | 1.25 days | 11 November 2020 8:00 | 12 November 2020 9:00 | 1 | 4256 | 10h | 07.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4258 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 25 November 2020 8:00 | 25 November 2020 13:00 | 1 | 4257 | 5h | 07.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4259 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 02 December 2020 8:00 | 03 December 2020 9:00 | 1 | 4258 | 10h | 07.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4260 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 16 December 2020 8:00 | 17 December 2020 9:00 | 1 | 4259 | 10h | 07.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4261 |  | Auto Scheduled | בחתימה | 0 days | 18 January 2021 8:00 | 18 January 2021 8:00 | 1 | 4260,4255 | 0h | 07.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4262 |  | Auto Scheduled | חתום | 0 days | 18 January 2021 8:00 | 18 January 2021 8:00 | 1 | 4261 | 0h | 07.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4263 |  | Auto Scheduled | 10: רחבי | 430.25 days | 06 August 2020 8:00 | 03 March 2022 13:00 | 0.40000000000000002 |  | 651h | 10 |  |  | hd_domain |  | nan |  | NA | As Soon As Possible | 2
4264 |  | Auto Scheduled | 10.01: ממשק עיתוד | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.01 | בעבודה |  | hd | מוריה | nan | BP | NA | As Soon As Possible | 3
4265 |  | Auto Scheduled | 10.01: ממשק עיתוד.BP | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.01.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4266 |  | Auto Scheduled | 10.01: ממשק עיתוד | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.01.BP.01 | בעבודה |  | parent | מוריה | nan | BP | NA | As Soon As Possible | 5
4267 |  | Auto Scheduled | Sub Tasks | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 10.01.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4268 |  | Auto Scheduled | כתיבת מסמך | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 10.01.BP.01.01.20 | טרם החל |  | MoM |  | nan | BP | NA | Must Start On | 7
4269 |  | Auto Scheduled | LifeCycle Tasks | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.13 |  | 40h | 10.01.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4270 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4268 | 0h | 10.01.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4271 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.01.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4272 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4271 | 10h | 10.01.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4273 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4272 | 5h | 10.01.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4274 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4273 | 10h | 10.01.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4275 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4274 | 10h | 10.01.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4276 |  | Auto Scheduled | בחתימה | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4275,4270 | 0h | 10.01.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4277 |  | Auto Scheduled | חתום | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4276 | 0h | 10.01.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4278 |  | Auto Scheduled | 10.02: ממשק יהלום - שובל | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.02 | בעבודה |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4279 |  | Auto Scheduled | 10.02: ממשק יהלום - שובל.BP | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.02.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4280 |  | Auto Scheduled | 10.02: ממשק יהלום - שובל | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.02.BP.01 | בעבודה |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4281 |  | Auto Scheduled | Sub Tasks | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 10.02.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4282 |  | Auto Scheduled | כתיבת מסמך | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 10.02.BP.01.01.20 | טרם החל |  | MoM |  | nan | BP | NA | Must Start On | 7
4283 |  | Auto Scheduled | LifeCycle Tasks | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.13 |  | 40h | 10.02.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4284 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4282 | 0h | 10.02.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4285 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.02.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4286 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4285 | 10h | 10.02.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4287 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4286 | 5h | 10.02.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4288 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4287 | 10h | 10.02.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4289 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4288 | 10h | 10.02.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4290 |  | Auto Scheduled | בחתימה | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4289,4284 | 0h | 10.02.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4291 |  | Auto Scheduled | חתום | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4290 | 0h | 10.02.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4292 |  | Auto Scheduled | 10.03: הרשאות | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.03 | בעבודה |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4293 |  | Auto Scheduled | 10.03: הרשאות.BP | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.03.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4294 |  | Auto Scheduled | 10.03: הרשאות | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.02 |  | 70h | 10.03.BP.01 | בעבודה |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4295 |  | Auto Scheduled | Sub Tasks | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 10.03.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4296 |  | Auto Scheduled | כתיבת מסמך | 33.75 days | 06 December 2020 8:00 | 14 January 2021 17:00 | 0 |  | 30h | 10.03.BP.01.01.20 | טרם החל |  | MoM |  | nan | BP | NA | Must Start On | 7
4297 |  | Auto Scheduled | LifeCycle Tasks | 130.5 days | 06 August 2020 8:00 | 14 January 2021 17:00 | 0.13 |  | 40h | 10.03.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4298 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4296 | 0h | 10.03.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4299 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.03.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4300 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4299 | 10h | 10.03.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4301 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4300 | 5h | 10.03.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4302 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4301 | 10h | 10.03.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4303 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4302 | 10h | 10.03.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4304 |  | Auto Scheduled | בחתימה | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4303,4298 | 0h | 10.03.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4305 |  | Auto Scheduled | חתום | 0 days | 14 January 2021 17:00 | 14 January 2021 17:00 | 0 | 4304 | 0h | 10.03.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4306 |  | Auto Scheduled | 10.04: BW | 298.13 days | 06 August 2020 8:00 | 05 September 2021 9:00 | 2.9999999999999999E-2 |  | 79h | 10.04 | בעבודה |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4307 |  | Auto Scheduled | 10.04: BW.BP | 298.13 days | 06 August 2020 8:00 | 05 September 2021 9:00 | 2.9999999999999999E-2 |  | 79h | 10.04.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4308 |  | Auto Scheduled | 10.04: BW | 298.13 days | 06 August 2020 8:00 | 05 September 2021 9:00 | 2.9999999999999999E-2 |  | 79h | 10.04.BP.01 | בעבודה |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4309 |  | Auto Scheduled | Sub Tasks | 15.88 days | 16 August 2021 8:00 | 05 September 2021 9:00 | 0 |  | 39h | 10.04.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4310 |  | Auto Scheduled | כתיבת מסמך | 12.38 days | 16 August 2021 8:00 | 30 August 2021 17:00 | 0 |  | 11h | 10.04.BP.01.01.20 | בתהליך |  | MoM |  | nan | BP | NA | Must Start On | 7
4311 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 1.25 days | 31 August 2021 8:00 | 01 September 2021 9:00 | 0 | 4310 | 10h | 10.04.BP.01.01.21 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4312 |  | Auto Scheduled | אישור אבי | 0.38 days | 01 September 2021 9:00 | 01 September 2021 12:00 | 0 | 4311 | 3h | 10.04.BP.01.01.22 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4313 |  | Auto Scheduled | אישור המנהלת | 0.5 days | 01 September 2021 12:00 | 01 September 2021 16:00 | 0 | 4312 | 4h | 10.04.BP.01.01.23 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4314 |  | Auto Scheduled | אישור מפקדת | 0.25 days | 01 September 2021 16:00 | 02 September 2021 9:00 | 0 | 4313 | 2h | 10.04.BP.01.01.24 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4315 |  | Auto Scheduled | אישור חטלו"ג | 0.25 days | 02 September 2021 9:00 | 02 September 2021 11:00 | 0 | 4314 | 2h | 10.04.BP.01.01.25 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4316 |  | Auto Scheduled | אישור מקל"ר | 0.25 days | 02 September 2021 11:00 | 02 September 2021 13:00 | 0 | 4315 | 2h | 10.04.BP.01.01.26 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4317 |  | Auto Scheduled | אישור ניר בשן | 0.25 days | 02 September 2021 13:00 | 02 September 2021 15:00 | 0 | 4316 | 2h | 10.04.BP.01.01.27 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4318 |  | Auto Scheduled | אישור שגיב שרביט | 0.38 days | 02 September 2021 15:00 | 05 September 2021 9:00 | 0 | 4317 | 3h | 10.04.BP.01.01.28 | טרם החל |  | MoM |  | nan | BP | NA | As Soon As Possible | 7
4319 |  | Auto Scheduled | LifeCycle Tasks | 298.13 days | 06 August 2020 8:00 | 05 September 2021 9:00 | 0.13 |  | 40h | 10.04.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4320 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 9:00 | 05 September 2021 9:00 | 0 | 4318 | 0h | 10.04.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4321 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.04.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4322 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4321 | 10h | 10.04.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4323 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4322 | 5h | 10.04.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4324 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4323 | 10h | 10.04.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4325 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4324 | 10h | 10.04.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4326 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 9:00 | 05 September 2021 9:00 | 0 | 4325,4320 | 0h | 10.04.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4327 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 9:00 | 05 September 2021 9:00 | 0 | 4326 | 0h | 10.04.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4328 |  | Auto Scheduled | 10.05: ZMEATED | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.02 |  | 71h | 10.05 | בעבודה |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4329 |  | Auto Scheduled | 10.05: ZMEATED.BP | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.02 |  | 71h | 10.05.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4330 |  | Auto Scheduled | 10.05: ZMEATED | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.02 |  | 71h | 10.05.BP.01 | בעבודה |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4331 |  | Auto Scheduled | Sub Tasks | 34.88 days | 19 October 2020 8:00 | 30 November 2020 17:00 | 0 |  | 31h | 10.05.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4332 |  | Auto Scheduled | כתיבת מסמך | 34.88 days | 19 October 2020 8:00 | 30 November 2020 17:00 | 0 |  | 31h | 10.05.BP.01.01.20 | טרם החל |  | MoM |  | nan | BP | NA | Must Start On | 7
4333 |  | Auto Scheduled | LifeCycle Tasks | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.13 |  | 40h | 10.05.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4334 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 30 November 2020 17:00 | 30 November 2020 17:00 | 0 | 4332 | 0h | 10.05.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4335 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.05.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4336 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4335 | 10h | 10.05.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4337 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4336 | 5h | 10.05.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4338 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4337 | 10h | 10.05.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4339 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4338 | 10h | 10.05.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4340 |  | Auto Scheduled | בחתימה | 0 days | 30 November 2020 17:00 | 30 November 2020 17:00 | 0 | 4339,4334 | 0h | 10.05.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4341 |  | Auto Scheduled | חתום | 0 days | 30 November 2020 17:00 | 30 November 2020 17:00 | 0 | 4340 | 0h | 10.05.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4342 |  | Auto Scheduled | 10.06: POD | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.02 |  | 71h | 10.06 | בעבודה |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4343 |  | Auto Scheduled | 10.06: POD.BP | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.02 |  | 71h | 10.06.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4344 |  | Auto Scheduled | 10.06: POD | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.02 |  | 71h | 10.06.BP.01 | בעבודה |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4345 |  | Auto Scheduled | Sub Tasks | 34.88 days | 19 October 2020 8:00 | 30 November 2020 17:00 | 0 |  | 31h | 10.06.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4346 |  | Auto Scheduled | כתיבת מסמך | 34.88 days | 19 October 2020 8:00 | 30 November 2020 17:00 | 0 |  | 31h | 10.06.BP.01.01.20 | טרם החל |  | MoM |  | nan | BP | NA | Must Start On | 7
4347 |  | Auto Scheduled | LifeCycle Tasks | 93.38 days | 06 August 2020 8:00 | 30 November 2020 17:00 | 0.13 |  | 40h | 10.06.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4348 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 30 November 2020 17:00 | 30 November 2020 17:00 | 0 | 4346 | 0h | 10.06.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4349 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.06.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4350 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4349 | 10h | 10.06.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4351 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4350 | 5h | 10.06.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4352 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4351 | 10h | 10.06.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4353 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4352 | 10h | 10.06.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4354 |  | Auto Scheduled | בחתימה | 0 days | 30 November 2020 17:00 | 30 November 2020 17:00 | 0 | 4353,4348 | 0h | 10.06.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4355 |  | Auto Scheduled | חתום | 0 days | 30 November 2020 17:00 | 30 November 2020 17:00 | 0 | 4354 | 0h | 10.06.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4356 |  | Auto Scheduled | 10.07: מורשי כניסה | 298 days | 06 August 2020 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 10.07 | בעבודה |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4357 |  | Auto Scheduled | 10.07: מורשי כניסה.BP | 298 days | 06 August 2020 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 10.07.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4358 |  | Auto Scheduled | 10.07: מורשי כניסה | 298 days | 06 August 2020 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 10.07.BP.01 | בעבודה |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4359 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.07.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4360 |  | Auto Scheduled | LifeCycle Tasks | 298 days | 06 August 2020 8:00 | 05 September 2021 8:00 | 0.13 |  | 40h | 10.07.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4361 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.07.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4362 |  | Auto Scheduled | טרם החל | 0.63 days | 06 August 2020 8:00 | 06 August 2020 13:00 | 1 |  | 5h | 10.07.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4363 |  | Auto Scheduled | בעבודה | 1.25 days | 06 August 2020 13:00 | 09 August 2020 14:00 | 0 | 4362 | 10h | 10.07.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4364 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 09 August 2020 14:00 | 10 August 2020 10:00 | 0 | 4363 | 5h | 10.07.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4365 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 10 August 2020 10:00 | 11 August 2020 11:00 | 0 | 4364 | 10h | 10.07.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4366 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 11 August 2020 11:00 | 12 August 2020 12:00 | 0 | 4365 | 10h | 10.07.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4367 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 4366,4361 | 0h | 10.07.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4368 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 0 | 4367 | 0h | 10.07.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4369 |  | Auto Scheduled | 10.08: מנוף | 223.38 days | 03 May 2021 8:00 | 03 March 2022 13:00 | 0.71999999999999997 |  | 180h | 10.08 | חתום |  | hd |  | nan | BP | NA | As Soon As Possible | 3
4370 |  | Auto Scheduled | 10.08: מנוף.BP | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 10.08.BP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4371 |  | Auto Scheduled | 10.08: מנוף | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 10.08.BP.01 | חתום |  | parent |  | nan | BP | NA | As Soon As Possible | 5
4372 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.08.BP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4373 |  | Auto Scheduled | LifeCycle Tasks | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 |  | 40h | 10.08.BP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4374 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.08.BP.01.02.01 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4375 |  | Auto Scheduled | טרם החל | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 |  | 5h | 10.08.BP.01.02.02 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4376 |  | Auto Scheduled | בעבודה | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4375 | 10h | 10.08.BP.01.02.03 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4377 |  | Auto Scheduled | ממתין להצגה | 0.63 days | 05 September 2021 8:00 | 05 September 2021 13:00 | 1 | 4376 | 5h | 10.08.BP.01.02.04 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4378 |  | Auto Scheduled | סיכום מסמך | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4377 | 10h | 10.08.BP.01.02.05 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4379 |  | Auto Scheduled | ממתין לאישור | 1.25 days | 05 September 2021 8:00 | 09 September 2021 9:00 | 1 | 4378 | 10h | 10.08.BP.01.02.06 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4380 |  | Auto Scheduled | בחתימה | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4379,4374 | 0h | 10.08.BP.01.02.07 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4381 |  | Auto Scheduled | חתום | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 | 4380 | 0h | 10.08.BP.01.02.08 |  |  | rule |  | nan | BP | NA | As Soon As Possible | 7
4382 |  | Auto Scheduled | 10.08: מנוף.INT | 132.25 days | 05 September 2021 8:00 | 03 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 10.08.INT |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4383 |  | Auto Scheduled | טרום מבצוע בה"ס דרום נדרש לאפשר במערכת סאפ להזין את נתוני האריזות כחלק מפרויקט מנו"ף. | 132.25 days | 05 September 2021 8:00 | 03 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 10.08.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | nan | INT | NA | As Soon As Possible | 5
4384 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.08.INT.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4385 |  | Auto Scheduled | LifeCycle Tasks | 132.25 days | 05 September 2021 8:00 | 03 March 2022 13:00 | 7.0000000000000007E-2 |  | 70h | 10.08.INT.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4386 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.08.INT.01.02.01 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4387 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 10.08.INT.01.02.02 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4388 |  | Auto Scheduled | יישום ופיתוח משימת ממשק | 28.13 days | 20 January 2022 8:00 | 23 February 2022 17:00 | 0 |  | 0h | 10.08.INT.01.02.03 |  |  | rule |  | logmar | INT | NA | Must Start On | 7
4389 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 24 February 2022 8:00 | 28 February 2022 15:00 | 0 | 4388 | 25h | 10.08.INT.01.02.04 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4390 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 28 February 2022 15:00 | 01 March 2022 16:00 | 0 | 4389 | 10h | 10.08.INT.01.02.05 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4391 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 01 March 2022 16:00 | 02 March 2022 17:00 | 0 | 4390 | 10h | 10.08.INT.01.02.06 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4392 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 03 March 2022 8:00 | 03 March 2022 13:00 | 0 | 4391 | 5h | 10.08.INT.01.02.07 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4393 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | 03 March 2022 13:00 | 03 March 2022 13:00 | 0 | 4392,4386 | 0h | 10.08.INT.01.02.08 |  |  | rule |  | nan | INT | NA | As Soon As Possible | 7
4394 |  | Auto Scheduled | 10.08: מנוף.SAP | 218.88 days | 03 May 2021 8:00 | 27 February 2022 13:00 | 0.82999999999999996 |  | 70h | 10.08.SAP |  |  | hd_1 |  | nan |  | NA | As Soon As Possible | 4
4395 |  | Auto Scheduled | הסבת נתונים פרויקט מנוף | 218.88 days | 03 May 2021 8:00 | 27 February 2022 13:00 | 0.82999999999999996 |  | 70h | 10.08.SAP.01 | יישום ופיתוח סאפ |  | parent |  | nan | SAP | NA | As Soon As Possible | 5
4396 |  | Auto Scheduled | Sub Tasks | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.08.SAP.01.01 |  |  | Sub Tasks |  | nan |  | NA | As Soon As Possible | 6
4397 |  | Auto Scheduled | LifeCycle Tasks | 218.88 days | 03 May 2021 8:00 | 27 February 2022 13:00 | 0.82999999999999996 |  | 70h | 10.08.SAP.01.02 |  |  | LC Tasks |  | nan |  | NA | As Soon As Possible | 6
4398 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | 05 September 2021 8:00 | 05 September 2021 8:00 | 1 |  | 0h | 10.08.SAP.01.02.01 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4399 |  | Auto Scheduled | תכנון והתחלת פיתוח | 2.5 days | 05 September 2021 8:00 | 12 September 2021 10:00 | 1 |  | 20h | 10.08.SAP.01.02.02 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4400 |  | Auto Scheduled | יישום ופיתוח סאפ | 212.63 days | 03 May 2021 8:00 | 17 February 2022 17:00 | 0.84999999999999998 |  | 0h | 10.08.SAP.01.02.03 |  |  | rule |  | logmar | SAP | NA | As Soon As Possible | 7
4401 |  | Auto Scheduled | פיתוח בדיקות קבלה | 3.13 days | 20 February 2022 8:00 | 22 February 2022 15:00 | 0 | 4400 | 25h | 10.08.SAP.01.02.04 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4402 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 1.25 days | 22 February 2022 15:00 | 23 February 2022 16:00 | 0 | 4401 | 10h | 10.08.SAP.01.02.05 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4403 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 1.25 days | 23 February 2022 16:00 | 24 February 2022 17:00 | 0 | 4402 | 10h | 10.08.SAP.01.02.06 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4404 |  | Auto Scheduled | הכנות להעלאה לאויר | 0.63 days | 27 February 2022 8:00 | 27 February 2022 13:00 | 0 | 4403 | 5h | 10.08.SAP.01.02.07 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4405 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | 27 February 2022 13:00 | 27 February 2022 13:00 | 0 | 4404,4398 | 0h | 10.08.SAP.01.02.08 |  |  | rule |  | nan | SAP | NA | As Soon As Possible | 7
4406 |  | Auto Scheduled | אינטגרציה | 185 days | 13 April 2022 8:00 | 29 November 2022 12:00 | 0 | 7 | 0h | A-00 |  |  | header |  | nan |  | NA | As Soon As Possible | 1
4407 |  | Auto Scheduled | FAT | 88 days | 29 November 2022 12:00 | 19 March 2023 14:00 | 0 | 4406 | 0h | B-00 |  |  | header |  | nan |  | NA | As Soon As Possible | 1
4408 |  | Auto Scheduled | SAT | 87 days | 19 March 2023 14:00 | 04 July 2023 17:00 | 0 | 4407 | 0h | C-00 |  |  | header |  | nan |  | NA | As Soon As Possible | 1