## Task_Table1
ID | Indicators | Task_Mode | name | Duration | Start_Date | Finish_Date | PercentC | preds | Scheduled_Work | RN | status | waiting | row_type | Owner | source | notes_2 | Deadline | Constraint_Type | OL
1 |  | Auto Scheduled | תכנית מרה"ס שלב ג | 829 days | January 10, 2020 8:00 AM | March 15, 2023 5:00 PM | 0.01 |  | 41,807h | 00 | [6 empty] | NA | As Soon As Possible | 1
2 |  | Auto Scheduled | אבני דרך חוזיות | 290 days | May 18, 2021 8:00 AM | June 27, 2022 5:00 PM | 0 |  | 0h | 00.01 | [6 empty] | NA | As Soon As Possible | 2
3 |  | Auto Scheduled | מוכנות למפגש עם הזכיין | 0 days | June 27, 2022 5:00 PM | June 27, 2022 5:00 PM | 0 | 9 | 0h | 00.01.01 | [6 empty] | NA | As Soon As Possible | 3
4 |  | Auto Scheduled | PDR סביבת אינטגרטציה המערך הייעודי | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.01.03 | [6 empty] | NA | As Soon As Possible | 3
5 |  | Auto Scheduled | CDR מערכת מידע מנהלתית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.01.04 | [6 empty] | NA | As Soon As Possible | 3
6 |  | Auto Scheduled | סיום הקמת המתחם ותשתית התקשוב לסביבת האינטגרציה | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.01.05 | [6 empty] | NA | As Soon As Possible | 3
7 |  | Auto Scheduled | מוכנות סביבת האינטגרציה | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.01.06 | [6 empty] | NA | As Soon As Possible | 3
8 |  | Auto Scheduled | אבני דרך פנימיות | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 0h | 00.02 | [6 empty] | NA | As Soon As Possible | 2
9 |  | Auto Scheduled | סיום ואישור מסמכי בלו-פרינט | 0 days | June 27, 2022 5:00 PM | June 27, 2022 5:00 PM | 0 | 40,616,1067,1216,1299,1344,1583,1605,1638,1892,2109,2296,2481,2755,3045,3306,3354,3709,3731,3851,4030,4133,4330,4432,4614,4743,4790,4869,4892,4906,4930,4952,4974,4997,5020,5034,5048,5070,5084,5098,5111 | 0h | 00.02.02 | [6 empty] | NA | As Soon As Possible | 3
10 |  | Auto Scheduled | סיום שלב היישום והפיתוח - קריטי לאינטגרציה | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 0h | 00.02.03 | [6 empty] | NA | As Soon As Possible | 3
11 |  | Auto Scheduled | סיום משימות יישום | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.02.03.01 | [6 empty] | NA | As Soon As Possible | 4
12 |  | Auto Scheduled | סיום משימות פיתוח | 0 days | February 13, 2023 5:00 PM | February 13, 2023 5:00 PM | 0 | 297,308,319,330,341,352,363,374,385,396,407,418,429,440,451,462,473,484,495,506,517,528,539,550,561,572,583,594,789,800,811,822,833,844,855,866,877,888,899,910,921,932,943,954,965,976,987,998,1009,1020,1184,1195,1243,1254,1265,1276,1451,1462,1473,1484,14 | 0h | 00.02.03.02 | [6 empty] | NA | As Soon As Possible | 4
13 |  | Auto Scheduled | סיום משימות ממשקים | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 142,153,164,175,186,197,208,219,230,241,252,263,274,285,678,689,700,711,722,733,744,755,766,777,1150,1161,1172,1406,1417,1428,1439,2358,2369,2501,2512,2523,2534,2545,2824,2835,3093,3104,3115,3126,3137,3148,3159,3388,3399,3410,3421,3432,3443,3454,3465,347 | 0h | 00.02.03.03 | [6 empty] | NA | As Soon As Possible | 4
14 |  | Auto Scheduled | סיום משימות זכיין - מרה"ס | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.02.03.04 | [6 empty] | NA | As Soon As Possible | 4
15 |  | Auto Scheduled | סיום משימות זכיין - זכיין | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 00.02.03.05 | [6 empty] | NA | As Soon As Possible | 4
16 |  | Auto Scheduled | 01: מלאי ואחסנה | 829 days | January 10, 2020 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 19,814h | 01 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
17 |  | Auto Scheduled | 01.01: קבלה מרכש | 766 days | April 8, 2020 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 3,490h | 01.01 | חתום | עינת | hd | עינת |  | BP | NA | As Soon As Possible | 3
18 |  | Auto Scheduled | 01.01: קבלה מרכש.BP | 408 days | April 8, 2020 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 160h | 01.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
19 |  | Auto Scheduled | 01.01: קבלה מרכש - BP | 408 days | April 8, 2020 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 160h | 01.01.BP.01 | חתום | עינת | parent | עינת |  | BP | NA | As Soon As Possible | 5
20 |  | Auto Scheduled | Sub Tasks | 408 days | April 8, 2020 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 120h | 01.01.BP.01.01 |  | עינת | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
21 |  | Auto Scheduled | עבור מחסנים מנוהלי WMS ,השינויים המרכזים בתהליך העבודה החזרה לספק לביטול מלאי טרם אחסנה פיזית: לא מבוצע תהליך קליטה למלאי מראש ניתן לבטל רק את האספקה הנכנסת. ובנוסף בפסילת בוחן לאחר קליטה למלאי בכושר1 לא מבטלים קליטה למלאי מבצעים נוהל החזרה לספק, כלומר | 1 day | April 8, 2020 8:00 AM | April 8, 2020 5:00 PM | 0 |  | 1h | 01.01.BP.01.01.01 | בוצע | אמל"ח | MoM | עינת | שרון רחמים | INT | NA | Must Start On | 7
22 |  | Auto Scheduled | מערכת SAP תנחה את מערכת WMS לצפי קבלות מלאי מרכש ע"י שידור אספקות נכנסות הכוללות את פריטי המשלוח: מדובר במכולה לא ניתן לדעת אילו פריטים מכילה, נדרשת גישה לקצין קישור נמלים למערכת שינוע נמלים (מערכת של משרד הביטחון). בנוסף נדרש לעדכן נוהל החזרה לספק חו"ל | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 01.01.BP.01.01.02 | בוצע | אמל"ח | MoM | עינת | שרון רחמים | INT | NA | As Soon As Possible | 7
23 |  | Auto Scheduled | כתיבת מסמך | 14 days | May 19, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 22 | 14h | 01.01.BP.01.01.20 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
24 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 9 days | June 8, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 | 23 | 9h | 01.01.BP.01.01.21 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
25 |  | Auto Scheduled | אישור מקל"ר | 24 days | June 21, 2021 8:00 AM | July 22, 2021 5:00 PM | 0 | 24 | 24h | 01.01.BP.01.01.22 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
26 |  | Auto Scheduled | אישור מפקדת | 3 days | July 23, 2021 8:00 AM | July 27, 2021 5:00 PM | 0 | 25 | 3h | 01.01.BP.01.01.23 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
27 |  | Auto Scheduled | אישור אבי | 7 days | July 28, 2021 8:00 AM | August 5, 2021 5:00 PM | 0 | 26 | 7h | 01.01.BP.01.01.24 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
28 |  | Auto Scheduled | אישור המנהלת | 5 days | August 6, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 27 | 5h | 01.01.BP.01.01.25 | בוצע | סיגל | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
29 |  | Auto Scheduled | אישור חטלו"ג | 19 days | August 13, 2021 8:00 AM | September 8, 2021 5:00 PM | 0 | 28 | 19h | 01.01.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
30 |  | Auto Scheduled | אישור שגיב שרביט | 17 days | September 9, 2021 8:00 AM | October 1, 2021 5:00 PM | 0 | 29 | 17h | 01.01.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
31 |  | Auto Scheduled | אישור ניר בשן | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
32 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 40h | 01.01.BP.01.02 |  | עינת | LC Tasks |  |  |  | NA | As Soon As Possible | 6
33 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | October 29, 2021 5:00 PM | October 29, 2021 5:00 PM | 0 | 31 | 0h | 01.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
34 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
35 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 34 | 10h | 01.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
36 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 35 | 5h | 01.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
37 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 36 | 10h | 01.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
38 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 37 | 10h | 01.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
39 |  | Auto Scheduled | בחתימה | 0 days | October 29, 2021 5:00 PM | October 29, 2021 5:00 PM | 0 | 38,33 | 0h | 01.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
40 |  | Auto Scheduled | חתום | 0 days | October 29, 2021 5:00 PM | October 29, 2021 5:00 PM | 0 | 39 | 0h | 01.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
41 |  | Auto Scheduled | 01.01: קבלה מרכש.CNV | 205 days | May 18, 2021 8:00 AM | February 28, 2022 5:00 PM | 0 |  | 60h | 01.01.CNV |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
42 |  | Auto Scheduled | הסבות הזמנות רכש-יש לשלוח למערכת הWMS את הזמנת המקור והקשר בין הזמנת המקור (מנה"ר) להזמנה החדשה (ZH01 +ZH92) - CNV | 205 days | May 18, 2021 8:00 AM | February 28, 2022 5:00 PM | 0 |  | 60h | 01.01.CNV.01 | יישום ופיתוח משימת הסבה |  | parent |  | requirements | CNV | NA | As Soon As Possible | 5
43 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.CNV.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
44 |  | Auto Scheduled | LifeCycle Tasks | 205 days | May 18, 2021 8:00 AM | February 28, 2022 5:00 PM | 0 |  | 60h | 01.01.CNV.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
45 |  | Auto Scheduled | סיום משימת משנה להסבה | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.CNV.01.02.01 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
46 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.CNV.01.02.02 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
47 |  | Manually Scheduled | יישום ופיתוח משימת הסבה | 10 days | December 21, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 46 | 0h | 01.01.CNV.01.02.03 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
48 |  | Auto Scheduled | פיתוח בדיקות קבלה | 10 days | January 4, 2022 8:00 AM | January 17, 2022 5:00 PM | 0 | 47 | 10h | 01.01.CNV.01.02.04 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
49 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 18, 2022 8:00 AM | January 31, 2022 5:00 PM | 0 | 48 | 10h | 01.01.CNV.01.02.05 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
50 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 1, 2022 8:00 AM | February 14, 2022 5:00 PM | 0 | 49 | 10h | 01.01.CNV.01.02.06 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
51 |  | Auto Scheduled | הכנות להעלאה לאויר | 10 days | February 15, 2022 8:00 AM | February 28, 2022 5:00 PM | 0 | 50 | 10h | 01.01.CNV.01.02.07 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
52 |  | Auto Scheduled | משימת הסבה עלתה לאויר | 0 days | February 28, 2022 5:00 PM | February 28, 2022 5:00 PM | 0 | 51,45 | 0h | 01.01.CNV.01.02.08 |  |  | rule |  |  | CNV | NA | As Soon As Possible | 7
53 |  | Auto Scheduled | 01.01: קבלה מרכש.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 330h | 01.01.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
54 |  | Auto Scheduled | נדרש לסכם את התהליך האו"שי ומערכות מידע שעבורו נדרש להעביר ליחידת מטמון (בדגש על שמנים מחו"ל) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.02 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
55 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
56 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
57 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
58 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 57 | 10h | 01.01.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
59 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 58 | 20h | 01.01.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
60 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 59,57 | 0h | 01.01.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
61 |  | Auto Scheduled | נדרש להשלים את תהליך האו"שי ,מי בע"ת צבאי שייפתח את האספקה נכנסת בSAP טרם ההגעה למחסני המרה"ס ( בהתאם ל LOT וההזמנה הרלוונטיים ) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.03 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
62 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
63 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
64 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
65 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 64 | 10h | 01.01.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
66 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 65 | 20h | 01.01.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
67 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 66,64 | 0h | 01.01.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
68 |  | Auto Scheduled | נדרש להתאים את תהליך רכש חו"ל – השלמת פרטי משלוח בשלב תאום האספקה. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.04 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
69 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
70 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
71 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
72 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 71 | 10h | 01.01.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
73 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 72 | 20h | 01.01.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
74 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 73,71 | 0h | 01.01.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
75 |  | Auto Scheduled | נדרש להגדיר בע"ת צבאי שיפתח אספקה נכנסת ב SAP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.05 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
76 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
77 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
78 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
79 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 78 | 10h | 01.01.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
80 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 79 | 20h | 01.01.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
81 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 80,78 | 0h | 01.01.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
82 |  | Auto Scheduled | נדרש לקבוע מה תהלחך הבחינה של ערכות (עץ מוצר)-כיום לא קיים בסאפ תהליך אושי - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.07 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
83 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
84 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
85 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
86 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 85 | 10h | 01.01.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
87 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 86 | 20h | 01.01.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
88 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 87,85 | 0h | 01.01.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
89 |  | Auto Scheduled | דוח אספקות שבוטלו ב WMS ונסגרו בSAP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.08 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
90 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
91 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
92 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
93 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 92 | 10h | 01.01.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
94 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 93 | 20h | 01.01.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
95 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 94,92 | 0h | 01.01.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
96 |  | Auto Scheduled | נדרש עבור כלל המשקים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.13 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
97 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
98 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
99 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.13.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
100 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 99 | 10h | 01.01.GEN.13.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
101 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 100 | 20h | 01.01.GEN.13.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
102 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 101,99 | 0h | 01.01.GEN.13.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
103 |  | Auto Scheduled | נדרש לאפיין דוח חריגים עבור צפי הזמנת/אספקות שלא התקבלו - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.14 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
104 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
105 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
106 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.14.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
107 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 106 | 10h | 01.01.GEN.14.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
108 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 107 | 20h | 01.01.GEN.14.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
109 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 108,106 | 0h | 01.01.GEN.14.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
110 |  | Auto Scheduled | נדרש לקבל החלטה על תהליך או"שי של קבלה למלאי עבור פריטים לא מקוטלגים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.15 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
111 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
112 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
113 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.15.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
114 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 113 | 10h | 01.01.GEN.15.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
115 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 114 | 20h | 01.01.GEN.15.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
116 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 115,113 | 0h | 01.01.GEN.15.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
117 |  | Auto Scheduled | נדרש לקבל החלטה על תהליך או"שי של קבלת פריט נעליים( לא יודעים איזה סוג נעליים התקבלו) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.16 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
118 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
119 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
120 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.16.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
121 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 120 | 10h | 01.01.GEN.16.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
122 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 121 | 20h | 01.01.GEN.16.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
123 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 122,120 | 0h | 01.01.GEN.16.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
124 |  | Auto Scheduled | נדרש החלטה עבור הוספת צ' ( ובדיקת החוקה באספקה הנכנסת ) באספקה הנכנסת - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.17 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
125 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
126 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.01.GEN.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
127 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.GEN.17.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
128 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 127 | 10h | 01.01.GEN.17.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
129 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 128 | 20h | 01.01.GEN.17.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
130 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 129,127 | 0h | 01.01.GEN.17.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
131 |  | Auto Scheduled | 01.01: קבלה מרכש.INT | 507 days | April 6, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 980h | 01.01.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
132 |  | Auto Scheduled | מערכת SAP תאפשר העברת שדרים למערכת WMS ע"ב אספקה נכנסת ומשלוח. (כולל קשר בין הזמנת מנה"ר להזמנה חדשה(ZH92) בעת הצורך) - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
133 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
134 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
135 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
136 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
137 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | July 6, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 136 | 0h | 01.01.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
138 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 10, 2021 8:00 AM | September 13, 2021 5:00 PM | 0 | 137 | 25h | 01.01.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
139 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 14, 2021 8:00 AM | September 27, 2021 5:00 PM | 0 | 138 | 10h | 01.01.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
140 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 28, 2021 8:00 AM | October 11, 2021 5:00 PM | 0 | 139 | 10h | 01.01.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
141 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 12, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 140 | 5h | 01.01.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
142 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 18, 2021 5:00 PM | October 18, 2021 5:00 PM | 0 | 141,135 | 0h | 01.01.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
143 |  | Auto Scheduled | מערכות WMS וSAP יאפשרו העברות שדרים לעדכון דו צדדי של שינויים באספקות כגון כמויות. - INT | 149 days | April 6, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
144 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
145 |  | Auto Scheduled | LifeCycle Tasks | 149 days | April 6, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
146 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
147 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
148 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | April 6, 2021 8:00 AM | May 8, 2021 5:00 PM | 0 | 147 | 0h | 01.01.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
149 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 148 | 25h | 01.01.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
150 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 14, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 149 | 10h | 01.01.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
151 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 28, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 150 | 10h | 01.01.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
152 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 12, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 151 | 5h | 01.01.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
153 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | July 16, 2021 5:00 PM | July 16, 2021 5:00 PM | 0 | 152,146 | 0h | 01.01.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
154 |  | Auto Scheduled | מערכות WMS וSAP יאפשרו העברת שדרים לעדכון קבלה בפועל ע"ב תנועות מלאי (לאתרי האחסון הרלוונטים בSAP) גם עבור אספקות חלקיות - INT | 197 days | May 18, 2021 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
155 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
156 |  | Auto Scheduled | LifeCycle Tasks | 197 days | May 18, 2021 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
157 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
158 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
159 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | November 4, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 | 158 | 0h | 01.01.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
160 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 9, 2021 8:00 AM | January 12, 2022 5:00 PM | 0 | 159 | 25h | 01.01.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
161 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 13, 2022 8:00 AM | January 26, 2022 5:00 PM | 0 | 160 | 10h | 01.01.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
162 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 27, 2022 8:00 AM | February 9, 2022 5:00 PM | 0 | 161 | 10h | 01.01.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
163 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 10, 2022 8:00 AM | February 16, 2022 5:00 PM | 0 | 162 | 5h | 01.01.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
164 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | February 16, 2022 5:00 PM | February 16, 2022 5:00 PM | 0 | 163,157 | 0h | 01.01.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
165 |  | Auto Scheduled | מערכת WMS תשלח שדר למערכת SAP עם נתוני קבלות למלאי. - INT | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
166 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
167 |  | Auto Scheduled | LifeCycle Tasks | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
168 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
169 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
170 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 10, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 169 | 0h | 01.01.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
171 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 14, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 170 | 25h | 01.01.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
172 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 18, 2022 8:00 AM | March 3, 2022 5:00 PM | 0 | 171 | 10h | 01.01.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
173 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 4, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 172 | 10h | 01.01.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
174 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 18, 2022 8:00 AM | March 24, 2022 5:00 PM | 0 | 173 | 5h | 01.01.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
175 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 24, 2022 5:00 PM | March 24, 2022 5:00 PM | 0 | 174,168 | 0h | 01.01.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
176 |  | Auto Scheduled | מערכות SAP וWMS יאפשרו העברת שדרים עם נתוני הסדרות - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
177 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
178 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
179 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
180 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
181 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 17/11/2021 | 23/11/2021 | 0 | 180 | 0h | 01.01.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
182 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 181 | 25h | 01.01.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
183 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 182 | 10h | 01.01.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
184 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 183 | 10h | 01.01.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
185 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 184 | 5h | 01.01.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
186 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 185,179 | 0h | 01.01.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
187 |  | Auto Scheduled | מערכות WMS וSAP יאפשרו העברת שדרים ע"ב אספקה נכנסת כולל הפרטים שיוזנו במערכת SAP. - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
188 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
189 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
190 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
191 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
192 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | July 9, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 191 | 0h | 01.01.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
193 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 13, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 192 | 25h | 01.01.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
194 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 17, 2021 8:00 AM | September 30, 2021 5:00 PM | 0 | 193 | 10h | 01.01.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
195 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 1, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 194 | 10h | 01.01.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
196 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 15, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 | 195 | 5h | 01.01.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
197 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 196,190 | 0h | 01.01.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
198 |  | Auto Scheduled | מערכות WMS וSAP יאפשרו העברת שדרים לקליטת צ'/מס"דים לאחר שינוי הסטאטוס מבירור כך שהמלאי בSAP יעודכן. - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
199 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
200 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
201 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.07.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
202 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.07.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
203 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 24/11/2021 | 21/12/2021 | 0 | 202 | 0h | 01.01.INT.07.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
204 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 203 | 25h | 01.01.INT.07.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
205 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 204 | 10h | 01.01.INT.07.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
206 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 205 | 10h | 01.01.INT.07.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
207 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 206 | 5h | 01.01.INT.07.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
208 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 207,201 | 0h | 01.01.INT.07.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
209 |  | Auto Scheduled | מערכת WMS תשלח שדר לעדכון אספקה נכנסת בSAP - INT | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
210 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
211 |  | Auto Scheduled | LifeCycle Tasks | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
212 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.08.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
213 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.08.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
214 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 29, 2021 8:00 AM | February 1, 2022 5:00 PM | 0 | 213 | 0h | 01.01.INT.08.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
215 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 2, 2022 8:00 AM | March 8, 2022 5:00 PM | 0 | 214 | 25h | 01.01.INT.08.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
216 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 9, 2022 8:00 AM | March 22, 2022 5:00 PM | 0 | 215 | 10h | 01.01.INT.08.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
217 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 23, 2022 8:00 AM | April 5, 2022 5:00 PM | 0 | 216 | 10h | 01.01.INT.08.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
218 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 6, 2022 8:00 AM | April 12, 2022 5:00 PM | 0 | 217 | 5h | 01.01.INT.08.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
219 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 218,212 | 0h | 01.01.INT.08.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
220 |  | Auto Scheduled | מערכת SAP תשלח חיווי האם האספקה עם הצ'/מסדים שנוספו תקינים - INT | 409 days | May 18, 2021 8:00 AM | December 9, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
221 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
222 |  | Auto Scheduled | LifeCycle Tasks | 409 days | May 18, 2021 8:00 AM | December 9, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
223 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.09.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
224 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.09.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
225 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 30, 2022 8:00 AM | October 1, 2022 5:00 PM | 0 | 224 | 0h | 01.01.INT.09.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
226 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 3, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 225 | 25h | 01.01.INT.09.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
227 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 7, 2022 8:00 AM | November 18, 2022 5:00 PM | 0 | 226 | 10h | 01.01.INT.09.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
228 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 21, 2022 8:00 AM | December 2, 2022 5:00 PM | 0 | 227 | 10h | 01.01.INT.09.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
229 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 5, 2022 8:00 AM | December 9, 2022 5:00 PM | 0 | 228 | 5h | 01.01.INT.09.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
230 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | December 9, 2022 5:00 PM | December 9, 2022 5:00 PM | 0 | 229,223 | 0h | 01.01.INT.09.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
231 |  | Auto Scheduled | מערכת SAP תעביר למערכת WMS את האינד' לפריט דרוש בחינה בקטלוג/דרוש בחינה לאחר קבלה דרך הנתונים הקטלוגיים - INT | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 70h | 01.01.INT.10 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
232 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
233 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 70h | 01.01.INT.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
234 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.10.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
235 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.10.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
236 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 1, 2022 8:00 AM | January 4, 2023 5:00 PM | 0 | 235 | 0h | 01.01.INT.10.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
237 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 5, 2023 8:00 AM | February 8, 2023 5:00 PM | 0 | 236 | 25h | 01.01.INT.10.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
238 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 9, 2023 8:00 AM | February 22, 2023 5:00 PM | 0 | 237 | 10h | 01.01.INT.10.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
239 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 23, 2023 8:00 AM | March 8, 2023 5:00 PM | 0 | 238 | 10h | 01.01.INT.10.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
240 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 9, 2023 8:00 AM | March 15, 2023 5:00 PM | 0 | 239 | 5h | 01.01.INT.10.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
241 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 240,234 | 0h | 01.01.INT.10.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
242 |  | Auto Scheduled | מערכת SAP תעביר למערכת WMS את נתוני הבחינה - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.11 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
243 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
244 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
245 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.11.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
246 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.11.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
247 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 23/01/2022 | 14/02/2022 | 0 | 246 | 0h | 01.01.INT.11.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
248 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 247 | 25h | 01.01.INT.11.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
249 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 248 | 10h | 01.01.INT.11.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
250 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 249 | 10h | 01.01.INT.11.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
251 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 250 | 5h | 01.01.INT.11.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
252 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 251,245 | 0h | 01.01.INT.11.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
253 |  | Auto Scheduled | מערכת WMS תעביר למערכת SAP את סטאטוס המלאים שטרם עברו בחינה לאחר קבלה/ מלאים שאוחסנו למרות שלא עברו בחינה זו - INT | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.12 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
254 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
255 |  | Auto Scheduled | LifeCycle Tasks | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 01.01.INT.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
256 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.12.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
257 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.12.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
258 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 1, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 257 | 0h | 01.01.INT.12.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
259 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 5, 2022 8:00 AM | October 7, 2022 5:00 PM | 0 | 258 | 25h | 01.01.INT.12.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
260 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 10, 2022 8:00 AM | October 21, 2022 5:00 PM | 0 | 259 | 10h | 01.01.INT.12.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
261 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 24, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 260 | 10h | 01.01.INT.12.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
262 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 0 | 261 | 5h | 01.01.INT.12.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
263 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | November 11, 2022 5:00 PM | November 11, 2022 5:00 PM | 0 | 262,256 | 0h | 01.01.INT.12.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
264 |  | Auto Scheduled | נדרש שיהיה ממשק בין נתוני נפח ומשקל בשלב הראשוני מSAP ,משלב המבצוע הדרגגתי WMS יעדכן את ה SAP(SAP יעדכו את 3 המרחבים) - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.13 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
265 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
266 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
267 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.13.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
268 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.13.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
269 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 17/02/2022 | 24/02/2022 | 0 | 268 | 0h | 01.01.INT.13.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
270 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 269 | 25h | 01.01.INT.13.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
271 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 270 | 10h | 01.01.INT.13.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
272 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 271 | 10h | 01.01.INT.13.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
273 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 272 | 5h | 01.01.INT.13.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
274 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 273,267 | 0h | 01.01.INT.13.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
275 |  | Auto Scheduled | בעת הקבלה למלאי מסימול חוץ ובאם לא נמצא מלאי בסימול החוץ נדרש לבטל את הקבלה בSAP ולהעביר את הפרטים לסטאטוס לבירור בWMS - INT | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.14 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
276 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
277 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.INT.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
278 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.INT.14.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
279 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.INT.14.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
280 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 28/02/2022 | 14/03/2022 | 0 | 279 | 0h | 01.01.INT.14.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
281 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 280 | 25h | 01.01.INT.14.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
282 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 281 | 10h | 01.01.INT.14.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
283 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 282 | 10h | 01.01.INT.14.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
284 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 283 | 5h | 01.01.INT.14.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
285 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 284,278 | 0h | 01.01.INT.14.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
286 |  | Auto Scheduled | 01.01: קבלה מרכש.SAP | 568 days | December 8, 2020 8:00 AM | February 9, 2023 5:00 PM | 0 |  | 1,960h | 01.01.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
287 |  | Auto Scheduled | מערכת SAP תאפשר המשך ביצוע תהליכי קבלה מרכש עבור מחסנים מיוחדים בתפעול SAP. - SAP | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
288 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
289 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
290 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
291 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
292 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 5, 2021 8:00 AM | July 8, 2021 5:00 PM | 0 | 291 | 0h | 01.01.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
293 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 9, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 292 | 25h | 01.01.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
294 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 13, 2021 8:00 AM | August 26, 2021 5:00 PM | 0 | 293 | 10h | 01.01.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
295 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 27, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 294 | 10h | 01.01.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
296 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 10, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 295 | 5h | 01.01.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
297 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 16, 2021 5:00 PM | September 16, 2021 5:00 PM | 0 | 296,290 | 0h | 01.01.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
298 |  | Auto Scheduled | מערכת SAP תיצור ישויות של אספקה נכנסת ומשלוח אל מול אתר אחסון רלוונטי לכושר - SAP | 152 days | May 18, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
299 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
300 |  | Auto Scheduled | LifeCycle Tasks | 152 days | May 18, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
301 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
302 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
303 |  | Manually Scheduled | יישום ופיתוח סאפ | 89 days | June 6, 2021 8:00 AM | October 6, 2021 5:00 PM | 0 | 302 | 0h | 01.01.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
304 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 7, 2021 8:00 AM | November 10, 2021 5:00 PM | 0 | 303 | 25h | 01.01.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
305 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 11, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 304 | 10h | 01.01.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
306 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 25, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 | 305 | 10h | 01.01.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
307 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 9, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 306 | 5h | 01.01.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
308 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 15, 2021 5:00 PM | December 15, 2021 5:00 PM | 0 | 307,301 | 0h | 01.01.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
309 |  | Auto Scheduled | מערכת SAP תאפשר זיכוי מלאי בהזמנת רכש בSAP בהנחה שהאספקה הנכנסת תבוטל באופן ידני ע"י המשתמש. - SAP | 125 days | May 8, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
310 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
311 |  | Auto Scheduled | LifeCycle Tasks | 125 days | May 8, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
312 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
313 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
314 |  | Manually Scheduled | יישום ופיתוח סאפ | 67 days | May 8, 2021 8:00 AM | August 8, 2021 5:00 PM | 0 | 313 | 0h | 01.01.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
315 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 9, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 314 | 25h | 01.01.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
316 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 13, 2021 8:00 AM | September 24, 2021 5:00 PM | 0 | 315 | 10h | 01.01.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
317 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 27, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 316 | 10h | 01.01.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
318 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 11, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 317 | 5h | 01.01.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
319 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 15, 2021 5:00 PM | October 15, 2021 5:00 PM | 0 | 318,312 | 0h | 01.01.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
320 |  | Auto Scheduled | מערכת SAP תסגור אספקות אל מול הכמות שהגיעה בפועל ויתרת המלאי תחזור להזמנה באופן אוטומטי - SAP | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
321 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
322 |  | Auto Scheduled | LifeCycle Tasks | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
323 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
324 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
325 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 8, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 324 | 0h | 01.01.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
326 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 325 | 25h | 01.01.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
327 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 326 | 10h | 01.01.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
328 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 327 | 10h | 01.01.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
329 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 328 | 5h | 01.01.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
330 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 329,323 | 0h | 01.01.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
331 |  | Auto Scheduled | מערכת SAP תאפשר המשך ביצוע תהליך ההחזרות בשני הסוגים עבור מחסנים מיוחדים בתפעול SAP. - SAP | 234 days | December 8, 2020 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
332 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
333 |  | Auto Scheduled | LifeCycle Tasks | 234 days | December 8, 2020 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
334 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
335 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
336 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | December 8, 2020 8:00 AM | January 9, 2021 5:00 PM | 0 | 335 | 0h | 01.01.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
337 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 11, 2021 8:00 AM | February 12, 2021 5:00 PM | 0 | 336 | 25h | 01.01.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
338 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 15, 2021 8:00 AM | February 26, 2021 5:00 PM | 0 | 337 | 10h | 01.01.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
339 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 1, 2021 8:00 AM | March 12, 2021 5:00 PM | 0 | 338 | 10h | 01.01.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
340 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 15, 2021 8:00 AM | March 19, 2021 5:00 PM | 0 | 339 | 5h | 01.01.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
341 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 340,334 | 0h | 01.01.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
342 |  | Auto Scheduled | מערכת SAP תאפשר זיכוי מלאי בהזמנת רכש בSAP בהנחה שהאספקה הנכנסת תבוטל באופן ידני ע"י המשתמש. לוודא כי תהליך SAP STANDARD תומך. - SAP | 145 days | April 10, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
343 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
344 |  | Auto Scheduled | LifeCycle Tasks | 145 days | April 10, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
345 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
346 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
347 |  | Manually Scheduled | יישום ופיתוח סאפ | 22 days | April 10, 2021 8:00 AM | May 10, 2021 5:00 PM | 0 | 346 | 0h | 01.01.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
348 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 11, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 347 | 25h | 01.01.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
349 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 348 | 10h | 01.01.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
350 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 349 | 10h | 01.01.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
351 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 13, 2021 8:00 AM | July 19, 2021 5:00 PM | 0 | 350 | 5h | 01.01.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
352 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 19, 2021 5:00 PM | July 19, 2021 5:00 PM | 0 | 351,345 | 0h | 01.01.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
353 |  | Auto Scheduled | עבור מחסנים מיוחדים מנוהלים SAP התהליך ימשיך לעבוד כפי שקיים היום. - SAP | 125 days | May 10, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
354 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
355 |  | Auto Scheduled | LifeCycle Tasks | 125 days | May 10, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
356 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
357 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
358 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 357 | 0h | 01.01.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
359 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 14, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 358 | 25h | 01.01.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
360 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 19, 2021 8:00 AM | July 30, 2021 5:00 PM | 0 | 359 | 10h | 01.01.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
361 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 2, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 360 | 10h | 01.01.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
362 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 16, 2021 8:00 AM | August 20, 2021 5:00 PM | 0 | 361 | 5h | 01.01.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
363 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 20, 2021 5:00 PM | August 20, 2021 5:00 PM | 0 | 362,356 | 0h | 01.01.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
364 |  | Auto Scheduled | מערכת SAP תאפשר בדיקת חוקות המלאי בשלב אספקה נכנסת במקום החוקות הקיימות בשלב הקבלה למלאי לדוגמא איזה מלאי נכנס לכל סוג כושר בקבלה מרכש. - SAP | 167 days | March 11, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
365 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
366 |  | Auto Scheduled | LifeCycle Tasks | 167 days | March 11, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
367 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
368 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
369 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 11, 2021 8:00 AM | April 14, 2021 5:00 PM | 0 | 368 | 0h | 01.01.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
370 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 15, 2021 8:00 AM | May 19, 2021 5:00 PM | 0 | 369 | 25h | 01.01.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
371 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 20, 2021 8:00 AM | June 2, 2021 5:00 PM | 0 | 370 | 10h | 01.01.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
372 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 3, 2021 8:00 AM | June 16, 2021 5:00 PM | 0 | 371 | 10h | 01.01.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
373 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 17, 2021 8:00 AM | June 23, 2021 5:00 PM | 0 | 372 | 5h | 01.01.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
374 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 23, 2021 5:00 PM | June 23, 2021 5:00 PM | 0 | 373,367 | 0h | 01.01.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
375 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סדרות ידני או מנתונים שיגיעו בממשק ממערכת WMS - SAP | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
376 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
377 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
378 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
379 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
380 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 16/11/2021 | 23/11/2021 | 0 | 379 | 0h | 01.01.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
381 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 380 | 25h | 01.01.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
382 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 381 | 10h | 01.01.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
383 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 382 | 10h | 01.01.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
384 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 383 | 5h | 01.01.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
385 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 384,378 | 0h | 01.01.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
386 |  | Auto Scheduled | מערכת SAP תאפשר הזנת הצ' או מס"ד בשלב האספקה הנכנסת. - SAP | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
387 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
388 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
389 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
390 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
391 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 22/11/2021 | 23/11/2021 | 0 | 390 | 0h | 01.01.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
392 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 391 | 25h | 01.01.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
393 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 392 | 10h | 01.01.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
394 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 393 | 10h | 01.01.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
395 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 394 | 5h | 01.01.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
396 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 395,389 | 0h | 01.01.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
397 |  | Auto Scheduled | מערכת SAP תאפשר ביצוע פעולות עבור מלאים בסטאטוס "בירור" . - SAP | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
398 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
399 |  | Auto Scheduled | LifeCycle Tasks | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
400 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
401 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
402 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 12, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 401 | 0h | 01.01.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
403 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 15, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 402 | 25h | 01.01.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
404 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 19, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 403 | 10h | 01.01.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
405 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 3, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 404 | 10h | 01.01.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
406 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 17, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 405 | 5h | 01.01.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
407 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 406,400 | 0h | 01.01.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
408 |  | Auto Scheduled | מערכת SAP לא תשדר למערכת הWMS סוגי הזמנות ש"י - SAP | 431 days | May 18, 2021 8:00 AM | January 10, 2023 5:00 PM | 0 |  | 70h | 01.01.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
409 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
410 |  | Auto Scheduled | LifeCycle Tasks | 431 days | May 18, 2021 8:00 AM | January 10, 2023 5:00 PM | 0 |  | 70h | 01.01.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
411 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
412 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
413 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 28, 2022 8:00 AM | November 1, 2022 5:00 PM | 0 | 412 | 0h | 01.01.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
414 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 2, 2022 8:00 AM | December 6, 2022 5:00 PM | 0 | 413 | 25h | 01.01.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
415 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 7, 2022 8:00 AM | December 20, 2022 5:00 PM | 0 | 414 | 10h | 01.01.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
416 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 21, 2022 8:00 AM | January 3, 2023 5:00 PM | 0 | 415 | 10h | 01.01.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
417 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 4, 2023 8:00 AM | January 10, 2023 5:00 PM | 0 | 416 | 5h | 01.01.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
418 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 10, 2023 5:00 PM | January 10, 2023 5:00 PM | 0 | 417,411 | 0h | 01.01.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
419 |  | Auto Scheduled | מערכת SAP תאפשר מתן אינדיקציה לפריט דרוש בחינה בקטלוג - SAP | 280 days | May 18, 2021 8:00 AM | June 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
420 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
421 |  | Auto Scheduled | LifeCycle Tasks | 280 days | May 18, 2021 8:00 AM | June 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
422 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
423 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
424 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 1, 2022 8:00 AM | April 4, 2022 5:00 PM | 0 | 423 | 0h | 01.01.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
425 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 5, 2022 8:00 AM | May 9, 2022 5:00 PM | 0 | 424 | 25h | 01.01.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
426 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 10, 2022 8:00 AM | May 23, 2022 5:00 PM | 0 | 425 | 10h | 01.01.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
427 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 24, 2022 8:00 AM | June 6, 2022 5:00 PM | 0 | 426 | 10h | 01.01.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
428 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 7, 2022 8:00 AM | June 13, 2022 5:00 PM | 0 | 427 | 5h | 01.01.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
429 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 13, 2022 5:00 PM | June 13, 2022 5:00 PM | 0 | 428,422 | 0h | 01.01.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
430 |  | Auto Scheduled | מערכת SAP תאפשר מתן אינדיקציה לפריט דרוש בחינה לאחר קבלה - SAP | 453 days | May 18, 2021 8:00 AM | February 9, 2023 5:00 PM | 0 |  | 70h | 01.01.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
431 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
432 |  | Auto Scheduled | LifeCycle Tasks | 453 days | May 18, 2021 8:00 AM | February 9, 2023 5:00 PM | 0 |  | 70h | 01.01.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
433 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
434 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
435 |  | Manually Scheduled | יישום ופיתוח סאפ | 23 days | November 1, 2022 8:00 AM | December 1, 2022 5:00 PM | 0 | 434 | 0h | 01.01.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
436 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 2, 2022 8:00 AM | January 5, 2023 5:00 PM | 0 | 435 | 25h | 01.01.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
437 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 6, 2023 8:00 AM | January 19, 2023 5:00 PM | 0 | 436 | 10h | 01.01.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
438 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 20, 2023 8:00 AM | February 2, 2023 5:00 PM | 0 | 437 | 10h | 01.01.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
439 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 3, 2023 8:00 AM | February 9, 2023 5:00 PM | 0 | 438 | 5h | 01.01.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
440 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 9, 2023 5:00 PM | February 9, 2023 5:00 PM | 0 | 439,433 | 0h | 01.01.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
441 |  | Auto Scheduled | מערכת SAP נדרשת לתת מענה לדיווח תהליך הבחינות. - SAP | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
442 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
443 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
444 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
445 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
446 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 13/01/2022 | 20/01/2022 | 0 | 445 | 0h | 01.01.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
447 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 446 | 25h | 01.01.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
448 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 447 | 10h | 01.01.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
449 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 448 | 10h | 01.01.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
450 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 449 | 5h | 01.01.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
451 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 450,444 | 0h | 01.01.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
452 |  | Auto Scheduled | מערכת SAP תאפשר באספקה נכנסת להציג אינ' לצורך לביצוע בחינה/סטאטוס הבחינה עבור פריט שתתקבל בממשק ממע' תב"ל או מע' חלופית שתפותח לצורך מתן מענה. - SAP | 344 days | May 18, 2021 8:00 AM | September 9, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.16 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
453 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
454 |  | Auto Scheduled | LifeCycle Tasks | 344 days | May 18, 2021 8:00 AM | September 9, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
455 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.16.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
456 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.16.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
457 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 31, 2022 8:00 AM | July 2, 2022 5:00 PM | 0 | 456 | 0h | 01.01.SAP.16.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
458 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 4, 2022 8:00 AM | August 5, 2022 5:00 PM | 0 | 457 | 25h | 01.01.SAP.16.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
459 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 8, 2022 8:00 AM | August 19, 2022 5:00 PM | 0 | 458 | 10h | 01.01.SAP.16.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
460 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 459 | 10h | 01.01.SAP.16.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
461 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 5, 2022 8:00 AM | September 9, 2022 5:00 PM | 0 | 460 | 5h | 01.01.SAP.16.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
462 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 9, 2022 5:00 PM | September 9, 2022 5:00 PM | 0 | 461,455 | 0h | 01.01.SAP.16.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
463 |  | Auto Scheduled | מערכת SAP תאפשר לסמן מלאים שטרם עברו בחינה לאחר קבלה / מלאים שאוחסנו למרות שלא עברו בחינה זו - SAP | 366 days | May 18, 2021 8:00 AM | October 11, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.17 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
464 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
465 |  | Auto Scheduled | LifeCycle Tasks | 366 days | May 18, 2021 8:00 AM | October 11, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
466 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.17.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
467 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.17.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
468 |  | Manually Scheduled | יישום ופיתוח סאפ | 153 days | January 2, 2022 8:00 AM | August 2, 2022 5:00 PM | 0 | 467 | 0h | 01.01.SAP.17.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
469 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 3, 2022 8:00 AM | September 6, 2022 5:00 PM | 0 | 468 | 25h | 01.01.SAP.17.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
470 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 7, 2022 8:00 AM | September 20, 2022 5:00 PM | 0 | 469 | 10h | 01.01.SAP.17.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
471 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 21, 2022 8:00 AM | October 4, 2022 5:00 PM | 0 | 470 | 10h | 01.01.SAP.17.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
472 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 5, 2022 8:00 AM | October 11, 2022 5:00 PM | 0 | 471 | 5h | 01.01.SAP.17.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
473 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 11, 2022 5:00 PM | October 11, 2022 5:00 PM | 0 | 472,466 | 0h | 01.01.SAP.17.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
474 |  | Auto Scheduled | מערכת SAP תאפשר לקבל החלטות שימוש מתאימות למלאי שטרם עבר בחינה לאחר קבלה - SAP | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.18 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
475 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.18.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
476 |  | Auto Scheduled | LifeCycle Tasks | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.18.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
477 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.18.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
478 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.18.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
479 |  | Manually Scheduled | יישום ופיתוח סאפ | 153 days | February 2, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 478 | 0h | 01.01.SAP.18.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
480 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 5, 2022 8:00 AM | October 7, 2022 5:00 PM | 0 | 479 | 25h | 01.01.SAP.18.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
481 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 10, 2022 8:00 AM | October 21, 2022 5:00 PM | 0 | 480 | 10h | 01.01.SAP.18.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
482 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 24, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 481 | 10h | 01.01.SAP.18.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
483 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 0 | 482 | 5h | 01.01.SAP.18.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
484 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 11, 2022 5:00 PM | November 11, 2022 5:00 PM | 0 | 483,477 | 0h | 01.01.SAP.18.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
485 |  | Auto Scheduled | מערכת SAP תאפשר ניהול מעקב וטיפול אחר הקבלות/ ההפרשים בדו"ח ZMDD - SAP | 281 days | May 18, 2021 8:00 AM | June 14, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.19 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
486 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.19.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
487 |  | Auto Scheduled | LifeCycle Tasks | 281 days | May 18, 2021 8:00 AM | June 14, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.19.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
488 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.19.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
489 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.19.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
490 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 2, 2022 8:00 AM | April 5, 2022 5:00 PM | 0 | 489 | 0h | 01.01.SAP.19.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
491 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 6, 2022 8:00 AM | May 10, 2022 5:00 PM | 0 | 490 | 25h | 01.01.SAP.19.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
492 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 11, 2022 8:00 AM | May 24, 2022 5:00 PM | 0 | 491 | 10h | 01.01.SAP.19.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
493 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 25, 2022 8:00 AM | June 7, 2022 5:00 PM | 0 | 492 | 10h | 01.01.SAP.19.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
494 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 8, 2022 8:00 AM | June 14, 2022 5:00 PM | 0 | 493 | 5h | 01.01.SAP.19.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
495 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 14, 2022 5:00 PM | June 14, 2022 5:00 PM | 0 | 494,488 | 0h | 01.01.SAP.19.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
496 |  | Auto Scheduled | מערכת SAP תשמור את הקשר בין הזמנת המקור(מנה"ר) לבין ההזמנה החדשה - SAP | 368 days | May 18, 2021 8:00 AM | October 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.20 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
497 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.20.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
498 |  | Auto Scheduled | LifeCycle Tasks | 368 days | May 18, 2021 8:00 AM | October 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.20.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
499 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.20.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
500 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.20.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
501 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 2, 2022 8:00 AM | August 4, 2022 5:00 PM | 0 | 500 | 0h | 01.01.SAP.20.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
502 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 5, 2022 8:00 AM | September 8, 2022 5:00 PM | 0 | 501 | 25h | 01.01.SAP.20.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
503 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 9, 2022 8:00 AM | September 22, 2022 5:00 PM | 0 | 502 | 10h | 01.01.SAP.20.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
504 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 23, 2022 8:00 AM | October 6, 2022 5:00 PM | 0 | 503 | 10h | 01.01.SAP.20.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
505 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 7, 2022 8:00 AM | October 13, 2022 5:00 PM | 0 | 504 | 5h | 01.01.SAP.20.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
506 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 13, 2022 5:00 PM | October 13, 2022 5:00 PM | 0 | 505,499 | 0h | 01.01.SAP.20.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
507 |  | Auto Scheduled | נדרש לקבל אינדיקציה כי לא קיים מלאי בסימול חוץ/מש"א בתהליך האספקות במערכת SAP - SAP | 238 days | May 18, 2021 8:00 AM | April 14, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.21 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
508 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.21.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
509 |  | Auto Scheduled | LifeCycle Tasks | 238 days | May 18, 2021 8:00 AM | April 14, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.21.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
510 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.21.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
511 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.21.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
512 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | December 31, 2021 8:00 AM | February 3, 2022 5:00 PM | 0 | 511 | 0h | 01.01.SAP.21.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
513 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 4, 2022 8:00 AM | March 10, 2022 5:00 PM | 0 | 512 | 25h | 01.01.SAP.21.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
514 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 11, 2022 8:00 AM | March 24, 2022 5:00 PM | 0 | 513 | 10h | 01.01.SAP.21.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
515 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 25, 2022 8:00 AM | April 7, 2022 5:00 PM | 0 | 514 | 10h | 01.01.SAP.21.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
516 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 8, 2022 8:00 AM | April 14, 2022 5:00 PM | 0 | 515 | 5h | 01.01.SAP.21.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
517 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | April 14, 2022 5:00 PM | April 14, 2022 5:00 PM | 0 | 516,510 | 0h | 01.01.SAP.21.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
518 |  | Auto Scheduled | בסוג אספקה של סימולי חוץ/מש"א נדרש להגדיר בסיבה לתועה את סימול החוץ במערכת SAP - SAP | 344 days | May 18, 2021 8:00 AM | September 9, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.22 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
519 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.22.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
520 |  | Auto Scheduled | LifeCycle Tasks | 344 days | May 18, 2021 8:00 AM | September 9, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.22.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
521 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.22.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
522 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.22.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
523 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 31, 2022 8:00 AM | July 3, 2022 5:00 PM | 0 | 522 | 0h | 01.01.SAP.22.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
524 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 4, 2022 8:00 AM | August 5, 2022 5:00 PM | 0 | 523 | 25h | 01.01.SAP.22.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
525 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 8, 2022 8:00 AM | August 19, 2022 5:00 PM | 0 | 524 | 10h | 01.01.SAP.22.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
526 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 525 | 10h | 01.01.SAP.22.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
527 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 5, 2022 8:00 AM | September 9, 2022 5:00 PM | 0 | 526 | 5h | 01.01.SAP.22.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
528 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 9, 2022 5:00 PM | September 9, 2022 5:00 PM | 0 | 527,521 | 0h | 01.01.SAP.22.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
529 |  | Auto Scheduled | יאוחסן בכושר 1 במערכת ה SAP - SAP | 368 days | May 18, 2021 8:00 AM | October 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.23 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
530 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.23.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
531 |  | Auto Scheduled | LifeCycle Tasks | 368 days | May 18, 2021 8:00 AM | October 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.23.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
532 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.23.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
533 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.23.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
534 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 3, 2022 8:00 AM | August 4, 2022 5:00 PM | 0 | 533 | 0h | 01.01.SAP.23.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
535 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 5, 2022 8:00 AM | September 8, 2022 5:00 PM | 0 | 534 | 25h | 01.01.SAP.23.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
536 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 9, 2022 8:00 AM | September 22, 2022 5:00 PM | 0 | 535 | 10h | 01.01.SAP.23.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
537 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 23, 2022 8:00 AM | October 6, 2022 5:00 PM | 0 | 536 | 10h | 01.01.SAP.23.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
538 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 7, 2022 8:00 AM | October 13, 2022 5:00 PM | 0 | 537 | 5h | 01.01.SAP.23.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
539 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 13, 2022 5:00 PM | October 13, 2022 5:00 PM | 0 | 538,532 | 0h | 01.01.SAP.23.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
540 |  | Auto Scheduled | נדרש עבור כלל המשקים - SAP | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.24 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
541 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.24.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
542 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.24.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
543 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.24.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
544 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.24.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
545 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 14/03/2022 | 30/03/2022 | 0 | 544 | 0h | 01.01.SAP.24.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
546 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 545 | 25h | 01.01.SAP.24.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
547 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 546 | 10h | 01.01.SAP.24.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
548 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 547 | 10h | 01.01.SAP.24.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
549 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 548 | 5h | 01.01.SAP.24.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
550 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 549,543 | 0h | 01.01.SAP.24.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
551 |  | Auto Scheduled | נדרשת אינדיקציה (באספקה נכנסת ) האם נדרש קבלה מרכש ( למלאי) למחסן מנוהל צבאי/ מנהול זכיין - SAP | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.25 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
552 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.25.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
553 |  | Auto Scheduled | LifeCycle Tasks | 119 days | May 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 |  | 70h | 01.01.SAP.25.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
554 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.25.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
555 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.25.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
556 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 22/03/2022 | 29/03/2022 | 0 | 555 | 0h | 01.01.SAP.25.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
557 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 556 | 25h | 01.01.SAP.25.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
558 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 557 | 10h | 01.01.SAP.25.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
559 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 558 | 10h | 01.01.SAP.25.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
560 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 559 | 5h | 01.01.SAP.25.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
561 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 560,554 | 0h | 01.01.SAP.25.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
562 |  | Auto Scheduled | נדרשת אינדיקציה (באספקה נכנסת ) האם המטען הגיע ונמצא במחסני הזכיין ( לא נכנס למלאי) - SAP | 302 days | May 18, 2021 8:00 AM | July 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.26 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
563 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.26.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
564 |  | Auto Scheduled | LifeCycle Tasks | 302 days | May 18, 2021 8:00 AM | July 13, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.26.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
565 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.26.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
566 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.26.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
567 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 31, 2022 8:00 AM | May 4, 2022 5:00 PM | 0 | 566 | 0h | 01.01.SAP.26.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
568 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 5, 2022 8:00 AM | June 8, 2022 5:00 PM | 0 | 567 | 25h | 01.01.SAP.26.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
569 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 9, 2022 8:00 AM | June 22, 2022 5:00 PM | 0 | 568 | 10h | 01.01.SAP.26.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
570 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 23, 2022 8:00 AM | July 6, 2022 5:00 PM | 0 | 569 | 10h | 01.01.SAP.26.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
571 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 7, 2022 8:00 AM | July 13, 2022 5:00 PM | 0 | 570 | 5h | 01.01.SAP.26.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
572 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 13, 2022 5:00 PM | July 13, 2022 5:00 PM | 0 | 571,565 | 0h | 01.01.SAP.26.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
573 |  | Auto Scheduled | נדרשת אינדיקציה (באספקה נכנסת ) האם נדרש קליטה למלאי - SAP | 434 days | May 18, 2021 8:00 AM | January 13, 2023 5:00 PM | 0 |  | 70h | 01.01.SAP.27 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
574 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.27.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
575 |  | Auto Scheduled | LifeCycle Tasks | 434 days | May 18, 2021 8:00 AM | January 13, 2023 5:00 PM | 0 |  | 70h | 01.01.SAP.27.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
576 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.27.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
577 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.27.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
578 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | October 3, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 577 | 0h | 01.01.SAP.27.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
579 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 7, 2022 8:00 AM | December 9, 2022 5:00 PM | 0 | 578 | 25h | 01.01.SAP.27.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
580 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 12, 2022 8:00 AM | December 23, 2022 5:00 PM | 0 | 579 | 10h | 01.01.SAP.27.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
581 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 26, 2022 8:00 AM | January 6, 2023 5:00 PM | 0 | 580 | 10h | 01.01.SAP.27.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
582 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 9, 2023 8:00 AM | January 13, 2023 5:00 PM | 0 | 581 | 5h | 01.01.SAP.27.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
583 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 13, 2023 5:00 PM | January 13, 2023 5:00 PM | 0 | 582,576 | 0h | 01.01.SAP.27.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
584 |  | Auto Scheduled | נדרש כי יוקם מק"ט גנרי (כגון מכולה) - SAP | 348 days | May 18, 2021 8:00 AM | September 15, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.28 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
585 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.28.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
586 |  | Auto Scheduled | LifeCycle Tasks | 348 days | May 18, 2021 8:00 AM | September 15, 2022 5:00 PM | 0 |  | 70h | 01.01.SAP.28.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
587 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.01.SAP.28.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
588 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 4, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 30 | 20h | 01.01.SAP.28.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
589 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 3, 2022 8:00 AM | July 7, 2022 5:00 PM | 0 | 588 | 0h | 01.01.SAP.28.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
590 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM | 0 | 589 | 25h | 01.01.SAP.28.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
591 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 12, 2022 8:00 AM | August 25, 2022 5:00 PM | 0 | 590 | 10h | 01.01.SAP.28.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
592 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 26, 2022 8:00 AM | September 8, 2022 5:00 PM | 0 | 591 | 10h | 01.01.SAP.28.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
593 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 9, 2022 8:00 AM | September 15, 2022 5:00 PM | 0 | 592 | 5h | 01.01.SAP.28.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
594 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 15, 2022 5:00 PM | September 15, 2022 5:00 PM | 0 | 593,587 | 0h | 01.01.SAP.28.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
595 |  | Auto Scheduled | 01.02: ערכות | 792 days | February 3, 2020 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 2,820h | 01.02 | בחתימה | מאור | hd | מאור |  | BP | NA | As Soon As Possible | 3
596 |  | Auto Scheduled | 01.02: ערכות.BP | 190 days | May 18, 2021 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 230h | 01.02.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
597 |  | Auto Scheduled | 01.02: ערכות - BP | 190 days | May 18, 2021 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 230h | 01.02.BP.01 | בחתימה | מאור | parent | מאור |  | BP | NA | As Soon As Possible | 5
598 |  | Auto Scheduled | Sub Tasks | 190 days | May 18, 2021 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 190h | 01.02.BP.01.01 |  | מאור | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
599 |  | Auto Scheduled | כתיבת מסמך | 76 days | May 18, 2021 8:00 AM | August 31, 2021 5:00 PM | 0 |  | 76h | 01.02.BP.01.01.20 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | Must Start On | 7
600 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 32 days | September 1, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 599 | 32h | 01.02.BP.01.01.21 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
601 |  | Auto Scheduled | אישור אבי | 51 days | October 15, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 600 | 51h | 01.02.BP.01.01.22 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
602 |  | Auto Scheduled | אישור המנהלת | 2 days | December 27, 2021 8:00 AM | December 28, 2021 5:00 PM | 0 | 601 | 2h | 01.02.BP.01.01.23 | בוצע | סיגל | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
603 |  | Auto Scheduled | אישור מפקדת | 2 days | December 29, 2021 8:00 AM | December 30, 2021 5:00 PM | 0 | 602 | 2h | 01.02.BP.01.01.24 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
604 |  | Auto Scheduled | אישור מקל"ר | 2 days | December 31, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 603 | 2h | 01.02.BP.01.01.25 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
605 |  | Auto Scheduled | אישור שגיב שרביט | 2 days | January 4, 2022 8:00 AM | January 5, 2022 5:00 PM | 0 | 604 | 2h | 01.02.BP.01.01.26 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
606 |  | Auto Scheduled | אישור ניר בשן | 22 days | January 6, 2022 8:00 AM | February 4, 2022 5:00 PM | 0 | 605 | 22h | 01.02.BP.01.01.27 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
607 |  | Auto Scheduled | אישור חטלו"ג | 1 day | February 7, 2022 8:00 AM | February 7, 2022 5:00 PM | 0 | 606 | 1h | 01.02.BP.01.01.28 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
608 |  | Auto Scheduled | LifeCycle Tasks | 190 days | May 18, 2021 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 40h | 01.02.BP.01.02 |  | מאור | LC Tasks |  |  |  | NA | As Soon As Possible | 6
609 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | February 7, 2022 5:00 PM | February 7, 2022 5:00 PM | 0 | 607 | 0h | 01.02.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
610 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.02.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
611 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 610 | 10h | 01.02.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
612 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 611 | 5h | 01.02.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
613 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 612 | 10h | 01.02.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
614 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 613 | 10h | 01.02.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
615 |  | Auto Scheduled | בחתימה | 0 days | February 7, 2022 5:00 PM | February 7, 2022 5:00 PM | 0 | 614,609 | 0h | 01.02.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
616 |  | Auto Scheduled | חתום | 0 days | February 7, 2022 5:00 PM | February 7, 2022 5:00 PM | 0 | 615 | 0h | 01.02.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
617 |  | Auto Scheduled | 01.02: ערכות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 210h | 01.02.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
618 |  | Auto Scheduled | נדרש להגדיר מהם התנאים לסיום הרכבת ערכה- כיום תהליך סגירת הפק"ע עובד במיילים בין מחסני ההרכבה לנציג מדור ניהול המלאי - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.01 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
619 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
620 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
621 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
622 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 621 | 10h | 01.02.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
623 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 622 | 20h | 01.02.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
624 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 623,621 | 0h | 01.02.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
625 |  | Auto Scheduled | נדרש לבחון מהם השיקולים המתבצעים ע"י המחסנאים ברצפת הייצור לצורך הכנסת פריטים לערכה (לפי פג"ת קרוב, לפי מק"ט תחליפי, לפי הומוגניות בתכולת הערכה וכו') - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
626 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
627 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
628 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
629 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 628 | 10h | 01.02.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
630 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 629 | 20h | 01.02.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
631 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 630,628 | 0h | 01.02.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
632 |  | Auto Scheduled | נדרש להגדיר תהליך מסודר לבחינת ערכות החוזרות מיחידות בעידן הזכיין - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.04 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
633 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
634 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
635 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
636 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 635 | 10h | 01.02.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
637 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 636 | 20h | 01.02.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
638 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 637,635 | 0h | 01.02.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
639 |  | Auto Scheduled | נדרש להגדיר תהליך בחינה מסודר לכלל הערכות הדורשות בחינה בעת קבלתן למלאי WMS - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.05 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
640 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
641 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
642 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
643 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 642 | 10h | 01.02.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
644 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 643 | 20h | 01.02.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
645 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 644,642 | 0h | 01.02.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
646 |  | Auto Scheduled | נדרש להגדיר תהליך או"שי לטיפול בשגויים בתהליך פירוק ערכות בWMS - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.06 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
647 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
648 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
649 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
650 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 649 | 10h | 01.02.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
651 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 650 | 20h | 01.02.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
652 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 651,649 | 0h | 01.02.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
653 |  | Auto Scheduled | נדרש להגדיר תהליך או"שי לטיפול בהפרשים בתהליך פירוק ערכות בWMS - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.07 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
654 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
655 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
656 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
657 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 656 | 10h | 01.02.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
658 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 657 | 20h | 01.02.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
659 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 658,656 | 0h | 01.02.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
660 |  | Auto Scheduled | נדרש להגדיר תהליך של קביעת סדרות אוטומטי (batch determination) לפריטי בנים של ערכות הנבנות בWMS - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.08 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
661 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
662 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.02.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
663 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
664 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 663 | 10h | 01.02.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
665 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 664 | 20h | 01.02.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
666 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 665,663 | 0h | 01.02.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
667 |  | Auto Scheduled | 01.02: ערכות.INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 700h | 01.02.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
668 |  | Auto Scheduled | מערכת הSAP תשלח את עצי המוצר הרלוונטים למערכת הזכיין (WMS) - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
669 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
670 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
671 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
672 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
673 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 6, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 672 | 0h | 01.02.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
674 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 673 | 25h | 01.02.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
675 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 674 | 10h | 01.02.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
676 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 675 | 10h | 01.02.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
677 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 676 | 5h | 01.02.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
678 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 677,671 | 0h | 01.02.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
679 |  | Auto Scheduled | מערכת SAP תאפשר יצירה ושידור פק"ע ייצור עבור תהליך ייצור ערכה ב WMS. - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
680 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
681 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
682 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
683 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
684 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | September 11, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 683 | 0h | 01.02.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
685 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 15, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 684 | 25h | 01.02.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
686 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 19, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 685 | 10h | 01.02.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
687 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 3, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 686 | 10h | 01.02.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
688 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 17, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 687 | 5h | 01.02.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
689 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 688,682 | 0h | 01.02.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
690 |  | Auto Scheduled | מערכת ה WMS תאפשר שליחת שדרים למערכת הSAP עבור ניפוק מלאי רכיבי הבנים לערכה - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
691 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
692 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
693 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
694 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
695 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | November 30, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 694 | 0h | 01.02.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
696 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 4, 2022 8:00 AM | February 7, 2022 5:00 PM | 0 | 695 | 25h | 01.02.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
697 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 8, 2022 8:00 AM | February 21, 2022 5:00 PM | 0 | 696 | 10h | 01.02.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
698 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 22, 2022 8:00 AM | March 7, 2022 5:00 PM | 0 | 697 | 10h | 01.02.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
699 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 8, 2022 8:00 AM | March 14, 2022 5:00 PM | 0 | 698 | 5h | 01.02.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
700 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 14, 2022 5:00 PM | March 14, 2022 5:00 PM | 0 | 699,693 | 0h | 01.02.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
701 |  | Auto Scheduled | מערכת ה WMS תאפשר שליחת שדרים למערכת הSAP עבור קבלה למלאי של ערכה מושלמת. - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
702 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
703 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
704 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
705 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
706 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 30, 2022 8:00 AM | October 3, 2022 5:00 PM | 0 | 705 | 0h | 01.02.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
707 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 4, 2022 8:00 AM | November 7, 2022 5:00 PM | 0 | 706 | 25h | 01.02.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
708 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 8, 2022 8:00 AM | November 21, 2022 5:00 PM | 0 | 707 | 10h | 01.02.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
709 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 22, 2022 8:00 AM | December 5, 2022 5:00 PM | 0 | 708 | 10h | 01.02.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
710 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 6, 2022 8:00 AM | December 12, 2022 5:00 PM | 0 | 709 | 5h | 01.02.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
711 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | December 12, 2022 5:00 PM | December 12, 2022 5:00 PM | 0 | 710,704 | 0h | 01.02.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
712 |  | Auto Scheduled | מערכת WMS תאפשר שליחת עדכון סטאטוס הפק"ע עם סיום בניית הערכה - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
713 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
714 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
715 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
716 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
717 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | March 3, 2022 8:00 AM | April 6, 2022 5:00 PM | 0 | 716 | 0h | 01.02.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
718 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 7, 2022 8:00 AM | May 11, 2022 5:00 PM | 0 | 717 | 25h | 01.02.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
719 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 12, 2022 8:00 AM | May 25, 2022 5:00 PM | 0 | 718 | 10h | 01.02.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
720 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 26, 2022 8:00 AM | June 8, 2022 5:00 PM | 0 | 719 | 10h | 01.02.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
721 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 9, 2022 8:00 AM | June 15, 2022 5:00 PM | 0 | 720 | 5h | 01.02.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
722 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | June 15, 2022 5:00 PM | June 15, 2022 5:00 PM | 0 | 721,715 | 0h | 01.02.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
723 |  | Auto Scheduled | מערכת ה WMS תאפשר פתיחת משימה של הוצאה\הכנסה של רכיבים לערכה קיימת במלאי - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
724 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
725 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
726 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
727 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
728 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 133 days | May 4, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 727 | 0h | 01.02.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
729 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 7, 2022 8:00 AM | December 9, 2022 5:00 PM | 0 | 728 | 25h | 01.02.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
730 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 12, 2022 8:00 AM | December 23, 2022 5:00 PM | 0 | 729 | 10h | 01.02.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
731 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 26, 2022 8:00 AM | January 6, 2023 5:00 PM | 0 | 730 | 10h | 01.02.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
732 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 9, 2023 8:00 AM | January 13, 2023 5:00 PM | 0 | 731 | 5h | 01.02.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
733 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 13, 2023 5:00 PM | January 13, 2023 5:00 PM | 0 | 732,726 | 0h | 01.02.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
734 |  | Auto Scheduled | מערכת ה WMS תאפשר שליחת שדר חיווי עבור פעולת הוצאה\הכנסה של רכיב לערכה קיימת - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
735 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
736 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
737 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.07.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
738 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.07.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
739 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | May 4, 2022 8:00 AM | June 7, 2022 5:00 PM | 0 | 738 | 0h | 01.02.INT.07.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
740 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 8, 2022 8:00 AM | July 12, 2022 5:00 PM | 0 | 739 | 25h | 01.02.INT.07.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
741 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 13, 2022 8:00 AM | July 26, 2022 5:00 PM | 0 | 740 | 10h | 01.02.INT.07.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
742 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 27, 2022 8:00 AM | August 9, 2022 5:00 PM | 0 | 741 | 10h | 01.02.INT.07.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
743 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 10, 2022 8:00 AM | August 16, 2022 5:00 PM | 0 | 742 | 5h | 01.02.INT.07.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
744 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 16, 2022 5:00 PM | August 16, 2022 5:00 PM | 0 | 743,737 | 0h | 01.02.INT.07.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
745 |  | Auto Scheduled | מערכת SAP תדע לשדר לWMS נתוני פק"ע לפירוק לטובת פירוק ערכות בWMS - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
746 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
747 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
748 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.08.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
749 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.08.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
750 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | February 2, 2022 8:00 AM | March 8, 2022 5:00 PM | 0 | 749 | 0h | 01.02.INT.08.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
751 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 9, 2022 8:00 AM | April 12, 2022 5:00 PM | 0 | 750 | 25h | 01.02.INT.08.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
752 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 13, 2022 8:00 AM | April 26, 2022 5:00 PM | 0 | 751 | 10h | 01.02.INT.08.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
753 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 27, 2022 8:00 AM | May 10, 2022 5:00 PM | 0 | 752 | 10h | 01.02.INT.08.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
754 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 11, 2022 8:00 AM | May 17, 2022 5:00 PM | 0 | 753 | 5h | 01.02.INT.08.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
755 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 17, 2022 5:00 PM | May 17, 2022 5:00 PM | 0 | 754,748 | 0h | 01.02.INT.08.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
756 |  | Auto Scheduled | מערכתWMS תדע לשדר לSAP על קבלת פריטים למלאי המחסן מערכות המפורקות בWMS - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
757 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
758 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
759 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.09.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
760 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.09.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
761 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | October 5, 2022 8:00 AM | November 8, 2022 5:00 PM | 0 | 760 | 0h | 01.02.INT.09.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
762 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 9, 2022 8:00 AM | December 13, 2022 5:00 PM | 0 | 761 | 25h | 01.02.INT.09.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
763 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 14, 2022 8:00 AM | December 27, 2022 5:00 PM | 0 | 762 | 10h | 01.02.INT.09.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
764 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 28, 2022 8:00 AM | January 10, 2023 5:00 PM | 0 | 763 | 10h | 01.02.INT.09.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
765 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 11, 2023 8:00 AM | January 17, 2023 5:00 PM | 0 | 764 | 5h | 01.02.INT.09.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
766 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 17, 2023 5:00 PM | January 17, 2023 5:00 PM | 0 | 765,759 | 0h | 01.02.INT.09.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
767 |  | Auto Scheduled | מערכתWMS תדע לשדר לSAP על הורדת הערכה ממלאי המחסן לאחר פירוק ערכה בWMS - INT | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.10 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
768 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
769 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.INT.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
770 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.INT.10.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
771 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.INT.10.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
772 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM | 0 | 771 | 0h | 01.02.INT.10.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
773 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 12, 2022 8:00 AM | September 15, 2022 5:00 PM | 0 | 772 | 25h | 01.02.INT.10.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
774 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 16, 2022 8:00 AM | September 29, 2022 5:00 PM | 0 | 773 | 10h | 01.02.INT.10.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
775 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 30, 2022 8:00 AM | October 13, 2022 5:00 PM | 0 | 774 | 10h | 01.02.INT.10.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
776 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 14, 2022 8:00 AM | October 20, 2022 5:00 PM | 0 | 775 | 5h | 01.02.INT.10.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
777 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 20, 2022 5:00 PM | October 20, 2022 5:00 PM | 0 | 776,770 | 0h | 01.02.INT.10.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
778 |  | Auto Scheduled | 01.02: ערכות.SAP | 792 days | February 3, 2020 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 1,540h | 01.02.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
779 |  | Auto Scheduled | מערכת SAP תאפשר יצירת\שינוי – עצי מוצר עבור אתר המרהס - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
780 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
781 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
782 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
783 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
784 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 8, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 783 | 0h | 01.02.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
785 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 784 | 25h | 01.02.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
786 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 785 | 10h | 01.02.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
787 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 786 | 10h | 01.02.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
788 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 787 | 5h | 01.02.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
789 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 788,782 | 0h | 01.02.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
790 |  | Auto Scheduled | תהליך יצירת עץ המוצר בSAP -התאמות למבנה הארגוני בלבד - SAP | 792 days | February 3, 2020 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
791 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
792 |  | Auto Scheduled | LifeCycle Tasks | 792 days | February 3, 2020 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
793 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
794 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
795 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 794 | 0h | 01.02.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
796 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 4, 2020 8:00 AM | March 9, 2020 5:00 PM | 0 | 795 | 25h | 01.02.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
797 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 10, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 796 | 10h | 01.02.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
798 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 24, 2020 8:00 AM | April 6, 2020 5:00 PM | 0 | 797 | 10h | 01.02.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
799 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 7, 2020 8:00 AM | April 13, 2020 5:00 PM | 0 | 798 | 5h | 01.02.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
800 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 799,793 | 0h | 01.02.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
801 |  | Auto Scheduled | מערכת SAP תדע לתמוך בתהליך בחירת סדרות לפריטי הבנים בעת יצירת הפק"ע - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
802 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
803 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
804 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
805 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
806 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 30/08/2021 | 31/10/2021 | 0 | 805 | 0h | 01.02.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
807 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 806 | 25h | 01.02.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
808 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 807 | 10h | 01.02.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
809 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 808 | 10h | 01.02.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
810 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 809 | 5h | 01.02.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
811 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 810,804 | 0h | 01.02.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
812 |  | Auto Scheduled | מערכת SAP תאפשר יצירת\שחרור הזמנות פק"ע ייצור באתר המרה"ס עבור אתרי אחסון מנהלים SAP - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
813 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
814 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
815 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
816 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
817 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 10, 2021 8:00 AM | September 11, 2021 5:00 PM | 0 | 816 | 0h | 01.02.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
818 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 13, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 817 | 25h | 01.02.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
819 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 818 | 10h | 01.02.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
820 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 1, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 819 | 10h | 01.02.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
821 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 15, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 | 820 | 5h | 01.02.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
822 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 19, 2021 5:00 PM | November 19, 2021 5:00 PM | 0 | 821,815 | 0h | 01.02.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
823 |  | Auto Scheduled | מערכת SAP תבצע בדיקת אחוז ההרכבה האפשרי והפריטים הזמינים בעת יצירת הפק"ע המיועדת לבנייה באתר WMS. לפי החלטת המשתמש נמשיך לשלבים הבאים או נבחר שלא לייצר עד לקבלת הפריטים למלאי הWMS. - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
824 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
825 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
826 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
827 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
828 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 0 | 827 | 0h | 01.02.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
829 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 2, 2022 8:00 AM | October 6, 2022 5:00 PM | 0 | 828 | 25h | 01.02.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
830 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 7, 2022 8:00 AM | October 20, 2022 5:00 PM | 0 | 829 | 10h | 01.02.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
831 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 21, 2022 8:00 AM | November 3, 2022 5:00 PM | 0 | 830 | 10h | 01.02.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
832 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 4, 2022 8:00 AM | November 10, 2022 5:00 PM | 0 | 831 | 5h | 01.02.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
833 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 10, 2022 5:00 PM | November 10, 2022 5:00 PM | 0 | 832,826 | 0h | 01.02.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
834 |  | Auto Scheduled | מערכת SAP תאפשר שחרור הזמנות פק"ע ייצור באתר המרהס עבור אתרי אחסון מנהלים WMS - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
835 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
836 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
837 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
838 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
839 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 21/12/2021 | 22/12/2021 | 0 | 838 | 0h | 01.02.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
840 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 839 | 25h | 01.02.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
841 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 840 | 10h | 01.02.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
842 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 841 | 10h | 01.02.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
843 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 842 | 5h | 01.02.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
844 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 843,837 | 0h | 01.02.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
845 |  | Auto Scheduled | מערכת SAP תאפשר ליקוט וזיכוי פרטי בנים הקיימים במחסני המרכזים (המנוהלים SAP) וניפוקם לבימ"ל - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
846 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
847 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
848 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
849 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
850 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 21/12/2021 | 23/01/2022 | 0 | 849 | 0h | 01.02.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
851 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 850 | 25h | 01.02.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
852 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 851 | 10h | 01.02.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
853 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 852 | 10h | 01.02.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
854 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 853 | 5h | 01.02.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
855 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 854,848 | 0h | 01.02.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
856 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת הזמנת\אספקת ויסות בתוך המרחב לWMS עבור ליקוט פריטי בנים הקיימים במחסני המרה"ס וניפוקם למחסן מנוהל SAP לצורך בניית ערכות - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
857 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
858 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
859 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
860 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
861 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 1, 2022 8:00 AM | December 5, 2022 5:00 PM | 0 | 860 | 0h | 01.02.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
862 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 6, 2022 8:00 AM | January 9, 2023 5:00 PM | 0 | 861 | 25h | 01.02.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
863 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 10, 2023 8:00 AM | January 23, 2023 5:00 PM | 0 | 862 | 10h | 01.02.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
864 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 24, 2023 8:00 AM | February 6, 2023 5:00 PM | 0 | 863 | 10h | 01.02.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
865 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 7, 2023 8:00 AM | February 13, 2023 5:00 PM | 0 | 864 | 5h | 01.02.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
866 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 13, 2023 5:00 PM | February 13, 2023 5:00 PM | 0 | 865,859 | 0h | 01.02.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
867 |  | Auto Scheduled | מערכת הSAP תאפשר ניפוק פריטים לפק"ע עבור ייצור ערכות - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
868 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
869 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
870 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
871 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
872 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | January 27, 2022 8:00 AM | March 2, 2022 5:00 PM | 0 | 871 | 0h | 01.02.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
873 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 3, 2022 8:00 AM | April 6, 2022 5:00 PM | 0 | 872 | 25h | 01.02.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
874 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 7, 2022 8:00 AM | April 20, 2022 5:00 PM | 0 | 873 | 10h | 01.02.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
875 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 21, 2022 8:00 AM | May 4, 2022 5:00 PM | 0 | 874 | 10h | 01.02.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
876 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 5, 2022 8:00 AM | May 11, 2022 5:00 PM | 0 | 875 | 5h | 01.02.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
877 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 11, 2022 5:00 PM | May 11, 2022 5:00 PM | 0 | 876,870 | 0h | 01.02.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
878 |  | Auto Scheduled | מערכת הSAP תאפשר קבלה למלאי של ערכות לאחר ייצור - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
879 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
880 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
881 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
882 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
883 |  | Manually Scheduled | יישום ופיתוח סאפ | 132 days | January 2, 2022 8:00 AM | July 2, 2022 5:00 PM | 0 | 882 | 0h | 01.02.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
884 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 4, 2022 8:00 AM | August 5, 2022 5:00 PM | 0 | 883 | 25h | 01.02.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
885 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 8, 2022 8:00 AM | August 19, 2022 5:00 PM | 0 | 884 | 10h | 01.02.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
886 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 885 | 10h | 01.02.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
887 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 5, 2022 8:00 AM | September 9, 2022 5:00 PM | 0 | 886 | 5h | 01.02.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
888 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 9, 2022 5:00 PM | September 9, 2022 5:00 PM | 0 | 887,881 | 0h | 01.02.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
889 |  | Auto Scheduled | ניפוק הערכה ישירות מבימ"ל – מערכת SAP תאפשר ניפוק הערכה מהבימ"ל ליחידות - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
890 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
891 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
892 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
893 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
894 |  | Manually Scheduled | יישום ופיתוח סאפ | 133 days | March 2, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 893 | 0h | 01.02.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
895 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 5, 2022 8:00 AM | October 7, 2022 5:00 PM | 0 | 894 | 25h | 01.02.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
896 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 10, 2022 8:00 AM | October 21, 2022 5:00 PM | 0 | 895 | 10h | 01.02.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
897 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 24, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 896 | 10h | 01.02.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
898 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 0 | 897 | 5h | 01.02.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
899 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 11, 2022 5:00 PM | November 11, 2022 5:00 PM | 0 | 898,892 | 0h | 01.02.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
900 |  | Auto Scheduled | העברת הערכה לאחסנה במחסני הזכיין –יש לאפשר העברת מלאי ערכות מא"א הבימל למערכת ה WMS - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
901 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
902 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
903 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
904 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
905 |  | Manually Scheduled | יישום ופיתוח סאפ | 67 days | July 2, 2022 8:00 AM | October 2, 2022 5:00 PM | 0 | 904 | 0h | 01.02.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
906 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 3, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 905 | 25h | 01.02.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
907 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 7, 2022 8:00 AM | November 18, 2022 5:00 PM | 0 | 906 | 10h | 01.02.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
908 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 21, 2022 8:00 AM | December 2, 2022 5:00 PM | 0 | 907 | 10h | 01.02.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
909 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 5, 2022 8:00 AM | December 9, 2022 5:00 PM | 0 | 908 | 5h | 01.02.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
910 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 9, 2022 5:00 PM | December 9, 2022 5:00 PM | 0 | 909,903 | 0h | 01.02.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
911 |  | Auto Scheduled | במידה ולא קיים 100% מהמלאי הנדרש לבניית הערכות בWMS, מערכת SAP לא תשדר את הפק"ע לWMS ותציג הודעת שגיאה למשתמש - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
912 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
913 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
914 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
915 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
916 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 2, 2022 8:00 AM | September 5, 2022 5:00 PM | 0 | 915 | 0h | 01.02.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
917 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2022 8:00 AM | October 10, 2022 5:00 PM | 0 | 916 | 25h | 01.02.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
918 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2022 8:00 AM | October 24, 2022 5:00 PM | 0 | 917 | 10h | 01.02.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
919 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2022 8:00 AM | November 7, 2022 5:00 PM | 0 | 918 | 10h | 01.02.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
920 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2022 8:00 AM | November 14, 2022 5:00 PM | 0 | 919 | 5h | 01.02.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
921 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 14, 2022 5:00 PM | November 14, 2022 5:00 PM | 0 | 920,914 | 0h | 01.02.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
922 |  | Auto Scheduled | מערכת wms תדע להגדיר את כל הסדרות של פריטי הבנים הדרושים לייצור ערכות לפי הלוגיקה שתיקבע ע"י מפקדת מרה"ס - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
923 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
924 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
925 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
926 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
927 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 13/02/2022 | 20/02/2022 | 0 | 926 | 0h | 01.02.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
928 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 927 | 25h | 01.02.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
929 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 928 | 10h | 01.02.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
930 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 929 | 10h | 01.02.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
931 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 930 | 5h | 01.02.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
932 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 931,925 | 0h | 01.02.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
933 |  | Auto Scheduled | מערכת הSAP תאפשר פתיחת פקע להוצאה \הכנסה של רכיבים מערכה קיימת - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
934 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
935 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
936 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
937 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
938 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 22/03/2022 | 25/04/2022 | 0 | 937 | 0h | 01.02.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
939 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 938 | 25h | 01.02.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
940 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 939 | 10h | 01.02.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
941 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 940 | 10h | 01.02.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
942 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 941 | 5h | 01.02.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
943 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 942,936 | 0h | 01.02.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
944 |  | Auto Scheduled | מערכת הSAP תאפשר קליטת תנועות מלאי יעודיות מהWMS על מנת לעדכן תכולת ערכה (הוצאה\הכנסה) עבור ערכה שנמצאת במלאי - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.16 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
945 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
946 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
947 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.16.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
948 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.16.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
949 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | February 2, 2022 8:00 AM | March 8, 2022 5:00 PM | 0 | 948 | 0h | 01.02.SAP.16.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
950 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 9, 2022 8:00 AM | April 12, 2022 5:00 PM | 0 | 949 | 25h | 01.02.SAP.16.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
951 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 13, 2022 8:00 AM | April 26, 2022 5:00 PM | 0 | 950 | 10h | 01.02.SAP.16.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
952 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 27, 2022 8:00 AM | May 10, 2022 5:00 PM | 0 | 951 | 10h | 01.02.SAP.16.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
953 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 11, 2022 8:00 AM | May 17, 2022 5:00 PM | 0 | 952 | 5h | 01.02.SAP.16.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
954 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 17, 2022 5:00 PM | May 17, 2022 5:00 PM | 0 | 953,947 | 0h | 01.02.SAP.16.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
955 |  | Auto Scheduled | מערכת ה SAP תשנה את הסטאטוס בפק"ע בהתאם לשדר מה WMS - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.17 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
956 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
957 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
958 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.17.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
959 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.17.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
960 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 5, 2022 8:00 AM | October 7, 2022 5:00 PM | 0 | 959 | 0h | 01.02.SAP.17.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
961 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 10, 2022 8:00 AM | November 11, 2022 5:00 PM | 0 | 960 | 25h | 01.02.SAP.17.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
962 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 14, 2022 8:00 AM | November 25, 2022 5:00 PM | 0 | 961 | 10h | 01.02.SAP.17.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
963 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 28, 2022 8:00 AM | December 9, 2022 5:00 PM | 0 | 962 | 10h | 01.02.SAP.17.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
964 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 12, 2022 8:00 AM | December 16, 2022 5:00 PM | 0 | 963 | 5h | 01.02.SAP.17.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
965 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 16, 2022 5:00 PM | December 16, 2022 5:00 PM | 0 | 964,958 | 0h | 01.02.SAP.17.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
966 |  | Auto Scheduled | מערכת SAP תעדכן את העיתוד על פעולות מלאיות שיבוצעו כתוצאה משדרי עידכון המלאי שהזכיין ישלח - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.18 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
967 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.18.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
968 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.18.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
969 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.18.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
970 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.18.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
971 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 22/05/2022 | 24/05/2022 | 0 | 970 | 0h | 01.02.SAP.18.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
972 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 971 | 25h | 01.02.SAP.18.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
973 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 972 | 10h | 01.02.SAP.18.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
974 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 973 | 10h | 01.02.SAP.18.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
975 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 974 | 5h | 01.02.SAP.18.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
976 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 975,969 | 0h | 01.02.SAP.18.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
977 |  | Auto Scheduled | מערכת SAP תאפשר שינוי הרשאות בהתאם לתהליכי העבודה המשתנים - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.19 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
978 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.19.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
979 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.19.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
980 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.19.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
981 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.19.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
982 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 23/05/2022 | 25/05/2022 | 0 | 981 | 0h | 01.02.SAP.19.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
983 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 982 | 25h | 01.02.SAP.19.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
984 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 983 | 10h | 01.02.SAP.19.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
985 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 984 | 10h | 01.02.SAP.19.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
986 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 985 | 5h | 01.02.SAP.19.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
987 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 986,980 | 0h | 01.02.SAP.19.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
988 |  | Auto Scheduled | יש להקים במערכת SAP אזורי MRP לייצור ערכות בהתאם לשינויים במבנה הארגוני - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.20 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
989 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.20.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
990 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.20.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
991 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.20.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
992 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.20.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
993 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 24/05/2022 | 26/05/2022 | 0 | 992 | 0h | 01.02.SAP.20.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
994 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 993 | 25h | 01.02.SAP.20.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
995 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 994 | 10h | 01.02.SAP.20.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
996 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 995 | 10h | 01.02.SAP.20.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
997 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 996 | 5h | 01.02.SAP.20.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
998 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 997,991 | 0h | 01.02.SAP.20.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
999 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת של פק"ע מסוג פירוק ערכה - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.21 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1000 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.21.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1001 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.21.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1002 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.21.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1003 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.21.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1004 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/05/2022 | 29/06/2022 | 0 | 1003 | 0h | 01.02.SAP.21.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1005 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1004 | 25h | 01.02.SAP.21.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1006 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1005 | 10h | 01.02.SAP.21.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1007 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1006 | 10h | 01.02.SAP.21.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1008 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1007 | 5h | 01.02.SAP.21.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1009 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1008,1002 | 0h | 01.02.SAP.21.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1010 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת של פק"ע מסוג הוצאה והכנסה של פריט לערכה - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.22 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1011 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.22.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1012 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.SAP.22.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1013 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.SAP.22.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1014 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.SAP.22.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1015 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 22/06/2022 | 28/07/2022 | 0 | 1014 | 0h | 01.02.SAP.22.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1016 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1015 | 25h | 01.02.SAP.22.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1017 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1016 | 10h | 01.02.SAP.22.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1018 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1017 | 10h | 01.02.SAP.22.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1019 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1018 | 5h | 01.02.SAP.22.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1020 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1019,1013 | 0h | 01.02.SAP.22.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1021 |  | Auto Scheduled | 01.02: ערכות.WMS | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 140h | 01.02.WMS |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1022 |  | Auto Scheduled | מערכתWMS תדע לשדר לSAP על קבלת פריטים למלאי המחסן מערכות המפורקות בWMS - WMS | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 70h | 01.02.WMS.01 | יישום ופיתוח מערכת ניהול מחסן - זכיין |  | parent |  | requirements | WMS | NA | As Soon As Possible | 5
1023 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.WMS.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1024 |  | Auto Scheduled | LifeCycle Tasks | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 70h | 01.02.WMS.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1025 |  | Auto Scheduled | סיום משימת משנה למערכת ניהול מחסן - זכיין | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.WMS.01.02.01 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1026 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 20h | 01.02.WMS.01.02.02 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1027 |  | Manually Scheduled | יישום ופיתוח מערכת ניהול מחסן - זכיין | 25 days | October 5, 2022 8:00 AM | November 8, 2022 5:00 PM | 0 | 1026 | 0h | 01.02.WMS.01.02.03 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1028 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 9, 2022 8:00 AM | December 13, 2022 5:00 PM | 0 | 1027 | 25h | 01.02.WMS.01.02.04 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1029 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 14, 2022 8:00 AM | December 27, 2022 5:00 PM | 0 | 1028 | 10h | 01.02.WMS.01.02.05 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1030 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 28, 2022 8:00 AM | January 10, 2023 5:00 PM | 0 | 1029 | 10h | 01.02.WMS.01.02.06 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1031 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 11, 2023 8:00 AM | January 17, 2023 5:00 PM | 0 | 1030 | 5h | 01.02.WMS.01.02.07 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1032 |  | Auto Scheduled | משימת WMS עלתה לאויר | 0 days | January 17, 2023 5:00 PM | January 17, 2023 5:00 PM | 0 | 1031,1025 | 0h | 01.02.WMS.01.02.08 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1033 |  | Auto Scheduled | מערכתWMS תדע לשדר לSAP על הורדת הערכה ממלאי המחסן לאחר פירוק ערכה בWMS - WMS | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.WMS.02 | יישום ופיתוח מערכת ניהול מחסן - זכיין |  | parent |  | requirements | WMS | NA | As Soon As Possible | 5
1034 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.WMS.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1035 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.02.WMS.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1036 |  | Auto Scheduled | סיום משימת משנה למערכת ניהול מחסן - זכיין | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.02.WMS.02.02.01 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1037 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | January 18, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1024 | 20h | 01.02.WMS.02.02.02 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1038 |  | Manually Scheduled | יישום ופיתוח מערכת ניהול מחסן - זכיין | 25 days | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM | 0 | 1037 | 0h | 01.02.WMS.02.02.03 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1039 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 12, 2022 8:00 AM | September 15, 2022 5:00 PM | 0 | 1038 | 25h | 01.02.WMS.02.02.04 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1040 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 16, 2022 8:00 AM | September 29, 2022 5:00 PM | 0 | 1039 | 10h | 01.02.WMS.02.02.05 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1041 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 30, 2022 8:00 AM | October 13, 2022 5:00 PM | 0 | 1040 | 10h | 01.02.WMS.02.02.06 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1042 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 14, 2022 8:00 AM | October 20, 2022 5:00 PM | 0 | 1041 | 5h | 01.02.WMS.02.02.07 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1043 |  | Auto Scheduled | משימת WMS עלתה לאויר | 0 days | October 20, 2022 5:00 PM | October 20, 2022 5:00 PM | 0 | 1042,1036 | 0h | 01.02.WMS.02.02.08 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
1044 |  | Auto Scheduled | 01.03: חיובים וזיכויים | 491 days | February 3, 2020 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 849h | 01.03 | בחתימה | אבי פרישמן | hd | מאור |  | BP | NA | As Soon As Possible | 3
1045 |  | Auto Scheduled | 01.03: חיובים וזיכויים.BP | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 199h | 01.03.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1046 |  | Auto Scheduled | 01.03: חיובים וזיכויים - BP | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 199h | 01.03.BP.01 | בחתימה | אבי פרישמן | parent | מאור |  | BP | NA | As Soon As Possible | 5
1047 |  | Auto Scheduled | Sub Tasks | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 159h | 01.03.BP.01.01 |  | אבי פרישמן | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1048 |  | Auto Scheduled | 03/09: תגובה של תקווה--1. ביטול חיוב עצמי וכל פעולת רוורס אחרת – במעבר למבנה ארגוני חדש יפתחו מחסנים / א"א חדשים לכן לא ניתן יהיה לבצע ביטולים היסטוריים. צריך לציין במסמך.--2. יש יותר מדי נושאים פתוחים בסוף המסמך – לא חושבת ששגיב יחתום במצב כזה.--3. עיצו | 2 days | May 18, 2021 8:00 AM | May 19, 2021 5:00 PM | 0 |  | 2h | 01.03.BP.01.01.01 | בוצע | מאור | MoM | מאור | תקווה רובינצ'יק | BP | NA | Must Start On | 7
1049 |  | Auto Scheduled | 23/09: חסרות סיבה לתנועה 262 וסיבות של סימולי החוץ--תוצרת גמורה המגיעה מהמשא/בימל שמבצעים 101 על סמך אספקה נכנסת עם סיבה לתנועה שבו רושמים סימול חוץ/ סימול של המשא , מתבצע שרשור של 902 זיכוי עם סיבה 262 | 2 days | May 20, 2021 8:00 AM | May 21, 2021 5:00 PM | 0 | 1048 | 2h | 01.03.BP.01.01.02 | בוצע | מאור | MoM | מאור | שרון רחמים | BP | NA | As Soon As Possible | 7
1050 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.03.BP.01.01.20 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1051 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 24 days | June 2, 2021 8:00 AM | July 5, 2021 5:00 PM | 0 | 1050 | 24h | 01.03.BP.01.01.21 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1052 |  | Auto Scheduled | אישור אבי | 8 days | July 6, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 1051 | 8h | 01.03.BP.01.01.22 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1053 |  | Auto Scheduled | אישור מקל"ר | 11 days | July 16, 2021 8:00 AM | July 30, 2021 5:00 PM | 0 | 1052 | 11h | 01.03.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1054 |  | Auto Scheduled | אישור המנהלת | 17 days | August 2, 2021 8:00 AM | August 24, 2021 5:00 PM | 0 | 1053 | 17h | 01.03.BP.01.01.24 | בוצע | סיגל | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1055 |  | Auto Scheduled | אישור מפקדת | 11 days | August 25, 2021 8:00 AM | September 8, 2021 5:00 PM | 0 | 1054 | 11h | 01.03.BP.01.01.25 | בוצע |  | MoM |  | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1056 |  | Auto Scheduled | אישור שגיב שרביט | 32 days | September 9, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 1055 | 32h | 01.03.BP.01.01.26 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1057 |  | Auto Scheduled | אישור ניר בשן | 8 days | October 25, 2021 8:00 AM | November 3, 2021 5:00 PM | 0 | 1056 | 8h | 01.03.BP.01.01.27 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
1058 |  | Auto Scheduled | אישור חטלו"ג | 33 days | November 4, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 | 1057 | 33h | 01.03.BP.01.01.28 | בוצע | מאור | MoM | מאור | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
1059 |  | Auto Scheduled | LifeCycle Tasks | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 40h | 01.03.BP.01.02 |  | אבי פרישמן | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1060 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 20, 2021 5:00 PM | December 20, 2021 5:00 PM | 0 | 1058 | 0h | 01.03.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1061 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.03.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1062 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1061 | 10h | 01.03.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1063 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1062 | 5h | 01.03.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1064 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1063 | 10h | 01.03.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1065 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1064 | 10h | 01.03.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1066 |  | Auto Scheduled | בחתימה | 0 days | December 20, 2021 5:00 PM | December 20, 2021 5:00 PM | 0 | 1065,1060 | 0h | 01.03.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1067 |  | Auto Scheduled | חתום | 0 days | December 20, 2021 5:00 PM | December 20, 2021 5:00 PM | 0 | 1066 | 0h | 01.03.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1068 |  | Auto Scheduled | 01.03: חיובים וזיכויים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 300h | 01.03.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1069 |  | Auto Scheduled | נדרש לסכם את אופן המימוש לתהליך קבלה מרכש מרק"ט מול זכיין ובהתאם לוודא דרישות בBP חיובים וזיכויים וקבלה מרכש. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.08 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1070 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1071 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1072 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1073 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1072 | 10h | 01.03.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1074 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1073 | 20h | 01.03.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1075 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1074,1072 | 0h | 01.03.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1076 |  | Auto Scheduled | נדרש להעביר לסוג תנועה 555. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.09 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1077 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1078 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1079 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.09.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1080 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1079 | 10h | 01.03.GEN.09.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1081 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1080 | 20h | 01.03.GEN.09.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1082 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1081,1079 | 0h | 01.03.GEN.09.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1083 |  | Auto Scheduled | נדרש לבחון איחוד של כלל התהליכים שעוברים לאספקה ללא סימוכין לטובת אחידות בין המשקים ואיחוד תהליכים. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.12 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1084 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1085 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1086 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.12.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1087 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1086 | 10h | 01.03.GEN.12.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1088 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1087 | 20h | 01.03.GEN.12.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1089 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1088,1086 | 0h | 01.03.GEN.12.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1090 |  | Auto Scheduled | נדרש לאחד את הקודי מאשר בהתאם למבנה הארגוני החדש. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.13 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1091 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1092 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1093 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.13.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1094 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1093 | 10h | 01.03.GEN.13.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1095 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1094 | 20h | 01.03.GEN.13.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1096 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1095,1093 | 0h | 01.03.GEN.13.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1097 |  | Auto Scheduled | נדרש לבחון את הכנסת משק המזון למערכת האישורים לצורך איחוד תהליכים בין המשקים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.16 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1098 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1099 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1100 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.16.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1101 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1100 | 10h | 01.03.GEN.16.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1102 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1101 | 20h | 01.03.GEN.16.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1103 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1102,1100 | 0h | 01.03.GEN.16.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1104 |  | Auto Scheduled | נדרש לסכם תהליך או"שי לשינוי מסמך לאחר שאושר/נדחה במערכת אישורים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.17 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1105 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1106 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1107 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.17.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1108 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1107 | 10h | 01.03.GEN.17.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1109 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1108 | 20h | 01.03.GEN.17.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1110 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1109,1107 | 0h | 01.03.GEN.17.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1111 |  | Auto Scheduled | נדרש לאפיין דוחות BW כגון דו"ח תנועות שלא עולות למערכת אישורים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.18 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1112 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.18.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1113 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.18.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1114 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.18.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1115 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1114 | 10h | 01.03.GEN.18.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1116 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1115 | 20h | 01.03.GEN.18.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1117 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1116,1114 | 0h | 01.03.GEN.18.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1118 |  | Auto Scheduled | נדרש לבחון את הפער בספירות במצב הקיים (הנחה שזה קורה בגלל זיכוי מבוצע לפני שמתבצע אישור במערכת האישורים.) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.19 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1119 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.19.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1120 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.19.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1121 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.19.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1122 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1121 | 10h | 01.03.GEN.19.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1123 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1122 | 20h | 01.03.GEN.19.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1124 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1123,1121 | 0h | 01.03.GEN.19.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1125 |  | Auto Scheduled | במצב הנוכחי מנפ"ר השמנים מעדכן תוקף לשמן ובמקביל מוציא הנחיה במייל למתחמי הדלק להדביק מדבקות עם התוקף החדש לכל השמנים והוארכו – נדרש לסכם את התהליך הסימון אריזות השמנים בWMS. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.20 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1126 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.20.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1127 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.20.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1128 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.20.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1129 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1128 | 10h | 01.03.GEN.20.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1130 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1129 | 20h | 01.03.GEN.20.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1131 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1130,1128 | 0h | 01.03.GEN.20.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1132 |  | Auto Scheduled | מיפוי סוגי תנועות וסיבות לתנועה ימופה מחדש ע"י חטלו"ג ותשלח טבלה חדשה ומעודכנת - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.21 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1133 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.21.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1134 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.03.GEN.21.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1135 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.GEN.21.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1136 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1135 | 10h | 01.03.GEN.21.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1137 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1136 | 20h | 01.03.GEN.21.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1138 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1137,1135 | 0h | 01.03.GEN.21.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1139 |  | Auto Scheduled | 01.03: חיובים וזיכויים.INT | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 210h | 01.03.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1140 |  | Auto Scheduled | עבור שמנים שחוזרים תקולים מבחינות מטמו"ן, מערכות SAP תאפשר העברת שדרים למערכת WMS לעדכון כושר הפריט לפגום והמשך טיפול בתהליכי גריטות ומכירות. - INT | 91 days | February 6, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.03.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1141 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1142 |  | Auto Scheduled | LifeCycle Tasks | 91 days | February 6, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.03.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1143 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1144 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1552 | 20h | 01.03.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1145 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 1 day | February 6, 2021 8:00 AM | February 6, 2021 5:00 PM | 0 | 1144 | 0h | 01.03.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1146 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 8, 2021 8:00 AM | March 12, 2021 5:00 PM | 0 | 1145 | 25h | 01.03.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1147 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 15, 2021 8:00 AM | March 26, 2021 5:00 PM | 0 | 1146 | 10h | 01.03.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1148 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 29, 2021 8:00 AM | April 9, 2021 5:00 PM | 0 | 1147 | 10h | 01.03.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1149 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 12, 2021 8:00 AM | April 16, 2021 5:00 PM | 0 | 1148 | 5h | 01.03.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1150 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1149,1143 | 0h | 01.03.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1151 |  | Auto Scheduled | מערכות WMS וSAP יאפשרו מענה של חיוב עצמי עבור קבלה מרכש מרק"ט - INT | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.03.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1152 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1153 |  | Auto Scheduled | LifeCycle Tasks | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.03.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1154 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1155 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1552 | 20h | 01.03.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1156 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 1155 | 0h | 01.03.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1157 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 4, 2020 8:00 AM | March 9, 2020 5:00 PM | 0 | 1156 | 25h | 01.03.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1158 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 10, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 1157 | 10h | 01.03.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1159 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 24, 2020 8:00 AM | April 6, 2020 5:00 PM | 0 | 1158 | 10h | 01.03.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1160 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 7, 2020 8:00 AM | April 13, 2020 5:00 PM | 0 | 1159 | 5h | 01.03.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1161 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1160,1154 | 0h | 01.03.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1162 |  | Auto Scheduled | מערכת הSAP תאפשר עדכון תוקף לסדרה עבור שמנים שחוזרים תקינים והעברת שדר לWMS לעדכון התוקף של הסדרה/מנה שנשלחה. - INT | 114 days | January 6, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.03.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1163 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1164 |  | Auto Scheduled | LifeCycle Tasks | 114 days | January 6, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.03.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1165 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1166 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1552 | 20h | 01.03.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1167 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 1 day | January 6, 2021 8:00 AM | January 6, 2021 5:00 PM | 0 | 1166 | 0h | 01.03.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1168 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 7, 2021 8:00 AM | February 10, 2021 5:00 PM | 0 | 1167 | 25h | 01.03.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1169 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 11, 2021 8:00 AM | February 24, 2021 5:00 PM | 0 | 1168 | 10h | 01.03.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1170 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 25, 2021 8:00 AM | March 10, 2021 5:00 PM | 0 | 1169 | 10h | 01.03.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1171 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 11, 2021 8:00 AM | March 17, 2021 5:00 PM | 0 | 1170 | 5h | 01.03.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1172 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1171,1165 | 0h | 01.03.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1173 |  | Auto Scheduled | 01.03: חיובים וזיכויים.SAP | 160 days | March 6, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 140h | 01.03.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1174 |  | Auto Scheduled | מערכות WMS SAP יאפשרו שינוי הרשאות בהתאם לתהליכי העבודה המשתנים - SAP | 160 days | March 6, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 70h | 01.03.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1175 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1176 |  | Auto Scheduled | LifeCycle Tasks | 160 days | March 6, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 70h | 01.03.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1177 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1178 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1552 | 20h | 01.03.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1179 |  | Manually Scheduled | יישום ופיתוח סאפ | 111 days | March 6, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 1178 | 0h | 01.03.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1180 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 9, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 1179 | 25h | 01.03.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1181 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 13, 2021 8:00 AM | September 24, 2021 5:00 PM | 0 | 1180 | 10h | 01.03.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1182 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 27, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 1181 | 10h | 01.03.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1183 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 11, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 1182 | 5h | 01.03.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1184 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 15, 2021 5:00 PM | October 15, 2021 5:00 PM | 0 | 1183,1177 | 0h | 01.03.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1185 |  | Auto Scheduled | מערכת SAP תאפשר איחוד קודי מאשר - SAP | 115 days | March 6, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 |  | 70h | 01.03.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1186 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1187 |  | Auto Scheduled | LifeCycle Tasks | 115 days | March 6, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 |  | 70h | 01.03.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1188 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.03.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1189 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1552 | 20h | 01.03.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1190 |  | Manually Scheduled | יישום ופיתוח סאפ | 67 days | March 6, 2021 8:00 AM | June 6, 2021 5:00 PM | 0 | 1189 | 0h | 01.03.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1191 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 7, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 1190 | 25h | 01.03.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1192 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 12, 2021 8:00 AM | July 23, 2021 5:00 PM | 0 | 1191 | 10h | 01.03.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1193 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 26, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 1192 | 10h | 01.03.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1194 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 9, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 1193 | 5h | 01.03.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1195 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 13, 2021 5:00 PM | August 13, 2021 5:00 PM | 0 | 1194,1188 | 0h | 01.03.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1196 |  | Auto Scheduled | 01.04: השקעות ופירוקים | 607 days | November 8, 2020 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 531h | 01.04 | בחתימה | 5 avi | hd | גל |  | BP | NA | As Soon As Possible | 3
1197 |  | Auto Scheduled | 01.04: השקעות ופירוקים.BP | 298 days | November 8, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 191h | 01.04.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1198 |  | Auto Scheduled | 01.04: השקעות ופירוקים - BP | 298 days | November 8, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 191h | 01.04.BP.01 | בחתימה | 5 avi | parent | גל |  | BP | NA | As Soon As Possible | 5
1199 |  | Auto Scheduled | Sub Tasks | 298 days | November 8, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 151h | 01.04.BP.01.01 |  | 5 avi | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1200 |  | Auto Scheduled | כתיבת מסמך | 11 days | November 8, 2020 8:00 AM | November 23, 2020 5:00 PM | 0 |  | 11h | 01.04.BP.01.01.20 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | Must Start On | 7
1201 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 28 days | November 24, 2020 8:00 AM | December 31, 2020 5:00 PM | 0 | 1200 | 28h | 01.04.BP.01.01.21 | בוצע |  | MoM |  | 2020-09-22 00:00:00 | BP | NA | As Soon As Possible | 7
1202 |  | Auto Scheduled | אישור מקל"ר | 10 days | January 1, 2021 8:00 AM | January 14, 2021 5:00 PM | 0 | 1201 | 10h | 01.04.BP.01.01.22 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
1203 |  | Auto Scheduled | אישור מפקדת | 34 days | January 15, 2021 8:00 AM | March 3, 2021 5:00 PM | 0 | 1202 | 34h | 01.04.BP.01.01.23 | בוצע | סיגל | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
1204 |  | Auto Scheduled | אישור חטלו"ג | 3 days | March 4, 2021 8:00 AM | March 8, 2021 5:00 PM | 0 | 1203 | 3h | 01.04.BP.01.01.24 | בוצע |  | MoM |  | 2020-10-20 00:00:00 | BP | NA | As Soon As Possible | 7
1205 |  | Auto Scheduled | אישור המנהלת | 22 days | March 9, 2021 8:00 AM | April 7, 2021 5:00 PM | 0 | 1204 | 2h | 01.04.BP.01.01.25 | בוצע | סיגל | MoM | ואל | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
1206 |  | Auto Scheduled | אישור שגיב שרביט | 132 days | April 8, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 1205 | 5h | 01.04.BP.01.01.26 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1207 |  | Auto Scheduled | אישור ניר בשן | 58 days | October 11, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 1206 | 58h | 01.04.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1208 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 40h | 01.04.BP.01.02 |  | 5 avi | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1209 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 29, 2021 5:00 PM | December 29, 2021 5:00 PM | 0 | 1207 | 0h | 01.04.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1210 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.04.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1211 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1210 | 10h | 01.04.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1212 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1211 | 5h | 01.04.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1213 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1212 | 10h | 01.04.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1214 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1213 | 10h | 01.04.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1215 |  | Auto Scheduled | בחתימה | 0 days | December 29, 2021 5:00 PM | December 29, 2021 5:00 PM | 0 | 1214,1209 | 0h | 01.04.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1216 |  | Auto Scheduled | חתום | 0 days | December 29, 2021 5:00 PM | December 29, 2021 5:00 PM | 0 | 1215 | 0h | 01.04.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1217 |  | Auto Scheduled | 01.04: השקעות ופירוקים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 60h | 01.04.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1218 |  | Auto Scheduled | אפיון מעבדה בBP מבנה אירגוני - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.04.GEN.01 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1219 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1220 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.04.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1221 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1222 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1221 | 10h | 01.04.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1223 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1222 | 20h | 01.04.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1224 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1223,1221 | 0h | 01.04.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1225 |  | Auto Scheduled | נדרש להציג דרישות לדו"חות תומכי תהליך בתחום האמר"לים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.04.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1226 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1227 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.04.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1228 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1229 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1228 | 10h | 01.04.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1230 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1229 | 20h | 01.04.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1231 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1230,1228 | 0h | 01.04.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1232 |  | Auto Scheduled | 01.04: השקעות ופירוקים.SAP | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 280h | 01.04.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1233 |  | Auto Scheduled | מערכת SAP תאפשר המשך עבודה תקינה בתהליך פתיחה, עדכון וסגירת הזמנות אחזקה ע"ב מרכזי עבודה וקבוצות מתכנן חדשות שייפתחו - SAP | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1234 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1235 |  | Auto Scheduled | LifeCycle Tasks | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1236 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1237 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 8, 2023 8:00 AM | March 7, 2023 5:00 PM | 0 | 1813 | 20h | 01.04.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1238 |  | Manually Scheduled | יישום ופיתוח סאפ | 67 days | June 5, 2021 8:00 AM | September 5, 2021 5:00 PM | 0 | 1237 | 0h | 01.04.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1239 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 1238 | 25h | 01.04.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1240 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 1239 | 10h | 01.04.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1241 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 1240 | 10h | 01.04.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1242 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 1241 | 5h | 01.04.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1243 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 1242,1236 | 0h | 01.04.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1244 |  | Auto Scheduled | מערכת SAP תאפשר המשך עבודה תקינה בתהליך פירוק והשקעה מתוך הזמנות אחזקה ע"ב אתרי אחסון ב-6100/6200/6300 חדשים שייפתחו - SAP | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1245 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1246 |  | Auto Scheduled | LifeCycle Tasks | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1247 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1248 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 8, 2023 8:00 AM | March 7, 2023 5:00 PM | 0 | 1813 | 20h | 01.04.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1249 |  | Manually Scheduled | יישום ופיתוח סאפ | 46 days | September 5, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 1248 | 0h | 01.04.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1250 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 8, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 1249 | 25h | 01.04.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1251 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 13, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 1250 | 10h | 01.04.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1252 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 27, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 1251 | 10h | 01.04.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1253 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 10, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 1252 | 5h | 01.04.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1254 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 14, 2022 5:00 PM | January 14, 2022 5:00 PM | 0 | 1253,1247 | 0h | 01.04.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1255 |  | Auto Scheduled | המלאי מאוחסן בWMS ומשוקף בIM בsap- - אתרים 6100,6200,6300. - SAP | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1256 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1257 |  | Auto Scheduled | LifeCycle Tasks | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1258 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1259 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 8, 2023 8:00 AM | March 7, 2023 5:00 PM | 0 | 1813 | 20h | 01.04.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1260 |  | Manually Scheduled | יישום ופיתוח סאפ | 45 days | October 5, 2021 8:00 AM | December 5, 2021 5:00 PM | 0 | 1259 | 0h | 01.04.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1261 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 6, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 1260 | 25h | 01.04.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1262 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 10, 2022 8:00 AM | January 21, 2022 5:00 PM | 0 | 1261 | 10h | 01.04.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1263 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 24, 2022 8:00 AM | February 4, 2022 5:00 PM | 0 | 1262 | 10h | 01.04.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1264 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 7, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 1263 | 5h | 01.04.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1265 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 11, 2022 5:00 PM | February 11, 2022 5:00 PM | 0 | 1264,1258 | 0h | 01.04.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1266 |  | Auto Scheduled | איו שינוי בחוקות ובמיקום החוקות של השקעות ופירוקים ע"פ חוקת המלאי - SAP | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1267 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1268 |  | Auto Scheduled | LifeCycle Tasks | 471 days | May 18, 2021 8:00 AM | March 7, 2023 5:00 PM | 0 |  | 70h | 01.04.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1269 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.04.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1270 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 8, 2023 8:00 AM | March 7, 2023 5:00 PM | 0 | 1813 | 20h | 01.04.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1271 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 5, 2021 8:00 AM | December 9, 2021 5:00 PM | 0 | 1270 | 0h | 01.04.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1272 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 10, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 1271 | 25h | 01.04.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1273 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 14, 2022 8:00 AM | January 27, 2022 5:00 PM | 0 | 1272 | 10h | 01.04.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1274 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 28, 2022 8:00 AM | February 10, 2022 5:00 PM | 0 | 1273 | 10h | 01.04.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1275 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 11, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 1274 | 5h | 01.04.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1276 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 17, 2022 5:00 PM | February 17, 2022 5:00 PM | 0 | 1275,1269 | 0h | 01.04.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1277 |  | Auto Scheduled | 01.05: ויסותים פנימיים | 147 days | May 18, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 |  | 242h | 01.05 | חתום | מוריה | hd | מוריה |  | BP | NA | As Soon As Possible | 3
1278 |  | Auto Scheduled | 01.05: ויסותים פנימיים.BP | 147 days | May 18, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 |  | 152h | 01.05.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1279 |  | Auto Scheduled | 01.05: ויסותים פנימיים - BP | 147 days | May 18, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 |  | 152h | 01.05.BP.01 | חתום | מוריה | parent | מוריה |  | BP | NA | As Soon As Possible | 5
1280 |  | Auto Scheduled | Sub Tasks | 147 days | May 18, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 |  | 112h | 01.05.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1281 |  | Auto Scheduled | 23/09: הערות של גלית אדרי | 6 days | May 18, 2021 8:00 AM | May 25, 2021 5:00 PM | 0 |  | 6h | 01.05.BP.01.01.01 | בוצע |  | MoM |  | גלית אדרי | BP | NA | Must Start On | 7
1282 |  | Auto Scheduled | כתיבת מסמך | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 20h | 01.05.BP.01.01.20 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1283 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 4 days | June 15, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 | 1282 | 4h | 01.05.BP.01.01.21 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1284 |  | Auto Scheduled | אישור מקל"ר | 11 days | June 21, 2021 8:00 AM | July 5, 2021 5:00 PM | 0 | 1283 | 11h | 01.05.BP.01.01.22 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
1285 |  | Auto Scheduled | אישור אבי | 19 days | July 6, 2021 8:00 AM | July 30, 2021 5:00 PM | 0 | 1284 | 19h | 01.05.BP.01.01.23 | בוצע | אבי | MoM | ואל | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
1286 |  | Auto Scheduled | אישור המנהלת | 44 days | August 2, 2021 8:00 AM | September 30, 2021 5:00 PM | 0 | 1285 | 3h | 01.05.BP.01.01.24 | בוצע | סיגל | MoM | ואל | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
1287 |  | Auto Scheduled | אישור מפקדת | 3 days | October 1, 2021 8:00 AM | October 5, 2021 5:00 PM | 0 | 1286 | 3h | 01.05.BP.01.01.25 | בוצע | מוריה | MoM | ואל | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
1288 |  | Auto Scheduled | אישור חטלו"ג | 5 days | October 6, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 1287 | 5h | 01.05.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
1289 |  | Auto Scheduled | אישור שגיב שרביט | 33 days | October 13, 2021 8:00 AM | November 26, 2021 5:00 PM | 0 | 1288 | 33h | 01.05.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1290 |  | Auto Scheduled | אישור ניר בשן | 8 days | November 29, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 | 1289 | 8h | 01.05.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1291 |  | Auto Scheduled | LifeCycle Tasks | 147 days | May 18, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 |  | 40h | 01.05.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1292 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 8, 2021 5:00 PM | December 8, 2021 5:00 PM | 0 | 1290 | 0h | 01.05.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1293 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.05.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1294 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1293 | 10h | 01.05.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1295 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1294 | 5h | 01.05.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1296 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1295 | 10h | 01.05.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1297 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1296 | 10h | 01.05.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1298 |  | Auto Scheduled | בחתימה | 0 days | December 8, 2021 5:00 PM | December 8, 2021 5:00 PM | 0 | 1297,1292 | 0h | 01.05.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1299 |  | Auto Scheduled | חתום | 0 days | December 8, 2021 5:00 PM | December 8, 2021 5:00 PM | 0 | 1298 | 0h | 01.05.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1300 |  | Auto Scheduled | 01.05: ויסותים פנימיים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 90h | 01.05.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1301 |  | Auto Scheduled | נדרש להעמיק בתהליך המבוצע להעברה בין אתרי אחסון בצעד אחד מספר תנועה 949 במשק הדלק ולהוסיף לרשימת הדרישות בBP ויסותים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.05.GEN.11 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1302 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.05.GEN.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1303 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.05.GEN.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1304 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.05.GEN.11.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1305 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1304 | 10h | 01.05.GEN.11.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1306 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1305 | 20h | 01.05.GEN.11.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1307 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1306,1304 | 0h | 01.05.GEN.11.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1308 |  | Auto Scheduled | נדרש להעמיק בתהליך המבוצע להעברה של מלאי בכושר 1 (QI) בין מחסנים בצעד אחד במשק החלפים ולהוסיף לרשימת הדרישות בBP ויסותים/כושרים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.05.GEN.12 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1309 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.05.GEN.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1310 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.05.GEN.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1311 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.05.GEN.12.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1312 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1311 | 10h | 01.05.GEN.12.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1313 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1312 | 20h | 01.05.GEN.12.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1314 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1313,1311 | 0h | 01.05.GEN.12.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1315 |  | Auto Scheduled | נושא ההפצה בחתך ראי מערכות ומחסנים יפורט בפרק ייעודי נפרד לכל סוגי המחסנים ותרחישי ההפצה בהתאמה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.05.GEN.14 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1316 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.05.GEN.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1317 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.05.GEN.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1318 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.05.GEN.14.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1319 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1318 | 10h | 01.05.GEN.14.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1320 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1319 | 20h | 01.05.GEN.14.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1321 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1320,1318 | 0h | 01.05.GEN.14.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1322 |  | Auto Scheduled | 01.06: אחסנה | 594 days | January 10, 2020 8:00 AM | April 20, 2022 5:00 PM | 0 |  | 1,434h | 01.06 | חתום | מוריה | hd | גל |  | BP | NA | As Soon As Possible | 3
1323 |  | Auto Scheduled | 01.06: אחסנה.BP | 487 days | June 9, 2020 8:00 AM | April 20, 2022 5:00 PM | 0 |  | 177h | 01.06.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1324 |  | Auto Scheduled | 01.06: אחסנה - BP | 487 days | June 9, 2020 8:00 AM | April 20, 2022 5:00 PM | 0 |  | 177h | 01.06.BP.01 | חתום | מוריה | parent | גל |  | BP | NA | As Soon As Possible | 5
1325 |  | Auto Scheduled | Sub Tasks | 487 days | June 9, 2020 8:00 AM | April 20, 2022 5:00 PM | 0 |  | 137h | 01.06.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1326 |  | Auto Scheduled | נדרש להתייחס שיהיו סטטוסים נוספים ל-10 כושרים (כגון ספירה, מלאי לפרויקט, מלאי חסום לחירום וכו')--יש להוסיף ולהתייחס למנפ"ר לאפשר לו לבצע באופן ידני בחירת פריט מכושר מסוים בזמן יצירת הדרישה / אישור הדרישה. | 1 day | June 9, 2020 8:00 AM | June 9, 2020 5:00 PM | 0 |  | 1h | 01.06.BP.01.01.01 | בוצע | מאיה | MoM | עינת | שרון רחמים | BP | NA | Must Start On | 7
1327 |  | Auto Scheduled | כתיבת מסמך | 36 days | May 18, 2021 8:00 AM | July 6, 2021 5:00 PM | 0 |  | 36h | 01.06.BP.01.01.20 | בוצע | אבי | MoM | ואל | 2020-09-07 00:00:00 | BP | NA | As Soon As Possible | 7
1328 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 7 days | July 7, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 1327 | 7h | 01.06.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1329 |  | Auto Scheduled | אישור אבי | 12 days | July 16, 2021 8:00 AM | August 2, 2021 5:00 PM | 0 | 1328 | 12h | 01.06.BP.01.01.22 | בוצע | אבי | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1330 |  | Auto Scheduled | אישור מקל"ר | 11 days | August 3, 2021 8:00 AM | August 17, 2021 5:00 PM | 0 | 1329 | 11h | 01.06.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
1331 |  | Auto Scheduled | אישור מפקדת | 15 days | August 18, 2021 8:00 AM | September 7, 2021 5:00 PM | 0 | 1330 | 15h | 01.06.BP.01.01.24 | בוצע | ואל | MoM | ואל | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
1332 |  | Auto Scheduled | אישור המנהלת | 110 days | September 8, 2021 8:00 AM | February 8, 2022 5:00 PM | 0 | 1331 | 4h | 01.06.BP.01.01.25 | בוצע | סיגל | MoM | 2020-10-18 00:00:00 | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
1333 |  | Auto Scheduled | אישור חטלו"ג | 1 day | February 9, 2022 8:00 AM | February 9, 2022 5:00 PM | 0 | 1332 | 1h | 01.06.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
1334 |  | Auto Scheduled | אישור שגיב שרביט | 39 days | February 10, 2022 8:00 AM | April 5, 2022 5:00 PM | 0 | 1333 | 39h | 01.06.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1335 |  | Auto Scheduled | אישור ניר בשן | 11 days | April 6, 2022 8:00 AM | April 20, 2022 5:00 PM | 0 | 1334 | 11h | 01.06.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1336 |  | Auto Scheduled | LifeCycle Tasks | 242 days | May 18, 2021 8:00 AM | April 20, 2022 5:00 PM | 0 |  | 40h | 01.06.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1337 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | April 20, 2022 5:00 PM | April 20, 2022 5:00 PM | 0 | 1335 | 0h | 01.06.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1338 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.06.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1339 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1338 | 10h | 01.06.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1340 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1339 | 5h | 01.06.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1341 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1340 | 10h | 01.06.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1342 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1341 | 10h | 01.06.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1343 |  | Auto Scheduled | בחתימה | 0 days | April 20, 2022 5:00 PM | April 20, 2022 5:00 PM | 0 | 1342,1337 | 0h | 01.06.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1344 |  | Auto Scheduled | חתום | 0 days | April 20, 2022 5:00 PM | April 20, 2022 5:00 PM | 0 | 1343 | 0h | 01.06.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1345 |  | Auto Scheduled | 01.06: אחסנה.BW | 498 days | February 3, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 55h | 01.06.BW |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1346 |  | Auto Scheduled | הצגת דוח מלאי כולל ברמה המק"ט והמחסן לכל המלאי הצה"לי - BW | 498 days | February 3, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 55h | 01.06.BW.01 | יישום ופיתוח דו"ח |  | parent |  | requirements | BW | NA | As Soon As Possible | 5
1347 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.BW.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1348 |  | Auto Scheduled | LifeCycle Tasks | 498 days | February 3, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 55h | 01.06.BW.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1349 |  | Auto Scheduled | סיום משימות משנה לדוחות ניהול | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.BW.01.02.01 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1350 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.BW.01.02.02 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1351 |  | Manually Scheduled | יישום ופיתוח דו"ח | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 1350 | 0h | 01.06.BW.01.02.03 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1352 |  | Auto Scheduled | פיתוח בדיקות קבלה | 10 days | February 4, 2020 8:00 AM | February 17, 2020 5:00 PM | 0 | 1351 | 10h | 01.06.BW.01.02.04 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1353 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 18, 2020 8:00 AM | March 2, 2020 5:00 PM | 0 | 1352 | 10h | 01.06.BW.01.02.05 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1354 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 3, 2020 8:00 AM | March 16, 2020 5:00 PM | 0 | 1353 | 10h | 01.06.BW.01.02.06 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1355 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 17, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 1354 | 5h | 01.06.BW.01.02.07 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1356 |  | Auto Scheduled | משימת דו"ח עלתה לאויר | 0 days | December 29, 2021 5:00 PM | December 29, 2021 5:00 PM | 0 | 1355,1350 | 0h | 01.06.BW.01.02.08 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1357 |  | Auto Scheduled | 01.06: אחסנה.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 150h | 01.06.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1358 |  | Auto Scheduled | בנית דוח מלאי כולל ברמה המק"ט והמחסן לכל סוגי המלאי הצה"לי דוח זה יכלול את כל המלאי מכל סוגי האחסנה השונים SAP- WM וIM- ובנוסף כל המלאי במערכת WMS. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1359 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1360 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1361 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1362 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1361 | 10h | 01.06.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1363 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1362 | 20h | 01.06.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1364 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1363,1361 | 0h | 01.06.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1365 |  | Auto Scheduled | נדרש לאפיין דוחות תפעוליים או BW לתמיכה בבקרה כגון דו"ח שריונים פתוחים, דוחות שגויים, דוח מלאי חסום כולל סיבת חסימה ועוד. דוח זה יכלול את כל המלאי מכל סוגי האחסנה השונים SAP- WM וIM- ובנוסף כל המלאי במערכת WMS. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.04 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1366 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1367 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1368 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1369 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1368 | 10h | 01.06.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1370 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1369 | 20h | 01.06.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1371 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1370,1368 | 0h | 01.06.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1372 |  | Auto Scheduled | נדרש לאשר את רשימת מחסנים מיוחדים מול מנהלת ומפקדת מרה"ס - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.05 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1373 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1374 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1375 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1376 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1375 | 10h | 01.06.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1377 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1376 | 20h | 01.06.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1378 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1377,1375 | 0h | 01.06.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1379 |  | Auto Scheduled | נדרש לסכם את לו"ז מימוש פרויקט מנוף ולסכם את תפיסת המענה מול הזכיין - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.06 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1380 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1381 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1382 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1383 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1382 | 10h | 01.06.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1384 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1383 | 20h | 01.06.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1385 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1384,1382 | 0h | 01.06.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1386 |  | Auto Scheduled | נדרש ב לסכם בדיוני זכיין את ניהול רמות מלאי חירום וקו אדום בBP אחסנה של WMS . - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.07 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1387 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1388 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.06.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1389 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1390 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1389 | 10h | 01.06.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1391 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1390 | 20h | 01.06.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1392 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1391,1389 | 0h | 01.06.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1393 |  | Auto Scheduled | 01.06: אחסנה.INT | 550 days | January 10, 2020 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 282h | 01.06.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1394 |  | Auto Scheduled | מערכת SAP תשלח שדר למערכת WMS עם נתוני המלאי הנדרשים לחסימה/לשחרור (מק"ט, כמות וכושר), כולל סיבת חסימה. - INT | 514 days | January 10, 2020 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 72h | 01.06.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1395 |  | Auto Scheduled | Sub Tasks | 353 days | January 10, 2020 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 2h | 01.06.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1396 |  | Auto Scheduled | נדרש לבחון מול הזכיין חסימה אוטומטית | 1 day | January 10, 2020 8:00 AM | January 10, 2020 5:00 PM | 0 |  | 1h | 01.06.INT.01.01.01 | בוצע | ואל | MoM | ואל | BP | WMS | NA | Must Start On | 7
1397 |  | Auto Scheduled | מע’ זכיין מובילה מחסן מלאי באחריות זכיין שיקוף חסימת המלאי במע' SAP נדרש להחליט באיזה רמה יסוכם בדיון מבנה ארגוני (אתר / אתר אחסון) | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 01.06.INT.01.01.02 | בוצע | ואל | MoM | ואל | BP | INT | NA | As Soon As Possible | 7
1398 |  | Auto Scheduled | LifeCycle Tasks | 168 days | May 8, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1399 |  | Auto Scheduled | סיום משימות משנה לממשק | 1 day | May 19, 2021 8:00 AM | May 19, 2021 5:00 PM | 0 | 1397 | 0h | 01.06.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1400 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1401 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | May 8, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 1400 | 0h | 01.06.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1402 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 11, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 1401 | 25h | 01.06.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1403 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 16, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 1402 | 10h | 01.06.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1404 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 30, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 1403 | 10h | 01.06.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1405 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 13, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 1404 | 5h | 01.06.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1406 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 19, 2021 5:00 PM | August 19, 2021 5:00 PM | 0 | 1405,1399 | 0h | 01.06.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1407 |  | Auto Scheduled | מערכת WMS תשלח שדר למערכת SAP על נתוני המלאי שנחסמו/שוחררו. העדכון יכול להתבצע במספר פעימות. - INT | 197 days | May 18, 2021 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 70h | 01.06.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1408 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1409 |  | Auto Scheduled | LifeCycle Tasks | 197 days | May 18, 2021 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 70h | 01.06.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1410 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1411 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1412 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 44 days | October 8, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 | 1411 | 0h | 01.06.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1413 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 9, 2021 8:00 AM | January 12, 2022 5:00 PM | 0 | 1412 | 25h | 01.06.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1414 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 13, 2022 8:00 AM | January 26, 2022 5:00 PM | 0 | 1413 | 10h | 01.06.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1415 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 27, 2022 8:00 AM | February 9, 2022 5:00 PM | 0 | 1414 | 10h | 01.06.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1416 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 10, 2022 8:00 AM | February 16, 2022 5:00 PM | 0 | 1415 | 5h | 01.06.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1417 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | February 16, 2022 5:00 PM | February 16, 2022 5:00 PM | 0 | 1416,1410 | 0h | 01.06.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1418 |  | Auto Scheduled | מערכת WMS תשלח שדר למערכת SAP עם נתוני המלאי שנחסמו כולל סיבת חסימה. - INT | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1419 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1420 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1421 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1422 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1423 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 15/08/2021 | 16/08/2021 | 0 | 1422 | 0h | 01.06.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1424 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1423 | 25h | 01.06.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1425 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1424 | 10h | 01.06.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1426 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1425 | 10h | 01.06.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1427 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1426 | 5h | 01.06.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1428 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1427,1421 | 0h | 01.06.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1429 |  | Auto Scheduled | מערכת WMS תשלח שדר עם נתוני הבקשה למערכת SAP. - INT | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 70h | 01.06.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
1430 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1431 |  | Auto Scheduled | LifeCycle Tasks | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 70h | 01.06.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1432 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1433 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1434 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | November 5, 2021 8:00 AM | December 9, 2021 5:00 PM | 0 | 1433 | 0h | 01.06.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1435 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 10, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 1434 | 25h | 01.06.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1436 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 14, 2022 8:00 AM | January 27, 2022 5:00 PM | 0 | 1435 | 10h | 01.06.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1437 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 28, 2022 8:00 AM | February 10, 2022 5:00 PM | 0 | 1436 | 10h | 01.06.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1438 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 11, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 1437 | 5h | 01.06.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1439 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | February 17, 2022 5:00 PM | February 17, 2022 5:00 PM | 0 | 1438,1432 | 0h | 01.06.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
1440 |  | Auto Scheduled | 01.06: אחסנה.SAP | 273 days | March 5, 2021 8:00 AM | March 22, 2022 5:00 PM | 0 |  | 770h | 01.06.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1441 |  | Auto Scheduled | מערכת SAP תאפשר את תהליכי האחסנה ובדיקת החוקות כפי שקיים היום - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1442 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1443 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1444 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1445 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1446 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/07/2021 | 26/07/2021 | 0 | 1445 | 0h | 01.06.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1447 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1446 | 25h | 01.06.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1448 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1447 | 10h | 01.06.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1449 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1448 | 10h | 01.06.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1450 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1449 | 5h | 01.06.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1451 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1450,1444 | 0h | 01.06.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1452 |  | Auto Scheduled | מערכת SAP תמשיך לאפשר את היכולת חסימה/שחרור בשגרה ובחירום ע"ב טרנ' zlq02 zblkstk ברמת הWM - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1453 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1454 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1455 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1456 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1457 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/07/2021 | 27/07/2021 | 0 | 1456 | 0h | 01.06.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1458 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1457 | 25h | 01.06.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1459 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1458 | 10h | 01.06.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1460 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1459 | 10h | 01.06.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1461 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1460 | 5h | 01.06.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1462 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1461,1455 | 0h | 01.06.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1463 |  | Auto Scheduled | מערכת SAP תפתח שריון עם נתוני המלאי הנדרשים לחסימה/לשחרור בWMS. - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1464 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1465 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1466 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1467 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1468 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 28/07/2021 | 16/08/2021 | 0 | 1467 | 0h | 01.06.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1469 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1468 | 25h | 01.06.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1470 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1469 | 10h | 01.06.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1471 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1470 | 10h | 01.06.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1472 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1471 | 5h | 01.06.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1473 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1472,1466 | 0h | 01.06.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1474 |  | Auto Scheduled | ביצוע הפעולה ב-SAP תתבצע ע"ב הרשאות ייעודיות לבע"ת (ע"י אוכלוסיית אנשים ספציפית שתקבע בהמשך דוגמא הנחיית מנפ"ר). - SAP | 221 days | May 18, 2021 8:00 AM | March 22, 2022 5:00 PM | 0 |  | 70h | 01.06.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1475 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1476 |  | Auto Scheduled | LifeCycle Tasks | 221 days | May 18, 2021 8:00 AM | March 22, 2022 5:00 PM | 0 |  | 70h | 01.06.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1477 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1478 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1479 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | December 8, 2021 8:00 AM | January 11, 2022 5:00 PM | 0 | 1478 | 0h | 01.06.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1480 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 12, 2022 8:00 AM | February 15, 2022 5:00 PM | 0 | 1479 | 25h | 01.06.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1481 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 16, 2022 8:00 AM | March 1, 2022 5:00 PM | 0 | 1480 | 10h | 01.06.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1482 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 2, 2022 8:00 AM | March 15, 2022 5:00 PM | 0 | 1481 | 10h | 01.06.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1483 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 16, 2022 8:00 AM | March 22, 2022 5:00 PM | 0 | 1482 | 5h | 01.06.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1484 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | March 22, 2022 5:00 PM | March 22, 2022 5:00 PM | 0 | 1483,1477 | 0h | 01.06.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1485 |  | Auto Scheduled | מערכת SAP תאפשר שינוי סטאטוס המלאי ע"ב הנתונים שהגיעו מWMS . - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1486 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1487 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1488 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1489 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1490 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 16/08/2021 | 25/08/2021 | 0 | 1489 | 0h | 01.06.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1491 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1490 | 25h | 01.06.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1492 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1491 | 10h | 01.06.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1493 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1492 | 10h | 01.06.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1494 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1493 | 5h | 01.06.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1495 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1494,1488 | 0h | 01.06.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1496 |  | Auto Scheduled | מערכת SAP תציג את הבקשה (דרך עדכון בשולחן עבודה), ותאפשר התחלת תהליך חסימה/שחרור ע"ס בקשת מדיניות לפריט זו. - SAP | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 70h | 01.06.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1497 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1498 |  | Auto Scheduled | LifeCycle Tasks | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 70h | 01.06.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1499 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1500 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1501 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 5, 2021 8:00 AM | December 9, 2021 5:00 PM | 0 | 1500 | 0h | 01.06.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1502 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 10, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 1501 | 25h | 01.06.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1503 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 14, 2022 8:00 AM | January 27, 2022 5:00 PM | 0 | 1502 | 10h | 01.06.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1504 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 28, 2022 8:00 AM | February 10, 2022 5:00 PM | 0 | 1503 | 10h | 01.06.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1505 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 11, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 1504 | 5h | 01.06.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1506 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 17, 2022 5:00 PM | February 17, 2022 5:00 PM | 0 | 1505,1499 | 0h | 01.06.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1507 |  | Auto Scheduled | מערכת SAP תאפשר איחוד קודי סיבה בין המרכזים השונים - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1508 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1509 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1510 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1511 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1512 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 24/08/2021 | 26/08/2021 | 0 | 1511 | 0h | 01.06.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1513 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1512 | 25h | 01.06.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1514 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1513 | 10h | 01.06.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1515 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1514 | 10h | 01.06.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1516 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1515 | 5h | 01.06.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1517 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1516,1510 | 0h | 01.06.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1518 |  | Auto Scheduled | קיסטום סיבות לתנועה 977/978 על פי סיבות החסימה שברשימת קודי הסיבות המאוחד. - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1519 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1520 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1521 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1522 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1523 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 18/08/2021 | 19/08/2021 | 0 | 1522 | 0h | 01.06.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1524 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1523 | 25h | 01.06.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1525 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1524 | 10h | 01.06.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1526 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1525 | 10h | 01.06.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1527 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1526 | 5h | 01.06.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1528 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1527,1521 | 0h | 01.06.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1529 |  | Auto Scheduled | הסבת נתונים פרויקט מנוף - SAP | 214 days | March 5, 2021 8:00 AM | December 29, 2021 5:00 PM | 0.02 |  | 70h | 01.06.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1530 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1531 |  | Auto Scheduled | LifeCycle Tasks | 214 days | March 5, 2021 8:00 AM | December 29, 2021 5:00 PM | 0.02 |  | 70h | 01.06.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1532 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1533 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1534 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 5, 2021 8:00 AM | April 8, 2021 5:00 PM | 7.0000000000000007E-2 | 1533 | 0h | 01.06.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1535 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 9, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 1534 | 25h | 01.06.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1536 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 14, 2021 8:00 AM | May 27, 2021 5:00 PM | 0 | 1535 | 10h | 01.06.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1537 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 28, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 1536 | 10h | 01.06.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1538 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 11, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 1537 | 5h | 01.06.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1539 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 17, 2021 5:00 PM | June 17, 2021 5:00 PM | 0 | 1538,1532 | 0h | 01.06.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1540 |  | Auto Scheduled | טרום מבצוע בה"ס דרום נדרש לאפשר במערכת SAP להזין את נתוני האריזות כחלק מפרויקט מנו"ף. - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1541 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1542 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1543 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1544 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1545 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 28/07/2021 | 30/08/2021 | 0 | 1544 | 0h | 01.06.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1546 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1545 | 25h | 01.06.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1547 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1546 | 10h | 01.06.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1548 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1547 | 10h | 01.06.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1549 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1548 | 5h | 01.06.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1550 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1549,1543 | 0h | 01.06.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1551 |  | Auto Scheduled | תחזוק חוקת הרשאות ב-SAP לבע"ת צבאיים לביצוע הפעולה לחסימה ב-WMS - SAP | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1552 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1553 |  | Auto Scheduled | LifeCycle Tasks | 162 days | May 18, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 |  | 70h | 01.06.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1554 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.06.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1555 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 2, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2441 | 20h | 01.06.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1556 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/08/2021 | 31/08/2021 | 0 | 1555 | 0h | 01.06.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1557 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1556 | 25h | 01.06.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1558 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1557 | 10h | 01.06.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1559 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1558 | 10h | 01.06.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1560 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1559 | 5h | 01.06.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1561 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1560,1554 | 0h | 01.06.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1562 |  | Auto Scheduled | 01.07: חוקת המלאי | 160 days | May 18, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 |  | 200h | 01.07 | סיכום מסמך | מוריה | hd | עינת |  | BP | NA | As Soon As Possible | 3
1563 |  | Auto Scheduled | 01.07: חוקת המלאי.BP | 160 days | May 18, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 |  | 200h | 01.07.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1564 |  | Auto Scheduled | 01.07: חוקת המלאי - BP | 160 days | May 18, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 |  | 200h | 01.07.BP.01 | סיכום מסמך | מוריה | parent | עינת |  | BP | NA | As Soon As Possible | 5
1565 |  | Auto Scheduled | Sub Tasks | 160 days | May 18, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 |  | 160h | 01.07.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1566 |  | Auto Scheduled | כתיבת מסמך | 56 days | May 18, 2021 8:00 AM | August 3, 2021 5:00 PM | 0 |  | 56h | 01.07.BP.01.01.20 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | Must Start On | 7
1567 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 12 days | August 4, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 1566 | 12h | 01.07.BP.01.01.21 | בוצע | מוריה | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1568 |  | Auto Scheduled | אישור אבי | 46 days | August 20, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 1567 | 46h | 01.07.BP.01.01.22 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1569 |  | Auto Scheduled | אישור המנהלת | 0 days | October 22, 2021 5:00 PM | October 22, 2021 5:00 PM | 0 | 1568 | 0h | 01.07.BP.01.01.23 | בוצע | סיגל | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1570 |  | Auto Scheduled | אישור מפקדת | 42 days | October 25, 2021 8:00 AM | December 21, 2021 5:00 PM | 0 | 1569 | 42h | 01.07.BP.01.01.24 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1571 |  | Auto Scheduled | אישור חטלו"ג | 1 day | December 22, 2021 8:00 AM | December 22, 2021 5:00 PM | 0 | 1570 | 1h | 01.07.BP.01.01.25 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1572 |  | Auto Scheduled | אישור מקל"ר | 1 day | December 23, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 1571 | 1h | 01.07.BP.01.01.26 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1573 |  | Auto Scheduled | אישור ניר בשן | 1 day | December 24, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 1572 | 1h | 01.07.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1574 |  | Auto Scheduled | אישור שגיב שרביט | 1 day | December 27, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 | 1573 | 1h | 01.07.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1575 |  | Auto Scheduled | LifeCycle Tasks | 160 days | May 18, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 |  | 40h | 01.07.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1576 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 27, 2021 5:00 PM | December 27, 2021 5:00 PM | 0 | 1574 | 0h | 01.07.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1577 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.07.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1578 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1577 | 10h | 01.07.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1579 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1578 | 5h | 01.07.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1580 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1579 | 10h | 01.07.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1581 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1580 | 10h | 01.07.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1582 |  | Auto Scheduled | בחתימה | 0 days | December 27, 2021 5:00 PM | December 27, 2021 5:00 PM | 0 | 1581,1576 | 0h | 01.07.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1583 |  | Auto Scheduled | חתום | 0 days | December 27, 2021 5:00 PM | December 27, 2021 5:00 PM | 0 | 1582 | 0h | 01.07.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1584 |  | Auto Scheduled | 01.09: 1003 | 249 days | May 18, 2021 8:00 AM | April 29, 2022 5:00 PM | 0 |  | 205h | 01.09 | בחתימה | מוריה | hd | מורן |  | BP | NA | As Soon As Possible | 3
1585 |  | Auto Scheduled | 01.09: 1003.BP | 249 days | May 18, 2021 8:00 AM | April 29, 2022 5:00 PM | 0 |  | 175h | 01.09.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1586 |  | Auto Scheduled | 01.09: 1003 - BP | 249 days | May 18, 2021 8:00 AM | April 29, 2022 5:00 PM | 0 |  | 175h | 01.09.BP.01 | בחתימה | מוריה | parent | מורן |  | BP | NA | As Soon As Possible | 5
1587 |  | Auto Scheduled | Sub Tasks | 249 days | May 18, 2021 8:00 AM | April 29, 2022 5:00 PM | 0 |  | 135h | 01.09.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1588 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.09.BP.01.01.20 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | Must Start On | 7
1589 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.09.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1590 |  | Auto Scheduled | אישור מקל"ר | 10 days | June 2, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 1589 | 10h | 01.09.BP.01.01.22 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1591 |  | Auto Scheduled | אישור אבי | 11 days | June 16, 2021 8:00 AM | June 30, 2021 5:00 PM | 0 | 1590 | 11h | 01.09.BP.01.01.23 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1592 |  | Auto Scheduled | אישור המנהלת | 3 days | July 1, 2021 8:00 AM | July 5, 2021 5:00 PM | 0 | 1591 | 3h | 01.09.BP.01.01.24 | בוצע | ואל | MoM | ואל | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1593 |  | Auto Scheduled | אישור מפקדת | 22 days | July 6, 2021 8:00 AM | August 4, 2021 5:00 PM | 0 | 1592 | 2h | 01.09.BP.01.01.25 | בוצע | ואל | MoM | ואל | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1594 |  | Auto Scheduled | אישור חטלו"ג | 131 days | August 5, 2021 8:00 AM | February 3, 2022 5:00 PM | 0 | 1593 | 5h | 01.09.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
1595 |  | Auto Scheduled | אישור שגיב שרביט | 2 days | February 4, 2022 8:00 AM | February 7, 2022 5:00 PM | 0 | 1594 | 23h | 01.09.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1596 |  | Auto Scheduled | אישור ניר בשן | 59 days | February 8, 2022 8:00 AM | April 29, 2022 5:00 PM | 0 | 1595 | 59h | 01.09.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1597 |  | Auto Scheduled | LifeCycle Tasks | 249 days | May 18, 2021 8:00 AM | April 29, 2022 5:00 PM | 0 |  | 40h | 01.09.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1598 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | April 29, 2022 5:00 PM | April 29, 2022 5:00 PM | 0 | 1596 | 0h | 01.09.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1599 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.09.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1600 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1599 | 10h | 01.09.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1601 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1600 | 5h | 01.09.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1602 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1601 | 10h | 01.09.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1603 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1602 | 10h | 01.09.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1604 |  | Auto Scheduled | בחתימה | 0 days | April 29, 2022 5:00 PM | April 29, 2022 5:00 PM | 0 | 1603,1598 | 0h | 01.09.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1605 |  | Auto Scheduled | חתום | 0 days | April 29, 2022 5:00 PM | April 29, 2022 5:00 PM | 0 | 1604 | 0h | 01.09.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1606 |  | Auto Scheduled | 01.09: 1003.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.09.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1607 |  | Auto Scheduled | נדרש לאפיין את הדוחות BI של SAP ו- WMS לתנועות המלאי המייצגים טפסי 1003 ולקבוע האם הדו"חות אונליין או יומיים. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.09.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1608 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.09.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1609 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.09.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1610 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.09.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1611 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1610 | 10h | 01.09.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1612 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1611 | 20h | 01.09.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1613 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1612,1610 | 0h | 01.09.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1614 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים | 792 days | February 3, 2020 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 1,523h | 01.11 | חתום | מאיה | hd | עינת |  | BP | NA | As Soon As Possible | 3
1615 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.BP | 114 days | May 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 |  | 168h | 01.11.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1616 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים - BP | 114 days | May 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 |  | 168h | 01.11.BP.01 | חתום | מאיה | parent | עינת |  | BP | NA | As Soon As Possible | 5
1617 |  | Auto Scheduled | Sub Tasks | 114 days | May 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 |  | 128h | 01.11.BP.01.01 |  | מאיה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1618 |  | Auto Scheduled | יש להגדיר כיצד יתבצע ספירת פריטים מיוחדים | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 01.11.BP.01.01.01 | בוצע | עינת | MoM | עינת | BP | BP | NA | Must Start On | 7
1619 |  | Auto Scheduled | יש להתאים בSAP את תדירות הספירה | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 01.11.BP.01.01.02 | בוצע | עינת | MoM | עינת | BP | BP | NA | As Soon As Possible | 7
1620 |  | Auto Scheduled | 1. טענה: הזכיין לא יכול לדווח על אי הילום מבלי להשלים /להיקנס--2. ממולץ להוסיף סטטוס נוסף במערכת הSAP לפני הסטטוס המומלץ לסגירת ההפרש --3. כיום בודקים האם פריט שנמצא בחוסר מול המרחב ובמידה ולא נמצא בודקים מול כל המרחבים, האם לזכיין תהיה האפשרות לחפש מלאי | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 01.11.BP.01.01.03 | בוצע | עינת | MoM | עינת | שרון רחמים | BP | NA | As Soon As Possible | 7
1621 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.11.BP.01.01.20 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1622 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.11.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1623 |  | Auto Scheduled | אישור אבי | 10 days | June 2, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 1622 | 10h | 01.11.BP.01.01.22 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1624 |  | Auto Scheduled | אישור מפקדת | 4 days | June 16, 2021 8:00 AM | June 21, 2021 5:00 PM | 0 | 1623 | 4h | 01.11.BP.01.01.23 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1625 |  | Auto Scheduled | אישור מקל"ר | 22 days | June 22, 2021 8:00 AM | July 21, 2021 5:00 PM | 0 | 1624 | 22h | 01.11.BP.01.01.24 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1626 |  | Auto Scheduled | אישור חטלו"ג | 16 days | July 22, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 1625 | 16h | 01.11.BP.01.01.25 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1627 |  | Auto Scheduled | אישור המנהלת | 14 days | August 13, 2021 8:00 AM | September 1, 2021 5:00 PM | 0 | 1626 | 14h | 01.11.BP.01.01.26 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1628 |  | Auto Scheduled | אישור שגיב שרביט | 27 days | September 2, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 1627 | 27h | 01.11.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1629 |  | Auto Scheduled | אישור ניר בשן | 10 days | October 11, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 1628 | 10h | 01.11.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
1630 |  | Auto Scheduled | LifeCycle Tasks | 114 days | May 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 |  | 40h | 01.11.BP.01.02 |  | מאיה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1631 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | October 22, 2021 5:00 PM | October 22, 2021 5:00 PM | 0 | 1629 | 0h | 01.11.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1632 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.11.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1633 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1632 | 10h | 01.11.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1634 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1633 | 5h | 01.11.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1635 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1634 | 10h | 01.11.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1636 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1635 | 10h | 01.11.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1637 |  | Auto Scheduled | בחתימה | 0 days | October 22, 2021 5:00 PM | October 22, 2021 5:00 PM | 0 | 1636,1631 | 0h | 01.11.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1638 |  | Auto Scheduled | חתום | 0 days | October 22, 2021 5:00 PM | October 22, 2021 5:00 PM | 0 | 1637 | 0h | 01.11.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1639 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.BW | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 55h | 01.11.BW |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1640 |  | Auto Scheduled | בדיקת התכנות שדוח BI ממערכת הזכיין תהיה משוקפת לדוח (BW)BI במערכת הsap - BW | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 55h | 01.11.BW.01 | יישום ופיתוח דו"ח |  | parent |  | requirements | BW | NA | As Soon As Possible | 5
1641 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.BW.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1642 |  | Auto Scheduled | LifeCycle Tasks | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 55h | 01.11.BW.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1643 |  | Auto Scheduled | סיום משימות משנה לדוחות ניהול | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.BW.01.02.01 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1644 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.BW.01.02.02 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1645 |  | Manually Scheduled | יישום ופיתוח דו"ח | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 1644 | 0h | 01.11.BW.01.02.03 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1646 |  | Auto Scheduled | פיתוח בדיקות קבלה | 10 days | February 4, 2020 8:00 AM | February 17, 2020 5:00 PM | 0 | 1645 | 10h | 01.11.BW.01.02.04 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1647 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 18, 2020 8:00 AM | March 2, 2020 5:00 PM | 0 | 1646 | 10h | 01.11.BW.01.02.05 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1648 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 3, 2020 8:00 AM | March 16, 2020 5:00 PM | 0 | 1647 | 10h | 01.11.BW.01.02.06 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1649 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 17, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 1648 | 5h | 01.11.BW.01.02.07 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1650 |  | Auto Scheduled | משימת דו"ח עלתה לאויר | 0 days | January 14, 2022 5:00 PM | January 14, 2022 5:00 PM | 0 | 1649,1644 | 0h | 01.11.BW.01.02.08 |  |  | rule |  |  | BW | NA | As Soon As Possible | 7
1651 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 180h | 01.11.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1652 |  | Auto Scheduled | אפיון דוחות ייעודים עבור שליטה ובקרה של תדירויות הספירה WMS - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.05 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1653 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1654 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1655 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1656 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1655 | 10h | 01.11.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1657 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1656 | 20h | 01.11.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1658 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1657,1655 | 0h | 01.11.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1659 |  | Auto Scheduled | בדיקת היתכנות שדוח BI ממערכת הזכיין תהיה משוקפת לדוח (BW)BI במערכת הsap - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.06 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1660 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1661 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1662 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1663 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1662 | 10h | 01.11.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1664 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1663 | 20h | 01.11.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1665 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1664,1662 | 0h | 01.11.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1666 |  | Auto Scheduled | נדרש לאפיין דוחות עבור דרג מטכ"לי לבקרה וניהול שליטה בספירות ורמות מלאי ( כגון דו"ח הפרשים, דוח הפרשים כספיים, דו"ח אובדנים) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.07 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1667 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1668 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1669 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1670 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1669 | 10h | 01.11.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1671 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1670 | 20h | 01.11.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1672 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1671,1669 | 0h | 01.11.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1673 |  | Auto Scheduled | נדרש לתקן את ה WF של משק הדלק בSAP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.10 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1674 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1675 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1676 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.10.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1677 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1676 | 10h | 01.11.GEN.10.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1678 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1677 | 20h | 01.11.GEN.10.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1679 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1678,1676 | 0h | 01.11.GEN.10.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1680 |  | Auto Scheduled | נדרש לקבל את החוקה עבור פריטים ייעודיים שנפתח עבורפ אי הילום לא חלוט - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.14 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1681 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1682 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1683 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.14.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1684 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1683 | 10h | 01.11.GEN.14.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1685 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1684 | 20h | 01.11.GEN.14.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1686 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1685,1683 | 0h | 01.11.GEN.14.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1687 |  | Auto Scheduled | WMS - הזכיין יידרש לתעד אצלו במערכת מי הבע"ת (גורם צבאי) שאישר את האי הילום הלא חלוט לאי הילום חלוט. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.15 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1688 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1689 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.11.GEN.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1690 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.GEN.15.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1691 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1690 | 10h | 01.11.GEN.15.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1692 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1691 | 20h | 01.11.GEN.15.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1693 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1692,1690 | 0h | 01.11.GEN.15.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1694 |  | Auto Scheduled | 01.11: ספירות מלאי, טיפול בהפרשים ואובדנים.SAP | 792 days | February 3, 2020 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 1,120h | 01.11.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1695 |  | Auto Scheduled | מערכת SAP תחזיק את חוקת תדירויות סוגי הספירה עבור מחסנים מנוהלי WMS למטרות בקרה במערכת הSAP - SAP | 246 days | February 5, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1696 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1697 |  | Auto Scheduled | LifeCycle Tasks | 246 days | February 5, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1698 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1699 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1700 |  | Manually Scheduled | יישום ופיתוח סאפ | 42 days | February 5, 2021 8:00 AM | April 5, 2021 5:00 PM | 0 | 1699 | 0h | 01.11.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1701 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 6, 2021 8:00 AM | May 10, 2021 5:00 PM | 0 | 1700 | 25h | 01.11.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1702 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 | 1701 | 10h | 01.11.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1703 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1702 | 10h | 01.11.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1704 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1703 | 5h | 01.11.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1705 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 14, 2021 5:00 PM | June 14, 2021 5:00 PM | 0 | 1704,1698 | 0h | 01.11.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1706 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת תכנון ספירה עבור מחסנים מיוחדים תחת אתר מרה"ס - SAP | 413 days | January 9, 2021 8:00 AM | August 10, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1707 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1708 |  | Auto Scheduled | LifeCycle Tasks | 413 days | January 9, 2021 8:00 AM | August 10, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1709 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1710 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1711 |  | Manually Scheduled | יישום ופיתוח סאפ | 364 days | January 9, 2021 8:00 AM | June 1, 2022 5:00 PM | 0 | 1710 | 0h | 01.11.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1712 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 2, 2022 8:00 AM | July 6, 2022 5:00 PM | 0 | 1711 | 25h | 01.11.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1713 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 7, 2022 8:00 AM | July 20, 2022 5:00 PM | 0 | 1712 | 10h | 01.11.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1714 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 21, 2022 8:00 AM | August 3, 2022 5:00 PM | 0 | 1713 | 10h | 01.11.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1715 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 4, 2022 8:00 AM | August 10, 2022 5:00 PM | 0 | 1714 | 5h | 01.11.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1716 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 10, 2022 5:00 PM | August 10, 2022 5:00 PM | 0 | 1715,1709 | 0h | 01.11.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1717 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סיריאלים וסדרות חדשות - SAP | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1718 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1719 |  | Auto Scheduled | LifeCycle Tasks | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1720 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1721 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1722 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 1721 | 0h | 01.11.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1723 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 4, 2020 8:00 AM | March 9, 2020 5:00 PM | 0 | 1722 | 25h | 01.11.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1724 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 10, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 1723 | 10h | 01.11.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1725 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 24, 2020 8:00 AM | April 6, 2020 5:00 PM | 0 | 1724 | 10h | 01.11.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1726 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 7, 2020 8:00 AM | April 13, 2020 5:00 PM | 0 | 1725 | 5h | 01.11.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1727 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1726,1720 | 0h | 01.11.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1728 |  | Auto Scheduled | מערכת SAP תאפשר תהליך דיווח אובדנים שהתקבל דרך הפרש ממערכת SAP או ממערכת WMS - SAP | 226 days | March 5, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1729 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1730 |  | Auto Scheduled | LifeCycle Tasks | 226 days | March 5, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1731 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1732 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1733 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 5, 2021 8:00 AM | April 8, 2021 5:00 PM | 0 | 1732 | 0h | 01.11.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1734 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 9, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 1733 | 25h | 01.11.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1735 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 14, 2021 8:00 AM | May 27, 2021 5:00 PM | 0 | 1734 | 10h | 01.11.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1736 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 28, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 1735 | 10h | 01.11.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1737 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 11, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 1736 | 5h | 01.11.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1738 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 17, 2021 5:00 PM | June 17, 2021 5:00 PM | 0 | 1737,1731 | 0h | 01.11.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1739 |  | Auto Scheduled | מערכת SAP תאפשר תהליך השוואה בין האובדנים המדווחים לבין מציאת פריט מאובדן "בעודף" במערכת SAP/WMS - SAP | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1740 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1741 |  | Auto Scheduled | LifeCycle Tasks | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1742 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1743 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1744 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | October 5, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 1743 | 0h | 01.11.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1745 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 9, 2021 8:00 AM | December 13, 2021 5:00 PM | 0 | 1744 | 25h | 01.11.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1746 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 14, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 | 1745 | 10h | 01.11.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1747 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 28, 2021 8:00 AM | January 10, 2022 5:00 PM | 0 | 1746 | 10h | 01.11.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1748 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 11, 2022 8:00 AM | January 17, 2022 5:00 PM | 0 | 1747 | 5h | 01.11.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1749 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 1748,1742 | 0h | 01.11.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1750 |  | Auto Scheduled | תנועת המלאי בSAP יתבצעו בעקבות יצירת מסמך ספירה עבור המק"טים שיש להם הפרש.--מסמך הספירה יקושר למסמכ/י הספירה שנוצרו בWMS.-- - SAP | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1751 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1752 |  | Auto Scheduled | LifeCycle Tasks | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1753 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1754 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1755 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | October 5, 2021 8:00 AM | November 7, 2021 5:00 PM | 0 | 1754 | 0h | 01.11.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1756 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 8, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 1755 | 25h | 01.11.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1757 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 13, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 1756 | 10h | 01.11.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1758 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 27, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 1757 | 10h | 01.11.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1759 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 10, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 1758 | 5h | 01.11.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1760 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 14, 2022 5:00 PM | January 14, 2022 5:00 PM | 0 | 1759,1753 | 0h | 01.11.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1761 |  | Auto Scheduled | נדרש להציג אי הילום לא חלוט במערכת ה-SAP - SAP | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1762 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1763 |  | Auto Scheduled | LifeCycle Tasks | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1764 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1765 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1766 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 21/06/2021 | 30/06/2021 | 0 | 1765 | 0h | 01.11.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1767 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1766 | 25h | 01.11.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1768 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1767 | 10h | 01.11.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1769 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1768 | 10h | 01.11.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1770 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1769 | 5h | 01.11.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1771 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1770,1764 | 0h | 01.11.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1772 |  | Auto Scheduled | מערכת SAP תאפשר סבב אישורים להפרשים כפי שקיים היום שהגיעו ממחסנים בתפעול SAP בלבד - SAP | 196 days | May 18, 2021 8:00 AM | February 15, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1773 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1774 |  | Auto Scheduled | LifeCycle Tasks | 196 days | May 18, 2021 8:00 AM | February 15, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1775 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1776 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1777 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 3, 2021 8:00 AM | December 7, 2021 5:00 PM | 0 | 1776 | 0h | 01.11.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1778 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 8, 2021 8:00 AM | January 11, 2022 5:00 PM | 0 | 1777 | 25h | 01.11.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1779 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 12, 2022 8:00 AM | January 25, 2022 5:00 PM | 0 | 1778 | 10h | 01.11.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1780 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 26, 2022 8:00 AM | February 8, 2022 5:00 PM | 0 | 1779 | 10h | 01.11.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1781 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 9, 2022 8:00 AM | February 15, 2022 5:00 PM | 0 | 1780 | 5h | 01.11.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1782 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 15, 2022 5:00 PM | February 15, 2022 5:00 PM | 0 | 1781,1775 | 0h | 01.11.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1783 |  | Auto Scheduled | מערכת SAP תאפשר ביצוע קיזוז ידני וקיזוז אוטומטי לפי החוקות הקיימות - SAP | 203 days | April 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1784 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1785 |  | Auto Scheduled | LifeCycle Tasks | 203 days | April 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1786 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1787 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1788 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | April 7, 2021 8:00 AM | May 11, 2021 5:00 PM | 0 | 1787 | 0h | 01.11.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1789 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 12, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 1788 | 25h | 01.11.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1790 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 1789 | 10h | 01.11.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1791 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 1790 | 10h | 01.11.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1792 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 14, 2021 8:00 AM | July 20, 2021 5:00 PM | 0 | 1791 | 5h | 01.11.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1793 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 20, 2021 5:00 PM | July 20, 2021 5:00 PM | 0 | 1792,1786 | 0h | 01.11.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1794 |  | Auto Scheduled | הפרשים פתוחים, אובדנים פתוחים, ספירות פתוחות - SAP | 203 days | April 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1795 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1796 |  | Auto Scheduled | LifeCycle Tasks | 203 days | April 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1797 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1798 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1799 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | April 7, 2021 8:00 AM | April 7, 2021 5:00 PM | 0 | 1798 | 0h | 01.11.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1800 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 8, 2021 8:00 AM | May 12, 2021 5:00 PM | 0 | 1799 | 25h | 01.11.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1801 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 13, 2021 8:00 AM | May 26, 2021 5:00 PM | 0 | 1800 | 10h | 01.11.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1802 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 27, 2021 8:00 AM | June 9, 2021 5:00 PM | 0 | 1801 | 10h | 01.11.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1803 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 10, 2021 8:00 AM | June 16, 2021 5:00 PM | 0 | 1802 | 5h | 01.11.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1804 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 16, 2021 5:00 PM | June 16, 2021 5:00 PM | 0 | 1803,1797 | 0h | 01.11.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1805 |  | Auto Scheduled | מערכת SAP תאפשר ארגון מחדש של עץ ה-WF בעקבות השינויים של בעלי התפקידים וההרשאות שלהם - SAP | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.11.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1806 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1807 |  | Auto Scheduled | LifeCycle Tasks | 456 days | May 18, 2021 8:00 AM | February 14, 2023 5:00 PM | 0 |  | 70h | 01.11.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1808 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1809 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1810 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 2, 2022 8:00 AM | December 6, 2022 5:00 PM | 0 | 1809 | 0h | 01.11.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1811 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 7, 2022 8:00 AM | January 10, 2023 5:00 PM | 0 | 1810 | 25h | 01.11.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1812 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 11, 2023 8:00 AM | January 24, 2023 5:00 PM | 0 | 1811 | 10h | 01.11.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1813 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 25, 2023 8:00 AM | February 7, 2023 5:00 PM | 0 | 1812 | 10h | 01.11.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1814 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 8, 2023 8:00 AM | February 14, 2023 5:00 PM | 0 | 1813 | 5h | 01.11.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1815 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 14, 2023 5:00 PM | February 14, 2023 5:00 PM | 0 | 1814,1808 | 0h | 01.11.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1816 |  | Auto Scheduled | מערכת SAP תאפשר ניהול Log שגויים הרלוונטיים לתהליך הספירות - SAP | 203 days | April 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1817 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1818 |  | Auto Scheduled | LifeCycle Tasks | 203 days | April 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1819 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1820 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1821 |  | Manually Scheduled | יישום ופיתוח סאפ | 23 days | April 7, 2021 8:00 AM | May 7, 2021 5:00 PM | 0 | 1820 | 0h | 01.11.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1822 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 1821 | 25h | 01.11.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1823 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 14, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 1822 | 10h | 01.11.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1824 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 28, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 1823 | 10h | 01.11.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1825 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 12, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 1824 | 5h | 01.11.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1826 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 16, 2021 5:00 PM | July 16, 2021 5:00 PM | 0 | 1825,1819 | 0h | 01.11.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1827 |  | Auto Scheduled | מערכת SAP נדרש לפתח יכולת תוכנית ספירות מובנית (כפי שקיים היום בדרג הנפרש)רשומות תכנון עבור מחסנים מיוחדים (ניהול צבאי) באתר מרה"ס - SAP | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1828 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1829 |  | Auto Scheduled | LifeCycle Tasks | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1830 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1831 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1832 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 24/03/2022 | 14/07/2022 | 0 | 1831 | 0h | 01.11.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1833 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1832 | 25h | 01.11.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1834 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1833 | 10h | 01.11.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1835 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1834 | 10h | 01.11.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1836 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1835 | 5h | 01.11.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1837 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1836,1830 | 0h | 01.11.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1838 |  | Auto Scheduled | בדומה לדרג הנפרש נדרש כי יישלח מייל עבור פתיחת אובדן לדרג המטכ"ל ובע"ת רלוונטיים - SAP | 204 days | April 6, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1839 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1840 |  | Auto Scheduled | LifeCycle Tasks | 204 days | April 6, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1841 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1842 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1843 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | April 6, 2021 8:00 AM | May 9, 2021 5:00 PM | 0 | 1842 | 0h | 01.11.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1844 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 1843 | 25h | 01.11.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1845 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 14, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 1844 | 10h | 01.11.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1846 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 28, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 1845 | 10h | 01.11.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1847 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 12, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 1846 | 5h | 01.11.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1848 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 16, 2021 5:00 PM | July 16, 2021 5:00 PM | 0 | 1847,1841 | 0h | 01.11.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1849 |  | Auto Scheduled | שליחת מייל כאשר יש אי הילום לא חלוט עבור פריטים ייעודיים שהמטכ"ל ייקבע - SAP | 268 days | January 6, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1850 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1851 |  | Auto Scheduled | LifeCycle Tasks | 268 days | January 6, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1852 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1853 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1854 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | January 6, 2021 8:00 AM | February 9, 2021 5:00 PM | 0 | 1853 | 0h | 01.11.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1855 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 10, 2021 8:00 AM | March 16, 2021 5:00 PM | 0 | 1854 | 25h | 01.11.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1856 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 17, 2021 8:00 AM | March 30, 2021 5:00 PM | 0 | 1855 | 10h | 01.11.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1857 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 31, 2021 8:00 AM | April 13, 2021 5:00 PM | 0 | 1856 | 10h | 01.11.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1858 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 14, 2021 8:00 AM | April 20, 2021 5:00 PM | 0 | 1857 | 5h | 01.11.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1859 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1858,1852 | 0h | 01.11.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1860 |  | Auto Scheduled | תיקוף דוחות קיימים אל מול שינוי מבנה ארגוני - SAP | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.16 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1861 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1862 |  | Auto Scheduled | LifeCycle Tasks | 510 days | February 3, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.11.SAP.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1863 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.11.SAP.16.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1864 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 20, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2982 | 20h | 01.11.SAP.16.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1865 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 1864 | 0h | 01.11.SAP.16.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1866 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 4, 2020 8:00 AM | March 9, 2020 5:00 PM | 0 | 1865 | 25h | 01.11.SAP.16.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1867 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 10, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 1866 | 10h | 01.11.SAP.16.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1868 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 24, 2020 8:00 AM | April 6, 2020 5:00 PM | 0 | 1867 | 10h | 01.11.SAP.16.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1869 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 7, 2020 8:00 AM | April 13, 2020 5:00 PM | 0 | 1868 | 5h | 01.11.SAP.16.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1870 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1869,1863 | 0h | 01.11.SAP.16.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1871 |  | Auto Scheduled | 01.12: גריטות והשמדות | 564 days | February 3, 2020 8:00 AM | March 31, 2022 5:00 PM | 0 |  | 1,314h | 01.12 | חתום | מוריה | hd | גל |  | BP | NA | As Soon As Possible | 3
1872 |  | Auto Scheduled | 01.12: גריטות והשמדות.BP | 343 days | December 8, 2020 8:00 AM | March 31, 2022 5:00 PM | 0 |  | 144h | 01.12.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1873 |  | Auto Scheduled | 01.12: גריטות והשמדות - BP | 343 days | December 8, 2020 8:00 AM | March 31, 2022 5:00 PM | 0 |  | 144h | 01.12.BP.01 | חתום | מוריה | parent | גל |  | BP | NA | As Soon As Possible | 5
1874 |  | Auto Scheduled | Sub Tasks | 343 days | December 8, 2020 8:00 AM | March 31, 2022 5:00 PM | 0 |  | 104h | 01.12.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1875 |  | Auto Scheduled | כתיבת מסמך | 11 days | December 8, 2020 8:00 AM | December 22, 2020 5:00 PM | 0 |  | 11h | 01.12.BP.01.01.20 | בוצע | אבי | MoM | ואל | תע - מוריה | BP | NA | Must Start On | 7
1876 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.12.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
1877 |  | Auto Scheduled | אישור אבי | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.12.BP.01.01.22 | בוצע | אבי | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1878 |  | Auto Scheduled | אישור מקל"ר | 11 days | June 2, 2021 8:00 AM | June 16, 2021 5:00 PM | 0 | 1877 | 11h | 01.12.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1879 |  | Auto Scheduled | אישור המנהלת | 2 days | June 17, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 | 1878 | 2h | 01.12.BP.01.01.24 | בוצע | סיגל | MoM | ואל | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1880 |  | Auto Scheduled | אישור מפקדת | 11 days | June 21, 2021 8:00 AM | July 5, 2021 5:00 PM | 0 | 1879 | 11h | 01.12.BP.01.01.25 | בוצע | סיגל | MoM | ואל | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1881 |  | Auto Scheduled | אישור חטלו"ג | 152 days | July 6, 2021 8:00 AM | February 2, 2022 5:00 PM | 0 | 1880 | 6h | 01.12.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-18 00:00:00 | BP | NA | As Soon As Possible | 7
1882 |  | Auto Scheduled | אישור שגיב שרביט | 32 days | February 3, 2022 8:00 AM | March 18, 2022 5:00 PM | 0 | 1881 | 32h | 01.12.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1883 |  | Auto Scheduled | אישור ניר בשן | 9 days | March 21, 2022 8:00 AM | March 31, 2022 5:00 PM | 0 | 1882 | 9h | 01.12.BP.01.01.28 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
1884 |  | Auto Scheduled | LifeCycle Tasks | 228 days | May 18, 2021 8:00 AM | March 31, 2022 5:00 PM | 0 |  | 40h | 01.12.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1885 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | March 31, 2022 5:00 PM | March 31, 2022 5:00 PM | 0 | 1883 | 0h | 01.12.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1886 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.12.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1887 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 1886 | 10h | 01.12.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1888 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 1887 | 5h | 01.12.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1889 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1888 | 10h | 01.12.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1890 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 1889 | 10h | 01.12.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1891 |  | Auto Scheduled | בחתימה | 0 days | March 31, 2022 5:00 PM | March 31, 2022 5:00 PM | 0 | 1890,1885 | 0h | 01.12.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1892 |  | Auto Scheduled | חתום | 0 days | March 31, 2022 5:00 PM | March 31, 2022 5:00 PM | 0 | 1891 | 0h | 01.12.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
1893 |  | Auto Scheduled | 01.12: גריטות והשמדות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 120h | 01.12.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1894 |  | Auto Scheduled | נדרש לוודא תקינות דוחות החזרות וגריטות (שינוי מבנה ארגוני עבור המרכזים קיים שלב מקדים לשלב הגריטות, מדובר בכלי שבאמצעותו ניתן לבדוק פריטים שיש להכניס לתהליך גריטה עקב עודף מלאי (מעל השיא שהוגדר)- נדרש לוודא שיש ביטוי לדוח זה ב-בשלב המימוש בתהליך החזרות | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.04 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1895 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1896 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1897 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1898 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1897 | 10h | 01.12.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1899 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1898 | 20h | 01.12.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1900 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1899,1897 | 0h | 01.12.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1901 |  | Auto Scheduled | נדרש להגדיר עבור מצב עתידי סיבות לפסילה אחידות אשר יסוכמו מול המשתמשים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.06 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1902 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1903 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1904 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1905 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1904 | 10h | 01.12.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1906 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1905 | 20h | 01.12.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1907 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1906,1904 | 0h | 01.12.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1908 |  | Auto Scheduled | נדרש להשלים את תהליך החלטת ועדת הפסילה לאחר ביצוע ZVP1 בכדי לוודא שלא נותר מלאי חסום באתרי האחסון ברמת המרכז - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.08 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1909 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1910 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1911 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1912 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1911 | 10h | 01.12.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1913 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1912 | 20h | 01.12.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1914 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1913,1911 | 0h | 01.12.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1915 |  | Auto Scheduled | nan - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.09 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
1916 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1917 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.12.GEN.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1918 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.GEN.09.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1919 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 1918 | 10h | 01.12.GEN.09.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1920 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 1919 | 20h | 01.12.GEN.09.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1921 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 1920,1918 | 0h | 01.12.GEN.09.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
1922 |  | Auto Scheduled | 01.12: גריטות והשמדות.SAP | 490 days | February 3, 2020 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 1,050h | 01.12.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
1923 |  | Auto Scheduled | מערכת SAP תאפשר המשך גריטות למחסנים מיוחדים ולתהליכי משקי הדלק כפי שקיים היום - SAP | 75 days | March 5, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1924 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1925 |  | Auto Scheduled | LifeCycle Tasks | 75 days | March 5, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1926 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1927 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1928 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 5, 2021 8:00 AM | April 8, 2021 5:00 PM | 0 | 1927 | 0h | 01.12.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1929 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 9, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 1928 | 25h | 01.12.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1930 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 14, 2021 8:00 AM | May 27, 2021 5:00 PM | 0 | 1929 | 10h | 01.12.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1931 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 28, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 1930 | 10h | 01.12.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1932 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 11, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 1931 | 5h | 01.12.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1933 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 17, 2021 5:00 PM | June 17, 2021 5:00 PM | 0 | 1932,1926 | 0h | 01.12.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1934 |  | Auto Scheduled | מערכת SAP תבצע איחוד תהליך העבודה למשקי ציוד לחימה וחלפים ולמזון כפי שמתואר עבור מר"ץ ודלק - SAP | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1935 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1936 |  | Auto Scheduled | LifeCycle Tasks | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1937 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1938 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1939 |  | Manually Scheduled | יישום ופיתוח סאפ | 66 days | February 3, 2020 8:00 AM | May 3, 2020 5:00 PM | 0 | 1938 | 0h | 01.12.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1940 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 4, 2020 8:00 AM | June 5, 2020 5:00 PM | 0 | 1939 | 25h | 01.12.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1941 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 8, 2020 8:00 AM | June 19, 2020 5:00 PM | 0 | 1940 | 10h | 01.12.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1942 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 22, 2020 8:00 AM | July 3, 2020 5:00 PM | 0 | 1941 | 10h | 01.12.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1943 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 6, 2020 8:00 AM | July 10, 2020 5:00 PM | 0 | 1942 | 5h | 01.12.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1944 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1943,1937 | 0h | 01.12.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1945 |  | Auto Scheduled | מערכת SAP תאפשר עדכון כושר לפריט כמיועד לגריטה ע"ב מסכי ZMIKO 'ZMIG ' MIGO - SAP | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1946 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1947 |  | Auto Scheduled | LifeCycle Tasks | 356 days | February 3, 2020 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1948 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1949 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1950 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 0 | 1949 | 0h | 01.12.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1951 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 4, 2020 8:00 AM | March 9, 2020 5:00 PM | 0 | 1950 | 25h | 01.12.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1952 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 10, 2020 8:00 AM | March 23, 2020 5:00 PM | 0 | 1951 | 10h | 01.12.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1953 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 24, 2020 8:00 AM | April 6, 2020 5:00 PM | 0 | 1952 | 10h | 01.12.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1954 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 7, 2020 8:00 AM | April 13, 2020 5:00 PM | 0 | 1953 | 5h | 01.12.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1955 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1954,1948 | 0h | 01.12.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1956 |  | Auto Scheduled | מערכת SAP תבצע איחוד תהליך העבודה למשקי ציוד לחימה וחלפים ומזון כפי שמתואר עבור מר"ץ ודלק - SAP | 88 days | May 18, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1957 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1958 |  | Auto Scheduled | LifeCycle Tasks | 88 days | May 18, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1959 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1960 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1961 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 5, 2021 8:00 AM | July 8, 2021 5:00 PM | 0 | 1960 | 0h | 01.12.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1962 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 9, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 1961 | 25h | 01.12.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1963 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 13, 2021 8:00 AM | August 26, 2021 5:00 PM | 0 | 1962 | 10h | 01.12.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1964 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 27, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 1963 | 10h | 01.12.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1965 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 10, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 1964 | 5h | 01.12.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1966 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 16, 2021 5:00 PM | September 16, 2021 5:00 PM | 0 | 1965,1959 | 0h | 01.12.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1967 |  | Auto Scheduled | מערכת SAP תאפשר בחירת פריטים לועדת הגריטה ע"ב מסך ZVP1 - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1968 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1969 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1970 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1971 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1972 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 20/05/2021 | 25/05/2021 | 0 | 1971 | 0h | 01.12.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1973 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 1972 | 25h | 01.12.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1974 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 1973 | 10h | 01.12.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1975 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 1974 | 10h | 01.12.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1976 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 1975 | 5h | 01.12.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1977 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 1976,1970 | 0h | 01.12.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1978 |  | Auto Scheduled | מערכת SAP תאפשר בחירת סיבה לפסילה עבור כל תהליך ע"ב מסך ZVP1 - SAP | 115 days | January 5, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1979 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1980 |  | Auto Scheduled | LifeCycle Tasks | 115 days | January 5, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1981 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1982 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1983 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | January 5, 2021 8:00 AM | February 6, 2021 5:00 PM | 0 | 1982 | 0h | 01.12.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1984 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 8, 2021 8:00 AM | March 12, 2021 5:00 PM | 0 | 1983 | 25h | 01.12.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1985 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 15, 2021 8:00 AM | March 26, 2021 5:00 PM | 0 | 1984 | 10h | 01.12.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1986 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 29, 2021 8:00 AM | April 9, 2021 5:00 PM | 0 | 1985 | 10h | 01.12.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1987 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 12, 2021 8:00 AM | April 16, 2021 5:00 PM | 0 | 1986 | 5h | 01.12.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1988 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 1987,1981 | 0h | 01.12.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1989 |  | Auto Scheduled | מערכת SAP תאפשר בדיקת כושר לפריט ע"ב מסך ZVP1 - SAP | 158 days | January 6, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
1990 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
1991 |  | Auto Scheduled | LifeCycle Tasks | 158 days | January 6, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
1992 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1993 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1994 |  | Manually Scheduled | יישום ופיתוח סאפ | 109 days | January 6, 2021 8:00 AM | June 6, 2021 5:00 PM | 0 | 1993 | 0h | 01.12.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1995 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 7, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 1994 | 25h | 01.12.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1996 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 12, 2021 8:00 AM | July 23, 2021 5:00 PM | 0 | 1995 | 10h | 01.12.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1997 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 26, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 1996 | 10h | 01.12.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1998 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 9, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 1997 | 5h | 01.12.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
1999 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 13, 2021 5:00 PM | August 13, 2021 5:00 PM | 0 | 1998,1992 | 0h | 01.12.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2000 |  | Auto Scheduled | תהליך גריטה למחסנים בתפעול WMS - מערכת SAP תאפשר פתיחת שריון עם נתוני המק"ט לטובת ביצוע חסימת המלאי ע"ב מסך- ZVP1 - SAP | 91 days | February 6, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2001 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2002 |  | Auto Scheduled | LifeCycle Tasks | 91 days | February 6, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2003 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2004 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2005 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | February 6, 2021 8:00 AM | March 11, 2021 5:00 PM | 0 | 2004 | 0h | 01.12.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2006 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 12, 2021 8:00 AM | April 15, 2021 5:00 PM | 0 | 2005 | 25h | 01.12.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2007 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 16, 2021 8:00 AM | April 29, 2021 5:00 PM | 0 | 2006 | 10h | 01.12.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2008 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 30, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 2007 | 10h | 01.12.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2009 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 14, 2021 8:00 AM | May 20, 2021 5:00 PM | 0 | 2008 | 5h | 01.12.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2010 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 20, 2021 5:00 PM | May 20, 2021 5:00 PM | 0 | 2009,2003 | 0h | 01.12.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2011 |  | Auto Scheduled | מערכת SAP תאפשר קבלת החלטה על סוג הפעולה שתבוצע לפריט ע"ב מסך ZVP2 - SAP | 130 days | May 18, 2021 8:00 AM | November 15, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2012 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2013 |  | Auto Scheduled | LifeCycle Tasks | 130 days | May 18, 2021 8:00 AM | November 15, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2014 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2015 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2016 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | September 6, 2021 8:00 AM | September 6, 2021 5:00 PM | 0 | 2015 | 0h | 01.12.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2017 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 7, 2021 8:00 AM | October 11, 2021 5:00 PM | 0 | 2016 | 25h | 01.12.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2018 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 12, 2021 8:00 AM | October 25, 2021 5:00 PM | 0 | 2017 | 10h | 01.12.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2019 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 26, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 2018 | 10h | 01.12.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2020 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 9, 2021 8:00 AM | November 15, 2021 5:00 PM | 0 | 2019 | 5h | 01.12.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2021 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 15, 2021 5:00 PM | November 15, 2021 5:00 PM | 0 | 2020,2014 | 0h | 01.12.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2022 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת שריון עם נתוני המק"ט הישן והחדש ללא ביצוע תנועות מלאי /השמדות לפריט ע"ב מסך ZVP2 - SAP | 154 days | May 18, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2023 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2024 |  | Auto Scheduled | LifeCycle Tasks | 154 days | May 18, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2025 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2026 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2027 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2026 | 0h | 01.12.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2028 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 11, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2027 | 25h | 01.12.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2029 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 15, 2021 8:00 AM | November 26, 2021 5:00 PM | 0 | 2028 | 10h | 01.12.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2030 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 29, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 2029 | 10h | 01.12.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2031 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 13, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 | 2030 | 5h | 01.12.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2032 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 17, 2021 5:00 PM | December 17, 2021 5:00 PM | 0 | 2031,2025 | 0h | 01.12.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2033 |  | Auto Scheduled | מערכת SAP תעדכן את סטאטוס המלאי בשריון ע"ב הנתונים שהתקבלו מWMS. העדכון יכול להיות מבוצע במספר פעימות עבור מצל"ח, מר"צ, דלק - SAP | 75 days | May 4, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2034 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2035 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 4, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2036 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2037 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2038 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 4, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 2037 | 0h | 01.12.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2039 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 8, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 2038 | 25h | 01.12.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2040 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 13, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2039 | 10h | 01.12.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2041 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2040 | 10h | 01.12.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2042 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 10, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 | 2041 | 5h | 01.12.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2043 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 16, 2021 5:00 PM | August 16, 2021 5:00 PM | 0 | 2042,2036 | 0h | 01.12.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2044 |  | Auto Scheduled | מערכת SAP תעדכן את כושר הפריטים ע"ב הנתונים שהתקבלו מWMS. העדכון יכול להיות מבוצע במספר פעימות. עבור מצל"ח, מר"צ, דלק - SAP | 73 days | April 7, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2045 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2046 |  | Auto Scheduled | LifeCycle Tasks | 73 days | April 7, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2047 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2048 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2049 |  | Manually Scheduled | יישום ופיתוח סאפ | 23 days | April 7, 2021 8:00 AM | May 7, 2021 5:00 PM | 0 | 2048 | 0h | 01.12.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2050 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 2049 | 25h | 01.12.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2051 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 14, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 2050 | 10h | 01.12.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2052 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 28, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 2051 | 10h | 01.12.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2053 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 12, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 2052 | 5h | 01.12.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2054 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 16, 2021 5:00 PM | July 16, 2021 5:00 PM | 0 | 2053,2047 | 0h | 01.12.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2055 |  | Auto Scheduled | מערכת SAP תאפשר ביצוע תנועות מלאי לעדכון כושר הפריט והוצאתו ממלאי חסום - SAP | 72 days | May 7, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2056 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2057 |  | Auto Scheduled | LifeCycle Tasks | 72 days | May 7, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2058 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2059 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2060 |  | Manually Scheduled | יישום ופיתוח סאפ | 22 days | May 7, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 2059 | 0h | 01.12.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2061 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 8, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 2060 | 25h | 01.12.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2062 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 13, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2061 | 10h | 01.12.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2063 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2062 | 10h | 01.12.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2064 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 10, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 | 2063 | 5h | 01.12.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2065 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 16, 2021 5:00 PM | August 16, 2021 5:00 PM | 0 | 2064,2058 | 0h | 01.12.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2066 |  | Auto Scheduled | מערכת SAP תאפשר מעקב והדפסת טפסים של מסמכי חומר ע"ב מסך ZVP1P - SAP | 87 days | May 18, 2021 8:00 AM | September 15, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2067 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2068 |  | Auto Scheduled | LifeCycle Tasks | 87 days | May 18, 2021 8:00 AM | September 15, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2069 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2070 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2071 |  | Manually Scheduled | יישום ופיתוח סאפ | 23 days | June 7, 2021 8:00 AM | July 7, 2021 5:00 PM | 0 | 2070 | 0h | 01.12.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2072 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 8, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 2071 | 25h | 01.12.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2073 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 12, 2021 8:00 AM | August 25, 2021 5:00 PM | 0 | 2072 | 10h | 01.12.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2074 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 26, 2021 8:00 AM | September 8, 2021 5:00 PM | 0 | 2073 | 10h | 01.12.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2075 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 9, 2021 8:00 AM | September 15, 2021 5:00 PM | 0 | 2074 | 5h | 01.12.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2076 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 15, 2021 5:00 PM | September 15, 2021 5:00 PM | 0 | 2075,2069 | 0h | 01.12.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2077 |  | Auto Scheduled | מערכת SAP תאפשר תמיכה בתהליכי העבודה בהתאם לשינוי בעמ"ט הכושרים החדשה - SAP | 109 days | May 18, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2078 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2079 |  | Auto Scheduled | LifeCycle Tasks | 109 days | May 18, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 70h | 01.12.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2080 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.12.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2081 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3425 | 20h | 01.12.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2082 |  | Manually Scheduled | יישום ופיתוח סאפ | 24 days | July 7, 2021 8:00 AM | August 7, 2021 5:00 PM | 0 | 2081 | 0h | 01.12.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2083 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 9, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 2082 | 25h | 01.12.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2084 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 13, 2021 8:00 AM | September 24, 2021 5:00 PM | 0 | 2083 | 10h | 01.12.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2085 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 27, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2084 | 10h | 01.12.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2086 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 11, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 2085 | 5h | 01.12.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2087 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 15, 2021 5:00 PM | October 15, 2021 5:00 PM | 0 | 2086,2080 | 0h | 01.12.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2088 |  | Auto Scheduled | 01.14: מבנה ארגוני | 485 days | February 3, 2020 8:00 AM | December 10, 2021 5:00 PM | 8.0000000000000002E-2 |  | 1,139h | 01.14 | ממתין לאישור | ואל | hd | מאור |  | BP | NA | As Soon As Possible | 3
2089 |  | Auto Scheduled | 01.14: מבנה ארגוני.BP | 149 days | May 18, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 |  | 189h | 01.14.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2090 |  | Auto Scheduled | 01.14: מבנה ארגוני - BP | 149 days | May 18, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 |  | 189h | 01.14.BP.01 | ממתין לאישור | ואל | parent | מאור |  | BP | NA | As Soon As Possible | 5
2091 |  | Auto Scheduled | Sub Tasks | 149 days | May 18, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 |  | 149h | 01.14.BP.01.01 |  | ואל | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2092 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.14.BP.01.01.20 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | Must Start On | 7
2093 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 33 days | June 2, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 2092 | 33h | 01.14.BP.01.01.21 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2094 |  | Auto Scheduled | אישור אבי | 53 days | July 19, 2021 8:00 AM | September 29, 2021 5:00 PM | 0 | 2093 | 53h | 01.14.BP.01.01.22 | בוצע | אבי | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
2095 |  | Auto Scheduled | אישור מפקדת | 6 days | September 30, 2021 8:00 AM | October 7, 2021 5:00 PM | 0 | 2094 | 6h | 01.14.BP.01.01.23 | בוצע | ואל | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
2096 |  | Auto Scheduled | אישור מקל"ר | 1 day | October 8, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2095 | 1h | 01.14.BP.01.01.24 | בוצע |  | MoM |  | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
2097 |  | Auto Scheduled | אישור המנהלת | 1 day | October 11, 2021 8:00 AM | October 11, 2021 5:00 PM | 0 | 2096 | 1h | 01.14.BP.01.01.25 | בוצע | סיגל | MoM | ואל | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
2098 |  | Auto Scheduled | אישור שגיב שרביט | 7 days | October 12, 2021 8:00 AM | October 20, 2021 5:00 PM | 0 | 2097 | 7h | 01.14.BP.01.01.26 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2099 |  | Auto Scheduled | אישור ניר בשן | 36 days | October 21, 2021 8:00 AM | December 9, 2021 5:00 PM | 0 | 2098 | 36h | 01.14.BP.01.01.27 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
2100 |  | Auto Scheduled | אישור חטלו"ג | 1 day | December 10, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 2099 | 1h | 01.14.BP.01.01.28 | בוצע |  | MoM |  | 2020-10-22 00:00:00 | BP | NA | As Soon As Possible | 7
2101 |  | Auto Scheduled | LifeCycle Tasks | 149 days | May 18, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 |  | 40h | 01.14.BP.01.02 |  | ואל | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2102 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 10, 2021 5:00 PM | December 10, 2021 5:00 PM | 0 | 2100 | 0h | 01.14.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2103 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.14.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2104 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 2103 | 10h | 01.14.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2105 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 2104 | 5h | 01.14.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2106 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2105 | 10h | 01.14.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2107 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 2106 | 10h | 01.14.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2108 |  | Auto Scheduled | בחתימה | 0 days | December 10, 2021 5:00 PM | December 10, 2021 5:00 PM | 0 | 2107,2102 | 0h | 01.14.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2109 |  | Auto Scheduled | חתום | 0 days | December 10, 2021 5:00 PM | December 10, 2021 5:00 PM | 0 | 2108 | 0h | 01.14.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2110 |  | Auto Scheduled | 01.14: מבנה ארגוני.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 180h | 01.14.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2111 |  | Auto Scheduled | נדרש לסכם את הלו"ז הנדרש למבצוע בימ"ל בSAP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2112 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2113 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2114 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2115 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2114 | 10h | 01.14.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2116 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2115 | 20h | 01.14.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2117 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2116,2114 | 0h | 01.14.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2118 |  | Auto Scheduled | נדרש להעמיק בתהליכי העבודה בבימ"ל, פתרון יינתן במסגרת BP בימ"לים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.03 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2119 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2120 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2121 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2122 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2121 | 10h | 01.14.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2123 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2122 | 20h | 01.14.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2124 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2123,2121 | 0h | 01.14.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2125 |  | Auto Scheduled | נדרש לעדכן את צו ארגון ולסכם את הסימולים האפסנאים החדשים במרה"ס - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.05 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2126 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2127 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2128 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2129 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2128 | 10h | 01.14.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2130 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2129 | 20h | 01.14.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2131 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2130,2128 | 0h | 01.14.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2132 |  | Auto Scheduled | נדרש לאתר את כלל אתרי האחסון הקיימים היום למחלקות ולעמדות בבימ"לים שמתאחדים ולייצר אתרי אחסון אחודים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.07 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2133 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2134 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2135 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2136 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2135 | 10h | 01.14.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2137 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2136 | 20h | 01.14.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2138 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2137,2135 | 0h | 01.14.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2139 |  | Auto Scheduled | נדרש לסכם את כלל האובייטקים הSAP הנדרשים לתהליך העבודה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.12 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2140 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2141 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2142 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.12.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2143 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2142 | 10h | 01.14.GEN.12.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2144 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2143 | 20h | 01.14.GEN.12.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2145 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2144,2142 | 0h | 01.14.GEN.12.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2146 |  | Auto Scheduled | נדרש להפיץ פקודת ניקוי צינור וספירות טרם מבצוע הבה"סים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.13 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2147 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2148 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.14.GEN.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2149 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.GEN.13.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2150 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2149 | 10h | 01.14.GEN.13.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2151 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2150 | 20h | 01.14.GEN.13.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2152 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2151,2149 | 0h | 01.14.GEN.13.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2153 |  | Auto Scheduled | 01.14: מבנה ארגוני.SAP | 473 days | February 3, 2020 8:00 AM | November 24, 2021 5:00 PM | 0.11 |  | 770h | 01.14.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2154 |  | Auto Scheduled | יוגדרו שלושה אתרים חדשים במערכת SAP שייצגו את שלושת המרחבים הפיזיים (צפון, מרכז, דרום) ויכילו את מלאי מרה"ס - SAP | 191 days | March 3, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2155 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2156 |  | Auto Scheduled | LifeCycle Tasks | 191 days | March 3, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2157 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2158 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2159 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | March 3, 2021 8:00 AM | March 3, 2021 5:00 PM | 1 | 2158 | 0h | 01.14.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2160 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 4, 2021 8:00 AM | April 7, 2021 5:00 PM | 0 | 2159 | 25h | 01.14.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2161 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 8, 2021 8:00 AM | April 21, 2021 5:00 PM | 0 | 2160 | 10h | 01.14.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2162 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 22, 2021 8:00 AM | May 5, 2021 5:00 PM | 0 | 2161 | 10h | 01.14.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2163 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 6, 2021 8:00 AM | May 12, 2021 5:00 PM | 0 | 2162 | 5h | 01.14.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2164 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 2163,2157 | 0h | 01.14.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2165 |  | Auto Scheduled | עבור כל מרחב יוגדרו 10 אתרי אחסון במערכת SAP חדשים לכל בסיס במרחב המייצגים המלאי וכושרים-- - SAP | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2166 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2167 |  | Auto Scheduled | LifeCycle Tasks | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2168 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2169 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2170 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | September 3, 2021 8:00 AM | September 3, 2021 5:00 PM | 1 | 2169 | 0h | 01.14.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2171 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2170 | 25h | 01.14.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2172 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 2171 | 10h | 01.14.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2173 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 2172 | 10h | 01.14.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2174 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2173 | 5h | 01.14.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2175 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 2174,2168 | 0h | 01.14.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2176 |  | Auto Scheduled | יוגדר אתר אחסון חדש במערכת SAP המייצג את בסיס הלווין למרחב צפון בנפרד ולמרחב מרכז בנפרד - SAP | 473 days | February 3, 2020 8:00 AM | November 24, 2021 5:00 PM | 0 |  | 70h | 01.14.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2177 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2178 |  | Auto Scheduled | LifeCycle Tasks | 473 days | February 3, 2020 8:00 AM | November 24, 2021 5:00 PM | 0 |  | 70h | 01.14.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2179 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2180 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2181 |  | Manually Scheduled | יישום ופיתוח סאפ | 22 days | February 3, 2020 8:00 AM | March 3, 2020 5:00 PM | 0 | 2180 | 0h | 01.14.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2182 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 4, 2020 8:00 AM | April 7, 2020 5:00 PM | 0 | 2181 | 25h | 01.14.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2183 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 8, 2020 8:00 AM | April 21, 2020 5:00 PM | 0 | 2182 | 10h | 01.14.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2184 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 22, 2020 8:00 AM | May 5, 2020 5:00 PM | 0 | 2183 | 10h | 01.14.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2185 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 6, 2020 8:00 AM | May 12, 2020 5:00 PM | 0 | 2184 | 5h | 01.14.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2186 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 2185,2179 | 0h | 01.14.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2187 |  | Auto Scheduled | הכושר יוצג ע"ב הספרה האחרונה בספרור אתר האחסון במערכת SAP - SAP | 168 days | April 3, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.44 |  | 70h | 01.14.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2188 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2189 |  | Auto Scheduled | LifeCycle Tasks | 168 days | April 3, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.44 |  | 70h | 01.14.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2190 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2191 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2192 |  | Manually Scheduled | יישום ופיתוח סאפ | 66 days | April 3, 2021 8:00 AM | July 5, 2021 5:00 PM | 0.90000000000000002 | 2191 | 0h | 01.14.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2193 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 6, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2192 | 25h | 01.14.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2194 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2193 | 10h | 01.14.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2195 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 24, 2021 8:00 AM | September 6, 2021 5:00 PM | 0 | 2194 | 10h | 01.14.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2196 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 7, 2021 8:00 AM | September 13, 2021 5:00 PM | 0 | 2195 | 5h | 01.14.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2197 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 13, 2021 5:00 PM | September 13, 2021 5:00 PM | 0 | 2196,2190 | 0h | 01.14.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2198 |  | Auto Scheduled | לכל אתר אחסון יוגדר סימול אפסנאי חדש בהתאם לשינוי בצו ארגון שיבוצע במערכת הSAP. - SAP | 191 days | March 3, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 |  | 70h | 01.14.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2199 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2200 |  | Auto Scheduled | LifeCycle Tasks | 191 days | March 3, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 |  | 70h | 01.14.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2201 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2202 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2203 |  | Manually Scheduled | יישום ופיתוח סאפ | 89 days | March 3, 2021 8:00 AM | July 3, 2021 5:00 PM | 0 | 2202 | 0h | 01.14.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2204 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 5, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 2203 | 25h | 01.14.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2205 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 9, 2021 8:00 AM | August 20, 2021 5:00 PM | 0 | 2204 | 10h | 01.14.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2206 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 23, 2021 8:00 AM | September 3, 2021 5:00 PM | 0 | 2205 | 10h | 01.14.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2207 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 6, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 2206 | 5h | 01.14.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2208 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 10, 2021 5:00 PM | September 10, 2021 5:00 PM | 0 | 2207,2201 | 0h | 01.14.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2209 |  | Auto Scheduled | אתרי אחסון ברמת IM/WM הקיימים כיום תחת אתר וקוד חברה של המרכז יקושרו/יוקמו לקוד חברה צה"ל ולאתר המרחבי החדש במערכת SAP - SAP | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.34999999999999998 |  | 70h | 01.14.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2210 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2211 |  | Auto Scheduled | LifeCycle Tasks | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.34999999999999998 |  | 70h | 01.14.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2212 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2213 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2214 |  | Manually Scheduled | יישום ופיתוח סאפ | 45 days | July 3, 2021 8:00 AM | September 3, 2021 5:00 PM | 0.90000000000000002 | 2213 | 0h | 01.14.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2215 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2214 | 25h | 01.14.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2216 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 2215 | 10h | 01.14.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2217 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 2216 | 10h | 01.14.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2218 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2217 | 5h | 01.14.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2219 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 2218,2212 | 0h | 01.14.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2220 |  | Auto Scheduled | הקמת אתר אחסון SAP למלאי המגיע מהחזרות במצ"מ - SAP | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2221 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2222 |  | Auto Scheduled | LifeCycle Tasks | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2223 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2224 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2225 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | September 3, 2021 8:00 AM | September 3, 2021 5:00 PM | 1 | 2224 | 0h | 01.14.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2226 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2225 | 25h | 01.14.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2227 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 2226 | 10h | 01.14.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2228 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 2227 | 10h | 01.14.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2229 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2228 | 5h | 01.14.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2230 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 2229,2223 | 0h | 01.14.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2231 |  | Auto Scheduled | פיתוח תוכניות הסבות מלאים - SAP | 473 days | February 3, 2020 8:00 AM | November 24, 2021 5:00 PM | 0 |  | 70h | 01.14.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2232 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2233 |  | Auto Scheduled | LifeCycle Tasks | 473 days | February 3, 2020 8:00 AM | November 24, 2021 5:00 PM | 0 |  | 70h | 01.14.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2234 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2235 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2236 |  | Manually Scheduled | יישום ופיתוח סאפ | 66 days | February 3, 2020 8:00 AM | May 3, 2020 5:00 PM | 0 | 2235 | 0h | 01.14.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2237 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 4, 2020 8:00 AM | June 5, 2020 5:00 PM | 0 | 2236 | 25h | 01.14.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2238 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 8, 2020 8:00 AM | June 19, 2020 5:00 PM | 0 | 2237 | 10h | 01.14.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2239 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 22, 2020 8:00 AM | July 3, 2020 5:00 PM | 0 | 2238 | 10h | 01.14.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2240 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 6, 2020 8:00 AM | July 10, 2020 5:00 PM | 0 | 2239 | 5h | 01.14.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2241 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 2240,2234 | 0h | 01.14.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2242 |  | Auto Scheduled | הגדרת מחסנים רזים למחסנים מיוחדים. - SAP | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 8.9999999999999997E-2 |  | 70h | 01.14.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2243 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2244 |  | Auto Scheduled | LifeCycle Tasks | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 8.9999999999999997E-2 |  | 70h | 01.14.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2245 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2246 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2247 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 18, 2021 8:00 AM | June 21, 2021 5:00 PM | 0.35999999999999999 | 2246 | 0h | 01.14.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2248 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2247 | 25h | 01.14.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2249 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2248 | 10h | 01.14.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2250 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2249 | 10h | 01.14.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2251 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2250 | 5h | 01.14.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2252 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2251,2245 | 0h | 01.14.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2253 |  | Auto Scheduled | הגדרת אתר אחסון מצ"מ תיקונים . - SAP | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2254 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2255 |  | Auto Scheduled | LifeCycle Tasks | 137 days | May 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0.01 |  | 70h | 01.14.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2256 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2257 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2258 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | September 3, 2021 8:00 AM | September 3, 2021 5:00 PM | 1 | 2257 | 0h | 01.14.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2259 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 2258 | 25h | 01.14.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2260 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 2259 | 10h | 01.14.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2261 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 2260 | 10h | 01.14.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2262 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2261 | 5h | 01.14.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2263 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 2262,2256 | 0h | 01.14.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2264 |  | Auto Scheduled | הגדרת מחסנים למחסנים מיוחדים. כולל מבנה פיסי מלא. כולל אסטרטגיות אחסון וליקוט ועוד. - SAP | 170 days | April 1, 2021 8:00 AM | November 24, 2021 5:00 PM | 5.9999999999999998E-2 |  | 70h | 01.14.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2265 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2266 |  | Auto Scheduled | LifeCycle Tasks | 170 days | April 1, 2021 8:00 AM | November 24, 2021 5:00 PM | 5.9999999999999998E-2 |  | 70h | 01.14.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2267 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.14.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2268 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | October 28, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 3731 | 20h | 01.14.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2269 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | April 1, 2021 8:00 AM | May 5, 2021 5:00 PM | 0.23999999999999999 | 2268 | 0h | 01.14.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2270 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 6, 2021 8:00 AM | June 9, 2021 5:00 PM | 0 | 2269 | 25h | 01.14.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2271 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 10, 2021 8:00 AM | June 23, 2021 5:00 PM | 0 | 2270 | 10h | 01.14.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2272 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 24, 2021 8:00 AM | July 7, 2021 5:00 PM | 0 | 2271 | 10h | 01.14.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2273 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 8, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 2272 | 5h | 01.14.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2274 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 14, 2021 5:00 PM | July 14, 2021 5:00 PM | 0 | 2273,2267 | 0h | 01.14.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2275 |  | Auto Scheduled | 01.15: כושרים | 533 days | February 3, 2020 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 1,074h | 01.15 | חתום | מוריה | hd | עינת |  | BP | NA | As Soon As Possible | 3
2276 |  | Auto Scheduled | 01.15: כושרים.BP | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 164h | 01.15.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2277 |  | Auto Scheduled | 01.15: כושרים - BP | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 164h | 01.15.BP.01 | חתום | מוריה | parent | עינת |  | BP | NA | As Soon As Possible | 5
2278 |  | Auto Scheduled | Sub Tasks | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 124h | 01.15.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2279 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.15.BP.01.01.20 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | Must Start On | 7
2280 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.15.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
2281 |  | Auto Scheduled | אישור אבי | 9 days | June 2, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 2280 | 9h | 01.15.BP.01.01.22 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2282 |  | Auto Scheduled | אישור מפקדת | 16 days | June 15, 2021 8:00 AM | July 6, 2021 5:00 PM | 0 | 2281 | 16h | 01.15.BP.01.01.23 | בוצע | עינת | MoM | עינת |  | BP | NA | As Soon As Possible | 7
2283 |  | Auto Scheduled | אישור מקל"ר | 8 days | July 7, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 2282 | 8h | 01.15.BP.01.01.24 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
2284 |  | Auto Scheduled | אישור המנהלת | 2 days | July 19, 2021 8:00 AM | July 20, 2021 5:00 PM | 0 | 2283 | 2h | 01.15.BP.01.01.25 | בוצע | סיגל | MoM | עינת | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
2285 |  | Auto Scheduled | אישור חטלו"ג | 17 days | July 21, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 2284 | 17h | 01.15.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
2286 |  | Auto Scheduled | אישור שגיב שרביט | 29 days | August 13, 2021 8:00 AM | September 22, 2021 5:00 PM | 0 | 2285 | 29h | 01.15.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2287 |  | Auto Scheduled | אישור ניר בשן | 21 days | September 23, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 | 2286 | 21h | 01.15.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2288 |  | Auto Scheduled | LifeCycle Tasks | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 40h | 01.15.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2289 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 2287 | 0h | 01.15.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2290 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.15.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2291 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 2290 | 10h | 01.15.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2292 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 2291 | 5h | 01.15.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2293 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2292 | 10h | 01.15.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2294 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 2293 | 10h | 01.15.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2295 |  | Auto Scheduled | בחתימה | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 2294,2289 | 0h | 01.15.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2296 |  | Auto Scheduled | חתום | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 2295 | 0h | 01.15.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2297 |  | Auto Scheduled | 01.15: כושרים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 210h | 01.15.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2298 |  | Auto Scheduled | נדרש לאפיין דוחות בsap עבור תמונת מצב מלאי לפי כושרים ( גם בשלב מבצוע הדרגתי בהתאם לשינוי מבנה ארגוני) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.01 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2299 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2300 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2301 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2302 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2301 | 10h | 01.15.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2303 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2302 | 20h | 01.15.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2304 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2303,2301 | 0h | 01.15.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2305 |  | Auto Scheduled | נדרש לאפיין דוח BW לפני כניסה וטיפול בבימ"ל - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2306 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2307 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2308 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2309 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2308 | 10h | 01.15.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2310 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2309 | 20h | 01.15.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2311 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2310,2308 | 0h | 01.15.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2312 |  | Auto Scheduled | דוחות עבור דרג מטכ"ל -נדרש לאפיין דוחות ייעודים עבור דרג המטכ"ל ( כגון דו"ח שגויים עבור שדרים שלא עבורו ו/או לא טופלו בין ה WMS ל , SAPדוח עבור משימות פתוחות ששלא טופלו ב SAP ל WMS ) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.03 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2313 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2314 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2315 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2316 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2315 | 10h | 01.15.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2317 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2316 | 20h | 01.15.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2318 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2317,2315 | 0h | 01.15.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2319 |  | Auto Scheduled | כאשר הזכיין מעביר סטאטוס של מלאי ( לדוגמא מבימל מכבסה מסטאטוס מיון לסטאטוס כשיר) נדרש ב סאפ העברת כושר בהתאמה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.04 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2320 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2321 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2322 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2323 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2322 | 10h | 01.15.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2324 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2323 | 20h | 01.15.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2325 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2324,2322 | 0h | 01.15.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2326 |  | Auto Scheduled | נדרש עדכן כי הוראת אט"ל עבור גריטת השמדות - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.05 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2327 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2328 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2329 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2330 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2329 | 10h | 01.15.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2331 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2330 | 20h | 01.15.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2332 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2331,2329 | 0h | 01.15.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2333 |  | Auto Scheduled | נדרש לבצע הסבה עבור משקים שיבוצעו עבורם עמ"ט כושרים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.06 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2334 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2335 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2336 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2337 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2336 | 10h | 01.15.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2338 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2337 | 20h | 01.15.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2339 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2338,2336 | 0h | 01.15.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2340 |  | Auto Scheduled | נדרש לאשר מי בע"ת שיינתן עבורו הרשאה לשימוש בטבלת BRF - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.07 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2341 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2342 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.15.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2343 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2344 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2343 | 10h | 01.15.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2345 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2344 | 20h | 01.15.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2346 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2345,2343 | 0h | 01.15.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2347 |  | Auto Scheduled | 01.15: כושרים.INT | 203 days | May 5, 2021 8:00 AM | February 11, 2022 5:00 PM | 0 |  | 140h | 01.15.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2348 |  | Auto Scheduled | מערכת SAP תאפשר העברת ממשקים ל WMS עבור שינוי כושר - INT | 183 days | May 5, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.15.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2349 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2350 |  | Auto Scheduled | LifeCycle Tasks | 183 days | May 5, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 01.15.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2351 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2352 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2353 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 133 days | May 5, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 | 2352 | 0h | 01.15.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2354 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 8, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 2353 | 25h | 01.15.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2355 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 13, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 2354 | 10h | 01.15.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2356 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 27, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 2355 | 10h | 01.15.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2357 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 10, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 2356 | 5h | 01.15.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2358 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 14, 2022 5:00 PM | January 14, 2022 5:00 PM | 0 | 2357,2351 | 0h | 01.15.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2359 |  | Auto Scheduled | מערכת WMS תאפשר העברת ממשקים ל SAP עבור שינוי כושר - INT | 194 days | May 18, 2021 8:00 AM | February 11, 2022 5:00 PM | 0 |  | 70h | 01.15.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2360 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2361 |  | Auto Scheduled | LifeCycle Tasks | 194 days | May 18, 2021 8:00 AM | February 11, 2022 5:00 PM | 0 |  | 70h | 01.15.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2362 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2363 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2364 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 132 days | June 5, 2021 8:00 AM | December 5, 2021 5:00 PM | 0 | 2363 | 0h | 01.15.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2365 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 6, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 2364 | 25h | 01.15.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2366 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 10, 2022 8:00 AM | January 21, 2022 5:00 PM | 0 | 2365 | 10h | 01.15.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2367 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 24, 2022 8:00 AM | February 4, 2022 5:00 PM | 0 | 2366 | 10h | 01.15.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2368 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 7, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 2367 | 5h | 01.15.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2369 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | February 11, 2022 5:00 PM | February 11, 2022 5:00 PM | 0 | 2368,2362 | 0h | 01.15.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2370 |  | Auto Scheduled | 01.15: כושרים.SAP | 533 days | February 3, 2020 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 560h | 01.15.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2371 |  | Auto Scheduled | מימוש כושרים אחוד במערכת SAP יתבצע עפ"י עמ"ט הכושרים עבור מחסנים מיוחדים ועבור מחסנים בתפעול מערכת WMS (א"א, הרשאות ועוד). - SAP | 170 days | April 7, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2372 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2373 |  | Auto Scheduled | LifeCycle Tasks | 170 days | April 7, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2374 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2375 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2376 |  | Manually Scheduled | יישום ופיתוח סאפ | 0 days | April 7, 2021 5:00 PM | April 7, 2021 5:00 PM | 8.0000000000000002E-2 | 2375 | 0h | 01.15.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2377 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 8, 2021 8:00 AM | May 12, 2021 5:00 PM | 0 | 2376 | 25h | 01.15.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2378 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 13, 2021 8:00 AM | May 26, 2021 5:00 PM | 0 | 2377 | 10h | 01.15.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2379 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 27, 2021 8:00 AM | June 9, 2021 5:00 PM | 0 | 2378 | 10h | 01.15.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2380 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 10, 2021 8:00 AM | June 16, 2021 5:00 PM | 0 | 2379 | 5h | 01.15.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2381 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 16, 2021 5:00 PM | June 16, 2021 5:00 PM | 0 | 2380,2374 | 0h | 01.15.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2382 |  | Auto Scheduled | מערכת SAP תאפשר תהליכי ועדת פסילה. - SAP | 142 days | May 18, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2383 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2384 |  | Auto Scheduled | LifeCycle Tasks | 142 days | May 18, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2385 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2386 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2387 |  | Manually Scheduled | יישום ופיתוח סאפ | 1 day | June 6, 2021 8:00 AM | June 6, 2021 5:00 PM | 0 | 2386 | 0h | 01.15.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2388 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 7, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 2387 | 25h | 01.15.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2389 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 12, 2021 8:00 AM | July 23, 2021 5:00 PM | 0 | 2388 | 10h | 01.15.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2390 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 26, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 2389 | 10h | 01.15.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2391 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 9, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 2390 | 5h | 01.15.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2392 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 13, 2021 5:00 PM | August 13, 2021 5:00 PM | 0 | 2391,2385 | 0h | 01.15.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2393 |  | Auto Scheduled | מערכת SAP תאפשר שינוי אובייקט הרשאה עבור המרות טכניות בין כושרים - SAP | 204 days | April 11, 2021 8:00 AM | January 20, 2022 5:00 PM | 0 |  | 70h | 01.15.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2394 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2395 |  | Auto Scheduled | LifeCycle Tasks | 204 days | April 11, 2021 8:00 AM | January 20, 2022 5:00 PM | 0 |  | 70h | 01.15.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2396 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2397 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2398 |  | Manually Scheduled | יישום ופיתוח סאפ | 155 days | April 11, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 2397 | 0h | 01.15.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2399 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 12, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 2398 | 25h | 01.15.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2400 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 17, 2021 8:00 AM | December 30, 2021 5:00 PM | 0 | 2399 | 10h | 01.15.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2401 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 31, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 2400 | 10h | 01.15.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2402 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 14, 2022 8:00 AM | January 20, 2022 5:00 PM | 0 | 2401 | 5h | 01.15.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2403 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 20, 2022 5:00 PM | January 20, 2022 5:00 PM | 0 | 2402,2396 | 0h | 01.15.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2404 |  | Auto Scheduled | ביצוע הסבות לכושרים המתאימים - SAP | 142 days | May 18, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2405 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2406 |  | Auto Scheduled | LifeCycle Tasks | 142 days | May 18, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2407 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2408 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2409 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 5, 2021 8:00 AM | July 8, 2021 5:00 PM | 0 | 2408 | 0h | 01.15.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2410 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 9, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 2409 | 25h | 01.15.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2411 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 13, 2021 8:00 AM | August 26, 2021 5:00 PM | 0 | 2410 | 10h | 01.15.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2412 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 27, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 2411 | 10h | 01.15.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2413 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 10, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 2412 | 5h | 01.15.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2414 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 16, 2021 5:00 PM | September 16, 2021 5:00 PM | 0 | 2413,2407 | 0h | 01.15.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2415 |  | Auto Scheduled | יש להקים טבלת חוקה בBRF שתייצג את עמ"ט הכושרים בכל תהליך עסקי. - SAP | 212 days | February 8, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2416 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2417 |  | Auto Scheduled | LifeCycle Tasks | 212 days | February 8, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2418 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2419 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2420 |  | Manually Scheduled | יישום ופיתוח סאפ | 0 days | February 8, 2021 5:00 PM | February 8, 2021 5:00 PM | 0 | 2419 | 0h | 01.15.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2421 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 9, 2021 8:00 AM | March 15, 2021 5:00 PM | 0 | 2420 | 25h | 01.15.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2422 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 16, 2021 8:00 AM | March 29, 2021 5:00 PM | 0 | 2421 | 10h | 01.15.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2423 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 30, 2021 8:00 AM | April 12, 2021 5:00 PM | 0 | 2422 | 10h | 01.15.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2424 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 13, 2021 8:00 AM | April 19, 2021 5:00 PM | 0 | 2423 | 5h | 01.15.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2425 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 2424,2418 | 0h | 01.15.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2426 |  | Auto Scheduled | מערכת SAP תאפשר שינוי אובייקט הרשאות עבור שימוש בטבלת BRF לפי משקים - SAP | 268 days | February 8, 2021 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 70h | 01.15.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2427 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2428 |  | Auto Scheduled | LifeCycle Tasks | 268 days | February 8, 2021 8:00 AM | February 16, 2022 5:00 PM | 0 |  | 70h | 01.15.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2429 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2430 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2431 |  | Manually Scheduled | יישום ופיתוח סאפ | 218 days | February 8, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 | 2430 | 0h | 01.15.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2432 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 9, 2021 8:00 AM | January 12, 2022 5:00 PM | 0 | 2431 | 25h | 01.15.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2433 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 13, 2022 8:00 AM | January 26, 2022 5:00 PM | 0 | 2432 | 10h | 01.15.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2434 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 27, 2022 8:00 AM | February 9, 2022 5:00 PM | 0 | 2433 | 10h | 01.15.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2435 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 10, 2022 8:00 AM | February 16, 2022 5:00 PM | 0 | 2434 | 5h | 01.15.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2436 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 16, 2022 5:00 PM | February 16, 2022 5:00 PM | 0 | 2435,2429 | 0h | 01.15.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2437 |  | Auto Scheduled | מערכת SAP תשנה את המלאי לכושר הרלוונטי כפי שהתקבל מה WMS - SAP | 153 days | May 18, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2438 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2439 |  | Auto Scheduled | LifeCycle Tasks | 153 days | May 18, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2440 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2441 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2442 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 5, 2021 8:00 AM | October 7, 2021 5:00 PM | 0 | 2441 | 0h | 01.15.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2443 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 8, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 2442 | 25h | 01.15.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2444 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 12, 2021 8:00 AM | November 25, 2021 5:00 PM | 0 | 2443 | 10h | 01.15.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2445 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 26, 2021 8:00 AM | December 9, 2021 5:00 PM | 0 | 2444 | 10h | 01.15.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2446 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 10, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 2445 | 5h | 01.15.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2447 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 16, 2021 5:00 PM | December 16, 2021 5:00 PM | 0 | 2446,2440 | 0h | 01.15.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2448 |  | Auto Scheduled | כאשר הזכיין מעביר סטאטוס של מלאי ( לדוגמא מבימל מכבסה מסטאטוס מיון לסטאטוס כשיר) נדרש ב סאפ העברת כושר בהתאמה - SAP | 478 days | February 3, 2020 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2449 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2450 |  | Auto Scheduled | LifeCycle Tasks | 478 days | February 3, 2020 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 70h | 01.15.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2451 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.15.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2452 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 4, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 4029 | 20h | 01.15.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2453 |  | Manually Scheduled | יישום ופיתוח סאפ | 131 days | February 3, 2020 8:00 AM | August 3, 2020 5:00 PM | 0 | 2452 | 0h | 01.15.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2454 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 4, 2020 8:00 AM | September 7, 2020 5:00 PM | 0 | 2453 | 25h | 01.15.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2455 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 8, 2020 8:00 AM | September 21, 2020 5:00 PM | 0 | 2454 | 10h | 01.15.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2456 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 22, 2020 8:00 AM | October 5, 2020 5:00 PM | 0 | 2455 | 10h | 01.15.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2457 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 6, 2020 8:00 AM | October 12, 2020 5:00 PM | 0 | 2456 | 5h | 01.15.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2458 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 2457,2451 | 0h | 01.15.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2459 |  | Auto Scheduled | 01.16: המרות טכניות | 654 days | February 8, 2020 8:00 AM | August 11, 2022 5:00 PM | 0 |  | 1,721h | 01.16 | חתום | מוריה | hd | מאור |  | BP | NA | As Soon As Possible | 3
2460 |  | Auto Scheduled | 01.16: המרות טכניות.BP | 576 days | February 8, 2020 8:00 AM | April 25, 2022 5:00 PM | 0 |  | 151h | 01.16.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2461 |  | Auto Scheduled | 01.16: המרות טכניות - BP | 576 days | February 8, 2020 8:00 AM | April 25, 2022 5:00 PM | 0 |  | 151h | 01.16.BP.01 | חתום | מוריה | parent | מאור |  | BP | NA | As Soon As Possible | 5
2462 |  | Auto Scheduled | Sub Tasks | 576 days | February 8, 2020 8:00 AM | April 25, 2022 5:00 PM | 0 |  | 111h | 01.16.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2463 |  | Auto Scheduled | 23/09: הערות שרון ותקווה | 0.13 days | February 8, 2020 8:00 AM | February 10, 2020 9:00 AM | 0 |  | 1h | 01.16.BP.01.01.01 | בוצע | מוריה | MoM | מאור | שרון רחמים | BP | NA | Must Start On | 7
2464 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.16.BP.01.01.20 | בוצע | מוריה | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
2465 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.16.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
2466 |  | Auto Scheduled | אישור אבי | 7 days | June 2, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 2465 | 7h | 01.16.BP.01.01.22 | בוצע | אבי | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
2467 |  | Auto Scheduled | אישור מקל"ר | 12 days | June 11, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2466 | 12h | 01.16.BP.01.01.23 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
2468 |  | Auto Scheduled | אישור המנהלת | 12 days | June 29, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 2467 | 12h | 01.16.BP.01.01.24 | בוצע | סיגל | MoM | מאור | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
2469 |  | Auto Scheduled | אישור מפקדת | 22 days | July 15, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 2468 | 2h | 01.16.BP.01.01.25 | בוצע | מאור | MoM | מאור | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
2470 |  | Auto Scheduled | אישור חטלו"ג | 131 days | August 16, 2021 8:00 AM | February 14, 2022 5:00 PM | 0 | 2469 | 5h | 01.16.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-19 00:00:00 | BP | NA | As Soon As Possible | 7
2471 |  | Auto Scheduled | אישור שגיב שרביט | 24 days | February 15, 2022 8:00 AM | March 18, 2022 5:00 PM | 0 | 2470 | 24h | 01.16.BP.01.01.27 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
2472 |  | Auto Scheduled | אישור ניר בשן | 26 days | March 21, 2022 8:00 AM | April 25, 2022 5:00 PM | 0 | 2471 | 26h | 01.16.BP.01.01.28 | בוצע | מאור | MoM | מאור | תע - מוריה | BP | NA | As Soon As Possible | 7
2473 |  | Auto Scheduled | LifeCycle Tasks | 245 days | May 18, 2021 8:00 AM | April 25, 2022 5:00 PM | 0 |  | 40h | 01.16.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2474 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | April 25, 2022 5:00 PM | April 25, 2022 5:00 PM | 0 | 2472 | 0h | 01.16.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2475 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.16.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2476 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 2475 | 10h | 01.16.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2477 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 2476 | 5h | 01.16.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2478 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2477 | 10h | 01.16.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2479 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 2478 | 10h | 01.16.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2480 |  | Auto Scheduled | בחתימה | 0 days | April 25, 2022 5:00 PM | April 25, 2022 5:00 PM | 0 | 2479,2474 | 0h | 01.16.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2481 |  | Auto Scheduled | חתום | 0 days | April 25, 2022 5:00 PM | April 25, 2022 5:00 PM | 0 | 2480 | 0h | 01.16.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2482 |  | Auto Scheduled | 01.16: המרות טכניות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.16.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2483 |  | Auto Scheduled | נדרש לאפיין דו"חות הנדרשים לטובת תהליך ההמרות - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.16.GEN.18 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2484 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.GEN.18.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2485 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.16.GEN.18.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2486 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.GEN.18.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2487 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2486 | 10h | 01.16.GEN.18.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2488 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2487 | 20h | 01.16.GEN.18.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2489 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2488,2486 | 0h | 01.16.GEN.18.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2490 |  | Auto Scheduled | 01.16: המרות טכניות.INT | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 350h | 01.16.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2491 |  | Auto Scheduled | מערכת SAP תשלח שדר למערכת הWMS עם נתוני אספקת צפי פנימי - INT | 179 days | May 18, 2021 8:00 AM | January 21, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2492 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2493 |  | Auto Scheduled | LifeCycle Tasks | 179 days | May 18, 2021 8:00 AM | January 21, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2494 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2495 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2496 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | October 11, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2495 | 0h | 01.16.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2497 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 15, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 | 2496 | 25h | 01.16.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2498 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 20, 2021 8:00 AM | December 31, 2021 5:00 PM | 0 | 2497 | 10h | 01.16.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2499 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 3, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 2498 | 10h | 01.16.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2500 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 17, 2022 8:00 AM | January 21, 2022 5:00 PM | 0 | 2499 | 5h | 01.16.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2501 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 21, 2022 5:00 PM | January 21, 2022 5:00 PM | 0 | 2500,2494 | 0h | 01.16.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2502 |  | Auto Scheduled | מערכת WMS תשלח שדר על קבלת הפריטים למלאי אל מול אספקת צפי הפנימי - INT | 202 days | May 18, 2021 8:00 AM | February 23, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2503 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2504 |  | Auto Scheduled | LifeCycle Tasks | 202 days | May 18, 2021 8:00 AM | February 23, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2505 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2506 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2507 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | November 11, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 2506 | 0h | 01.16.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2508 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 16, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 | 2507 | 25h | 01.16.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2509 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 20, 2022 8:00 AM | February 2, 2022 5:00 PM | 0 | 2508 | 10h | 01.16.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2510 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 3, 2022 8:00 AM | February 16, 2022 5:00 PM | 0 | 2509 | 10h | 01.16.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2511 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 17, 2022 8:00 AM | February 23, 2022 5:00 PM | 0 | 2510 | 5h | 01.16.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2512 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | February 23, 2022 5:00 PM | February 23, 2022 5:00 PM | 0 | 2511,2505 | 0h | 01.16.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2513 |  | Auto Scheduled | מערכת WMS תשלח שדר לSAP עם הנתונים המסומנים להמרה לטובת תהליך המרה - INT | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2514 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2515 |  | Auto Scheduled | LifeCycle Tasks | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2516 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2517 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2518 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 29, 2021 8:00 AM | February 1, 2022 5:00 PM | 0 | 2517 | 0h | 01.16.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2519 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 2, 2022 8:00 AM | March 8, 2022 5:00 PM | 0 | 2518 | 25h | 01.16.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2520 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 9, 2022 8:00 AM | March 22, 2022 5:00 PM | 0 | 2519 | 10h | 01.16.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2521 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 23, 2022 8:00 AM | April 5, 2022 5:00 PM | 0 | 2520 | 10h | 01.16.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2522 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 6, 2022 8:00 AM | April 12, 2022 5:00 PM | 0 | 2521 | 5h | 01.16.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2523 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 2522,2516 | 0h | 01.16.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2524 |  | Auto Scheduled | מערכת SAP תשלח שדר עם הנתונים הרלוונטים למערכת הWMS - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2525 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2526 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2527 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2528 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2529 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 20/12/2021 | 30/12/2021 | 0 | 2528 | 0h | 01.16.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2530 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2529 | 25h | 01.16.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2531 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2530 | 10h | 01.16.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2532 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2531 | 10h | 01.16.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2533 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2532 | 5h | 01.16.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2534 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2533,2527 | 0h | 01.16.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2535 |  | Auto Scheduled | מערכת WMS תשלח שדר עדכון של הסטאטוסים למערכת הSAP - INT | 214 days | May 18, 2021 8:00 AM | March 11, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2536 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2537 |  | Auto Scheduled | LifeCycle Tasks | 214 days | May 18, 2021 8:00 AM | March 11, 2022 5:00 PM | 0 |  | 70h | 01.16.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2538 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2539 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2540 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | November 30, 2021 8:00 AM | January 2, 2022 5:00 PM | 0 | 2539 | 0h | 01.16.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2541 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 3, 2022 8:00 AM | February 4, 2022 5:00 PM | 0 | 2540 | 25h | 01.16.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2542 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 7, 2022 8:00 AM | February 18, 2022 5:00 PM | 0 | 2541 | 10h | 01.16.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2543 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 21, 2022 8:00 AM | March 4, 2022 5:00 PM | 0 | 2542 | 10h | 01.16.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2544 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 7, 2022 8:00 AM | March 11, 2022 5:00 PM | 0 | 2543 | 5h | 01.16.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2545 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 11, 2022 5:00 PM | March 11, 2022 5:00 PM | 0 | 2544,2538 | 0h | 01.16.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2546 |  | Auto Scheduled | 01.16: המרות טכניות.SAP | 414 days | January 11, 2021 8:00 AM | August 11, 2022 5:00 PM | 0 |  | 1,190h | 01.16.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2547 |  | Auto Scheduled | תשתית החוקה המתבצעת בעת ההמרה תעבור לשלב מוקדם יותר בתהליך. - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2548 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2549 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2550 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2551 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2552 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 22/08/2021 | 14/10/2021 | 0 | 2551 | 0h | 01.16.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2553 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2552 | 25h | 01.16.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2554 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2553 | 10h | 01.16.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2555 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2554 | 10h | 01.16.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2556 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2555 | 5h | 01.16.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2557 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2556,2550 | 0h | 01.16.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2558 |  | Auto Scheduled | מערכת SAP תרחיב את החוקה הקיימת עבור מבנה ארגוני חדש - SAP | 247 days | February 9, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2559 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2560 |  | Auto Scheduled | LifeCycle Tasks | 247 days | February 9, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2561 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2562 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2563 |  | Manually Scheduled | יישום ופיתוח סאפ | 197 days | February 9, 2021 8:00 AM | November 10, 2021 5:00 PM | 0 | 2562 | 0h | 01.16.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2564 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 11, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 2563 | 25h | 01.16.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2565 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 16, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2564 | 10h | 01.16.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2566 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 30, 2021 8:00 AM | January 12, 2022 5:00 PM | 0 | 2565 | 10h | 01.16.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2567 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 13, 2022 8:00 AM | January 19, 2022 5:00 PM | 0 | 2566 | 5h | 01.16.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2568 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 19, 2022 5:00 PM | January 19, 2022 5:00 PM | 0 | 2567,2561 | 0h | 01.16.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2569 |  | Auto Scheduled | מערכת SAP תאפשר עבודה תהליך המרות טכניות במבנה ארגוני הקיים והמבנה הארגוני החדש - SAP | 177 days | May 18, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2570 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2571 |  | Auto Scheduled | LifeCycle Tasks | 177 days | May 18, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2572 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2573 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2574 |  | Manually Scheduled | יישום ופיתוח סאפ | 89 days | July 10, 2021 8:00 AM | November 10, 2021 5:00 PM | 0 | 2573 | 0h | 01.16.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2575 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 11, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 2574 | 25h | 01.16.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2576 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 16, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 2575 | 10h | 01.16.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2577 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 30, 2021 8:00 AM | January 12, 2022 5:00 PM | 0 | 2576 | 10h | 01.16.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2578 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 13, 2022 8:00 AM | January 19, 2022 5:00 PM | 0 | 2577 | 5h | 01.16.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2579 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 19, 2022 5:00 PM | January 19, 2022 5:00 PM | 0 | 2578,2572 | 0h | 01.16.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2580 |  | Auto Scheduled | מערכת SAP תאפשר המשך תהליך עבודה להמרות טכניות עבור מחסנים מיוחדים - SAP | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2581 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2582 |  | Auto Scheduled | LifeCycle Tasks | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2583 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2584 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2585 |  | Manually Scheduled | יישום ופיתוח סאפ | 46 days | October 10, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 2584 | 0h | 01.16.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2586 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 13, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2585 | 25h | 01.16.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2587 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 17, 2022 8:00 AM | January 28, 2022 5:00 PM | 0 | 2586 | 10h | 01.16.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2588 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 31, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 2587 | 10h | 01.16.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2589 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 14, 2022 8:00 AM | February 18, 2022 5:00 PM | 0 | 2588 | 5h | 01.16.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2590 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 18, 2022 5:00 PM | February 18, 2022 5:00 PM | 0 | 2589,2583 | 0h | 01.16.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2591 |  | Auto Scheduled | מערכת SAP תאפשר הזנת מק"ט נוכחי ומק"ט חדש ע"ב טרנזקציות ZMH1/2 - SAP | 201 days | May 18, 2021 8:00 AM | February 22, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2592 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2593 |  | Auto Scheduled | LifeCycle Tasks | 201 days | May 18, 2021 8:00 AM | February 22, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2594 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2595 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2596 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 10, 2021 8:00 AM | December 14, 2021 5:00 PM | 0 | 2595 | 0h | 01.16.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2597 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 15, 2021 8:00 AM | January 18, 2022 5:00 PM | 0 | 2596 | 25h | 01.16.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2598 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 19, 2022 8:00 AM | February 1, 2022 5:00 PM | 0 | 2597 | 10h | 01.16.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2599 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 2, 2022 8:00 AM | February 15, 2022 5:00 PM | 0 | 2598 | 10h | 01.16.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2600 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 16, 2022 8:00 AM | February 22, 2022 5:00 PM | 0 | 2599 | 5h | 01.16.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2601 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 22, 2022 5:00 PM | February 22, 2022 5:00 PM | 0 | 2600,2594 | 0h | 01.16.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2602 |  | Auto Scheduled | מערכת SAP תאפשר בדיקת החוקות להמרה בין מק"טים - SAP | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2603 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2604 |  | Auto Scheduled | LifeCycle Tasks | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2605 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2606 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2607 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | December 10, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 2606 | 0h | 01.16.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2608 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 14, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 2607 | 25h | 01.16.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2609 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 18, 2022 8:00 AM | March 3, 2022 5:00 PM | 0 | 2608 | 10h | 01.16.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2610 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 4, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 2609 | 10h | 01.16.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2611 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 18, 2022 8:00 AM | March 24, 2022 5:00 PM | 0 | 2610 | 5h | 01.16.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2612 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | March 24, 2022 5:00 PM | March 24, 2022 5:00 PM | 0 | 2611,2605 | 0h | 01.16.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2613 |  | Auto Scheduled | מערכת SAP לא תבצע תנועות מלאי באופן אוטומטי לאחר בדיקת חוקות תקינות כאשר ההמרה מיועדת לביצוע במחסן שמנוהל WMS - SAP | 125 days | February 5, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2614 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2615 |  | Auto Scheduled | LifeCycle Tasks | 125 days | February 5, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2616 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2617 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2618 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | February 5, 2021 8:00 AM | March 11, 2021 5:00 PM | 0 | 2617 | 0h | 01.16.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2619 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 12, 2021 8:00 AM | April 15, 2021 5:00 PM | 0 | 2618 | 25h | 01.16.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2620 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 16, 2021 8:00 AM | April 29, 2021 5:00 PM | 0 | 2619 | 10h | 01.16.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2621 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 30, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 2620 | 10h | 01.16.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2622 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 14, 2021 8:00 AM | May 20, 2021 5:00 PM | 0 | 2621 | 5h | 01.16.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2623 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 20, 2021 5:00 PM | May 20, 2021 5:00 PM | 0 | 2622,2616 | 0h | 01.16.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2624 |  | Auto Scheduled | מערכת SAP תקדים את בדיקת כלל החוקות לשלב של טרם פתיחת הפק"ע (חוקות במסך ZMH1 וMIGO) - SAP | 144 days | January 11, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2625 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2626 |  | Auto Scheduled | LifeCycle Tasks | 144 days | January 11, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2627 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2628 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2629 |  | Manually Scheduled | יישום ופיתוח סאפ | 44 days | January 11, 2021 8:00 AM | March 11, 2021 5:00 PM | 0 | 2628 | 0h | 01.16.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2630 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 12, 2021 8:00 AM | April 15, 2021 5:00 PM | 0 | 2629 | 25h | 01.16.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2631 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 16, 2021 8:00 AM | April 29, 2021 5:00 PM | 0 | 2630 | 10h | 01.16.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2632 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 30, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 2631 | 10h | 01.16.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2633 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 14, 2021 8:00 AM | May 20, 2021 5:00 PM | 0 | 2632 | 5h | 01.16.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2634 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 20, 2021 5:00 PM | May 20, 2021 5:00 PM | 0 | 2633,2627 | 0h | 01.16.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2635 |  | Auto Scheduled | מערכת SAP תציג הודעת שגיאה עם סיבה שבגללה נפלה בדיקת החוקה - SAP | 121 days | February 11, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2636 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2637 |  | Auto Scheduled | LifeCycle Tasks | 121 days | February 11, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2638 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2639 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2640 |  | Manually Scheduled | יישום ופיתוח סאפ | 43 days | February 11, 2021 8:00 AM | April 11, 2021 5:00 PM | 0 | 2639 | 0h | 01.16.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2641 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 12, 2021 8:00 AM | May 14, 2021 5:00 PM | 0 | 2640 | 25h | 01.16.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2642 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 17, 2021 8:00 AM | May 28, 2021 5:00 PM | 0 | 2641 | 10h | 01.16.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2643 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 31, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 2642 | 10h | 01.16.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2644 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 14, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 | 2643 | 5h | 01.16.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2645 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 18, 2021 5:00 PM | June 18, 2021 5:00 PM | 0 | 2644,2638 | 0h | 01.16.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2646 |  | Auto Scheduled | מערכת SAP לא תפתח פק"ע, לא תבצע תנועות מלאי ולא תשלח שדרים במידה ובדיקת החוקה אינה עוברת תקינה - SAP | 137 days | March 11, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2647 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2648 |  | Auto Scheduled | LifeCycle Tasks | 137 days | March 11, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2649 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2650 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2651 |  | Manually Scheduled | יישום ופיתוח סאפ | 88 days | March 11, 2021 8:00 AM | July 11, 2021 5:00 PM | 0 | 2650 | 0h | 01.16.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2652 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 12, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 2651 | 25h | 01.16.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2653 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 16, 2021 8:00 AM | August 27, 2021 5:00 PM | 0 | 2652 | 10h | 01.16.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2654 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 30, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 2653 | 10h | 01.16.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2655 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 2654 | 5h | 01.16.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2656 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 17, 2021 5:00 PM | September 17, 2021 5:00 PM | 0 | 2655,2649 | 0h | 01.16.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2657 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת הזמנת רכש עם מק"ט רכש שצפוי להגיע - SAP | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2658 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2659 |  | Auto Scheduled | LifeCycle Tasks | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2660 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2661 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2662 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 11, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 2661 | 0h | 01.16.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2663 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 13, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 2662 | 25h | 01.16.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2664 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 17, 2021 8:00 AM | September 30, 2021 5:00 PM | 0 | 2663 | 10h | 01.16.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2665 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 1, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 2664 | 10h | 01.16.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2666 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 15, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 | 2665 | 5h | 01.16.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2667 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 2666,2660 | 0h | 01.16.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2668 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת הזמנת צפי פנימי עם המק"טים שהגיעו בפועל - SAP | 136 days | May 18, 2021 8:00 AM | November 23, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2669 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2670 |  | Auto Scheduled | LifeCycle Tasks | 136 days | May 18, 2021 8:00 AM | November 23, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2671 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2672 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2673 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 2672 | 0h | 01.16.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2674 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 15, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 2673 | 25h | 01.16.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2675 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 20, 2021 8:00 AM | November 2, 2021 5:00 PM | 0 | 2674 | 10h | 01.16.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2676 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 3, 2021 8:00 AM | November 16, 2021 5:00 PM | 0 | 2675 | 10h | 01.16.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2677 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 17, 2021 8:00 AM | November 23, 2021 5:00 PM | 0 | 2676 | 5h | 01.16.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2678 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 23, 2021 5:00 PM | November 23, 2021 5:00 PM | 0 | 2677,2671 | 0h | 01.16.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2679 |  | Auto Scheduled | מערכת SAP תאפשר קישור פתיחת הזמנת צפי פנימי עם הזמנת הרכש המקורית - SAP | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2680 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2681 |  | Auto Scheduled | LifeCycle Tasks | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2682 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2683 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2684 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 11, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 2683 | 0h | 01.16.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2685 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 15, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 2684 | 25h | 01.16.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2686 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 19, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 2685 | 10h | 01.16.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2687 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 3, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 2686 | 10h | 01.16.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2688 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 17, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 2687 | 5h | 01.16.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2689 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 2688,2682 | 0h | 01.16.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2690 |  | Auto Scheduled | מערכת SAP תסגור את הזמנת הצפי הפנימי לאחר קבלת הפריטים למלאי - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2691 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2692 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2693 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2694 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2695 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 14/11/2021 | 21/11/2021 | 0 | 2694 | 0h | 01.16.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2696 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2695 | 25h | 01.16.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2697 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2696 | 10h | 01.16.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2698 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2697 | 10h | 01.16.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2699 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2698 | 5h | 01.16.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2700 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2699,2693 | 0h | 01.16.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2701 |  | Auto Scheduled | מערכת SAP תפתח פק"ע לביצוע המרה הכוללת שריון החומר אשר אותו מעוניינים להמיר בהתאם לנתונים שנשלחו מWMS - SAP | 114 days | May 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2702 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2703 |  | Auto Scheduled | LifeCycle Tasks | 114 days | May 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2704 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2705 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2706 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 12, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 2705 | 0h | 01.16.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2707 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 16, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 2706 | 25h | 01.16.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2708 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 20, 2021 8:00 AM | October 1, 2021 5:00 PM | 0 | 2707 | 10h | 01.16.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2709 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 4, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 2708 | 10h | 01.16.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2710 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 2709 | 5h | 01.16.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2711 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 22, 2021 5:00 PM | October 22, 2021 5:00 PM | 0 | 2710,2704 | 0h | 01.16.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2712 |  | Auto Scheduled | מערכת SAP תאפשר החלטה על אישור/סירוב (שחרור) של הפק"ע ועדכון נתונים ע"י מפקדת המרה"ס - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.16 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2713 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2714 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.16.SAP.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2715 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.16.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2716 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.16.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2717 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 13/12/2021 | 30/12/2021 | 0 | 2716 | 0h | 01.16.SAP.16.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2718 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2717 | 25h | 01.16.SAP.16.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2719 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2718 | 10h | 01.16.SAP.16.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2720 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2719 | 10h | 01.16.SAP.16.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2721 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2720 | 5h | 01.16.SAP.16.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2722 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2721,2715 | 0h | 01.16.SAP.16.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2723 |  | Auto Scheduled | מערכת SAP תנהל סטאטוסים על הפק"עות בהתאם לשדרים שהתקבלו - SAP | 323 days | May 18, 2021 8:00 AM | August 11, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.17 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2724 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2725 |  | Auto Scheduled | LifeCycle Tasks | 323 days | May 18, 2021 8:00 AM | August 11, 2022 5:00 PM | 0 |  | 70h | 01.16.SAP.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2726 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.16.SAP.17.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2727 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 2, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4314 | 20h | 01.16.SAP.17.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2728 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 1, 2022 8:00 AM | June 2, 2022 5:00 PM | 0 | 2727 | 0h | 01.16.SAP.17.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2729 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 3, 2022 8:00 AM | July 7, 2022 5:00 PM | 0 | 2728 | 25h | 01.16.SAP.17.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2730 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 8, 2022 8:00 AM | July 21, 2022 5:00 PM | 0 | 2729 | 10h | 01.16.SAP.17.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2731 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 22, 2022 8:00 AM | August 4, 2022 5:00 PM | 0 | 2730 | 10h | 01.16.SAP.17.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2732 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 5, 2022 8:00 AM | August 11, 2022 5:00 PM | 0 | 2731 | 5h | 01.16.SAP.17.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2733 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 11, 2022 5:00 PM | August 11, 2022 5:00 PM | 0 | 2732,2726 | 0h | 01.16.SAP.17.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2734 |  | Auto Scheduled | 01.17: סדרות | 270 days | February 8, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 1,699h | 01.17 | חתום | מוריה | hd | עינת |  | BP | NA | As Soon As Possible | 3
2735 |  | Auto Scheduled | 01.17: סדרות.BP | 60 days | May 18, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 |  | 129h | 01.17.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2736 |  | Auto Scheduled | 01.17: סדרות - BP | 60 days | May 18, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 |  | 129h | 01.17.BP.01 | חתום | מוריה | parent | עינת |  | BP | NA | As Soon As Possible | 5
2737 |  | Auto Scheduled | Sub Tasks | 57 days | May 18, 2021 8:00 AM | August 4, 2021 5:00 PM | 0 |  | 89h | 01.17.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2738 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.17.BP.01.01.20 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | Must Start On | 7
2739 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 01.17.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
2740 |  | Auto Scheduled | אישור אבי | 6 days | June 2, 2021 8:00 AM | June 9, 2021 5:00 PM | 0 | 2739 | 6h | 01.17.BP.01.01.22 | בוצע | אבי | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2741 |  | Auto Scheduled | אישור מקל"ר | 16 days | June 10, 2021 8:00 AM | July 1, 2021 5:00 PM | 0 | 2740 | 16h | 01.17.BP.01.01.23 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
2742 |  | Auto Scheduled | אישור מפקדת | 3 days | July 2, 2021 8:00 AM | July 6, 2021 5:00 PM | 0 | 2741 | 3h | 01.17.BP.01.01.24 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2743 |  | Auto Scheduled | אישור המנהלת | 2 days | July 7, 2021 8:00 AM | July 8, 2021 5:00 PM | 0 | 2742 | 2h | 01.17.BP.01.01.25 | בוצע | סיגל | MoM | עינת | 2020-10-15 00:00:00 | BP | NA | As Soon As Possible | 7
2744 |  | Auto Scheduled | אישור חטלו"ג | 16 days | July 9, 2021 8:00 AM | July 30, 2021 5:00 PM | 0 | 2743 | 16h | 01.17.BP.01.01.26 | בוצע |  | MoM |  | 2020-10-14 00:00:00 | BP | NA | As Soon As Possible | 7
2745 |  | Auto Scheduled | אישור ניר בשן | 2 days | August 2, 2021 8:00 AM | August 3, 2021 5:00 PM | 0 | 2744 | 23h | 01.17.BP.01.01.27 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2746 |  | Auto Scheduled | אישור שגיב שרביט | 1 day | August 4, 2021 8:00 AM | August 4, 2021 5:00 PM | 0 | 2745 | 1h | 01.17.BP.01.01.28 | בוצע | עינת | MoM | עינת | תע - מוריה | BP | NA | As Soon As Possible | 7
2747 |  | Auto Scheduled | LifeCycle Tasks | 60 days | May 18, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 |  | 40h | 01.17.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2748 |  | Auto Scheduled | סיום משימות בלו-פרינט | 1 day | August 5, 2021 8:00 AM | August 5, 2021 5:00 PM | 0 | 2746 | 0h | 01.17.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2749 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.17.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2750 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 2749 | 10h | 01.17.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2751 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 2750 | 5h | 01.17.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2752 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2751 | 10h | 01.17.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2753 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 2752 | 10h | 01.17.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2754 |  | Auto Scheduled | בחתימה | 1 day | August 6, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 2753,2748 | 0h | 01.17.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2755 |  | Auto Scheduled | חתום | 1 day | August 9, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2754 | 0h | 01.17.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
2756 |  | Auto Scheduled | 01.17: סדרות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 240h | 01.17.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2757 |  | Auto Scheduled | נדרש להגדיר לזכיין כי באם לא קיימת סדרת ספק יש להגדיר קוד סדרה כנומרטור (וכל פעולות ערך מוסף נלוות) והעברת הקוד למערכת ה SAP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.01 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2758 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2759 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2760 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2761 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2760 | 10h | 01.17.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2762 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2761 | 20h | 01.17.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2763 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2762,2760 | 0h | 01.17.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2764 |  | Auto Scheduled | נדרש לבצע התאמות עבור תפיסת הפתרון החדשה בטפסים/דוחות דרג נפרש - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.03 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2765 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2766 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2767 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2768 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2767 | 10h | 01.17.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2769 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2768 | 20h | 01.17.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2770 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2769,2767 | 0h | 01.17.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2771 |  | Auto Scheduled | כאשר מבצעים שינוי בסדרה לא ניתן לבצע תהליכים לוגיסטיים במידה וקיימת סדרה כבר בתהליך ( לדוג' ניפוקים). - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.04 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2772 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2773 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2774 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2775 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2774 | 10h | 01.17.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2776 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2775 | 20h | 01.17.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2777 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2776,2774 | 0h | 01.17.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2778 |  | Auto Scheduled | נדרש לבחון מה הסבות הנדרשות בעת העלייה לאוויר ( לדוג' לשתול במהלך שלנו אצוות יצרן – בשדה היעודי בסדרות פתוחות עם המספר בקוד סדרה. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.05 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2779 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2780 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2781 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2782 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2781 | 10h | 01.17.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2783 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2782 | 20h | 01.17.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2784 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2783,2781 | 0h | 01.17.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2785 |  | Auto Scheduled | העברת DATA עבור סדרות שקיימות ב SAP (סדרות שהיו קיימות טרם עלייה לאוויר ) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.06 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2786 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2787 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2788 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2789 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2788 | 10h | 01.17.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2790 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2789 | 20h | 01.17.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2791 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2790,2788 | 0h | 01.17.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2792 |  | Auto Scheduled | תיקוף דוחות ומקומות בהם נדרש אצוות יצרן (שדה "סדרת ספק" ב SAP ) . - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.07 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2793 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2794 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2795 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2796 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2795 | 10h | 01.17.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2797 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2796 | 20h | 01.17.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2798 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2797,2795 | 0h | 01.17.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2799 |  | Auto Scheduled | עבור דלק, יאפינו יכולת לשלוף סדרה לפי חציונים (או טווח תאריכים) במספר שנים. לדוגמא חציון ראשון של השנים 2020, 2021. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.08 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2800 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2801 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2802 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2803 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2802 | 10h | 01.17.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2804 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2803 | 20h | 01.17.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2805 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2804,2802 | 0h | 01.17.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2806 |  | Auto Scheduled | דוחות עבור דרג מטכ"ל -נדרש לאפיין דוחות ייעודים עבור דרג המטכ"ל ( כגון דו"ח שגויים לפתיחת סדרות , דו"ח טיפול בפגומים או פג"ת , דוח סטאטוסים (WMS ) עבור כל סדרה ) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.09 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
2807 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2808 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.17.GEN.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2809 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.GEN.09.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2810 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 2809 | 10h | 01.17.GEN.09.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2811 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 2810 | 20h | 01.17.GEN.09.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2812 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 2811,2809 | 0h | 01.17.GEN.09.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
2813 |  | Auto Scheduled | 01.17: סדרות.INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 140h | 01.17.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2814 |  | Auto Scheduled | מערכת הSAP תפיץ נתוני סדרה לWMS , לשלושת המרחבים עבור פתיחת סדרות/שינוי מאפיינים/סטאטוס סדרות - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2815 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2816 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2817 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2818 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2819 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 19/10/2021 | 15/11/2021 | 0 | 2818 | 0h | 01.17.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2820 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2819 | 25h | 01.17.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2821 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2820 | 10h | 01.17.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2822 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2821 | 10h | 01.17.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2823 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2822 | 5h | 01.17.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2824 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2823,2817 | 0h | 01.17.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2825 |  | Auto Scheduled | מערכת הWMS תאפשר לפתוח סדרות ושינוי מאפייני סדרה , מערכת WMS תשלח בממשק לSAP את השינוי שבוצע (מערכת SAP תעדכן את יתר המרחיבם ע"ב דרישה מספר 94) - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
2826 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2827 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2828 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2829 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2830 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 15/11/2021 | 21/12/2021 | 0 | 2829 | 0h | 01.17.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2831 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2830 | 25h | 01.17.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2832 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2831 | 10h | 01.17.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2833 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2832 | 10h | 01.17.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2834 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2833 | 5h | 01.17.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2835 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2834,2828 | 0h | 01.17.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
2836 |  | Auto Scheduled | 01.17: סדרות.SAP | 270 days | February 8, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 1,190h | 01.17.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
2837 |  | Auto Scheduled | מערכת SAP תאפשר לפתוח סדרות עם נומרטור פנימי ומאפיינים רלוונטים כגון תהליך ייצור, פג"ת, ספק, גודל יחידה/חלקים באריזה/כשל"פ ע"ב מסך MSC1N - SAP | 120 days | February 8, 2021 5:00 PM | July 26, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2838 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2839 |  | Auto Scheduled | LifeCycle Tasks | 120 days | February 8, 2021 5:00 PM | July 26, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2840 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2841 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2842 |  | Manually Scheduled | יישום ופיתוח סאפ | 0 days | February 8, 2021 5:00 PM | February 8, 2021 5:00 PM | 0 | 2841 | 0h | 01.17.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2843 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 9, 2021 8:00 AM | March 15, 2021 5:00 PM | 0 | 2842 | 25h | 01.17.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2844 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 16, 2021 8:00 AM | March 29, 2021 5:00 PM | 0 | 2843 | 10h | 01.17.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2845 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 30, 2021 8:00 AM | April 12, 2021 5:00 PM | 0 | 2844 | 10h | 01.17.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2846 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 13, 2021 8:00 AM | April 19, 2021 5:00 PM | 0 | 2845 | 5h | 01.17.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2847 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 2846,2840 | 0h | 01.17.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2848 |  | Auto Scheduled | מערכת SAP תאפשר גזירת שדה פג"ת מנתוני החומר - SAP | 121 days | February 8, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2849 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2850 |  | Auto Scheduled | LifeCycle Tasks | 121 days | February 8, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2851 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2852 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2853 |  | Manually Scheduled | יישום ופיתוח סאפ | 44 days | February 8, 2021 8:00 AM | April 8, 2021 5:00 PM | 0 | 2852 | 0h | 01.17.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2854 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 9, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 2853 | 25h | 01.17.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2855 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 14, 2021 8:00 AM | May 27, 2021 5:00 PM | 0 | 2854 | 10h | 01.17.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2856 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 28, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 2855 | 10h | 01.17.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2857 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 11, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 2856 | 5h | 01.17.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2858 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 17, 2021 5:00 PM | June 17, 2021 5:00 PM | 0 | 2857,2851 | 0h | 01.17.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2859 |  | Auto Scheduled | מערכת SAP תמשיך לאפשר הזנת מספר סדרה באופן ידני - SAP | 101 days | March 8, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2860 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2861 |  | Auto Scheduled | LifeCycle Tasks | 101 days | March 8, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2862 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2863 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2864 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 8, 2021 8:00 AM | April 9, 2021 5:00 PM | 0 | 2863 | 0h | 01.17.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2865 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 12, 2021 8:00 AM | May 14, 2021 5:00 PM | 0 | 2864 | 25h | 01.17.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2866 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 17, 2021 8:00 AM | May 28, 2021 5:00 PM | 0 | 2865 | 10h | 01.17.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2867 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 31, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 2866 | 10h | 01.17.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2868 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 14, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 | 2867 | 5h | 01.17.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2869 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 18, 2021 5:00 PM | June 18, 2021 5:00 PM | 0 | 2868,2862 | 0h | 01.17.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2870 |  | Auto Scheduled | מערכת SAP תקבע טווח מספרים לקודי סדרה שונים בין מרחבים - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2871 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2872 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2873 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2874 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2875 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 15/08/2021 | 13/09/2021 | 0 | 2874 | 0h | 01.17.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2876 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2875 | 25h | 01.17.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2877 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2876 | 10h | 01.17.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2878 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2877 | 10h | 01.17.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2879 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2878 | 5h | 01.17.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2880 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2879,2873 | 0h | 01.17.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2881 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סדרות ומספור קוד סדרה גם כאשר לא מנהלים אצוות יצרן - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2882 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2883 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2884 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2885 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2886 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 23/08/2021 | 25/08/2021 | 0 | 2885 | 0h | 01.17.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2887 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2886 | 25h | 01.17.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2888 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2887 | 10h | 01.17.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2889 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2888 | 10h | 01.17.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2890 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2889 | 5h | 01.17.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2891 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2890,2884 | 0h | 01.17.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2892 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סדרה ע"ב מסך MIGO עבור סדרות במחסנים מנוהלי SAP - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2893 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2894 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2895 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2896 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2897 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 23/08/2021 | 29/08/2021 | 0 | 2896 | 0h | 01.17.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2898 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2897 | 25h | 01.17.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2899 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2898 | 10h | 01.17.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2900 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2899 | 10h | 01.17.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2901 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2900 | 5h | 01.17.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2902 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2901,2895 | 0h | 01.17.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2903 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סדרה ע"ב מסך VL32N עבור סדרות במחסנים מנוהלי SAP סדרות מזון - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2904 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2905 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2906 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2907 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2908 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/08/2021 | 29/08/2021 | 0 | 2907 | 0h | 01.17.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2909 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2908 | 25h | 01.17.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2910 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2909 | 10h | 01.17.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2911 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2910 | 10h | 01.17.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2912 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2911 | 5h | 01.17.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2913 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2912,2906 | 0h | 01.17.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2914 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סדרה ע"ב מסך MSC1N או דרך מרק"ט על בסיס נתונים שנשלחו - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2915 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2916 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2917 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2918 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2919 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 26/08/2021 | 19/09/2021 | 0 | 2918 | 0h | 01.17.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2920 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2919 | 25h | 01.17.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2921 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2920 | 10h | 01.17.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2922 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2921 | 10h | 01.17.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2923 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2922 | 5h | 01.17.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2924 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2923,2917 | 0h | 01.17.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2925 |  | Auto Scheduled | סדרות פיקטיביות ממערכת מרק"ט למערכת WMS - SAP | 74 days | May 10, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2926 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2927 |  | Auto Scheduled | LifeCycle Tasks | 74 days | May 10, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2928 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2929 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2930 |  | Manually Scheduled | יישום ופיתוח סאפ | 24 days | May 10, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 2929 | 0h | 01.17.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2931 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 11, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 2930 | 25h | 01.17.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2932 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 16, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 2931 | 10h | 01.17.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2933 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 30, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 2932 | 10h | 01.17.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2934 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 13, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 2933 | 5h | 01.17.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2935 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 19, 2021 5:00 PM | August 19, 2021 5:00 PM | 0 | 2934,2928 | 0h | 01.17.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2936 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת סדרה במסגרת פתיחת פק"ע ע"ב מסך ZCO01 - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2937 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2938 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2939 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2940 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2941 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 19/09/2021 | 30/09/2021 | 0 | 2940 | 0h | 01.17.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2942 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 2941 | 25h | 01.17.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2943 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 2942 | 10h | 01.17.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2944 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 2943 | 10h | 01.17.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2945 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 2944 | 5h | 01.17.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2946 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 2945,2939 | 0h | 01.17.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2947 |  | Auto Scheduled | מערכת הSAP תאפשר פתיחת סדרה בתהליך הערכות - SAP | 75 days | May 7, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2948 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2949 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 7, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2950 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2951 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2952 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 7, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 2951 | 0h | 01.17.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2953 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 11, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 2952 | 25h | 01.17.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2954 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 16, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 2953 | 10h | 01.17.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2955 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 30, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 2954 | 10h | 01.17.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2956 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 13, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 2955 | 5h | 01.17.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2957 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 19, 2021 5:00 PM | August 19, 2021 5:00 PM | 0 | 2956,2950 | 0h | 01.17.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2958 |  | Auto Scheduled | מערכת SAP תאפשר לפתוח סדרה בתהליך המרות ( נדרש כי מלאי הסדרה לא תתאפשר לניפוק כל עוד לא בוצע המרה במערכת WMS ) - SAP | 138 days | March 10, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2959 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2960 |  | Auto Scheduled | LifeCycle Tasks | 138 days | March 10, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2961 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2962 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2963 |  | Manually Scheduled | יישום ופיתוח סאפ | 89 days | March 10, 2021 8:00 AM | July 10, 2021 5:00 PM | 0 | 2962 | 0h | 01.17.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2964 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 12, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 2963 | 25h | 01.17.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2965 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 16, 2021 8:00 AM | August 27, 2021 5:00 PM | 0 | 2964 | 10h | 01.17.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2966 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 30, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 2965 | 10h | 01.17.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2967 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 2966 | 5h | 01.17.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2968 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 17, 2021 5:00 PM | September 17, 2021 5:00 PM | 0 | 2967,2961 | 0h | 01.17.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2969 |  | Auto Scheduled | מערכת SAP תאפשר לפתוח סדרה בתהליך חיוב עצמי, במחסנים מיוחדים מנוהלי SAP וניהול צבאי בלבד. - SAP | 74 days | May 10, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2970 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2971 |  | Auto Scheduled | LifeCycle Tasks | 74 days | May 10, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2972 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2973 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2974 |  | Manually Scheduled | יישום ופיתוח סאפ | 24 days | May 10, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 2973 | 0h | 01.17.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2975 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 11, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 2974 | 25h | 01.17.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2976 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 16, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 2975 | 10h | 01.17.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2977 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 30, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 2976 | 10h | 01.17.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2978 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 13, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 2977 | 5h | 01.17.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2979 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 19, 2021 5:00 PM | August 19, 2021 5:00 PM | 0 | 2978,2972 | 0h | 01.17.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2980 |  | Auto Scheduled | מערכת SAP תאפשר לשנות מאפייני סדרות , - SAP | 160 days | May 10, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2981 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2982 |  | Auto Scheduled | LifeCycle Tasks | 160 days | May 10, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 70h | 01.17.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2983 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2984 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2985 |  | Manually Scheduled | יישום ופיתוח סאפ | 111 days | May 10, 2021 8:00 AM | October 10, 2021 5:00 PM | 0 | 2984 | 0h | 01.17.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2986 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 11, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 2985 | 25h | 01.17.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2987 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 15, 2021 8:00 AM | November 26, 2021 5:00 PM | 0 | 2986 | 10h | 01.17.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2988 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 29, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 2987 | 10h | 01.17.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2989 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 13, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 | 2988 | 5h | 01.17.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2990 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 17, 2021 5:00 PM | December 17, 2021 5:00 PM | 0 | 2989,2983 | 0h | 01.17.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2991 |  | Auto Scheduled | מערכת SAP תאפשר שינוי סטטוס סדרה באמצעות הגו'ב הליילי (בחינת מאפייני פג"ת) - SAP | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.17.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
2992 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
2993 |  | Auto Scheduled | LifeCycle Tasks | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.17.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
2994 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2995 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2996 |  | Manually Scheduled | יישום ופיתוח סאפ | 132 days | June 10, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 2995 | 0h | 01.17.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2997 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 13, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 2996 | 25h | 01.17.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2998 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 17, 2022 8:00 AM | January 28, 2022 5:00 PM | 0 | 2997 | 10h | 01.17.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
2999 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 31, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 2998 | 10h | 01.17.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3000 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 14, 2022 8:00 AM | February 18, 2022 5:00 PM | 0 | 2999 | 5h | 01.17.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3001 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 18, 2022 5:00 PM | February 18, 2022 5:00 PM | 0 | 3000,2994 | 0h | 01.17.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3002 |  | Auto Scheduled | מערכת SAP תאפשר שינוי פג"ת לסדרה לפי שינוי במאפייני החומר באמצעות הגו'ב הליילי (בחינת מאפייני פג"ת) - SAP | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.17.SAP.16 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3003 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3004 |  | Auto Scheduled | LifeCycle Tasks | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.17.SAP.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3005 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.16.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3006 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.16.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3007 |  | Manually Scheduled | יישום ופיתוח סאפ | 111 days | July 10, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 3006 | 0h | 01.17.SAP.16.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3008 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 13, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 3007 | 25h | 01.17.SAP.16.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3009 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 17, 2022 8:00 AM | January 28, 2022 5:00 PM | 0 | 3008 | 10h | 01.17.SAP.16.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3010 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 31, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 3009 | 10h | 01.17.SAP.16.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3011 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 14, 2022 8:00 AM | February 18, 2022 5:00 PM | 0 | 3010 | 5h | 01.17.SAP.16.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3012 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 18, 2022 5:00 PM | February 18, 2022 5:00 PM | 0 | 3011,3005 | 0h | 01.17.SAP.16.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3013 |  | Auto Scheduled | מערכת SAP נדרשות לתת מענה לדוחות בפריטי דלק בחלוקה לחציון/ טווח תאריכים במספר שנים. - SAP | 178 days | May 18, 2021 8:00 AM | January 20, 2022 5:00 PM | 0 |  | 70h | 01.17.SAP.17 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3014 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3015 |  | Auto Scheduled | LifeCycle Tasks | 178 days | May 18, 2021 8:00 AM | January 20, 2022 5:00 PM | 0 |  | 70h | 01.17.SAP.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3016 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.17.SAP.17.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3017 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 29, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4667 | 20h | 01.17.SAP.17.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3018 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | October 10, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 3017 | 0h | 01.17.SAP.17.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3019 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 12, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 3018 | 25h | 01.17.SAP.17.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3020 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 17, 2021 8:00 AM | December 30, 2021 5:00 PM | 0 | 3019 | 10h | 01.17.SAP.17.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3021 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 31, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 3020 | 10h | 01.17.SAP.17.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3022 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 14, 2022 8:00 AM | January 20, 2022 5:00 PM | 0 | 3021 | 5h | 01.17.SAP.17.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3023 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 20, 2022 5:00 PM | January 20, 2022 5:00 PM | 0 | 3022,3016 | 0h | 01.17.SAP.17.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3024 |  | Auto Scheduled | 01.18: בימ"לים | 290 days | May 18, 2021 8:00 AM | June 27, 2022 5:00 PM | 0 |  | 1,573h | 01.18 | סיכום מסמך | מוריה | hd | עינת |  | BP | NA | As Soon As Possible | 3
3025 |  | Auto Scheduled | 01.18: בימ"לים.BP | 290 days | May 18, 2021 8:00 AM | June 27, 2022 5:00 PM | 0 |  | 163h | 01.18.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3026 |  | Auto Scheduled | 01.18: בימ"לים - BP | 290 days | May 18, 2021 8:00 AM | June 27, 2022 5:00 PM | 0 |  | 163h | 01.18.BP.01 | סיכום מסמך | מוריה | parent | עינת |  | BP | NA | As Soon As Possible | 5
3027 |  | Auto Scheduled | Sub Tasks | 290 days | May 18, 2021 8:00 AM | June 27, 2022 5:00 PM | 0 |  | 123h | 01.18.BP.01.01 |  | מוריה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3028 |  | Auto Scheduled | כתיבת מסמך | 45 days | May 18, 2021 8:00 AM | July 19, 2021 5:00 PM | 0 |  | 45h | 01.18.BP.01.01.20 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | Must Start On | 7
3029 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 9 days | July 20, 2021 8:00 AM | July 30, 2021 5:00 PM | 0 | 3028 | 9h | 01.18.BP.01.01.21 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
3030 |  | Auto Scheduled | אישור אבי | 174 days | August 2, 2021 8:00 AM | March 31, 2022 5:00 PM | 0 | 3029 | 7h | 01.18.BP.01.01.22 | בוצע | אבי | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
3031 |  | Auto Scheduled | אישור המנהלת | 3 days | April 1, 2022 8:00 AM | April 5, 2022 5:00 PM | 0 | 3030 | 3h | 01.18.BP.01.01.23 | בוצע | אבי | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
3032 |  | Auto Scheduled | אישור מקל"ר | 4 days | April 6, 2022 8:00 AM | April 11, 2022 5:00 PM | 0 | 3031 | 4h | 01.18.BP.01.01.24 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3033 |  | Auto Scheduled | אישור מפקדת | 5 days | April 12, 2022 8:00 AM | April 18, 2022 5:00 PM | 0 | 3032 | 5h | 01.18.BP.01.01.25 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
3034 |  | Auto Scheduled | אישור שגיב שרביט | 9 days | April 19, 2022 8:00 AM | April 29, 2022 5:00 PM | 0 | 3033 | 9h | 01.18.BP.01.01.26 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
3035 |  | Auto Scheduled | אישור ניר בשן | 8 days | May 2, 2022 8:00 AM | May 11, 2022 5:00 PM | 0 | 3034 | 8h | 01.18.BP.01.01.27 | בוצע | מוריה | MoM | מוריה | תע - מוריה | BP | NA | As Soon As Possible | 7
3036 |  | Auto Scheduled | אישור חטלו"ג | 33 days | May 12, 2022 8:00 AM | June 27, 2022 5:00 PM | 0 | 3035 | 33h | 01.18.BP.01.01.28 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3037 |  | Auto Scheduled | LifeCycle Tasks | 290 days | May 18, 2021 8:00 AM | June 27, 2022 5:00 PM | 0 |  | 40h | 01.18.BP.01.02 |  | מוריה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3038 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | June 27, 2022 5:00 PM | June 27, 2022 5:00 PM | 0 | 3036 | 0h | 01.18.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3039 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 01.18.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3040 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 3039 | 10h | 01.18.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3041 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3040 | 5h | 01.18.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3042 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3041 | 10h | 01.18.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3043 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3042 | 10h | 01.18.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3044 |  | Auto Scheduled | בחתימה | 0 days | June 27, 2022 5:00 PM | June 27, 2022 5:00 PM | 0 | 3043,3038 | 0h | 01.18.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3045 |  | Auto Scheduled | חתום | 0 days | June 27, 2022 5:00 PM | June 27, 2022 5:00 PM | 0 | 3044 | 0h | 01.18.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3046 |  | Auto Scheduled | 01.18: בימ"לים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 150h | 01.18.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3047 |  | Auto Scheduled | במצב הקיים גם מלאי שהינו בתיקון נחשב כמלאי מטכלי של המשק.--בדוחות המלאי נדרש שיישקף את המלאי כולל המלאי שנמצא בתיקון --נדרש לקבוע רשימת דוחות - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.01 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3048 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3049 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3050 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3051 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3050 | 10h | 01.18.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3052 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3051 | 20h | 01.18.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3053 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3052,3050 | 0h | 01.18.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3054 |  | Auto Scheduled | הפקת דו"ח צריכות מהBW.תיקוף דוחות עבור בימ"לים ב SAP כגון הפקת דו"ח צריכות מהBW - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3055 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3056 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3057 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3058 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3057 | 10h | 01.18.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3059 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3058 | 20h | 01.18.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3060 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3059,3057 | 0h | 01.18.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3061 |  | Auto Scheduled | נדרש לקבוע מה הדרך בו ייקבע שכר עידוד עבור כלל המשקים בבימ"לים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.04 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3062 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3063 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3064 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3065 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3064 | 10h | 01.18.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3066 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3065 | 20h | 01.18.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3067 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3066,3064 | 0h | 01.18.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3068 |  | Auto Scheduled | נדרשת החלטה ללו"ז מעבר וללו"ז אפיון תהליכי העבודה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.10 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3069 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3070 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3071 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.10.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3072 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3071 | 10h | 01.18.GEN.10.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3073 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3072 | 20h | 01.18.GEN.10.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3074 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3073,3071 | 0h | 01.18.GEN.10.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3075 |  | Auto Scheduled | נדרש לקבל קובץ מעודכן של המתחם אחסנה אחוד - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.11 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3076 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3077 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 01.18.GEN.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3078 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.GEN.11.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3079 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3078 | 10h | 01.18.GEN.11.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3080 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3079 | 20h | 01.18.GEN.11.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3081 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3080,3078 | 0h | 01.18.GEN.11.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3082 |  | Auto Scheduled | 01.18: בימ"לים.INT | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 490h | 01.18.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3083 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס לבימ"ל מנוהל WMS - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3084 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3085 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3086 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3087 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3088 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 22/11/2021 | 24/11/2021 | 0 | 3087 | 0h | 01.18.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3089 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3088 | 25h | 01.18.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3090 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3089 | 10h | 01.18.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3091 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3090 | 10h | 01.18.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3092 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3091 | 5h | 01.18.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3093 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3092,3086 | 0h | 01.18.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3094 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן מנוהל WMS במרה"ס לבימ"ל מנוהל SAP ( באתר 0010) - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3095 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3096 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3097 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3098 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3099 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 23/11/2021 | 25/11/2021 | 0 | 3098 | 0h | 01.18.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3100 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3099 | 25h | 01.18.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3101 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3100 | 10h | 01.18.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3102 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3101 | 10h | 01.18.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3103 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3102 | 5h | 01.18.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3104 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3103,3097 | 0h | 01.18.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3105 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס לחלון קבלה בבימ"ל מנוהל WMS - INT | 90 days | May 18, 2021 8:00 AM | September 20, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3106 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3107 |  | Auto Scheduled | LifeCycle Tasks | 90 days | May 18, 2021 8:00 AM | September 20, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3108 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3109 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3110 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | June 8, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3109 | 0h | 01.18.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3111 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 13, 2021 8:00 AM | August 16, 2021 5:00 PM | 0 | 3110 | 25h | 01.18.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3112 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 17, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3111 | 10h | 01.18.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3113 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 31, 2021 8:00 AM | September 13, 2021 5:00 PM | 0 | 3112 | 10h | 01.18.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3114 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 14, 2021 8:00 AM | September 20, 2021 5:00 PM | 0 | 3113 | 5h | 01.18.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3115 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | September 20, 2021 5:00 PM | September 20, 2021 5:00 PM | 0 | 3114,3108 | 0h | 01.18.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3116 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן מנוהל WMS במרה"ס לבימ"ל מנוהל SAP ( באתר מרה"ס ) - INT | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3117 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3118 |  | Auto Scheduled | LifeCycle Tasks | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3119 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3120 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3121 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | July 9, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 3120 | 0h | 01.18.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3122 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 13, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 3121 | 25h | 01.18.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3123 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 17, 2021 8:00 AM | September 30, 2021 5:00 PM | 0 | 3122 | 10h | 01.18.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3124 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 1, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3123 | 10h | 01.18.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3125 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 15, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 | 3124 | 5h | 01.18.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3126 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 3125,3119 | 0h | 01.18.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3127 |  | Auto Scheduled | מערכת WMS תאפשר ניפוק פריטים " גמורים" ממחסן גמורים בבימ"ל ( אתר מרה"ס מנוהל WMS) למחסן מיוחד מנוהל SAP ( באתר מרה"ס ) - INT | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3128 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3129 |  | Auto Scheduled | LifeCycle Tasks | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3130 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3131 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3132 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | September 12, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3131 | 0h | 01.18.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3133 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 15, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 3132 | 25h | 01.18.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3134 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 19, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 3133 | 10h | 01.18.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3135 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 3, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 3134 | 10h | 01.18.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3136 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 17, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 3135 | 5h | 01.18.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3137 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 3136,3130 | 0h | 01.18.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3138 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים " גמורים" ממחסן גמורים בבימ"ל ( אתר מרה"ס) למחסן מנוהל WMS ( באתר מרה"ס ) - INT | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 01.18.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3139 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3140 |  | Auto Scheduled | LifeCycle Tasks | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 01.18.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3141 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3142 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3143 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 12, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 3142 | 0h | 01.18.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3144 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 14, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 3143 | 25h | 01.18.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3145 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 18, 2022 8:00 AM | March 3, 2022 5:00 PM | 0 | 3144 | 10h | 01.18.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3146 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 4, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 3145 | 10h | 01.18.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3147 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 18, 2022 8:00 AM | March 24, 2022 5:00 PM | 0 | 3146 | 5h | 01.18.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3148 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 24, 2022 5:00 PM | March 24, 2022 5:00 PM | 0 | 3147,3141 | 0h | 01.18.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3149 |  | Auto Scheduled | מערכת SAP וWMS יאפשרו תעדוף ניפוקים בעדיפות גבוהה של פריטים הנמצאים במחסני הבימ"ל למחסני WMS בכדי לאפשר ניפוק מהיר לדרג הנפרש בשע"ח - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3150 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3151 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.INT.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3152 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.INT.07.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3153 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.INT.07.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3154 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 26/12/2021 | 28/12/2021 | 0 | 3153 | 0h | 01.18.INT.07.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3155 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3154 | 25h | 01.18.INT.07.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3156 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3155 | 10h | 01.18.INT.07.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3157 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3156 | 10h | 01.18.INT.07.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3158 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3157 | 5h | 01.18.INT.07.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3159 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3158,3152 | 0h | 01.18.INT.07.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3160 |  | Auto Scheduled | 01.18: בימ"לים.SAP | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 770h | 01.18.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3161 |  | Auto Scheduled | מערכת SAP נדרשת לתמוך את שינוי מבנה ארגוני של איחוד מחלקות לבימ"ל מכני אחוד - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3162 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3163 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3164 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3165 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3166 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 15/11/2021 | 17/11/2021 | 0 | 3165 | 0h | 01.18.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3167 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3166 | 25h | 01.18.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3168 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3167 | 10h | 01.18.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3169 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3168 | 10h | 01.18.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3170 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3169 | 5h | 01.18.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3171 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3170,3164 | 0h | 01.18.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3172 |  | Auto Scheduled | מערכת SAP נדרשת לתמוך את שינוי מבנה ארגוני של איחוד מחסן ח"ח וטכני - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3173 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3174 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3175 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3176 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3177 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 17/11/2021 | 21/11/2021 | 0 | 3176 | 0h | 01.18.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3178 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3177 | 25h | 01.18.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3179 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3178 | 10h | 01.18.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3180 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3179 | 10h | 01.18.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3181 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3180 | 5h | 01.18.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3182 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3181,3175 | 0h | 01.18.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3183 |  | Auto Scheduled | עבור פריטים רלוונטים הנמצאים פיזית בבימ"לים בכושרים 2,3 נדרשים להופיע במהלך MRP - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3184 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3185 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3186 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3187 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3188 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 21/11/2021 | 22/11/2021 | 0 | 3187 | 0h | 01.18.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3189 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3188 | 25h | 01.18.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3190 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3189 | 10h | 01.18.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3191 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3190 | 10h | 01.18.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3192 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3191 | 5h | 01.18.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3193 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3192,3186 | 0h | 01.18.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3194 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס למחסן ח"ח/טכני בבימ"ל מנוהל SAP ( באתר 0010) - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3195 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3196 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3197 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3198 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3199 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 21/11/2021 | 23/11/2021 | 0 | 3198 | 0h | 01.18.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3200 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3199 | 25h | 01.18.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3201 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3200 | 10h | 01.18.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3202 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3201 | 10h | 01.18.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3203 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3202 | 5h | 01.18.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3204 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3203,3197 | 0h | 01.18.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3205 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן מיוחד במרה"ס לחלון קבלה בבימ"ל מנוהל SAP ( באתר מרה"ס ) - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3206 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3207 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3208 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3209 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3210 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 24/11/2021 | 28/11/2021 | 0 | 3209 | 0h | 01.18.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3211 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3210 | 25h | 01.18.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3212 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3211 | 10h | 01.18.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3213 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3212 | 10h | 01.18.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3214 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3213 | 5h | 01.18.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3215 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3214,3208 | 0h | 01.18.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3216 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק ח"ח/טכני פנים בימ"ל (ממחסן ח"ח/טכני ( אתר 0010) לחלון קבלה בבימ"ל (אתר מרה"ס)) - SAP | 134 days | May 18, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3217 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3218 |  | Auto Scheduled | LifeCycle Tasks | 134 days | May 18, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3219 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3220 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3221 |  | Manually Scheduled | יישום ופיתוח סאפ | 46 days | July 12, 2021 8:00 AM | September 12, 2021 5:00 PM | 0 | 3220 | 0h | 01.18.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3222 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 13, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 3221 | 25h | 01.18.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3223 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 18, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 3222 | 10h | 01.18.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3224 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 1, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 3223 | 10h | 01.18.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3225 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 15, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 | 3224 | 5h | 01.18.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3226 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 19, 2021 5:00 PM | November 19, 2021 5:00 PM | 0 | 3225,3219 | 0h | 01.18.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3227 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים " גמורים" ממחסן גמורים בבימ"ל ( אתר מרה"ס) למחסן מיוחד מנוהל SAP ( באתר מרה"ס ) - SAP | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.18.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3228 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3229 |  | Auto Scheduled | LifeCycle Tasks | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 01.18.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3230 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3231 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3232 |  | Manually Scheduled | יישום ופיתוח סאפ | 88 days | August 12, 2021 8:00 AM | December 12, 2021 5:00 PM | 0 | 3231 | 0h | 01.18.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3233 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 13, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 3232 | 25h | 01.18.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3234 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 17, 2022 8:00 AM | January 28, 2022 5:00 PM | 0 | 3233 | 10h | 01.18.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3235 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 31, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 3234 | 10h | 01.18.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3236 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 14, 2022 8:00 AM | February 18, 2022 5:00 PM | 0 | 3235 | 5h | 01.18.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3237 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 18, 2022 5:00 PM | February 18, 2022 5:00 PM | 0 | 3236,3230 | 0h | 01.18.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3238 |  | Auto Scheduled | מערכת SAP תאפשר ניפוק פריטים ממחסן גמורים בבימ"ל (מנוהל SAP באתר מרה"ס) לאתר 0010 - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3239 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3240 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3241 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3242 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3243 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 13/12/2021 | 15/12/2021 | 0 | 3242 | 0h | 01.18.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3244 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3243 | 25h | 01.18.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3245 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3244 | 10h | 01.18.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3246 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3245 | 10h | 01.18.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3247 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3246 | 5h | 01.18.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3248 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3247,3241 | 0h | 01.18.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3249 |  | Auto Scheduled | מערכת SAP תאפשר צריכה/צריכה במשימה - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3250 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3251 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3252 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3253 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3254 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 14/12/2021 | 21/12/2021 | 0 | 3253 | 0h | 01.18.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3255 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3254 | 25h | 01.18.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3256 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3255 | 10h | 01.18.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3257 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3256 | 10h | 01.18.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3258 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3257 | 5h | 01.18.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3259 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3258,3252 | 0h | 01.18.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3260 |  | Auto Scheduled | מערכת SAP תאפשר חיוב עצמי ממציאת פריט/חיוב עצמי על אפסניה מייצור - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3261 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3262 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3263 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3264 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3265 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 20/12/2021 | 27/12/2021 | 0 | 3264 | 0h | 01.18.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3266 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3265 | 25h | 01.18.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3267 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3266 | 10h | 01.18.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3268 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3267 | 10h | 01.18.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3269 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3268 | 5h | 01.18.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3270 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3269,3263 | 0h | 01.18.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3271 |  | Auto Scheduled | מערכת SAP תאפשר השמדה עבור פריטים מנוהלים בבימ"לים - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3272 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3273 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 01.18.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3274 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 01.18.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3275 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | June 15, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5066 | 20h | 01.18.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3276 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 23/12/2021 | 27/12/2021 | 0 | 3275 | 0h | 01.18.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3277 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3276 | 25h | 01.18.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3278 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3277 | 10h | 01.18.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3279 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3278 | 10h | 01.18.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3280 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3279 | 5h | 01.18.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3281 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3280,3274 | 0h | 01.18.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3282 |  | Auto Scheduled | 02: שרשרת אספקה | 635 days | October 8, 2020 8:00 AM | March 15, 2023 5:00 PM | 0.01 |  | 9,769h | 02 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
3283 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת | 313 days | October 8, 2020 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 262h | 02.01 | ממתין לאישור | אבי פרישמן | hd | פריאל |  | BP | NA | As Soon As Possible | 3
3284 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת.BP | 300 days | October 8, 2020 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 162h | 02.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3285 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת - BP | 300 days | October 8, 2020 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 162h | 02.01.BP.01 | ממתין לאישור | אבי פרישמן | parent | פריאל |  | BP | NA | As Soon As Possible | 5
3286 |  | Auto Scheduled | Sub Tasks | 300 days | October 8, 2020 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 122h | 02.01.BP.01.01 |  | אבי פרישמן | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3287 |  | Auto Scheduled | 1. באחריות אמל"ח בשיתוף פעולה עם המשתמשים, לרכז את כלל המסמכים, מסכים ותהליכים העלולים להפגע כתוצאה מהשינויים (כדוגמת הקישור בין לקוח למיכליות ברמת ארגון מכירות דלק) לצורך ביצוע ההתאמות על ידנו. | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.01.BP.01.01.10 | בוצע | פריאל | MoM | פריאל | מאיה | BP | NA | Must Start On | 7
3288 |  | Auto Scheduled | 2. יש לבדוק האם משק הדלקים שינוהל SAP בלבד יכלל באתר וארגון מכירות מרהס. באחריות אמלח למול אבי | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 02.01.BP.01.01.11 | בוצע | אבי | MoM | פריאל | מאיה | BP | NA | As Soon As Possible | 7
3289 |  | Auto Scheduled | כתיבת מסמך | 26 days | May 18, 2021 8:00 AM | June 22, 2021 5:00 PM | 0 |  | 26h | 02.01.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3290 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 4 days | June 23, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3289 | 4h | 02.01.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3291 |  | Auto Scheduled | אישור מקל"ר | 14 days | June 29, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 3290 | 14h | 02.01.BP.01.01.32 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3292 |  | Auto Scheduled | אישור אבי | 31 days | July 19, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3291 | 31h | 02.01.BP.01.01.33 | בוצע | אבי | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3293 |  | Auto Scheduled | אישור המנהלת | 24 days | August 31, 2021 8:00 AM | October 1, 2021 5:00 PM | 0 | 3292 | 2h | 02.01.BP.01.01.34 | בוצע | סיגל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3294 |  | Auto Scheduled | אישור מפקדת | 15 days | October 4, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 3293 | 15h | 02.01.BP.01.01.35 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3295 |  | Auto Scheduled | אישור חטלו"ג | 2 days | October 25, 2021 8:00 AM | October 26, 2021 5:00 PM | 0 | 3294 | 2h | 02.01.BP.01.01.36 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3296 |  | Auto Scheduled | אישור שגיב שרביט | 3 days | October 27, 2021 8:00 AM | October 29, 2021 5:00 PM | 0 | 3295 | 3h | 02.01.BP.01.01.37 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3297 |  | Auto Scheduled | אישור ניר בשן | 23 days | November 1, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 | 3296 | 23h | 02.01.BP.01.01.38 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3298 |  | Auto Scheduled | LifeCycle Tasks | 142 days | May 18, 2021 8:00 AM | December 1, 2021 5:00 PM | 0 |  | 40h | 02.01.BP.01.02 |  | אבי פרישמן | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3299 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 1, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 | 3297 | 0h | 02.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3300 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3301 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 3300 | 10h | 02.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3302 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3301 | 5h | 02.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3303 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3302 | 10h | 02.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3304 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3303 | 10h | 02.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3305 |  | Auto Scheduled | בחתימה | 0 days | December 1, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 | 3304,3299 | 0h | 02.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3306 |  | Auto Scheduled | חתום | 0 days | December 1, 2021 5:00 PM | December 1, 2021 5:00 PM | 0 | 3305 | 0h | 02.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3307 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.01.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3308 |  | Auto Scheduled | יש להעביר דמ"צ לדוחות בנושא - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.01.GEN.15 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3309 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.01.GEN.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3310 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.01.GEN.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3311 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.01.GEN.15.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3312 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3311 | 10h | 02.01.GEN.15.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3313 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3312 | 20h | 02.01.GEN.15.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3314 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3313,3311 | 0h | 02.01.GEN.15.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3315 |  | Auto Scheduled | 02.01: מבנה ארגוני - שרשרת - > אספקה ליחידות.SAP | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 70h | 02.01.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3316 |  | Auto Scheduled | מערכת הSAP תאפשר פיצול אספקות במרחבים שטרם מובצעו בשלב המבצוע ההדרגתי על ידי נקודות המשלוח החדשות והישנות. - SAP | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 70h | 02.01.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3317 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.01.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3318 |  | Auto Scheduled | LifeCycle Tasks | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 70h | 02.01.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3319 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.01.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3320 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | November 23, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 | 5350 | 20h | 02.01.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3321 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/01/2022 | 31/01/2022 | 0 | 3320 | 0h | 02.01.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3322 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3321 | 25h | 02.01.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3323 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3322 | 10h | 02.01.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3324 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3323 | 10h | 02.01.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3325 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3324 | 5h | 02.01.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3326 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3325,3319 | 0h | 02.01.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3327 |  | Auto Scheduled | 02.02: אספקה ליחידות | 547 days | January 7, 2021 5:00 PM | February 13, 2023 5:00 PM | 0 |  | 2,354h | 02.02 | ממתין לאישור | פריאל ישי | hd | פריאל |  | BP | NA | As Soon As Possible | 3
3328 |  | Auto Scheduled | 02.02: אספקה ליחידות.BP | 123 days | May 18, 2021 8:00 AM | November 4, 2021 5:00 PM | 0 |  | 304h | 02.02.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3329 |  | Auto Scheduled | 02.02: אספקה ליחידות - BP | 123 days | May 18, 2021 8:00 AM | November 4, 2021 5:00 PM | 0 |  | 304h | 02.02.BP.01 | ממתין לאישור | פריאל ישי | parent | פריאל |  | BP | NA | As Soon As Possible | 5
3330 |  | Auto Scheduled | Sub Tasks | 123 days | May 18, 2021 8:00 AM | November 4, 2021 5:00 PM | 0 |  | 264h | 02.02.BP.01.01 |  | פריאל ישי | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3331 |  | Auto Scheduled | הפער המרכזי הוא נושא ניהול המצ"מ – האם ינוהל באתר אחסון נפרד מבחינת מערכת ה-SAP או לא. לאחר סגירת הנושא במבנה הארגוני נוכל לסכם את ה-BP. | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | 02.02.BP.01.01.10 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | Must Start On | 7
3332 |  | Auto Scheduled | (הסבר – את רוב הפעולות הקשורות החזרה החלטנו שנדרש לבצע בSAP אבל אם לא יהיה אתר אחסון נפרד המצ"מ יאבד שליטה במלאי ולכן אולי נצטרך לעדכן את הBP) | 22 days | May 18, 2021 8:00 AM | June 16, 2021 5:00 PM | 0 |  | 22h | 02.02.BP.01.01.11 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
3333 |  | Auto Scheduled | מבחינת יישום שרשרת לא משנה באיזו מערכת המצ"מ יעבוד, למשתמשים זה משנה כי אם לא יהיה להם אתר אחסון נפרד בSAP הם לא יוכלו לבצע את הפעולות בSAP כמו שקבעו (חוששים לאבד שליטה במלאי). | 24 days | May 18, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 |  | 23h | 02.02.BP.01.01.12 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
3334 |  | Auto Scheduled | אבי מכיר את הסוגייה וסוגיות נוספות שבעייתיות בנושא המצ"ב, שגם מלאי העלו. מה הסטאטוס? | 45 days | May 18, 2021 8:00 AM | July 19, 2021 5:00 PM | 0 |  | 24h | 02.02.BP.01.01.13 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
3335 |  | Auto Scheduled | המיפוי (/BP) של כל התהליך נשלח לאישור ב19.05. ממתין לאישור אמל"ח. | 68 days | May 18, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 25h | 02.02.BP.01.01.14 | בוצע |  | MoM |  | מאיה | BP | NA | As Soon As Possible | 7
3336 |  | Auto Scheduled | כמו כן, נשלח לאישור BP אספקה ללא סימוכין - מה הסטאטוס? | 89 days | May 18, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 26h | 02.02.BP.01.01.15 | בוצע |  | MoM |  | מאיה | BP | NA | As Soon As Possible | 7
3337 |  | Auto Scheduled | כתיבת מסמך | 4 days | May 18, 2021 8:00 AM | May 21, 2021 5:00 PM | 0 |  | 4h | 02.02.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3338 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 25 days | May 24, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 3337 | 25h | 02.02.BP.01.01.31 | בוצע | פריאל | MoM |  |  | BP | NA | As Soon As Possible | 7
3339 |  | Auto Scheduled | אישור מקל"ר | 16 days | June 28, 2021 8:00 AM | July 19, 2021 5:00 PM | 0 | 3338 | 16h | 02.02.BP.01.01.32 | בוצע |  | MoM |  | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
3340 |  | Auto Scheduled | אישור אבי | 34 days | July 20, 2021 8:00 AM | September 3, 2021 5:00 PM | 0 | 3339 | 34h | 02.02.BP.01.01.33 | בוצע | אבי | MoM | פריאל | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
3341 |  | Auto Scheduled | אישור מפקדת | 15 days | September 6, 2021 8:00 AM | September 24, 2021 5:00 PM | 0 | 3340 | 15h | 02.02.BP.01.01.35 | בוצע |  | MoM | פריאל | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
3342 |  | Auto Scheduled | אישור חטלו"ג | 2 days | September 27, 2021 8:00 AM | September 28, 2021 5:00 PM | 0 | 3341 | 2h | 02.02.BP.01.01.36 | בוצע |  | MoM |  | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
3343 |  | Auto Scheduled | אישור שגיב שרביט | 3 days | September 29, 2021 8:00 AM | October 1, 2021 5:00 PM | 0 | 3342 | 3h | 02.02.BP.01.01.37 | בוצע |  | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
3344 |  | Auto Scheduled | אישור המנהלת | 11 days | October 4, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 3343 | 11h | 02.02.BP.01.01.38 | בוצע | סיגל | MoM | פריאל | 2020-10-28 00:00:00 | BP | NA | As Soon As Possible | 7
3345 |  | Auto Scheduled | אישור ניר בשן | 13 days | October 19, 2021 8:00 AM | November 4, 2021 5:00 PM | 0 | 3344 | 13h | 02.02.BP.01.01.39 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3346 |  | Auto Scheduled | LifeCycle Tasks | 123 days | May 18, 2021 8:00 AM | November 4, 2021 5:00 PM | 0 |  | 40h | 02.02.BP.01.02 |  | פריאל ישי | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3347 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | November 4, 2021 5:00 PM | November 4, 2021 5:00 PM | 0 | 3345 | 0h | 02.02.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3348 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.02.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3349 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 3348 | 10h | 02.02.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3350 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3349 | 5h | 02.02.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3351 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3350 | 10h | 02.02.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3352 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3351 | 10h | 02.02.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3353 |  | Auto Scheduled | בחתימה | 0 days | November 4, 2021 5:00 PM | November 4, 2021 5:00 PM | 0 | 3352,3347 | 0h | 02.02.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3354 |  | Auto Scheduled | חתום | 0 days | November 4, 2021 5:00 PM | November 4, 2021 5:00 PM | 0 | 3353 | 0h | 02.02.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3355 |  | Auto Scheduled | 02.02: אספקה ליחידות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 90h | 02.02.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3356 |  | Auto Scheduled | וקטור הניפוק ופיצול אספקות - יושלמו בהמשך. חוקות אלו ינוהלו אצל הזכיין. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.02.GEN.01 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3357 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3358 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.02.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3359 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3360 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3359 | 10h | 02.02.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3361 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3360 | 20h | 02.02.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3362 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3361,3359 | 0h | 02.02.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3363 |  | Auto Scheduled | נדרש לוודא את אופן ניהול גדלי האריזה בעידן הזכיין. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.02.GEN.05 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3364 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.GEN.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3365 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.02.GEN.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3366 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.GEN.05.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3367 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3366 | 10h | 02.02.GEN.05.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3368 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3367 | 20h | 02.02.GEN.05.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3369 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3368,3366 | 0h | 02.02.GEN.05.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3370 |  | Auto Scheduled | נדרש לקבל דמ"ץ דוחות לבקרה אחר תהליך שרשרת האספקה. - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.02.GEN.08 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3371 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3372 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.02.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3373 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3374 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3373 | 10h | 02.02.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3375 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3374 | 20h | 02.02.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3376 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3375,3373 | 0h | 02.02.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3377 |  | Auto Scheduled | 02.02: אספקה ליחידות.INT | 310 days | January 7, 2021 5:00 PM | March 17, 2022 5:00 PM | 0 |  | 910h | 02.02.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3378 |  | Auto Scheduled | מערכת ה-SAP תשלח הזמנות למערכת ה-WMS לטובת ליקוט, אריזה והפצה ליחידה. - INT | 310 days | January 7, 2021 5:00 PM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3379 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3380 |  | Auto Scheduled | LifeCycle Tasks | 310 days | January 7, 2021 5:00 PM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3381 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3382 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3383 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 0 days | January 7, 2021 5:00 PM | January 7, 2021 5:00 PM | 0 | 3382 | 0h | 02.02.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3384 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 8, 2021 8:00 AM | February 11, 2021 5:00 PM | 0 | 3383 | 25h | 02.02.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3385 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 12, 2021 8:00 AM | February 25, 2021 5:00 PM | 0 | 3384 | 10h | 02.02.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3386 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 26, 2021 8:00 AM | March 11, 2021 5:00 PM | 0 | 3385 | 10h | 02.02.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3387 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 12, 2021 8:00 AM | March 18, 2021 5:00 PM | 0 | 3386 | 5h | 02.02.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3388 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 3387,3381 | 0h | 02.02.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3389 |  | Auto Scheduled | במקרים שנשלחים למערכת ה-WMS הזמנות ללא ציון מספר הסדרה, יש לוודא בחירת הסדרה ע"י מערכת ה- WMS בהתאם למאפייני הפריט (FIFO, LIFO וכד) ועדכון הסדרה במערכות הSAP – יבוצע באספקה לאחר ליקוט המלאי במערכת הWMS. - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3390 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3391 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3392 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3393 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3394 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 15/06/2021 | 21/06/2021 | 0 | 3393 | 0h | 02.02.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3395 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3394 | 25h | 02.02.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3396 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3395 | 10h | 02.02.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3397 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3396 | 10h | 02.02.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3398 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3397 | 5h | 02.02.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3399 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3398,3392 | 0h | 02.02.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3400 |  | Auto Scheduled | מערכת ה- WMS תשלח (בממשק אוטומטי) למערכת ה-SAP את אספקות ה- WMS (או כל ישות מקבילה) כולל נתוני התכולה המתוכננים ומועד אספקה מתוכנן.--הנתונים יכללו, מספר הזמנה (כולל שורה), לקוח, משאית, פריטים, כמויות, אמצעי אריזה/ניטול, נתוני מסלול וכו'. - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3401 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3402 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3403 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3404 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3405 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | October 5, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 3404 | 0h | 02.02.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3406 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 9, 2021 8:00 AM | December 13, 2021 5:00 PM | 0 | 3405 | 25h | 02.02.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3407 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 14, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 | 3406 | 10h | 02.02.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3408 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 28, 2021 8:00 AM | January 10, 2022 5:00 PM | 0 | 3407 | 10h | 02.02.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3409 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 11, 2022 8:00 AM | January 17, 2022 5:00 PM | 0 | 3408 | 5h | 02.02.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3410 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 3409,3403 | 0h | 02.02.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3411 |  | Auto Scheduled | מערכת ה WMS תתמוך בשליחת סטטוסים/חיוויים (שישלחו אונליין) למערכת ה SAP, ומערכת הSAP תאפשר קבלת עדכון סטטוס בהתאם לסטטוס האספקה הקיים במערכת הWMS לשלבים הבאים: "בליקוט", "לוקט", "הועבר למחסן הפצה", "הועמס למשאית", "מוכן להפצה ישירות מהמחסן", "יצא למשלוח" | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3412 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3413 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3414 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3415 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3416 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | July 7, 2021 8:00 AM | August 10, 2021 5:00 PM | 0 | 3415 | 0h | 02.02.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3417 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 3416 | 25h | 02.02.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3418 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 15, 2021 8:00 AM | September 28, 2021 5:00 PM | 0 | 3417 | 10h | 02.02.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3419 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 29, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 3418 | 10h | 02.02.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3420 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 13, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 3419 | 5h | 02.02.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3421 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 19, 2021 5:00 PM | October 19, 2021 5:00 PM | 0 | 3420,3414 | 0h | 02.02.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3422 |  | Auto Scheduled | מערכת ה SAP תשלח שדר עדכון נתוני האספקה/משלוח למסופון POD רק לאחר העמסה בפועל על המשאית. - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3423 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3424 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3425 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3426 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3427 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 14/07/2021 | 22/08/2021 | 0 | 3426 | 0h | 02.02.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3428 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3427 | 25h | 02.02.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3429 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3428 | 10h | 02.02.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3430 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3429 | 10h | 02.02.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3431 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3430 | 5h | 02.02.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3432 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3431,3425 | 0h | 02.02.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3433 |  | Auto Scheduled | מערכת ה-WMS תשדר את סטטוס האספקה ואת תנועות הניפוק למערכת ה-SAP - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3434 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3435 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3436 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3437 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3438 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 28/07/2021 | 17/08/2021 | 0 | 3437 | 0h | 02.02.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3439 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3438 | 25h | 02.02.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3440 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3439 | 10h | 02.02.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3441 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3440 | 10h | 02.02.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3442 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3441 | 5h | 02.02.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3443 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3442,3436 | 0h | 02.02.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3444 |  | Auto Scheduled | הנתיב שיוזן בהזמנה יהיה פיקטיבי ובעת יצירת האספקה במערכת ה SAP יתקבלו נתוני המסלול ממערכת הTMS ויוזנו לאספקה שתיווצר במערכת הSAP. - INT | 269 days | March 8, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3445 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3446 |  | Auto Scheduled | LifeCycle Tasks | 269 days | March 8, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3447 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.07.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3448 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.07.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3449 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | March 8, 2021 8:00 AM | April 9, 2021 5:00 PM | 0 | 3448 | 0h | 02.02.INT.07.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3450 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 12, 2021 8:00 AM | May 14, 2021 5:00 PM | 0 | 3449 | 25h | 02.02.INT.07.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3451 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 17, 2021 8:00 AM | May 28, 2021 5:00 PM | 0 | 3450 | 10h | 02.02.INT.07.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3452 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 31, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 3451 | 10h | 02.02.INT.07.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3453 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 14, 2021 8:00 AM | June 18, 2021 5:00 PM | 0 | 3452 | 5h | 02.02.INT.07.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3454 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | June 18, 2021 5:00 PM | June 18, 2021 5:00 PM | 0 | 3453,3447 | 0h | 02.02.INT.07.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3455 |  | Auto Scheduled | מערכת ה- WMS תשלח שדרים למערכת ה- SAP לשיקוף המשלוחים שייפתחו לצורך הפצת האספקות ליחידות - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.08 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3456 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3457 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3458 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.08.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3459 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.08.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3460 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 16/08/2021 | 24/08/2021 | 0 | 3459 | 0h | 02.02.INT.08.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3461 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3460 | 25h | 02.02.INT.08.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3462 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3461 | 10h | 02.02.INT.08.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3463 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3462 | 10h | 02.02.INT.08.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3464 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3463 | 5h | 02.02.INT.08.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3465 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3464,3458 | 0h | 02.02.INT.08.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3466 |  | Auto Scheduled | מערכת ה – WMS תשלח שדר למערכת הSAP לצורך קישור אריזות לאספקה ולשימוש המידע ב – POD - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.09 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3467 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3468 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3469 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.09.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3470 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.09.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3471 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 6, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 3470 | 0h | 02.02.INT.09.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3472 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3471 | 25h | 02.02.INT.09.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3473 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 3472 | 10h | 02.02.INT.09.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3474 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 3473 | 10h | 02.02.INT.09.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3475 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 3474 | 5h | 02.02.INT.09.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3476 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 3475,3469 | 0h | 02.02.INT.09.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3477 |  | Auto Scheduled | מערכת הPOD תתמוך בשליחת סטטוס "קבלת משלוח" למערכת הSAP - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.10 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3478 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3479 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3480 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.10.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3481 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.10.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3482 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 18/08/2021 | 13/09/2021 | 0 | 3481 | 0h | 02.02.INT.10.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3483 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3482 | 25h | 02.02.INT.10.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3484 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3483 | 10h | 02.02.INT.10.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3485 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3484 | 10h | 02.02.INT.10.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3486 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3485 | 5h | 02.02.INT.10.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3487 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3486,3480 | 0h | 02.02.INT.10.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3488 |  | Auto Scheduled | הזמנת הניפוק המעודכנת תעבור בממשק למרחב המנפק הרלוונטי - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.11 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3489 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3490 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3491 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.11.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3492 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.11.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3493 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | June 8, 2021 8:00 AM | July 10, 2021 5:00 PM | 0 | 3492 | 0h | 02.02.INT.11.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3494 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 12, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 3493 | 25h | 02.02.INT.11.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3495 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 16, 2021 8:00 AM | August 27, 2021 5:00 PM | 0 | 3494 | 10h | 02.02.INT.11.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3496 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 30, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 3495 | 10h | 02.02.INT.11.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3497 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 3496 | 5h | 02.02.INT.11.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3498 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | September 17, 2021 5:00 PM | September 17, 2021 5:00 PM | 0 | 3497,3491 | 0h | 02.02.INT.11.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3499 |  | Auto Scheduled | מערכת הwms תשלח שדר למערכת הSAP לצורך יצירת משלוח מהמרחב המקבל ליחידה. - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.12 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3500 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3501 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3502 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.12.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3503 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.12.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3504 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 13/09/2021 | 30/09/2021 | 0 | 3503 | 0h | 02.02.INT.12.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3505 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3504 | 25h | 02.02.INT.12.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3506 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3505 | 10h | 02.02.INT.12.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3507 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3506 | 10h | 02.02.INT.12.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3508 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3507 | 5h | 02.02.INT.12.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3509 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3508,3502 | 0h | 02.02.INT.12.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3510 |  | Auto Scheduled | מערכת הSAP תאפשר לשלוח הזמנות למערכת הWMS ללא בדיקת זמינות פריטים במשק המזון בלבד לטובת תכנון הפצה - INT | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.13 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3511 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3512 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.INT.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3513 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.INT.13.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3514 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.INT.13.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3515 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 19/09/2021 | 17/10/2021 | 0 | 3514 | 0h | 02.02.INT.13.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3516 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3515 | 25h | 02.02.INT.13.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3517 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3516 | 10h | 02.02.INT.13.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3518 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3517 | 10h | 02.02.INT.13.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3519 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3518 | 5h | 02.02.INT.13.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3520 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3519,3513 | 0h | 02.02.INT.13.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3521 |  | Auto Scheduled | 02.02: אספקה ליחידות.SAP | 461 days | May 10, 2021 8:00 AM | February 13, 2023 5:00 PM | 0 |  | 1,050h | 02.02.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3522 |  | Auto Scheduled | מערכת ה-SAP תכלול חוקות בדרישה בהתאם למבנה הארגוני החדש של המרה"ס - SAP | 243 days | May 10, 2021 8:00 AM | April 13, 2022 5:00 PM | 0.01 |  | 70h | 02.02.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3523 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3524 |  | Auto Scheduled | LifeCycle Tasks | 243 days | May 10, 2021 8:00 AM | April 13, 2022 5:00 PM | 0.01 |  | 70h | 02.02.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3525 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3526 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3527 |  | Manually Scheduled | יישום ופיתוח סאפ | 193 days | May 10, 2021 8:00 AM | February 2, 2022 5:00 PM | 0.02 | 3526 | 0h | 02.02.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3528 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 3, 2022 8:00 AM | March 9, 2022 5:00 PM | 0 | 3527 | 25h | 02.02.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3529 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 10, 2022 8:00 AM | March 23, 2022 5:00 PM | 0 | 3528 | 10h | 02.02.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3530 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 24, 2022 8:00 AM | April 6, 2022 5:00 PM | 0 | 3529 | 10h | 02.02.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3531 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 7, 2022 8:00 AM | April 13, 2022 5:00 PM | 0 | 3530 | 5h | 02.02.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3532 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | April 13, 2022 5:00 PM | April 13, 2022 5:00 PM | 0 | 3531,3525 | 0h | 02.02.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3533 |  | Auto Scheduled | מערכת ה-SAP תאפשר אישור ידני/אוטומטי לדרישה מותאם למבנה הארגוני החדש של המרה"ס - SAP | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3534 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3535 |  | Auto Scheduled | LifeCycle Tasks | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3536 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3537 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3538 |  | Manually Scheduled | יישום ופיתוח סאפ | 300 days | July 12, 2021 8:00 AM | September 2, 2022 5:00 PM | 0 | 3537 | 0h | 02.02.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3539 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 5, 2022 8:00 AM | October 7, 2022 5:00 PM | 0 | 3538 | 25h | 02.02.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3540 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 10, 2022 8:00 AM | October 21, 2022 5:00 PM | 0 | 3539 | 10h | 02.02.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3541 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 24, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 3540 | 10h | 02.02.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3542 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 0 | 3541 | 5h | 02.02.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3543 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 11, 2022 5:00 PM | November 11, 2022 5:00 PM | 0 | 3542,3536 | 0h | 02.02.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3544 |  | Auto Scheduled | מערכת הSAP תאפשר פיצול אספקות במרחבים שטרם מובצעו בשלב המבצוע ההדרגתי על ידי נקודות המשלוח החדשות והישנות. - SAP | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3545 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3546 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3547 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3548 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3549 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/01/2022 | 31/01/2022 | 0 | 3548 | 0h | 02.02.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3550 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3549 | 25h | 02.02.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3551 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3550 | 10h | 02.02.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3552 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3551 | 10h | 02.02.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3553 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3552 | 5h | 02.02.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3554 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3553,3547 | 0h | 02.02.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3555 |  | Auto Scheduled | מערכת ה-SAP תתמוך באפשרות של פתיחת דרישה, למולה תאפשר פתיחת הזמנה בצורה אוטומטית ו/או באישור ידני. - SAP | 344 days | May 18, 2021 8:00 AM | September 9, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3556 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3557 |  | Auto Scheduled | LifeCycle Tasks | 344 days | May 18, 2021 8:00 AM | September 9, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3558 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3559 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3560 |  | Manually Scheduled | יישום ופיתוח סאפ | 0 days | July 2, 2022 5:00 PM | July 2, 2022 5:00 PM | 0 | 3559 | 0h | 02.02.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3561 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 4, 2022 8:00 AM | August 5, 2022 5:00 PM | 0 | 3560 | 25h | 02.02.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3562 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 8, 2022 8:00 AM | August 19, 2022 5:00 PM | 0 | 3561 | 10h | 02.02.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3563 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 0 | 3562 | 10h | 02.02.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3564 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 5, 2022 8:00 AM | September 9, 2022 5:00 PM | 0 | 3563 | 5h | 02.02.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3565 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 9, 2022 5:00 PM | September 9, 2022 5:00 PM | 0 | 3564,3558 | 0h | 02.02.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3566 |  | Auto Scheduled | תינתן אפשרות לשליטה בהזמנות שישלחו לזכיין ע"י בעלי תפקידים שיוגדרו לכך - SAP | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3567 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3568 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3569 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3570 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3571 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 20/02/2022 | 30/03/2022 | 0 | 3570 | 0h | 02.02.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3572 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3571 | 25h | 02.02.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3573 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3572 | 10h | 02.02.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3574 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3573 | 10h | 02.02.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3575 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3574 | 5h | 02.02.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3576 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3575,3569 | 0h | 02.02.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3577 |  | Auto Scheduled | תינתן אפשרות לשינוי אתר אחסון מנפק בשלבי הדרישה וההזמנה מה שיאפשר שליטה בבחירת גורם מנפק – צבאי או זכיין. - SAP | 413 days | May 18, 2021 8:00 AM | December 15, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3578 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3579 |  | Auto Scheduled | LifeCycle Tasks | 413 days | May 18, 2021 8:00 AM | December 15, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3580 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3581 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3582 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 3, 2022 8:00 AM | October 6, 2022 5:00 PM | 0 | 3581 | 0h | 02.02.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3583 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 7, 2022 8:00 AM | November 10, 2022 5:00 PM | 0 | 3582 | 25h | 02.02.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3584 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 11, 2022 8:00 AM | November 24, 2022 5:00 PM | 0 | 3583 | 10h | 02.02.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3585 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 25, 2022 8:00 AM | December 8, 2022 5:00 PM | 0 | 3584 | 10h | 02.02.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3586 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 9, 2022 8:00 AM | December 15, 2022 5:00 PM | 0 | 3585 | 5h | 02.02.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3587 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 15, 2022 5:00 PM | December 15, 2022 5:00 PM | 0 | 3586,3580 | 0h | 02.02.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3588 |  | Auto Scheduled | מערכת ה-SAP תאפשר פתיחת אספקה כנגד הזמנת STO ולמול האספקות הסופיות המתקבלות ממערכת הWMS. - SAP | 412 days | May 18, 2021 8:00 AM | December 14, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3589 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3590 |  | Auto Scheduled | LifeCycle Tasks | 412 days | May 18, 2021 8:00 AM | December 14, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3591 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3592 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3593 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 1, 2022 8:00 AM | October 5, 2022 5:00 PM | 0 | 3592 | 0h | 02.02.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3594 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 6, 2022 8:00 AM | November 9, 2022 5:00 PM | 0 | 3593 | 25h | 02.02.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3595 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 10, 2022 8:00 AM | November 23, 2022 5:00 PM | 0 | 3594 | 10h | 02.02.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3596 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 24, 2022 8:00 AM | December 7, 2022 5:00 PM | 0 | 3595 | 10h | 02.02.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3597 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 8, 2022 8:00 AM | December 14, 2022 5:00 PM | 0 | 3596 | 5h | 02.02.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3598 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 14, 2022 5:00 PM | December 14, 2022 5:00 PM | 0 | 3597,3591 | 0h | 02.02.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3599 |  | Auto Scheduled | מערכת ה – SAP תתמוך ביצירת סטאטוסים/חיוויים ברמת כותרת, לדוגמה: "הגיע ליחידה" ו"נופק" . - SAP | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3600 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3601 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3602 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3603 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3604 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 28/12/2021 | 17/01/2022 | 0 | 3603 | 0h | 02.02.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3605 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3604 | 25h | 02.02.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3606 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3605 | 10h | 02.02.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3607 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3606 | 10h | 02.02.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3608 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3607 | 5h | 02.02.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3609 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3608,3602 | 0h | 02.02.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3610 |  | Auto Scheduled | מערכת ה SAP תתמוך בהפקת טפסי שילוח - SAP | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.09 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3611 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.09.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3612 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.09.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3613 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.09.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3614 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.09.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3615 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 25/04/2022 | 16/05/2022 | 0 | 3614 | 0h | 02.02.SAP.09.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3616 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3615 | 25h | 02.02.SAP.09.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3617 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3616 | 10h | 02.02.SAP.09.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3618 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3617 | 10h | 02.02.SAP.09.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3619 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3618 | 5h | 02.02.SAP.09.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3620 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3619,3613 | 0h | 02.02.SAP.09.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3621 |  | Auto Scheduled | מערכת הSAP תאפשר שינוי אתר אחסון מקבל ליחידה שלא מקושרת אליה במערכת. - SAP | 455 days | May 18, 2021 8:00 AM | February 13, 2023 5:00 PM | 0 |  | 70h | 02.02.SAP.10 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3622 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3623 |  | Auto Scheduled | LifeCycle Tasks | 455 days | May 18, 2021 8:00 AM | February 13, 2023 5:00 PM | 0 |  | 70h | 02.02.SAP.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3624 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.10.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3625 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.10.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3626 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 1, 2022 8:00 AM | December 5, 2022 5:00 PM | 0 | 3625 | 0h | 02.02.SAP.10.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3627 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 6, 2022 8:00 AM | January 9, 2023 5:00 PM | 0 | 3626 | 25h | 02.02.SAP.10.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3628 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 10, 2023 8:00 AM | January 23, 2023 5:00 PM | 0 | 3627 | 10h | 02.02.SAP.10.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3629 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 24, 2023 8:00 AM | February 6, 2023 5:00 PM | 0 | 3628 | 10h | 02.02.SAP.10.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3630 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 7, 2023 8:00 AM | February 13, 2023 5:00 PM | 0 | 3629 | 5h | 02.02.SAP.10.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3631 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 13, 2023 5:00 PM | February 13, 2023 5:00 PM | 0 | 3630,3624 | 0h | 02.02.SAP.10.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3632 |  | Auto Scheduled | ההזמנה תנופק מהמרחב המנפק הראשון למרחב המנפק השני למחסן ההפצה. - SAP | 366 days | May 18, 2021 8:00 AM | October 11, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.11 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3633 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.11.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3634 |  | Auto Scheduled | LifeCycle Tasks | 366 days | May 18, 2021 8:00 AM | October 11, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.11.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3635 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.11.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3636 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.11.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3637 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 29, 2022 8:00 AM | August 2, 2022 5:00 PM | 0 | 3636 | 0h | 02.02.SAP.11.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3638 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 3, 2022 8:00 AM | September 6, 2022 5:00 PM | 0 | 3637 | 25h | 02.02.SAP.11.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3639 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 7, 2022 8:00 AM | September 20, 2022 5:00 PM | 0 | 3638 | 10h | 02.02.SAP.11.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3640 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 21, 2022 8:00 AM | October 4, 2022 5:00 PM | 0 | 3639 | 10h | 02.02.SAP.11.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3641 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 5, 2022 8:00 AM | October 11, 2022 5:00 PM | 0 | 3640 | 5h | 02.02.SAP.11.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3642 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 11, 2022 5:00 PM | October 11, 2022 5:00 PM | 0 | 3641,3635 | 0h | 02.02.SAP.11.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3643 |  | Auto Scheduled | מערכת הSAP תאפשר לציין בטופס השילוח כי נדרש להוביל את המשלוח למחסן ההפצה במרכז המקבל ולא ישירות ליחידה. - SAP | 390 days | May 18, 2021 8:00 AM | November 14, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.12 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3644 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.12.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3645 |  | Auto Scheduled | LifeCycle Tasks | 390 days | May 18, 2021 8:00 AM | November 14, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.12.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3646 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.12.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3647 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.12.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3648 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 2, 2022 8:00 AM | September 5, 2022 5:00 PM | 0 | 3647 | 0h | 02.02.SAP.12.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3649 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 6, 2022 8:00 AM | October 10, 2022 5:00 PM | 0 | 3648 | 25h | 02.02.SAP.12.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3650 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 11, 2022 8:00 AM | October 24, 2022 5:00 PM | 0 | 3649 | 10h | 02.02.SAP.12.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3651 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 25, 2022 8:00 AM | November 7, 2022 5:00 PM | 0 | 3650 | 10h | 02.02.SAP.12.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3652 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 8, 2022 8:00 AM | November 14, 2022 5:00 PM | 0 | 3651 | 5h | 02.02.SAP.12.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3653 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 14, 2022 5:00 PM | November 14, 2022 5:00 PM | 0 | 3652,3646 | 0h | 02.02.SAP.12.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3654 |  | Auto Scheduled | מערכת הSAP תתמוך ביצירת משלוח על סמך האספקה המקורית. - SAP | 368 days | May 18, 2021 8:00 AM | October 13, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.13 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3655 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.13.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3656 |  | Auto Scheduled | LifeCycle Tasks | 368 days | May 18, 2021 8:00 AM | October 13, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.13.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3657 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.13.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3658 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.13.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3659 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 2, 2022 8:00 AM | August 4, 2022 5:00 PM | 0 | 3658 | 0h | 02.02.SAP.13.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3660 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 5, 2022 8:00 AM | September 8, 2022 5:00 PM | 0 | 3659 | 25h | 02.02.SAP.13.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3661 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 9, 2022 8:00 AM | September 22, 2022 5:00 PM | 0 | 3660 | 10h | 02.02.SAP.13.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3662 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 23, 2022 8:00 AM | October 6, 2022 5:00 PM | 0 | 3661 | 10h | 02.02.SAP.13.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3663 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 7, 2022 8:00 AM | October 13, 2022 5:00 PM | 0 | 3662 | 5h | 02.02.SAP.13.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3664 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 13, 2022 5:00 PM | October 13, 2022 5:00 PM | 0 | 3663,3657 | 0h | 02.02.SAP.13.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3665 |  | Auto Scheduled | ניפוק מהמרחב השני ליחידה - SAP | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.14 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3666 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3667 |  | Auto Scheduled | LifeCycle Tasks | 218 days | May 18, 2021 8:00 AM | March 17, 2022 5:00 PM | 0 |  | 70h | 02.02.SAP.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3668 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.14.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3669 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.14.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3670 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 16/02/2022 | 23/02/2022 | 0 | 3669 | 0h | 02.02.SAP.14.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3671 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3670 | 25h | 02.02.SAP.14.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3672 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3671 | 10h | 02.02.SAP.14.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3673 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3672 | 10h | 02.02.SAP.14.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3674 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3673 | 5h | 02.02.SAP.14.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3675 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3674,3668 | 0h | 02.02.SAP.14.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3676 |  | Auto Scheduled | נדרש להוסיף/לוודא בעת יצירת דרישה לניפוק לגורם חוץ קיום שדה חובה למילוי מספר הספק המקבל - SAP | 434 days | May 18, 2021 8:00 AM | January 13, 2023 5:00 PM | 0 |  | 70h | 02.02.SAP.15 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3677 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3678 |  | Auto Scheduled | LifeCycle Tasks | 434 days | May 18, 2021 8:00 AM | January 13, 2023 5:00 PM | 0 |  | 70h | 02.02.SAP.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3679 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.02.SAP.15.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3680 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | February 18, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 5398 | 20h | 02.02.SAP.15.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3681 |  | Manually Scheduled | יישום ופיתוח סאפ | 177 days | March 5, 2022 8:00 AM | November 5, 2022 5:00 PM | 0 | 3680 | 0h | 02.02.SAP.15.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3682 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 7, 2022 8:00 AM | December 9, 2022 5:00 PM | 0 | 3681 | 25h | 02.02.SAP.15.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3683 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 12, 2022 8:00 AM | December 23, 2022 5:00 PM | 0 | 3682 | 10h | 02.02.SAP.15.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3684 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 26, 2022 8:00 AM | January 6, 2023 5:00 PM | 0 | 3683 | 10h | 02.02.SAP.15.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3685 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 9, 2023 8:00 AM | January 13, 2023 5:00 PM | 0 | 3684 | 5h | 02.02.SAP.15.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3686 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 13, 2023 5:00 PM | January 13, 2023 5:00 PM | 0 | 3685,3679 | 0h | 02.02.SAP.15.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3687 |  | Auto Scheduled | 02.04: ויסות פנים ובין מרחבים | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 159h | 02.04 | חתום | אבי פרישמן | hd | מוריה |  | BP | NA | As Soon As Possible | 3
3688 |  | Auto Scheduled | 02.04: ויסות פנים ובין מרחבים.BP | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 159h | 02.04.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3689 |  | Auto Scheduled | 02.04: ויסות פנים ובין מרחבים - BP | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 159h | 02.04.BP.01 | חתום | אבי פרישמן | parent | מוריה |  | BP | NA | As Soon As Possible | 5
3690 |  | Auto Scheduled | Sub Tasks | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 119h | 02.04.BP.01.01 |  | אבי פרישמן | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3691 |  | Auto Scheduled | תגובות שונות | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.04.BP.01.01.10 | בוצע | ואל | MoM | ואל | תקווה רובינצ'יק | BP | NA | Must Start On | 7
3692 |  | Auto Scheduled | כתיבת מסמך | 6 days | May 18, 2021 8:00 AM | May 25, 2021 5:00 PM | 0 |  | 6h | 02.04.BP.01.01.30 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
3693 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 23 days | May 26, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 3692 | 23h | 02.04.BP.01.01.31 | בוצע | מוריה | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
3694 |  | Auto Scheduled | אישור מקל"ר | 14 days | June 28, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 3693 | 14h | 02.04.BP.01.01.32 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
3695 |  | Auto Scheduled | אישור אבי | 19 days | July 16, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 3694 | 19h | 02.04.BP.01.01.33 | בוצע | אבי | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
3696 |  | Auto Scheduled | אישור המנהלת | 44 days | August 12, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 3695 | 3h | 02.04.BP.01.01.34 | בוצע | סיגל | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
3697 |  | Auto Scheduled | אישור מפקדת | 3 days | October 13, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 3696 | 3h | 02.04.BP.01.01.35 | בוצע | מוריה | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
3698 |  | Auto Scheduled | אישור חטלו"ג | 5 days | October 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 3697 | 5h | 02.04.BP.01.01.36 | בוצע |  | MoM |  | 2020-10-21 00:00:00 | BP | NA | As Soon As Possible | 7
3699 |  | Auto Scheduled | אישור שגיב שרביט | 33 days | October 25, 2021 8:00 AM | December 8, 2021 5:00 PM | 0 | 3698 | 33h | 02.04.BP.01.01.37 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
3700 |  | Auto Scheduled | אישור ניר בשן | 8 days | December 9, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 | 3699 | 8h | 02.04.BP.01.01.38 | בוצע | ואל | MoM | ואל | תע - מוריה | BP | NA | As Soon As Possible | 7
3701 |  | Auto Scheduled | LifeCycle Tasks | 155 days | May 18, 2021 8:00 AM | December 20, 2021 5:00 PM | 0 |  | 40h | 02.04.BP.01.02 |  | אבי פרישמן | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3702 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 20, 2021 5:00 PM | December 20, 2021 5:00 PM | 0 | 3700 | 0h | 02.04.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3703 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.04.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3704 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 3703 | 10h | 02.04.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3705 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3704 | 5h | 02.04.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3706 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3705 | 10h | 02.04.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3707 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3706 | 10h | 02.04.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3708 |  | Auto Scheduled | בחתימה | 0 days | December 20, 2021 5:00 PM | December 20, 2021 5:00 PM | 0 | 3707,3702 | 0h | 02.04.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3709 |  | Auto Scheduled | חתום | 0 days | December 20, 2021 5:00 PM | December 20, 2021 5:00 PM | 0 | 3708 | 0h | 02.04.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3710 |  | Auto Scheduled | 02.06: החזרות מיחידות | 249 days | December 7, 2020 8:00 AM | November 18, 2021 5:00 PM | 0.02 |  | 707h | 02.06 | ממתין לאישור | אבי פרישמן | hd | רועי |  | BP | NA | As Soon As Possible | 3
3711 |  | Auto Scheduled | 02.06: החזרות מיחידות.BP | 117 days | May 18, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 |  | 157h | 02.06.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3712 |  | Auto Scheduled | 02.06: החזרות מיחידות - BP | 117 days | May 18, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 |  | 157h | 02.06.BP.01 | ממתין לאישור | אבי פרישמן | parent | רועי |  | BP | NA | As Soon As Possible | 5
3713 |  | Auto Scheduled | Sub Tasks | 117 days | May 18, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 |  | 117h | 02.06.BP.01.01 |  | אבי פרישמן | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3714 |  | Auto Scheduled | כתיבת מסמך | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | 02.06.BP.01.01.30 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | Must Start On | 7
3715 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 7 days | June 16, 2021 8:00 AM | June 24, 2021 5:00 PM | 0 | 3714 | 7h | 02.06.BP.01.01.31 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3716 |  | Auto Scheduled | אישור המנהלת | 16 days | June 25, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 3715 | 16h | 02.06.BP.01.01.32 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3717 |  | Auto Scheduled | אישור מפקדת | 4 days | July 19, 2021 8:00 AM | July 22, 2021 5:00 PM | 0 | 3716 | 4h | 02.06.BP.01.01.33 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3718 |  | Auto Scheduled | אישור אבי | 7 days | July 23, 2021 8:00 AM | August 2, 2021 5:00 PM | 0 | 3717 | 7h | 02.06.BP.01.01.34 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3719 |  | Auto Scheduled | אישור מקל"ר | 1 day | August 3, 2021 8:00 AM | August 3, 2021 5:00 PM | 0 | 3718 | 1h | 02.06.BP.01.01.35 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3720 |  | Auto Scheduled | אישור חטלו"ג | 17 days | August 4, 2021 8:00 AM | August 26, 2021 5:00 PM | 0 | 3719 | 17h | 02.06.BP.01.01.36 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
3721 |  | Auto Scheduled | אישור שגיב שרביט | 4 days | August 27, 2021 8:00 AM | September 1, 2021 5:00 PM | 0 | 3720 | 4h | 02.06.BP.01.01.37 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3722 |  | Auto Scheduled | אישור ניר בשן | 40 days | September 2, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 | 3721 | 40h | 02.06.BP.01.01.38 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3723 |  | Auto Scheduled | LifeCycle Tasks | 117 days | May 18, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 |  | 40h | 02.06.BP.01.02 |  | אבי פרישמן | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3724 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | October 27, 2021 5:00 PM | October 27, 2021 5:00 PM | 0 | 3722 | 0h | 02.06.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3725 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.06.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3726 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 3725 | 10h | 02.06.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3727 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3726 | 5h | 02.06.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3728 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3727 | 10h | 02.06.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3729 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3728 | 10h | 02.06.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3730 |  | Auto Scheduled | בחתימה | 0 days | October 27, 2021 5:00 PM | October 27, 2021 5:00 PM | 0 | 3729,3724 | 0h | 02.06.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3731 |  | Auto Scheduled | חתום | 0 days | October 27, 2021 5:00 PM | October 27, 2021 5:00 PM | 0 | 3730 | 0h | 02.06.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3732 |  | Auto Scheduled | 02.06: החזרות מיחידות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 60h | 02.06.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3733 |  | Auto Scheduled | יש לגבש איפיון חוקת טבלת ההחלטה לקביעת אתר אחסון בתהליך ההחזרה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.06.GEN.02 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3734 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.GEN.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3735 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.06.GEN.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3736 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.GEN.02.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3737 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3736 | 10h | 02.06.GEN.02.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3738 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3737 | 20h | 02.06.GEN.02.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3739 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3738,3736 | 0h | 02.06.GEN.02.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3740 |  | Auto Scheduled | יש לבחון חוקה במשק השמנים כך שבמידה והמלאי המוחזר בתוקף חצי שנה טרם פגותו ובמעמד סדיר מתבצע זיכוי תקציבי בפריט התחייבות שמנים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.06.GEN.03 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
3741 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3742 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.06.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3743 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3744 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 3743 | 10h | 02.06.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3745 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3744 | 20h | 02.06.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3746 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 3745,3743 | 0h | 02.06.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
3747 |  | Auto Scheduled | 02.06: החזרות מיחידות.INT | 203 days | February 8, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 |  | 140h | 02.06.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3748 |  | Auto Scheduled | מערכת ה-SAP תשדר למערכת ה-WMS את הזמנת ההחזרה - INT | 153 days | February 8, 2021 5:00 PM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3749 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3750 |  | Auto Scheduled | LifeCycle Tasks | 153 days | February 8, 2021 5:00 PM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3751 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3752 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3753 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 0 days | February 8, 2021 5:00 PM | February 8, 2021 5:00 PM | 0 | 3752 | 0h | 02.06.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3754 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 9, 2021 8:00 AM | March 15, 2021 5:00 PM | 0 | 3753 | 25h | 02.06.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3755 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 16, 2021 8:00 AM | March 29, 2021 5:00 PM | 0 | 3754 | 10h | 02.06.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3756 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 30, 2021 8:00 AM | April 12, 2021 5:00 PM | 0 | 3755 | 10h | 02.06.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3757 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 13, 2021 8:00 AM | April 19, 2021 5:00 PM | 0 | 3756 | 5h | 02.06.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3758 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 3757,3751 | 0h | 02.06.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3759 |  | Auto Scheduled | מערכת ה-SAP תאפשר לבצע העברה של המלאי למערכת ה- WMS לטובת ניהול אחסנת הפריטים. תתאפשר ההעברה לכל מחסן מנוהל WMS. בצורה פשוטה ללא כל שלבי שרשרת האספקה. - INT | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 02.06.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3760 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3761 |  | Auto Scheduled | LifeCycle Tasks | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 02.06.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3762 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3763 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3764 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 6, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 3763 | 0h | 02.06.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3765 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3764 | 25h | 02.06.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3766 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 3765 | 10h | 02.06.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3767 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 3766 | 10h | 02.06.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3768 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 3767 | 5h | 02.06.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3769 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 3768,3762 | 0h | 02.06.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3770 |  | Auto Scheduled | 02.06: החזרות מיחידות.SAP | 199 days | December 7, 2020 8:00 AM | September 9, 2021 5:00 PM | 2.9999999999999999E-2 |  | 350h | 02.06.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3771 |  | Auto Scheduled | מערכת SAP תאפשר לפתוח דרישת החזרה למרה"ס - SAP | 155 days | February 5, 2021 8:00 AM | September 9, 2021 5:00 PM | 0.11 |  | 70h | 02.06.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3772 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3773 |  | Auto Scheduled | LifeCycle Tasks | 155 days | February 5, 2021 8:00 AM | September 9, 2021 5:00 PM | 0.11 |  | 70h | 02.06.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3774 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3775 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3776 |  | Manually Scheduled | יישום ופיתוח סאפ | 66 days | February 5, 2021 8:00 AM | May 7, 2021 5:00 PM | 0.22 | 3775 | 0h | 02.06.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3777 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 3776 | 25h | 02.06.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3778 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 14, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 3777 | 10h | 02.06.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3779 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 28, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 3778 | 10h | 02.06.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3780 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 12, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 3779 | 5h | 02.06.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3781 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 16, 2021 5:00 PM | July 16, 2021 5:00 PM | 0 | 3780,3774 | 0h | 02.06.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3782 |  | Auto Scheduled | מערכת SAP תאפשר לנהל חוקת החזרות למרה"ס על פי טבלת BRF - SAP | 158 days | February 2, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3783 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3784 |  | Auto Scheduled | LifeCycle Tasks | 158 days | February 2, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3785 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3786 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3787 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | February 2, 2021 8:00 AM | March 6, 2021 5:00 PM | 0 | 3786 | 0h | 02.06.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3788 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 8, 2021 8:00 AM | April 9, 2021 5:00 PM | 0 | 3787 | 25h | 02.06.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3789 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 12, 2021 8:00 AM | April 23, 2021 5:00 PM | 0 | 3788 | 10h | 02.06.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3790 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 26, 2021 8:00 AM | May 7, 2021 5:00 PM | 0 | 3789 | 10h | 02.06.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3791 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 10, 2021 8:00 AM | May 14, 2021 5:00 PM | 0 | 3790 | 5h | 02.06.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3792 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 3791,3785 | 0h | 02.06.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3793 |  | Auto Scheduled | מערכת SAP תאפשר לסמן החזרה בדחיפה או במשיכה - SAP | 134 days | March 6, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3794 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3795 |  | Auto Scheduled | LifeCycle Tasks | 134 days | March 6, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3796 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3797 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3798 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 6, 2021 8:00 AM | April 8, 2021 5:00 PM | 0 | 3797 | 0h | 02.06.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3799 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 9, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 3798 | 25h | 02.06.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3800 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 14, 2021 8:00 AM | May 27, 2021 5:00 PM | 0 | 3799 | 10h | 02.06.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3801 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 28, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 3800 | 10h | 02.06.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3802 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 11, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 3801 | 5h | 02.06.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3803 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 17, 2021 5:00 PM | June 17, 2021 5:00 PM | 0 | 3802,3796 | 0h | 02.06.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3804 |  | Auto Scheduled | נדרש להוסיף בעת יצירת דרישת ההחזרה מגורם חוץ שדה חובה למילוי מספר הספק המקבל - SAP | 83 days | May 18, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3805 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3806 |  | Auto Scheduled | LifeCycle Tasks | 83 days | May 18, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3807 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3808 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3809 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 19/07/2021 | 26/07/2021 | 0 | 3808 | 0h | 02.06.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3810 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3809 | 25h | 02.06.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3811 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3810 | 10h | 02.06.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3812 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3811 | 10h | 02.06.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3813 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3812 | 5h | 02.06.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3814 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3813,3807 | 0h | 02.06.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3815 |  | Auto Scheduled | יש ליצור סיבת דרישת החזרה ייעודית - החזרה מתיקון גורמי חוץ. - SAP | 199 days | December 7, 2020 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3816 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3817 |  | Auto Scheduled | LifeCycle Tasks | 199 days | December 7, 2020 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 70h | 02.06.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3818 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.06.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3819 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | August 13, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 5898 | 20h | 02.06.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3820 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | December 7, 2020 8:00 AM | January 8, 2021 5:00 PM | 0 | 3819 | 0h | 02.06.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3821 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 11, 2021 8:00 AM | February 12, 2021 5:00 PM | 0 | 3820 | 25h | 02.06.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3822 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 15, 2021 8:00 AM | February 26, 2021 5:00 PM | 0 | 3821 | 10h | 02.06.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3823 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 1, 2021 8:00 AM | March 12, 2021 5:00 PM | 0 | 3822 | 10h | 02.06.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3824 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 15, 2021 8:00 AM | March 19, 2021 5:00 PM | 0 | 3823 | 5h | 02.06.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3825 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 3824,3818 | 0h | 02.06.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3826 |  | Auto Scheduled | 02.08: מכירות | 359 days | October 8, 2020 8:00 AM | February 22, 2022 5:00 PM | 0 |  | 1,153h | 02.08 | ממתין לאישור | תהילה | hd | רועי |  | BP | NA | As Soon As Possible | 3
3827 |  | Auto Scheduled | 02.08: מכירות.BP | 287 days | October 8, 2020 8:00 AM | November 12, 2021 5:00 PM | 0 |  | 173h | 02.08.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3828 |  | Auto Scheduled | 02.08: מכירות - BP | 287 days | October 8, 2020 8:00 AM | November 12, 2021 5:00 PM | 0 |  | 173h | 02.08.BP.01 | ממתין לאישור | תהילה | parent | רועי |  | BP | NA | As Soon As Possible | 5
3829 |  | Auto Scheduled | Sub Tasks | 287 days | October 8, 2020 8:00 AM | November 12, 2021 5:00 PM | 0 |  | 133h | 02.08.BP.01.01 |  | תהילה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3830 |  | Auto Scheduled | ע"פ תהילה יצחק, עדיין התהליך האושי לא סגור ולכן כרגע מקפיאים את ההתקדמות. יש לספק לו"ז | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.08.BP.01.01.10 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | Must Start On | 7
3831 |  | Auto Scheduled | ע"פ מסמכי המרכז קיים מחסן מכירות אחד בדרום. ע"פ המשתמשים נדרש מתחם מכירות בכל מרחב | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 02.08.BP.01.01.11 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
3832 |  | Auto Scheduled | תהילה: -BP מחולק לשלושה תתי תהליכים שונים. השבוע סוכם עקרונית עם אבי על מבנה הארגוני של מתחמי המכירות בנוסף נסגרו מספר סוגיות אושיות משמעותיות. ועכשיו ניתן לזמן את הדיונים הבאים בנושא. יתואם שבוע הבא גם למול משהב"ט. | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 02.08.BP.01.01.12 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
3833 |  | Auto Scheduled | מה עלה מהדיונים? | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 02.08.BP.01.01.13 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | As Soon As Possible | 7
3834 |  | Auto Scheduled | כתיבת מסמך | 46 days | May 18, 2021 8:00 AM | July 20, 2021 5:00 PM | 0 |  | 46h | 02.08.BP.01.01.30 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3835 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 9 days | July 21, 2021 8:00 AM | August 2, 2021 5:00 PM | 0 | 3834 | 9h | 02.08.BP.01.01.31 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3836 |  | Auto Scheduled | אישור המנהלת | 4 days | August 3, 2021 8:00 AM | August 6, 2021 5:00 PM | 0 | 3835 | 4h | 02.08.BP.01.01.32 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3837 |  | Auto Scheduled | אישור מקל"ר | 7 days | August 9, 2021 8:00 AM | August 17, 2021 5:00 PM | 0 | 3836 | 7h | 02.08.BP.01.01.33 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3838 |  | Auto Scheduled | אישור מפקדת | 10 days | August 18, 2021 8:00 AM | August 31, 2021 5:00 PM | 0 | 3837 | 10h | 02.08.BP.01.01.34 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3839 |  | Auto Scheduled | אישור אבי | 4 days | September 1, 2021 8:00 AM | September 6, 2021 5:00 PM | 0 | 3838 | 4h | 02.08.BP.01.01.35 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3840 |  | Auto Scheduled | אישור חטלו"ג | 5 days | September 7, 2021 8:00 AM | September 13, 2021 5:00 PM | 0 | 3839 | 5h | 02.08.BP.01.01.36 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3841 |  | Auto Scheduled | אישור שגיב שרביט | 4 days | September 14, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 3840 | 4h | 02.08.BP.01.01.37 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3842 |  | Auto Scheduled | אישור ניר בשן | 40 days | September 20, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 3841 | 40h | 02.08.BP.01.01.38 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
3843 |  | Auto Scheduled | LifeCycle Tasks | 129 days | May 18, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 |  | 40h | 02.08.BP.01.02 |  | תהילה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3844 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 3842 | 0h | 02.08.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3845 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.08.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3846 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 3845 | 10h | 02.08.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3847 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 3846 | 5h | 02.08.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3848 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 3847 | 10h | 02.08.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3849 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 3848 | 10h | 02.08.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3850 |  | Auto Scheduled | בחתימה | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 3849,3844 | 0h | 02.08.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3851 |  | Auto Scheduled | חתום | 0 days | November 12, 2021 5:00 PM | November 12, 2021 5:00 PM | 0 | 3850 | 0h | 02.08.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
3852 |  | Auto Scheduled | 02.08: מכירות.INT | 227 days | March 11, 2021 8:00 AM | January 21, 2022 5:00 PM | 0 |  | 490h | 02.08.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3853 |  | Auto Scheduled | מערכת SAP תאפשר לשדר למערכת WMS את האספקה - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3854 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3855 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3856 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3857 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3858 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 14/09/2021 | 17/10/2021 | 0 | 3857 | 0h | 02.08.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3859 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3858 | 25h | 02.08.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3860 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3859 | 10h | 02.08.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3861 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3860 | 10h | 02.08.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3862 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3861 | 5h | 02.08.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3863 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3862,3856 | 0h | 02.08.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3864 |  | Auto Scheduled | מערכת WMS תאפשר עדכון מערכת SAP על כך שהאספקה נופקה - INT | 75 days | May 10, 2021 8:00 AM | August 20, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3865 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3866 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 10, 2021 8:00 AM | August 20, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3867 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3868 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3869 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 3868 | 0h | 02.08.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3870 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 14, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 3869 | 25h | 02.08.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3871 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 19, 2021 8:00 AM | July 30, 2021 5:00 PM | 0 | 3870 | 10h | 02.08.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3872 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 2, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 3871 | 10h | 02.08.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3873 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 16, 2021 8:00 AM | August 20, 2021 5:00 PM | 0 | 3872 | 5h | 02.08.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3874 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 20, 2021 5:00 PM | August 20, 2021 5:00 PM | 0 | 3873,3867 | 0h | 02.08.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3875 |  | Auto Scheduled | מערכת SAP תאפשר בדיקת מלאי בשיקוף ממערכת WMS - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3876 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3877 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3878 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3879 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3880 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 25/10/2021 | 28/10/2021 | 0 | 3879 | 0h | 02.08.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3881 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3880 | 25h | 02.08.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3882 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3881 | 10h | 02.08.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3883 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3882 | 10h | 02.08.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3884 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3883 | 5h | 02.08.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3885 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3884,3878 | 0h | 02.08.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3886 |  | Auto Scheduled | מערכת SAP תאפשר לשדר למערכת WMS את האספקה - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3887 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3888 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3889 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3890 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3891 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 27/10/2021 | 14/11/2021 | 0 | 3890 | 0h | 02.08.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3892 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3891 | 25h | 02.08.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3893 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3892 | 10h | 02.08.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3894 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3893 | 10h | 02.08.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3895 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3894 | 5h | 02.08.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3896 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3895,3889 | 0h | 02.08.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3897 |  | Auto Scheduled | מערכת WMS תאפשר עדכון מערכת SAP על כך שהאספקה נופקה - INT | 110 days | March 11, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3898 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3899 |  | Auto Scheduled | LifeCycle Tasks | 110 days | March 11, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3900 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3901 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3902 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | March 11, 2021 8:00 AM | April 14, 2021 5:00 PM | 0 | 3901 | 0h | 02.08.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3903 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 15, 2021 8:00 AM | May 19, 2021 5:00 PM | 0 | 3902 | 25h | 02.08.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3904 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 20, 2021 8:00 AM | June 2, 2021 5:00 PM | 0 | 3903 | 10h | 02.08.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3905 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 3, 2021 8:00 AM | June 16, 2021 5:00 PM | 0 | 3904 | 10h | 02.08.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3906 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 17, 2021 8:00 AM | June 23, 2021 5:00 PM | 0 | 3905 | 5h | 02.08.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3907 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | June 23, 2021 5:00 PM | June 23, 2021 5:00 PM | 0 | 3906,3900 | 0h | 02.08.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3908 |  | Auto Scheduled | מערכת SAP תאפשר בדיקת מלאי בשיקוף ממערכת WMS - INT | 179 days | May 18, 2021 8:00 AM | January 21, 2022 5:00 PM | 0 |  | 70h | 02.08.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3909 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3910 |  | Auto Scheduled | LifeCycle Tasks | 179 days | May 18, 2021 8:00 AM | January 21, 2022 5:00 PM | 0 |  | 70h | 02.08.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3911 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3912 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3913 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | October 11, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 3912 | 0h | 02.08.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3914 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 15, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 | 3913 | 25h | 02.08.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3915 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 20, 2021 8:00 AM | December 31, 2021 5:00 PM | 0 | 3914 | 10h | 02.08.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3916 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 3, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 3915 | 10h | 02.08.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3917 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 17, 2022 8:00 AM | January 21, 2022 5:00 PM | 0 | 3916 | 5h | 02.08.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3918 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 21, 2022 5:00 PM | January 21, 2022 5:00 PM | 0 | 3917,3911 | 0h | 02.08.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3919 |  | Auto Scheduled | מערכת SAP תאפשר לשדר למערכת WMS את האספקה - INT | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
3920 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3921 |  | Auto Scheduled | LifeCycle Tasks | 113 days | May 18, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 |  | 70h | 02.08.INT.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3922 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.INT.07.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3923 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.INT.07.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3924 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 0 days | August 12, 2021 5:00 PM | August 12, 2021 5:00 PM | 0 | 3923 | 0h | 02.08.INT.07.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3925 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 13, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 3924 | 25h | 02.08.INT.07.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3926 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 17, 2021 8:00 AM | September 30, 2021 5:00 PM | 0 | 3925 | 10h | 02.08.INT.07.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3927 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 1, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3926 | 10h | 02.08.INT.07.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3928 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 15, 2021 8:00 AM | October 21, 2021 5:00 PM | 0 | 3927 | 5h | 02.08.INT.07.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3929 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 21, 2021 5:00 PM | October 21, 2021 5:00 PM | 0 | 3928,3922 | 0h | 02.08.INT.07.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
3930 |  | Auto Scheduled | 02.08: מכירות.SAP | 294 days | January 7, 2021 8:00 AM | February 22, 2022 5:00 PM | 0 |  | 490h | 02.08.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
3931 |  | Auto Scheduled | מערכת SAP תאפשר לפתוח בל"מ על סמך בל"מ ממשהב"ט - SAP | 155 days | January 7, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3932 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3933 |  | Auto Scheduled | LifeCycle Tasks | 155 days | January 7, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3934 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3935 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3936 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | January 7, 2021 8:00 AM | February 10, 2021 5:00 PM | 0 | 3935 | 0h | 02.08.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3937 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 11, 2021 8:00 AM | March 17, 2021 5:00 PM | 0 | 3936 | 25h | 02.08.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3938 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 18, 2021 8:00 AM | March 31, 2021 5:00 PM | 0 | 3937 | 10h | 02.08.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3939 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 1, 2021 8:00 AM | April 14, 2021 5:00 PM | 0 | 3938 | 10h | 02.08.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3940 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 15, 2021 8:00 AM | April 21, 2021 5:00 PM | 0 | 3939 | 5h | 02.08.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3941 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 3940,3934 | 0h | 02.08.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3942 |  | Auto Scheduled | מערכת SAP תאפשר שינוי סטאטוס הבל"מ - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3943 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3944 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3945 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3946 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3947 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 13/07/2021 | 28/07/2021 | 0 | 3946 | 0h | 02.08.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3948 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 3947 | 25h | 02.08.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3949 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 3948 | 10h | 02.08.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3950 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 3949 | 10h | 02.08.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3951 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 3950 | 5h | 02.08.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3952 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 3951,3945 | 0h | 02.08.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3953 |  | Auto Scheduled | מערכת SAP תאפשר עדכון אתר ואתר אחסון - SAP | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3954 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3955 |  | Auto Scheduled | LifeCycle Tasks | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3956 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3957 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3958 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 8, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 3957 | 0h | 02.08.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3959 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3958 | 25h | 02.08.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3960 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 3959 | 10h | 02.08.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3961 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 3960 | 10h | 02.08.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3962 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 3961 | 5h | 02.08.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3963 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 3962,3956 | 0h | 02.08.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3964 |  | Auto Scheduled | מערכת SAP תאפשר ליצור הזמנת מכירה מסוג ZOR לאחר אישור הבל"מ במערכת - SAP | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3965 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3966 |  | Auto Scheduled | LifeCycle Tasks | 133 days | May 18, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3967 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3968 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3969 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 6, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 3968 | 0h | 02.08.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3970 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 10, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 3969 | 25h | 02.08.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3971 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 15, 2021 8:00 AM | October 28, 2021 5:00 PM | 0 | 3970 | 10h | 02.08.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3972 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 29, 2021 8:00 AM | November 11, 2021 5:00 PM | 0 | 3971 | 10h | 02.08.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3973 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 12, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 3972 | 5h | 02.08.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3974 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 18, 2021 5:00 PM | November 18, 2021 5:00 PM | 0 | 3973,3967 | 0h | 02.08.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3975 |  | Auto Scheduled | מערכת SAP תאפשר ניהול נתוני לקוח לצורך תיאום אספקה - SAP | 89 days | May 18, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3976 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3977 |  | Auto Scheduled | LifeCycle Tasks | 89 days | May 18, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3978 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3979 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3980 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 8, 2021 8:00 AM | July 10, 2021 5:00 PM | 0 | 3979 | 0h | 02.08.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3981 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 12, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 3980 | 25h | 02.08.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3982 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 16, 2021 8:00 AM | August 27, 2021 5:00 PM | 0 | 3981 | 10h | 02.08.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3983 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 30, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 3982 | 10h | 02.08.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3984 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 3983 | 5h | 02.08.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3985 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 17, 2021 5:00 PM | September 17, 2021 5:00 PM | 0 | 3984,3978 | 0h | 02.08.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3986 |  | Auto Scheduled | מערכת SAP תאפשר פתיחת לוט על סמך מלאי - SAP | 201 days | May 18, 2021 8:00 AM | February 22, 2022 5:00 PM | 0 |  | 70h | 02.08.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3987 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3988 |  | Auto Scheduled | LifeCycle Tasks | 201 days | May 18, 2021 8:00 AM | February 22, 2022 5:00 PM | 0 |  | 70h | 02.08.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
3989 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3990 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3991 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | November 10, 2021 8:00 AM | December 14, 2021 5:00 PM | 0 | 3990 | 0h | 02.08.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3992 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 15, 2021 8:00 AM | January 18, 2022 5:00 PM | 0 | 3991 | 25h | 02.08.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3993 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 19, 2022 8:00 AM | February 1, 2022 5:00 PM | 0 | 3992 | 10h | 02.08.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3994 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 2, 2022 8:00 AM | February 15, 2022 5:00 PM | 0 | 3993 | 10h | 02.08.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3995 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 16, 2022 8:00 AM | February 22, 2022 5:00 PM | 0 | 3994 | 5h | 02.08.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3996 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 22, 2022 5:00 PM | February 22, 2022 5:00 PM | 0 | 3995,3989 | 0h | 02.08.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
3997 |  | Auto Scheduled | מערכת SAP תאפשר ניהול נתוני לקוח לצורך תיאום אספקה - SAP | 154 days | January 8, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
3998 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
3999 |  | Auto Scheduled | LifeCycle Tasks | 154 days | January 8, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 |  | 70h | 02.08.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4000 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.08.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4001 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6140 | 20h | 02.08.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4002 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | January 8, 2021 8:00 AM | February 11, 2021 5:00 PM | 0 | 4001 | 0h | 02.08.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4003 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 12, 2021 8:00 AM | March 18, 2021 5:00 PM | 0 | 4002 | 25h | 02.08.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4004 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 19, 2021 8:00 AM | April 1, 2021 5:00 PM | 0 | 4003 | 10h | 02.08.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4005 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 2, 2021 8:00 AM | April 15, 2021 5:00 PM | 0 | 4004 | 10h | 02.08.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4006 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 16, 2021 8:00 AM | April 22, 2021 5:00 PM | 0 | 4005 | 5h | 02.08.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4007 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 4006,4000 | 0h | 02.08.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4008 |  | Auto Scheduled | 02.11: החלפות | 332 days | October 8, 2020 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 653h | 02.11 | ממתין לאישור | רמ"ח תו"ב | hd | רועי |  | BP | NA | As Soon As Possible | 3
4009 |  | Auto Scheduled | 02.11: החלפות.BP | 280 days | October 8, 2020 8:00 AM | November 3, 2021 5:00 PM | 0 |  | 163h | 02.11.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4010 |  | Auto Scheduled | 02.11: החלפות - BP | 280 days | October 8, 2020 8:00 AM | November 3, 2021 5:00 PM | 0 |  | 163h | 02.11.BP.01 | ממתין לאישור | רמ"ח תו"ב | parent | רועי |  | BP | NA | As Soon As Possible | 5
4011 |  | Auto Scheduled | Sub Tasks | 280 days | October 8, 2020 8:00 AM | November 3, 2021 5:00 PM | 0 |  | 123h | 02.11.BP.01.01 |  | רמ"ח תו"ב | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4012 |  | Auto Scheduled | ממתינים להחלטות או"שיות ברמת חטלוג ומנהלת המרהס שלפיה תגזר תפיסת הפתרון. נפתח כמה פעמים ע"י משתמשים - מה הסטאטוס? | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.11.BP.01.01.10 | בוצע | תהילה | MoM | תהילה | מאיה | BP | NA | Must Start On | 7
4013 |  | Auto Scheduled | כתיבת מסמך | 26 days | May 18, 2021 8:00 AM | June 22, 2021 5:00 PM | 0 |  | 26h | 02.11.BP.01.01.30 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4014 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 14 days | June 23, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4013 | 14h | 02.11.BP.01.01.31 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4015 |  | Auto Scheduled | אישור המנהלת | 8 days | July 13, 2021 8:00 AM | July 22, 2021 5:00 PM | 0 | 4014 | 8h | 02.11.BP.01.01.32 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4016 |  | Auto Scheduled | אישור מפקדת | 2 days | July 23, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4015 | 2h | 02.11.BP.01.01.33 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4017 |  | Auto Scheduled | אישור אבי | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4016 | 10h | 02.11.BP.01.01.34 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4018 |  | Auto Scheduled | אישור מקל"ר | 1 day | August 10, 2021 8:00 AM | August 10, 2021 5:00 PM | 0 | 4017 | 1h | 02.11.BP.01.01.35 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4019 |  | Auto Scheduled | אישור חטלו"ג | 17 days | August 11, 2021 8:00 AM | September 2, 2021 5:00 PM | 0 | 4018 | 17h | 02.11.BP.01.01.36 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4020 |  | Auto Scheduled | אישור שגיב שרביט | 4 days | September 3, 2021 8:00 AM | September 8, 2021 5:00 PM | 0 | 4019 | 4h | 02.11.BP.01.01.37 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4021 |  | Auto Scheduled | אישור ניר בשן | 40 days | September 9, 2021 8:00 AM | November 3, 2021 5:00 PM | 0 | 4020 | 40h | 02.11.BP.01.01.38 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4022 |  | Auto Scheduled | LifeCycle Tasks | 122 days | May 18, 2021 8:00 AM | November 3, 2021 5:00 PM | 0 |  | 40h | 02.11.BP.01.02 |  | רמ"ח תו"ב | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4023 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | November 3, 2021 5:00 PM | November 3, 2021 5:00 PM | 0 | 4021 | 0h | 02.11.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4024 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.11.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4025 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4024 | 10h | 02.11.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4026 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4025 | 5h | 02.11.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4027 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4026 | 10h | 02.11.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4028 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4027 | 10h | 02.11.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4029 |  | Auto Scheduled | בחתימה | 0 days | November 3, 2021 5:00 PM | November 3, 2021 5:00 PM | 0 | 4028,4023 | 0h | 02.11.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4030 |  | Auto Scheduled | חתום | 0 days | November 3, 2021 5:00 PM | November 3, 2021 5:00 PM | 0 | 4029 | 0h | 02.11.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4031 |  | Auto Scheduled | 02.11: החלפות.INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.11.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4032 |  | Auto Scheduled | מערכת ה-SAP תאפשר לשדר את האספקה/אספקות למערכת ה-WMS - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.11.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4033 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4034 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.11.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4035 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4036 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4037 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 13/07/2021 | 20/07/2021 | 0 | 4036 | 0h | 02.11.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4038 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4037 | 25h | 02.11.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4039 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4038 | 10h | 02.11.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4040 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4039 | 10h | 02.11.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4041 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4040 | 5h | 02.11.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4042 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4041,4035 | 0h | 02.11.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4043 |  | Auto Scheduled | 02.11: החלפות.SAP | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 350h | 02.11.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4044 |  | Auto Scheduled | מערכת SAP תאפשר לפתוח דרישת ניפוק ZN01 מהמרה"ס מסוג החלפה - SAP | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 02.11.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4045 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4046 |  | Auto Scheduled | LifeCycle Tasks | 174 days | May 18, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 02.11.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4047 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4048 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4049 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | October 5, 2021 8:00 AM | November 7, 2021 5:00 PM | 0 | 4048 | 0h | 02.11.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4050 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 8, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 4049 | 25h | 02.11.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4051 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 13, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 4050 | 10h | 02.11.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4052 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 27, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 4051 | 10h | 02.11.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4053 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 10, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 4052 | 5h | 02.11.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4054 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 14, 2022 5:00 PM | January 14, 2022 5:00 PM | 0 | 4053,4047 | 0h | 02.11.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4055 |  | Auto Scheduled | מערכת SAP תאפשר לנהל חוקת ניפוק למרה"ס על פי טבלת החלטה - SAP | 109 days | May 18, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4056 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4057 |  | Auto Scheduled | LifeCycle Tasks | 109 days | May 18, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4058 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4059 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4060 |  | Manually Scheduled | יישום ופיתוח סאפ | 46 days | June 7, 2021 8:00 AM | August 7, 2021 5:00 PM | 0 | 4059 | 0h | 02.11.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4061 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 9, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 4060 | 25h | 02.11.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4062 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 13, 2021 8:00 AM | September 24, 2021 5:00 PM | 0 | 4061 | 10h | 02.11.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4063 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 27, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 4062 | 10h | 02.11.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4064 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 11, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 4063 | 5h | 02.11.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4065 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 15, 2021 5:00 PM | October 15, 2021 5:00 PM | 0 | 4064,4058 | 0h | 02.11.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4066 |  | Auto Scheduled | מערכת SAP תאפשר עריכת/מחיקה של הזמנת ניפוק מסוג z21 - SAP | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4067 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4068 |  | Auto Scheduled | LifeCycle Tasks | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4069 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4070 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4071 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 7, 2021 8:00 AM | August 10, 2021 5:00 PM | 0 | 4070 | 0h | 02.11.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4072 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 4071 | 25h | 02.11.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4073 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 15, 2021 8:00 AM | September 28, 2021 5:00 PM | 0 | 4072 | 10h | 02.11.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4074 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 29, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 4073 | 10h | 02.11.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4075 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 13, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 4074 | 5h | 02.11.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4076 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 19, 2021 5:00 PM | October 19, 2021 5:00 PM | 0 | 4075,4069 | 0h | 02.11.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4077 |  | Auto Scheduled | מערכת ה-SAP תאפשר לפתוח אספקה כנגד אספקה - SAP | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4078 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4079 |  | Auto Scheduled | LifeCycle Tasks | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4080 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4081 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4082 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 7, 2021 8:00 AM | August 10, 2021 5:00 PM | 0 | 4081 | 0h | 02.11.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4083 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 4082 | 25h | 02.11.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4084 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 15, 2021 8:00 AM | September 28, 2021 5:00 PM | 0 | 4083 | 10h | 02.11.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4085 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 29, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 4084 | 10h | 02.11.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4086 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 13, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 4085 | 5h | 02.11.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4087 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 19, 2021 5:00 PM | October 19, 2021 5:00 PM | 0 | 4086,4080 | 0h | 02.11.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4088 |  | Auto Scheduled | מערכת הSAP תאפשר לבצע קליטה של הזמנת ניפוק ההחלפה למלאי לאתר אחסון מיוחד המשוייך למרה"ס (ב-SAP שאינו מקושר ל-WMS ) - SAP | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4089 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4090 |  | Auto Scheduled | LifeCycle Tasks | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.11.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4091 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4092 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4093 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 7, 2021 8:00 AM | August 10, 2021 5:00 PM | 0 | 4092 | 0h | 02.11.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4094 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 4093 | 25h | 02.11.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4095 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 15, 2021 8:00 AM | September 28, 2021 5:00 PM | 0 | 4094 | 10h | 02.11.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4096 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 29, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 4095 | 10h | 02.11.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4097 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 13, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 4096 | 5h | 02.11.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4098 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 19, 2021 5:00 PM | October 19, 2021 5:00 PM | 0 | 4097,4091 | 0h | 02.11.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4099 |  | Auto Scheduled | 02.11: החלפות.WMS | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.11.WMS |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4100 |  | Auto Scheduled | מערכת ה-WMS תאפשר לשדר את ביצוע הניפוק ועדכון מלאים שנופקו להחלפה ל-SAP - WMS | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.11.WMS.01 | יישום ופיתוח מערכת ניהול מחסן - זכיין |  | parent |  | requirements | WMS | NA | As Soon As Possible | 5
4101 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.WMS.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4102 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.11.WMS.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4103 |  | Auto Scheduled | סיום משימת משנה למערכת ניהול מחסן - זכיין | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.11.WMS.01.02.01 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4104 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | July 15, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 6496 | 20h | 02.11.WMS.01.02.02 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4105 |  | Manually Scheduled | יישום ופיתוח מערכת ניהול מחסן - זכיין | 25 days | 15/07/2021 | 22/07/2021 | 0 | 4104 | 0h | 02.11.WMS.01.02.03 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4106 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4105 | 25h | 02.11.WMS.01.02.04 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4107 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4106 | 10h | 02.11.WMS.01.02.05 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4108 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4107 | 10h | 02.11.WMS.01.02.06 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4109 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4108 | 5h | 02.11.WMS.01.02.07 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4110 |  | Auto Scheduled | משימת WMS עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4109,4103 | 0h | 02.11.WMS.01.02.08 |  |  | rule |  |  | WMS | NA | As Soon As Possible | 7
4111 |  | Auto Scheduled | 02.12: תיקונים | 547 days | October 8, 2020 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 1,227h | 02.12 | סיכום מסמך | פריאל ישי | hd | פריאל |  | BP | NA | As Soon As Possible | 3
4112 |  | Auto Scheduled | 02.12: תיקונים.BP | 348 days | October 8, 2020 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 147h | 02.12.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4113 |  | Auto Scheduled | 02.12: תיקונים - BP | 348 days | October 8, 2020 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 147h | 02.12.BP.01 | סיכום מסמך | פריאל ישי | parent | פריאל |  | BP | NA | As Soon As Possible | 5
4114 |  | Auto Scheduled | Sub Tasks | 348 days | October 8, 2020 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 107h | 02.12.BP.01.01 |  | פריאל ישי | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4115 |  | Auto Scheduled | גדי מתנגד להפצת המסמך (סיכום דיון) עד שתתקיים ישיבה נוספת איתם - מה הסטאטוס? | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.12.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | Must Start On | 7
4116 |  | Auto Scheduled | כתיבת מסמך | 16 days | May 18, 2021 8:00 AM | June 8, 2021 5:00 PM | 0 |  | 16h | 02.12.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4117 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 110 days | June 9, 2021 8:00 AM | November 9, 2021 5:00 PM | 0 | 4116 | 26h | 02.12.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4118 |  | Auto Scheduled | אישור מקל"ר | 12 days | November 10, 2021 8:00 AM | November 25, 2021 5:00 PM | 0 | 4117 | 12h | 02.12.BP.01.01.32 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4119 |  | Auto Scheduled | אישור אבי | 8 days | November 26, 2021 8:00 AM | December 7, 2021 5:00 PM | 0 | 4118 | 8h | 02.12.BP.01.01.33 | בוצע | אבי | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4120 |  | Auto Scheduled | אישור מפקדת | 15 days | December 8, 2021 8:00 AM | December 28, 2021 5:00 PM | 0 | 4119 | 15h | 02.12.BP.01.01.34 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4121 |  | Auto Scheduled | אישור חטלו"ג | 2 days | December 29, 2021 8:00 AM | December 30, 2021 5:00 PM | 0 | 4120 | 2h | 02.12.BP.01.01.35 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4122 |  | Auto Scheduled | אישור שגיב שרביט | 3 days | December 31, 2021 8:00 AM | January 4, 2022 5:00 PM | 0 | 4121 | 3h | 02.12.BP.01.01.36 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4123 |  | Auto Scheduled | אישור המנהלת | 11 days | January 5, 2022 8:00 AM | January 19, 2022 5:00 PM | 0 | 4122 | 11h | 02.12.BP.01.01.37 | בוצע | סיגל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4124 |  | Auto Scheduled | אישור ניר בשן | 13 days | January 20, 2022 8:00 AM | February 7, 2022 5:00 PM | 0 | 4123 | 13h | 02.12.BP.01.01.38 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4125 |  | Auto Scheduled | LifeCycle Tasks | 190 days | May 18, 2021 8:00 AM | February 7, 2022 5:00 PM | 0 |  | 40h | 02.12.BP.01.02 |  | פריאל ישי | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4126 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | February 7, 2022 5:00 PM | February 7, 2022 5:00 PM | 0 | 4124 | 0h | 02.12.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4127 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.12.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4128 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4127 | 10h | 02.12.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4129 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4128 | 5h | 02.12.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4130 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4129 | 10h | 02.12.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4131 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4130 | 10h | 02.12.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4132 |  | Auto Scheduled | בחתימה | 0 days | February 7, 2022 5:00 PM | February 7, 2022 5:00 PM | 0 | 4131,4126 | 0h | 02.12.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4133 |  | Auto Scheduled | חתום | 0 days | February 7, 2022 5:00 PM | February 7, 2022 5:00 PM | 0 | 4132 | 0h | 02.12.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4134 |  | Auto Scheduled | 02.12: תיקונים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.12.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4135 |  | Auto Scheduled | מהו התהליך המוסדר של תיקון במחסני זכיין (כמו במכבסה) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.12.GEN.04 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4136 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4137 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.12.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4138 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4139 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4138 | 10h | 02.12.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4140 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4139 | 20h | 02.12.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4141 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4140,4138 | 0h | 02.12.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4142 |  | Auto Scheduled | 02.12: תיקונים.INT | 314 days | January 9, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 490h | 02.12.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4143 |  | Auto Scheduled | מערכת הSAP תאפשר שליחת הזמנות החזרה למערכת הWMS לטובת תכנון איסוף פריטים מהיחידה. - INT | 256 days | January 9, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4144 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4145 |  | Auto Scheduled | LifeCycle Tasks | 256 days | January 9, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4146 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4147 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4148 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 87 days | January 9, 2021 8:00 AM | May 10, 2021 5:00 PM | 0 | 4147 | 0h | 02.12.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4149 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 11, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4148 | 25h | 02.12.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4150 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4149 | 10h | 02.12.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4151 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4150 | 10h | 02.12.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4152 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 13, 2021 8:00 AM | July 19, 2021 5:00 PM | 0 | 4151 | 5h | 02.12.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4153 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | July 19, 2021 5:00 PM | July 19, 2021 5:00 PM | 0 | 4152,4146 | 0h | 02.12.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4154 |  | Auto Scheduled | מערכת הWMS תאפשר עדכון מערכת הSAP בנתוני האיסוף. - INT | 177 days | May 18, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4155 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4156 |  | Auto Scheduled | LifeCycle Tasks | 177 days | May 18, 2021 8:00 AM | January 19, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4157 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4158 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4159 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 45 days | September 9, 2021 8:00 AM | November 10, 2021 5:00 PM | 0 | 4158 | 0h | 02.12.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4160 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 11, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 4159 | 25h | 02.12.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4161 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 16, 2021 8:00 AM | December 29, 2021 5:00 PM | 0 | 4160 | 10h | 02.12.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4162 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 30, 2021 8:00 AM | January 12, 2022 5:00 PM | 0 | 4161 | 10h | 02.12.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4163 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 13, 2022 8:00 AM | January 19, 2022 5:00 PM | 0 | 4162 | 5h | 02.12.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4164 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | January 19, 2022 5:00 PM | January 19, 2022 5:00 PM | 0 | 4163,4157 | 0h | 02.12.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4165 |  | Auto Scheduled | מערכת ה SAP תאפשר שליחת שדר למסופון הPOD הכולל את הפריטים הנדרשים לאיסוף מהיחידה. - INT | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4166 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4167 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4168 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4169 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4170 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 19/09/2021 | 26/10/2021 | 0 | 4169 | 0h | 02.12.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4171 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4170 | 25h | 02.12.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4172 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4171 | 10h | 02.12.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4173 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4172 | 10h | 02.12.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4174 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4173 | 5h | 02.12.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4175 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4174,4168 | 0h | 02.12.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4176 |  | Auto Scheduled | מערכת הSAP תשלח שדר למערכת הWMS לטובת תכנון שינוע מטען מהמצ"מ לבימ"ל ולהיפך ללא קבלה למלאי באמצעות מערכת הYMS. - INT | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4177 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4178 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4179 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4180 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4181 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | July 8, 2021 8:00 AM | August 11, 2021 5:00 PM | 0 | 4180 | 0h | 02.12.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4182 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 12, 2021 8:00 AM | September 15, 2021 5:00 PM | 0 | 4181 | 25h | 02.12.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4183 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 16, 2021 8:00 AM | September 29, 2021 5:00 PM | 0 | 4182 | 10h | 02.12.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4184 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 30, 2021 8:00 AM | October 13, 2021 5:00 PM | 0 | 4183 | 10h | 02.12.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4185 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 14, 2021 8:00 AM | October 20, 2021 5:00 PM | 0 | 4184 | 5h | 02.12.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4186 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 20, 2021 5:00 PM | October 20, 2021 5:00 PM | 0 | 4185,4179 | 0h | 02.12.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4187 |  | Auto Scheduled | מערכת ה- WMS תשלח (בממשק אוטומטי) למערכת ה-SAP את השדר לשינוע כולל נתוני התכולה המתוכננים ומועד אספקה מתוכנן. נתונים אלו יעדכנו את האספקה במערכת הSAP. הנתונים יכללו, מספר הזמנה (כולל שורה), לקוח, משאית, פריטים, כמויות, אמצעי אריזה, נתוני מסלול וכו'. - | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4188 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4189 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4190 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4191 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4192 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 4191 | 0h | 02.12.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4193 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 15, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 4192 | 25h | 02.12.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4194 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 20, 2021 8:00 AM | November 2, 2021 5:00 PM | 0 | 4193 | 10h | 02.12.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4195 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 3, 2021 8:00 AM | November 16, 2021 5:00 PM | 0 | 4194 | 10h | 02.12.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4196 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 17, 2021 8:00 AM | November 23, 2021 5:00 PM | 0 | 4195 | 5h | 02.12.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4197 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | November 23, 2021 5:00 PM | November 23, 2021 5:00 PM | 0 | 4196,4190 | 0h | 02.12.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4198 |  | Auto Scheduled | מערכת הSAP תתמוך בהעברת הזמנת החוב Z25M לזכיין לטובת תכנון הפצת הפריט מהבימ"ל ליחידה - INT | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4199 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4200 |  | Auto Scheduled | LifeCycle Tasks | 199 days | May 18, 2021 8:00 AM | February 18, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4201 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4202 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4203 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | November 9, 2021 8:00 AM | December 12, 2021 5:00 PM | 0 | 4202 | 0h | 02.12.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4204 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 13, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 4203 | 25h | 02.12.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4205 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 17, 2022 8:00 AM | January 28, 2022 5:00 PM | 0 | 4204 | 10h | 02.12.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4206 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 31, 2022 8:00 AM | February 11, 2022 5:00 PM | 0 | 4205 | 10h | 02.12.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4207 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 14, 2022 8:00 AM | February 18, 2022 5:00 PM | 0 | 4206 | 5h | 02.12.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4208 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | February 18, 2022 5:00 PM | February 18, 2022 5:00 PM | 0 | 4207,4201 | 0h | 02.12.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4209 |  | Auto Scheduled | מערכת הSAP תתמוך בהעברת הזמנת החוב Z25M לזכיין לטובת תכנון הפצת הפריט מהמצ"מ ליחידה - INT | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.07 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4210 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4211 |  | Auto Scheduled | LifeCycle Tasks | 223 days | May 18, 2021 8:00 AM | March 24, 2022 5:00 PM | 0 |  | 70h | 02.12.INT.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4212 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.INT.07.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4213 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.INT.07.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4214 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 12, 2021 8:00 AM | January 13, 2022 5:00 PM | 0 | 4213 | 0h | 02.12.INT.07.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4215 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 14, 2022 8:00 AM | February 17, 2022 5:00 PM | 0 | 4214 | 25h | 02.12.INT.07.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4216 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 18, 2022 8:00 AM | March 3, 2022 5:00 PM | 0 | 4215 | 10h | 02.12.INT.07.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4217 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 4, 2022 8:00 AM | March 17, 2022 5:00 PM | 0 | 4216 | 10h | 02.12.INT.07.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4218 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 18, 2022 8:00 AM | March 24, 2022 5:00 PM | 0 | 4217 | 5h | 02.12.INT.07.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4219 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 24, 2022 5:00 PM | March 24, 2022 5:00 PM | 0 | 4218,4212 | 0h | 02.12.INT.07.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4220 |  | Auto Scheduled | 02.12: תיקונים.SAP | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 560h | 02.12.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4221 |  | Auto Scheduled | מערכת ה-SAP תכלול חוקות בדרישה בהתאם למבנה הארגוני החדש של המרה"ס - SAP | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4222 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4223 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4224 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4225 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4226 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 12, 2021 8:00 AM | August 13, 2021 5:00 PM | 0 | 4225 | 0h | 02.12.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4227 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 16, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 4226 | 25h | 02.12.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4228 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 20, 2021 8:00 AM | October 1, 2021 5:00 PM | 0 | 4227 | 10h | 02.12.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4229 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 4, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 4228 | 10h | 02.12.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4230 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 18, 2021 8:00 AM | October 22, 2021 5:00 PM | 0 | 4229 | 5h | 02.12.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4231 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 22, 2021 5:00 PM | October 22, 2021 5:00 PM | 0 | 4230,4224 | 0h | 02.12.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4232 |  | Auto Scheduled | מערכת ה-SAP תאפשר אישור ידני/אוטומטי לדרישה מותאם למבנה הארגוני החדש של המרה"ס - SAP | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4233 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4234 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4235 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4236 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4237 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 12, 2021 8:00 AM | September 15, 2021 5:00 PM | 0 | 4236 | 0h | 02.12.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4238 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 16, 2021 8:00 AM | October 20, 2021 5:00 PM | 0 | 4237 | 25h | 02.12.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4239 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 21, 2021 8:00 AM | November 3, 2021 5:00 PM | 0 | 4238 | 10h | 02.12.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4240 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 4, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 | 4239 | 10h | 02.12.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4241 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 18, 2021 8:00 AM | November 24, 2021 5:00 PM | 0 | 4240 | 5h | 02.12.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4242 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 24, 2021 5:00 PM | November 24, 2021 5:00 PM | 0 | 4241,4235 | 0h | 02.12.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4243 |  | Auto Scheduled | מערכת הSAP תאפשר ביצוע קבלת מלאי למצ"מ תיקונים SAPי. - SAP | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4244 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4245 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4246 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4247 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4248 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 29/12/2021 | 25/01/2022 | 0 | 4247 | 0h | 02.12.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4249 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4248 | 25h | 02.12.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4250 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4249 | 10h | 02.12.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4251 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4250 | 10h | 02.12.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4252 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4251 | 5h | 02.12.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4253 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4252,4246 | 0h | 02.12.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4254 |  | Auto Scheduled | מערכת הSAP תאפשר יצירת הזמנת חוב בעת קבלת המלאי במצ"מ עם סימוכין להזמנת ההחזרה. - SAP | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4255 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4256 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4257 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4258 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4259 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 12, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 4258 | 0h | 02.12.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4260 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 15, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 4259 | 25h | 02.12.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4261 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 19, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 4260 | 10h | 02.12.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4262 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 3, 2021 8:00 AM | December 16, 2021 5:00 PM | 0 | 4261 | 10h | 02.12.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4263 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 17, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 4262 | 5h | 02.12.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4264 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 4263,4257 | 0h | 02.12.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4265 |  | Auto Scheduled | מערכת הSAP תאפשר ביצוע קבלת פריטים בבימ"ל. - SAP | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4266 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4267 |  | Auto Scheduled | LifeCycle Tasks | 165 days | May 18, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4268 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4269 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4270 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 15/12/2021 | 16/12/2021 | 0 | 4269 | 0h | 02.12.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4271 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4270 | 25h | 02.12.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4272 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4271 | 10h | 02.12.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4273 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4272 | 10h | 02.12.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4274 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4273 | 5h | 02.12.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4275 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4274,4268 | 0h | 02.12.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4276 |  | Auto Scheduled | מערכת הSAP תאפשר לבצע תהליך זיכוי יחידה, העברת כושר לפריט וסגירת הזמנת חוב Z25M. - SAP | 299 days | May 18, 2021 8:00 AM | July 8, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4277 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4278 |  | Auto Scheduled | LifeCycle Tasks | 299 days | May 18, 2021 8:00 AM | July 8, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4279 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4280 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4281 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 29, 2022 8:00 AM | May 1, 2022 5:00 PM | 0 | 4280 | 0h | 02.12.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4282 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 2, 2022 8:00 AM | June 3, 2022 5:00 PM | 0 | 4281 | 25h | 02.12.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4283 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 6, 2022 8:00 AM | June 17, 2022 5:00 PM | 0 | 4282 | 10h | 02.12.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4284 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 20, 2022 8:00 AM | July 1, 2022 5:00 PM | 0 | 4283 | 10h | 02.12.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4285 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 4, 2022 8:00 AM | July 8, 2022 5:00 PM | 0 | 4284 | 5h | 02.12.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4286 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 8, 2022 5:00 PM | July 8, 2022 5:00 PM | 0 | 4285,4279 | 0h | 02.12.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4287 |  | Auto Scheduled | מערכת הSAP תתמוך בשליחת מייל אוטומטי ליחידה עם הפריטים הפסולים ומספר ההזמנה. - SAP | 346 days | May 18, 2021 8:00 AM | September 13, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4288 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4289 |  | Auto Scheduled | LifeCycle Tasks | 346 days | May 18, 2021 8:00 AM | September 13, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4290 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4291 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4292 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 1, 2022 8:00 AM | July 5, 2022 5:00 PM | 0 | 4291 | 0h | 02.12.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4293 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 6, 2022 8:00 AM | August 9, 2022 5:00 PM | 0 | 4292 | 25h | 02.12.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4294 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 10, 2022 8:00 AM | August 23, 2022 5:00 PM | 0 | 4293 | 10h | 02.12.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4295 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 24, 2022 8:00 AM | September 6, 2022 5:00 PM | 0 | 4294 | 10h | 02.12.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4296 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 7, 2022 8:00 AM | September 13, 2022 5:00 PM | 0 | 4295 | 5h | 02.12.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4297 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 13, 2022 5:00 PM | September 13, 2022 5:00 PM | 0 | 4296,4290 | 0h | 02.12.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4298 |  | Auto Scheduled | מערכת ה-SAP תתמוך באפשרות של פתיחת דרישה, ולמולה תאפשר פתיחת הזמנה בצורה אוטומטית ו/או באישור ידני. - SAP | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.08 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4299 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4300 |  | Auto Scheduled | LifeCycle Tasks | 389 days | May 18, 2021 8:00 AM | November 11, 2022 5:00 PM | 0 |  | 70h | 02.12.SAP.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4301 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.12.SAP.08.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4302 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | December 7, 2021 8:00 AM | January 3, 2022 5:00 PM | 0 | 6686 | 20h | 02.12.SAP.08.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4303 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | August 2, 2022 8:00 AM | September 3, 2022 5:00 PM | 0 | 4302 | 0h | 02.12.SAP.08.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4304 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 5, 2022 8:00 AM | October 7, 2022 5:00 PM | 0 | 4303 | 25h | 02.12.SAP.08.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4305 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 10, 2022 8:00 AM | October 21, 2022 5:00 PM | 0 | 4304 | 10h | 02.12.SAP.08.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4306 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 24, 2022 8:00 AM | November 4, 2022 5:00 PM | 0 | 4305 | 10h | 02.12.SAP.08.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4307 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 0 | 4306 | 5h | 02.12.SAP.08.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4308 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 11, 2022 5:00 PM | November 11, 2022 5:00 PM | 0 | 4307,4301 | 0h | 02.12.SAP.08.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4309 |  | Auto Scheduled | 02.13: השאלות | 250 days | February 2, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 658h | 02.13 | ממתין לאישור | אבי פרישמן | hd | רועי |  | BP | NA | As Soon As Possible | 3
4310 |  | Auto Scheduled | 02.13: השאלות.BP | 169 days | May 18, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 |  | 168h | 02.13.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4311 |  | Auto Scheduled | 02.13: השאלות - BP | 169 days | May 18, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 |  | 168h | 02.13.BP.01 | ממתין לאישור | אבי פרישמן | parent | רועי |  | BP | NA | As Soon As Possible | 5
4312 |  | Auto Scheduled | Sub Tasks | 169 days | May 18, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 |  | 128h | 02.13.BP.01.01 |  | אבי פרישמן | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4313 |  | Auto Scheduled | כתיבת מסמך | 9 days | May 18, 2021 8:00 AM | May 28, 2021 5:00 PM | 0 |  | 9h | 02.13.BP.01.01.80 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | Must Start On | 7
4314 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 24 days | May 31, 2021 8:00 AM | July 1, 2021 5:00 PM | 0 | 4313 | 24h | 02.13.BP.01.01.81 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4315 |  | Auto Scheduled | אישור מקל"ר | 10 days | July 2, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 4314 | 10h | 02.13.BP.01.01.82 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4316 |  | Auto Scheduled | אישור המנהלת | 44 days | July 16, 2021 8:00 AM | September 15, 2021 5:00 PM | 0 | 4315 | 3h | 02.13.BP.01.01.83 | בוצע | סיגל | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4317 |  | Auto Scheduled | אישור מפקדת | 11 days | September 16, 2021 8:00 AM | September 30, 2021 5:00 PM | 0 | 4316 | 11h | 02.13.BP.01.01.84 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4318 |  | Auto Scheduled | אישור אבי | 10 days | October 1, 2021 8:00 AM | October 14, 2021 5:00 PM | 0 | 4317 | 10h | 02.13.BP.01.01.85 | בוצע | אבי | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4319 |  | Auto Scheduled | אישור חטלו"ג | 17 days | October 15, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 4318 | 17h | 02.13.BP.01.01.86 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4320 |  | Auto Scheduled | אישור שגיב שרביט | 4 days | November 9, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 4319 | 4h | 02.13.BP.01.01.87 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4321 |  | Auto Scheduled | אישור ניר בשן | 40 days | November 15, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 4320 | 40h | 02.13.BP.01.01.88 | בוצע | תהילה | MoM | תהילה | תע = שרשרת | BP | NA | As Soon As Possible | 7
4322 |  | Auto Scheduled | LifeCycle Tasks | 169 days | May 18, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 |  | 40h | 02.13.BP.01.02 |  | אבי פרישמן | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4323 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | January 7, 2022 5:00 PM | January 7, 2022 5:00 PM | 0 | 4321 | 0h | 02.13.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4324 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.13.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4325 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4324 | 10h | 02.13.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4326 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4325 | 5h | 02.13.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4327 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4326 | 10h | 02.13.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4328 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4327 | 10h | 02.13.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4329 |  | Auto Scheduled | בחתימה | 0 days | January 7, 2022 5:00 PM | January 7, 2022 5:00 PM | 0 | 4328,4323 | 0h | 02.13.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4330 |  | Auto Scheduled | חתום | 0 days | January 7, 2022 5:00 PM | January 7, 2022 5:00 PM | 0 | 4329 | 0h | 02.13.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4331 |  | Auto Scheduled | 02.13: השאלות.SAP | 250 days | February 2, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 490h | 02.13.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4332 |  | Auto Scheduled | מערכת SAP תאפשר לאשר/לדחות להקטין כמות של השאלה ליחידה - SAP | 75 days | March 5, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4333 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4334 |  | Auto Scheduled | LifeCycle Tasks | 75 days | March 5, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4335 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4336 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4337 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | March 5, 2021 8:00 AM | April 8, 2021 5:00 PM | 0 | 4336 | 0h | 02.13.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4338 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | April 9, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 4337 | 25h | 02.13.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4339 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | May 14, 2021 8:00 AM | May 27, 2021 5:00 PM | 0 | 4338 | 10h | 02.13.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4340 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | May 28, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 4339 | 10h | 02.13.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4341 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | June 11, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 4340 | 5h | 02.13.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4342 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | June 17, 2021 5:00 PM | June 17, 2021 5:00 PM | 0 | 4341,4335 | 0h | 02.13.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4343 |  | Auto Scheduled | מערכת הSAP תאפשר לבצע הארכת תוקף השאלה (מסך zlend) - SAP | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 70h | 02.13.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4344 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4345 |  | Auto Scheduled | LifeCycle Tasks | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 70h | 02.13.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4346 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4347 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4348 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | October 5, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 4347 | 0h | 02.13.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4349 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 9, 2021 8:00 AM | December 13, 2021 5:00 PM | 0 | 4348 | 25h | 02.13.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4350 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 14, 2021 8:00 AM | December 27, 2021 5:00 PM | 0 | 4349 | 10h | 02.13.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4351 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 28, 2021 8:00 AM | January 10, 2022 5:00 PM | 0 | 4350 | 10h | 02.13.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4352 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 11, 2022 8:00 AM | January 17, 2022 5:00 PM | 0 | 4351 | 5h | 02.13.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4353 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4352,4346 | 0h | 02.13.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4354 |  | Auto Scheduled | מערכת ה-SAP תאפשר לבצע קיזוז וסגירת הזמנת החזרת השאלה Z25 על סמך מימוש החזרה מסוג הזמנה z23באופן אוטומטי - SAP | 132 days | May 18, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4355 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4356 |  | Auto Scheduled | LifeCycle Tasks | 132 days | May 18, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4357 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4358 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4359 |  | Manually Scheduled | יישום ופיתוח סאפ | 0 days | September 8, 2021 5:00 PM | September 8, 2021 5:00 PM | 0 | 4358 | 0h | 02.13.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4360 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 9, 2021 8:00 AM | October 13, 2021 5:00 PM | 0 | 4359 | 25h | 02.13.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4361 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 14, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 | 4360 | 10h | 02.13.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4362 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 28, 2021 8:00 AM | November 10, 2021 5:00 PM | 0 | 4361 | 10h | 02.13.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4363 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 11, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 | 4362 | 5h | 02.13.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4364 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 17, 2021 5:00 PM | November 17, 2021 5:00 PM | 0 | 4363,4357 | 0h | 02.13.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4365 |  | Auto Scheduled | אפשרות של צ' להופיע בשתי הזמנות שונות במקביל (במקרה שלנו Z23 ו-Z25). - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4366 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4367 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4368 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4369 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4370 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 15/07/2021 | 22/07/2021 | 0 | 4369 | 0h | 02.13.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4371 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4370 | 25h | 02.13.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4372 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4371 | 10h | 02.13.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4373 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4372 | 10h | 02.13.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4374 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4373 | 5h | 02.13.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4375 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4374,4368 | 0h | 02.13.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4376 |  | Auto Scheduled | אפשרות הזנה של מספר תיק השאלה (שדה מספרי) משהב"ט בהזמנת ההשאלה לגורם חיצוני (סימולי חוץ). - SAP | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4377 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4378 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4379 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4380 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4381 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | 21/07/2021 | 28/07/2021 | 0 | 4380 | 0h | 02.13.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4382 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4381 | 25h | 02.13.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4383 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4382 | 10h | 02.13.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4384 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4383 | 10h | 02.13.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4385 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4384 | 5h | 02.13.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4386 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4385,4379 | 0h | 02.13.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4387 |  | Auto Scheduled | במעמד החזרה של פריט מגורם חיצוני, קיזוז השאלה על סמך הצלבה של פרטי הפריט בנוסף להצלבה של מספר ספק. - SAP | 95 days | February 2, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4388 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4389 |  | Auto Scheduled | LifeCycle Tasks | 95 days | February 2, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4390 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4391 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4392 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | February 2, 2021 8:00 AM | March 8, 2021 5:00 PM | 0 | 4391 | 0h | 02.13.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4393 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | March 9, 2021 8:00 AM | April 12, 2021 5:00 PM | 0 | 4392 | 25h | 02.13.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4394 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | April 13, 2021 8:00 AM | April 26, 2021 5:00 PM | 0 | 4393 | 10h | 02.13.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4395 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 27, 2021 8:00 AM | May 10, 2021 5:00 PM | 0 | 4394 | 10h | 02.13.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4396 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | May 11, 2021 8:00 AM | May 17, 2021 5:00 PM | 0 | 4395 | 5h | 02.13.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4397 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 4396,4390 | 0h | 02.13.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4398 |  | Auto Scheduled | נדרש להוסיף בעת יצירת הדרישה לניפוק השאלה לגורם חוץ שדה חובה למילוי מספר הספק המקבל - SAP | 203 days | February 8, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4399 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4400 |  | Auto Scheduled | LifeCycle Tasks | 203 days | February 8, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 |  | 70h | 02.13.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4401 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.13.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4402 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6929 | 20h | 02.13.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4403 |  | Manually Scheduled | יישום ופיתוח סאפ | 153 days | February 8, 2021 8:00 AM | September 8, 2021 5:00 PM | 0 | 4402 | 0h | 02.13.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4404 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 9, 2021 8:00 AM | October 13, 2021 5:00 PM | 0 | 4403 | 25h | 02.13.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4405 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 14, 2021 8:00 AM | October 27, 2021 5:00 PM | 0 | 4404 | 10h | 02.13.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4406 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 28, 2021 8:00 AM | November 10, 2021 5:00 PM | 0 | 4405 | 10h | 02.13.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4407 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 11, 2021 8:00 AM | November 17, 2021 5:00 PM | 0 | 4406 | 5h | 02.13.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4408 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 17, 2021 5:00 PM | November 17, 2021 5:00 PM | 0 | 4407,4401 | 0h | 02.13.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4409 |  | Auto Scheduled | 02.18: טיפול בהפרשים | 635 days | October 8, 2020 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 1,144h | 02.18 | ממתין לאישור | פריאל ישי | hd | פריאל |  | BP | NA | As Soon As Possible | 3
4410 |  | Auto Scheduled | 02.18: טיפול בהפרשים.BP | 394 days | October 8, 2020 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 174h | 02.18.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4411 |  | Auto Scheduled | 02.18: טיפול בהפרשים - BP | 394 days | October 8, 2020 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 174h | 02.18.BP.01 | ממתין לאישור | פריאל ישי | parent | פריאל |  | BP | NA | As Soon As Possible | 5
4412 |  | Auto Scheduled | Sub Tasks | 394 days | October 8, 2020 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 134h | 02.18.BP.01.01 |  | פריאל ישי | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4413 |  | Auto Scheduled | היה דיון ב-2.8. עד הדיון, פריאל בודק האם קשור לעוד מקומות ואיך משפיע. מה הסטאטוס? | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 02.18.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | As Soon As Possible | 7
4414 |  | Auto Scheduled | אמלח נדרש לאשר מול חטלו"ג שהניפוק יהיה בשלב יציאת המשאית למחסן ההפצה. | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.18.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | Must Start On | 7
4415 |  | Auto Scheduled | כתיבת מסמך | 16 days | May 18, 2021 8:00 AM | June 8, 2021 5:00 PM | 0 |  | 16h | 02.18.BP.01.01.30 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4416 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 22 days | June 9, 2021 8:00 AM | July 8, 2021 5:00 PM | 0 | 4415 | 22h | 02.18.BP.01.01.31 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4417 |  | Auto Scheduled | אישור מקל"ר | 42 days | July 9, 2021 8:00 AM | September 6, 2021 5:00 PM | 0 | 4416 | 42h | 02.18.BP.01.01.32 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4418 |  | Auto Scheduled | אישור אבי | 8 days | September 7, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 4417 | 8h | 02.18.BP.01.01.33 | בוצע | אבי | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4419 |  | Auto Scheduled | אישור המנהלת | 88 days | September 17, 2021 8:00 AM | January 18, 2022 5:00 PM | 0 | 4418 | 26h | 02.18.BP.01.01.34 | בוצע | סיגל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4420 |  | Auto Scheduled | אישור שגיב שרביט | 45 days | January 19, 2022 8:00 AM | March 22, 2022 5:00 PM | 0 | 4419 | 3h | 02.18.BP.01.01.35 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4421 |  | Auto Scheduled | אישור מפקדת | 13 days | March 23, 2022 8:00 AM | April 8, 2022 5:00 PM | 0 | 4420 | 13h | 02.18.BP.01.01.36 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4422 |  | Auto Scheduled | אישור חטלו"ג | 1 day | April 11, 2022 8:00 AM | April 11, 2022 5:00 PM | 0 | 4421 | 1h | 02.18.BP.01.01.37 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4423 |  | Auto Scheduled | אישור ניר בשן | 1 day | April 12, 2022 8:00 AM | April 12, 2022 5:00 PM | 0 | 4422 | 1h | 02.18.BP.01.01.38 | בוצע | פריאל | MoM |  | פריאל | BP | NA | As Soon As Possible | 7
4424 |  | Auto Scheduled | LifeCycle Tasks | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 40h | 02.18.BP.01.02 |  | פריאל ישי | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4425 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 4423 | 0h | 02.18.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4426 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.18.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4427 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4426 | 10h | 02.18.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4428 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4427 | 5h | 02.18.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4429 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4428 | 10h | 02.18.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4430 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4429 | 10h | 02.18.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4431 |  | Auto Scheduled | בחתימה | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 4430,4425 | 0h | 02.18.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4432 |  | Auto Scheduled | חתום | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 4431 | 0h | 02.18.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4433 |  | Auto Scheduled | 02.18: טיפול בהפרשים.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 60h | 02.18.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4434 |  | Auto Scheduled | לבדוק אפשרות השלמת הפריטים שלא הגיעו ליחידה ללא רישום - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.18.GEN.06 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4435 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4436 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.18.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4437 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4438 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4437 | 10h | 02.18.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4439 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4438 | 20h | 02.18.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4440 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4439,4437 | 0h | 02.18.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4441 |  | Auto Scheduled | לבחון השלכות שינוי התפיסה של 'מלאי בדרך' כפועל יוצא משינוי עיתוי הניפוק למול המצב הקיים - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.18.GEN.08 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4442 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.GEN.08.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4443 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.18.GEN.08.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4444 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.GEN.08.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4445 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4444 | 10h | 02.18.GEN.08.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4446 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4445 | 20h | 02.18.GEN.08.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4447 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4446,4444 | 0h | 02.18.GEN.08.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4448 |  | Auto Scheduled | 02.18: טיפול בהפרשים.INT | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 420h | 02.18.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4449 |  | Auto Scheduled | מערכת הPOD תתמוך בשליחת שדר אודות סטטוס האספקה למערכת הSAP לטובת הפקת דוחות. - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.18.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4450 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4451 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.18.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4452 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4453 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4454 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 26/10/2021 | 19/01/2022 | 0 | 4453 | 0h | 02.18.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4455 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4454 | 25h | 02.18.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4456 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4455 | 10h | 02.18.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4457 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4456 | 10h | 02.18.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4458 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4457 | 5h | 02.18.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4459 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4458,4452 | 0h | 02.18.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4460 |  | Auto Scheduled | מערכת הWMS תתמוך בביצוע ניפוק המלאי ושידור הפעולה למערכת הSAP. - INT | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 70h | 02.18.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4461 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4462 |  | Auto Scheduled | LifeCycle Tasks | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 70h | 02.18.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4463 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4464 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4465 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 29, 2021 8:00 AM | February 1, 2022 5:00 PM | 0 | 4464 | 0h | 02.18.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4466 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 2, 2022 8:00 AM | March 8, 2022 5:00 PM | 0 | 4465 | 25h | 02.18.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4467 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 9, 2022 8:00 AM | March 22, 2022 5:00 PM | 0 | 4466 | 10h | 02.18.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4468 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 23, 2022 8:00 AM | April 5, 2022 5:00 PM | 0 | 4467 | 10h | 02.18.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4469 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 6, 2022 8:00 AM | April 12, 2022 5:00 PM | 0 | 4468 | 5h | 02.18.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4470 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 4469,4463 | 0h | 02.18.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4471 |  | Auto Scheduled | מערכת הWMS תאפשר ביצוע פעולת רוורס לתנועת ניפוק ושליחת שדר למערכת הSAP כאשר משלוח יצא מהמרה"ס אבל מסיבה כלשהי לא הגיע ליחידה, והמשאית חזרה עם הציוד למחסן הפצה. - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.18.INT.03 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4472 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4473 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.18.INT.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4474 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.03.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4475 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.INT.03.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4476 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 16/12/2021 | 16/01/2022 | 0 | 4475 | 0h | 02.18.INT.03.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4477 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4476 | 25h | 02.18.INT.03.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4478 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4477 | 10h | 02.18.INT.03.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4479 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4478 | 10h | 02.18.INT.03.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4480 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4479 | 5h | 02.18.INT.03.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4481 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4480,4474 | 0h | 02.18.INT.03.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4482 |  | Auto Scheduled | מערכת הWMS תשלח בממשק למערכת הSAP את תיקון המלאי שבוצע ובקישור לאספקה - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.18.INT.04 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4483 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4484 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.18.INT.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4485 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.04.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4486 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.INT.04.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4487 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 30/12/2021 | 30/01/2022 | 0 | 4486 | 0h | 02.18.INT.04.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4488 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4487 | 25h | 02.18.INT.04.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4489 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4488 | 10h | 02.18.INT.04.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4490 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4489 | 10h | 02.18.INT.04.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4491 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4490 | 5h | 02.18.INT.04.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4492 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4491,4485 | 0h | 02.18.INT.04.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4493 |  | Auto Scheduled | מערכת הPOD תתמוך בשליחת שדר למערכת הSAP לטובת עדכון סטטוס באספקה. - INT | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 70h | 02.18.INT.05 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4494 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4495 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 70h | 02.18.INT.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4496 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.05.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4497 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.INT.05.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4498 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | December 1, 2022 8:00 AM | January 4, 2023 5:00 PM | 0 | 4497 | 0h | 02.18.INT.05.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4499 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | January 5, 2023 8:00 AM | February 8, 2023 5:00 PM | 0 | 4498 | 25h | 02.18.INT.05.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4500 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | February 9, 2023 8:00 AM | February 22, 2023 5:00 PM | 0 | 4499 | 10h | 02.18.INT.05.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4501 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | February 23, 2023 8:00 AM | March 8, 2023 5:00 PM | 0 | 4500 | 10h | 02.18.INT.05.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4502 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | March 9, 2023 8:00 AM | March 15, 2023 5:00 PM | 0 | 4501 | 5h | 02.18.INT.05.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4503 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 4502,4496 | 0h | 02.18.INT.05.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4504 |  | Auto Scheduled | מערכת הWMS ומערכת הSAP נדרשות לאפשר ניפוק בדחיפה וניפוק במשיכה. - INT | 366 days | May 18, 2021 8:00 AM | October 11, 2022 5:00 PM | 0 |  | 70h | 02.18.INT.06 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4505 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4506 |  | Auto Scheduled | LifeCycle Tasks | 366 days | May 18, 2021 8:00 AM | October 11, 2022 5:00 PM | 0 |  | 70h | 02.18.INT.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4507 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.INT.06.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4508 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.INT.06.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4509 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 0 days | August 2, 2022 5:00 PM | August 2, 2022 5:00 PM | 0 | 4508 | 0h | 02.18.INT.06.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4510 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 3, 2022 8:00 AM | September 6, 2022 5:00 PM | 0 | 4509 | 25h | 02.18.INT.06.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4511 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 7, 2022 8:00 AM | September 20, 2022 5:00 PM | 0 | 4510 | 10h | 02.18.INT.06.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4512 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 21, 2022 8:00 AM | October 4, 2022 5:00 PM | 0 | 4511 | 10h | 02.18.INT.06.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4513 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 5, 2022 8:00 AM | October 11, 2022 5:00 PM | 0 | 4512 | 5h | 02.18.INT.06.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4514 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | October 11, 2022 5:00 PM | October 11, 2022 5:00 PM | 0 | 4513,4507 | 0h | 02.18.INT.06.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4515 |  | Auto Scheduled | 02.18: טיפול בהפרשים.SAP | 289 days | January 7, 2021 8:00 AM | February 15, 2022 5:00 PM | 0 |  | 490h | 02.18.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4516 |  | Auto Scheduled | מערכת הSAP תתמוך בביצוע ניפוק המלאי. - SAP | 289 days | January 7, 2021 8:00 AM | February 15, 2022 5:00 PM | 0 |  | 70h | 02.18.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4517 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4518 |  | Auto Scheduled | LifeCycle Tasks | 289 days | January 7, 2021 8:00 AM | February 15, 2022 5:00 PM | 0 |  | 70h | 02.18.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4519 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4520 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4521 |  | Manually Scheduled | יישום ופיתוח סאפ | 239 days | January 7, 2021 8:00 AM | December 7, 2021 5:00 PM | 0 | 4520 | 0h | 02.18.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4522 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | December 8, 2021 8:00 AM | January 11, 2022 5:00 PM | 0 | 4521 | 25h | 02.18.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4523 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | January 12, 2022 8:00 AM | January 25, 2022 5:00 PM | 0 | 4522 | 10h | 02.18.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4524 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | January 26, 2022 8:00 AM | February 8, 2022 5:00 PM | 0 | 4523 | 10h | 02.18.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4525 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | February 9, 2022 8:00 AM | February 15, 2022 5:00 PM | 0 | 4524 | 5h | 02.18.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4526 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | February 15, 2022 5:00 PM | February 15, 2022 5:00 PM | 0 | 4525,4519 | 0h | 02.18.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4527 |  | Auto Scheduled | מערכת הSAP תאפשר להגדיר סטטוס "מלאי בדרך" לפני קליטתו ביחידה בפועל. - SAP | 181 days | May 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 02.18.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4528 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4529 |  | Auto Scheduled | LifeCycle Tasks | 181 days | May 7, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 |  | 70h | 02.18.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4530 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4531 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4532 |  | Manually Scheduled | יישום ופיתוח סאפ | 132 days | May 7, 2021 8:00 AM | November 7, 2021 5:00 PM | 0 | 4531 | 0h | 02.18.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4533 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | November 8, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 4532 | 25h | 02.18.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4534 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | December 13, 2021 8:00 AM | December 24, 2021 5:00 PM | 0 | 4533 | 10h | 02.18.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4535 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | December 27, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 4534 | 10h | 02.18.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4536 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | January 10, 2022 8:00 AM | January 14, 2022 5:00 PM | 0 | 4535 | 5h | 02.18.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4537 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | January 14, 2022 5:00 PM | January 14, 2022 5:00 PM | 0 | 4536,4530 | 0h | 02.18.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4538 |  | Auto Scheduled | מערכת הSAP תאפשר תיקון מלאי המקושר לאספקה בהתאם לשדר שהתקבל ממערכת הWMS. - SAP | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4539 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4540 |  | Auto Scheduled | LifeCycle Tasks | 111 days | May 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4541 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4542 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4543 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | July 7, 2021 8:00 AM | August 10, 2021 5:00 PM | 0 | 4542 | 0h | 02.18.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4544 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | August 11, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 4543 | 25h | 02.18.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4545 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | September 15, 2021 8:00 AM | September 28, 2021 5:00 PM | 0 | 4544 | 10h | 02.18.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4546 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | September 29, 2021 8:00 AM | October 12, 2021 5:00 PM | 0 | 4545 | 10h | 02.18.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4547 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | October 13, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 4546 | 5h | 02.18.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4548 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | October 19, 2021 5:00 PM | October 19, 2021 5:00 PM | 0 | 4547,4541 | 0h | 02.18.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4549 |  | Auto Scheduled | מערכת הSAP תתמוך בזיכוי / חיוב תקציב היחידה בכל טיפול בהפרשים - SAP | 75 days | May 7, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.04 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4550 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4551 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 7, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4552 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.04.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4553 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.04.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4554 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 7, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 4553 | 0h | 02.18.SAP.04.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4555 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 11, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 4554 | 25h | 02.18.SAP.04.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4556 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 16, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4555 | 10h | 02.18.SAP.04.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4557 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 30, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 4556 | 10h | 02.18.SAP.04.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4558 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 13, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 4557 | 5h | 02.18.SAP.04.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4559 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 19, 2021 5:00 PM | August 19, 2021 5:00 PM | 0 | 4558,4552 | 0h | 02.18.SAP.04.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4560 |  | Auto Scheduled | מערכת הSAP תתמוך בעדכון מלאי היחידה לאחר ביצוע קבלת מלאי בדרך . - SAP | 75 days | May 7, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.05 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4561 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.05.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4562 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 7, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.05.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4563 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.05.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4564 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.05.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4565 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | May 7, 2021 8:00 AM | June 10, 2021 5:00 PM | 0 | 4564 | 0h | 02.18.SAP.05.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4566 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 11, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 4565 | 25h | 02.18.SAP.05.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4567 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 16, 2021 8:00 AM | July 29, 2021 5:00 PM | 0 | 4566 | 10h | 02.18.SAP.05.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4568 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 30, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 4567 | 10h | 02.18.SAP.05.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4569 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 13, 2021 8:00 AM | August 19, 2021 5:00 PM | 0 | 4568 | 5h | 02.18.SAP.05.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4570 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | August 19, 2021 5:00 PM | August 19, 2021 5:00 PM | 0 | 4569,4563 | 0h | 02.18.SAP.05.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4571 |  | Auto Scheduled | מערכת הSAP תתמוך בקבלת סטאטוס האספקה ממערכת הPOD. - SAP | 74 days | April 10, 2021 8:00 AM | July 22, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.06 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4572 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4573 |  | Auto Scheduled | LifeCycle Tasks | 74 days | April 10, 2021 8:00 AM | July 22, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4574 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.06.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4575 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.06.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4576 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | April 10, 2021 8:00 AM | May 13, 2021 5:00 PM | 0 | 4575 | 0h | 02.18.SAP.06.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4577 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 14, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 | 4576 | 25h | 02.18.SAP.06.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4578 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 18, 2021 8:00 AM | July 1, 2021 5:00 PM | 0 | 4577 | 10h | 02.18.SAP.06.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4579 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | July 2, 2021 8:00 AM | July 15, 2021 5:00 PM | 0 | 4578 | 10h | 02.18.SAP.06.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4580 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 16, 2021 8:00 AM | July 22, 2021 5:00 PM | 0 | 4579 | 5h | 02.18.SAP.06.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4581 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 22, 2021 5:00 PM | July 22, 2021 5:00 PM | 0 | 4580,4574 | 0h | 02.18.SAP.06.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4582 |  | Auto Scheduled | מערכת SAP תתמוך באפשרות לעדכן פערים בין הכמות באספקה לכמות בפועל . - SAP | 112 days | January 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.07 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4583 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4584 |  | Auto Scheduled | LifeCycle Tasks | 112 days | January 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 02.18.SAP.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4585 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.18.SAP.07.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4586 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7119 | 20h | 02.18.SAP.07.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4587 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | January 8, 2021 8:00 AM | February 11, 2021 5:00 PM | 0 | 4586 | 0h | 02.18.SAP.07.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4588 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 12, 2021 8:00 AM | March 18, 2021 5:00 PM | 0 | 4587 | 25h | 02.18.SAP.07.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4589 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 19, 2021 8:00 AM | April 1, 2021 5:00 PM | 0 | 4588 | 10h | 02.18.SAP.07.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4590 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | April 2, 2021 8:00 AM | April 15, 2021 5:00 PM | 0 | 4589 | 10h | 02.18.SAP.07.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4591 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 16, 2021 8:00 AM | April 22, 2021 5:00 PM | 0 | 4590 | 5h | 02.18.SAP.07.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4592 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 4591,4585 | 0h | 02.18.SAP.07.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4593 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות | 197 days | October 9, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 619h | 02.21 | ממתין לאישור |  | hd | מאור |  | BP | NA | As Soon As Possible | 3
4594 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות.BP | 197 days | October 9, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 169h | 02.21.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4595 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות - BP | 197 days | October 9, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 169h | 02.21.BP.01 | ממתין לאישור |  | parent | מאור |  | BP | NA | As Soon As Possible | 5
4596 |  | Auto Scheduled | Sub Tasks | 192 days | October 9, 2020 8:00 AM | July 5, 2021 5:00 PM | 0 |  | 129h | 02.21.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4597 |  | Auto Scheduled | כתיבת מסמך | 51 days | October 9, 2020 8:00 AM | December 18, 2020 5:00 PM | 0 |  | 51h | 02.21.BP.01.01.30 | בוצע | מאור | MoM | מאור | תע = שרשרת | BP | NA | Must Start On | 7
4598 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 5 days | December 21, 2020 8:00 AM | December 25, 2020 5:00 PM | 0 | 4597 | 5h | 02.21.BP.01.01.31 | בוצע | מאור | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4599 |  | Auto Scheduled | אישור המנהלת | 3 days | December 28, 2020 8:00 AM | December 30, 2020 5:00 PM | 0 | 4598 | 3h | 02.21.BP.01.01.32 | בוצע | סיגל | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4600 |  | Auto Scheduled | אישור מקל"ר | 9 days | December 31, 2020 8:00 AM | January 12, 2021 5:00 PM | 0 | 4599 | 9h | 02.21.BP.01.01.33 | בוצע | מאור | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4601 |  | Auto Scheduled | אישור אבי | 65 days | January 13, 2021 8:00 AM | April 13, 2021 5:00 PM | 0 | 4600 | 2h | 02.21.BP.01.01.34 | בוצע | אבי | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4602 |  | Auto Scheduled | אישור מפקדת | 15 days | April 14, 2021 8:00 AM | May 4, 2021 5:00 PM | 0 | 4601 | 15h | 02.21.BP.01.01.35 | בוצע | מאור | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4603 |  | Auto Scheduled | אישור ניר בשן | 10 days | May 5, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 | 4602 | 10h | 02.21.BP.01.01.36 | בוצע | מאור | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4604 |  | Auto Scheduled | אישור שגיב שרביט | 33 days | May 19, 2021 8:00 AM | July 2, 2021 5:00 PM | 0 | 4603 | 33h | 02.21.BP.01.01.37 | בוצע | מאור | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4605 |  | Auto Scheduled | אישור חטלו"ג | 1 day | July 5, 2021 8:00 AM | July 5, 2021 5:00 PM | 0 | 4604 | 1h | 02.21.BP.01.01.38 | בוצע | מאור | MoM | מאור |  | BP | NA | As Soon As Possible | 7
4606 |  | Auto Scheduled | LifeCycle Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 02.21.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4607 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 5, 2021 5:00 PM | July 5, 2021 5:00 PM | 0 | 4605 | 0h | 02.21.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4608 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.21.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4609 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4608 | 10h | 02.21.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4610 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4609 | 5h | 02.21.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4611 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4610 | 10h | 02.21.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4612 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4611 | 10h | 02.21.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4613 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4612,4607 | 0h | 02.21.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4614 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4613 | 0h | 02.21.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4615 |  | Auto Scheduled | 02.21: רענון ערכות של יחידות.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 450h | 02.21.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4616 |  | Auto Scheduled | נדרש לתזמן את פתיחת הזמנות ההחזרה מהיחידות כך שייפתחו כאשר המלאי ביחידות מגיע לחצי שנה טרם פג"ת - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.01 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4617 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4618 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4619 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4620 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4619 | 10h | 02.21.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4621 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4620 | 20h | 02.21.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4622 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4621,4619 | 0h | 02.21.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4623 |  | Auto Scheduled | נדרש לתאם עם חיל טנ"א תהליך שיתמוך בעבודה עם תכניות אחזקה בתכנון הריענון - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.03 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4624 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4625 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4626 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4627 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4626 | 10h | 02.21.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4628 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4627 | 20h | 02.21.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4629 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4628,4626 | 0h | 02.21.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4630 |  | Auto Scheduled | נדרש למפות את החוקות הקיימות במסכי הdfps שמזון עובדים איתם כיום כדי להכניס את הלוגיקות בתהליך העתידי במסכי האחזקה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.04 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4631 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.04.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4632 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.04.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4633 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.04.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4634 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4633 | 10h | 02.21.GEN.04.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4635 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4634 | 20h | 02.21.GEN.04.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4636 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4635,4633 | 0h | 02.21.GEN.04.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4637 |  | Auto Scheduled | נדרש לקבל תשובה ממפקדת מרה"ס על התהליך העתידי האחוד שהוצע בBP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.06 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4638 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.06.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4639 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.06.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4640 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.06.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4641 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4640 | 10h | 02.21.GEN.06.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4642 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4641 | 20h | 02.21.GEN.06.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4643 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4642,4640 | 0h | 02.21.GEN.06.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4644 |  | Auto Scheduled | נדרש לקבוע דיון עם נציגי כלל המשקים להגדרה מתי בתהליך וכיצד הזמנות ההחזרה והניפוק יהפכו לדרישות (ע"י המערכת/ באופן ידני ע"י מרה"ס/ היחידות) - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.07 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4645 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.07.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4646 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.07.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4647 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.07.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4648 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4647 | 10h | 02.21.GEN.07.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4649 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4648 | 20h | 02.21.GEN.07.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4650 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4649,4647 | 0h | 02.21.GEN.07.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4651 |  | Auto Scheduled | נדרש לוודא שבBP החזרות מופיעה התייחסות להחזרה לטובת ריענון וזיכוי תקציבי עבור סימולים במעמד סדיר - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.10 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4652 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.10.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4653 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.10.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4654 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.10.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4655 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4654 | 10h | 02.21.GEN.10.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4656 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4655 | 20h | 02.21.GEN.10.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4657 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4656,4654 | 0h | 02.21.GEN.10.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4658 |  | Auto Scheduled | נדרש לכתוב דרישות לאור התהליך שיאושר ע"י המפקדת - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.14 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4659 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.14.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4660 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.14.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4661 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.14.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4662 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4661 | 10h | 02.21.GEN.14.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4663 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4662 | 20h | 02.21.GEN.14.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4664 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4663,4661 | 0h | 02.21.GEN.14.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4665 |  | Auto Scheduled | לבדוק האם וכיצד ניתן להעלות את הדרישה האוטומטית בשולחן עבודה של אחראי המלאי בגדוד+ מנפ"ר במרה"ס - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.15 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4666 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.15.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4667 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.15.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4668 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.15.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4669 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4668 | 10h | 02.21.GEN.15.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4670 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4669 | 20h | 02.21.GEN.15.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4671 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4670,4668 | 0h | 02.21.GEN.15.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4672 |  | Auto Scheduled | לוודא שהמערכת מאפשרת להחזיר גם פריט שהפג"ת שלו עבר בBP החזרות- שו"ש מרה"ס ב'- תוך הגדרת חוקות עבור החזרת פריטים שהפג"ת שלהם עבר - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.16 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4673 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.16.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4674 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.16.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4675 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.16.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4676 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4675 | 10h | 02.21.GEN.16.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4677 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4676 | 20h | 02.21.GEN.16.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4678 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4677,4675 | 0h | 02.21.GEN.16.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4679 |  | Auto Scheduled | נדרש להציג למפקדת מרה"ס דפ"אות לתהליכים אוטומטיים מבוססי MRP - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.17 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4680 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.17.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4681 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.17.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4682 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.17.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4683 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4682 | 10h | 02.21.GEN.17.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4684 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4683 | 20h | 02.21.GEN.17.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4685 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4684,4682 | 0h | 02.21.GEN.17.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4686 |  | Auto Scheduled | נדרש להגדיר במערכת ריצת MRP שתקבע השלמה לתקן ליחידות בסימולי חירום בלבד עבור כל משק לפי פרמטרים שיוגדרו ע"י משתמש במפקדת מרה"ס - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.18 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4687 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.18.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4688 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.18.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4689 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.18.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4690 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4689 | 10h | 02.21.GEN.18.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4691 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4690 | 20h | 02.21.GEN.18.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4692 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4691,4689 | 0h | 02.21.GEN.18.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4693 |  | Auto Scheduled | נדרש לסכם האם להחליף את סוג מסמך ZDLK לZN01 עבור משק השמנים המנוהלים בWMS - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.20 | משימה בעבודה |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4694 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.20.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4695 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.20.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4696 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.20.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4697 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4696 | 10h | 02.21.GEN.20.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4698 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4697 | 20h | 02.21.GEN.20.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4699 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4698,4696 | 0h | 02.21.GEN.20.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4700 |  | Auto Scheduled | במידה ויסוכם שנשארים עם ZDLK יש לוודא שבדו"ח שמרכז את ההזמנות למרה"ס יהיה מענה גם לZDLK - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.21 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4701 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.21.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4702 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.21.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4703 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.21.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4704 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4703 | 10h | 02.21.GEN.21.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4705 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4704 | 20h | 02.21.GEN.21.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4706 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4705,4703 | 0h | 02.21.GEN.21.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4707 |  | Auto Scheduled | כדי לדעת להבדיל בין מה שמנוהל בSAP ומה מנוהל בWMS נדרש להגדיר חוקות וסיבות שונות עבור משק הדלק בנפרד ומשק השמנים בנפרד - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.22 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4708 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.22.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4709 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.22.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4710 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.22.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4711 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4710 | 10h | 02.21.GEN.22.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4712 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4711 | 20h | 02.21.GEN.22.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4713 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4712,4710 | 0h | 02.21.GEN.22.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4714 |  | Auto Scheduled | כאשר נוצרת דרישת החזרה באופן אוטומטי ע"י המערכת נדרש לוודא שיש סמן השלמה אוטומטי שמעביר את המסמך מסטאטוס N1 לסטאטוס Z1 - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.23 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4715 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.23.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4716 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.21.GEN.23.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4717 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.21.GEN.23.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4718 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4717 | 10h | 02.21.GEN.23.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4719 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4718 | 20h | 02.21.GEN.23.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4720 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4719,4717 | 0h | 02.21.GEN.23.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4721 |  | Auto Scheduled | 02.23: MRP | 316 days | October 8, 2020 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 297h | 02.23 | סיכום מסמך | מאיה | hd | פריאל |  | BP | NA | As Soon As Possible | 3
4722 |  | Auto Scheduled | 02.23: MRP.BP | 316 days | October 8, 2020 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 157h | 02.23.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4723 |  | Auto Scheduled | 02.23: MRP - BP | 316 days | October 8, 2020 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 157h | 02.23.BP.01 | סיכום מסמך | מאיה | parent | פריאל |  | BP | NA | As Soon As Possible | 5
4724 |  | Auto Scheduled | Sub Tasks | 316 days | October 8, 2020 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 117h | 02.23.BP.01.01 |  | מאיה | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4725 |  | Auto Scheduled | היום יש ביזור פנימי במרכזים בצורה ידנית (חוץ מחנויות מכר) האם יש שינוי ממה שקורה היום?--אמל"ח נדרש לעדכן האם נדרש התהליך בעידן במרה"ס | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.23.BP.01.01.10 | בוצע |  | MoM |  | מאיה | BP | NA | Must Start On | 7
4726 |  | Auto Scheduled | כתיבת מסמך | 25 days | May 18, 2021 8:00 AM | June 21, 2021 5:00 PM | 0 |  | 25h | 02.23.BP.01.01.30 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4727 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 38 days | June 22, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 4726 | 38h | 02.23.BP.01.01.31 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4728 |  | Auto Scheduled | אישור אבי | 8 days | August 13, 2021 8:00 AM | August 24, 2021 5:00 PM | 0 | 4727 | 8h | 02.23.BP.01.01.32 | בוצע | אבי | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4729 |  | Auto Scheduled | אישור חטלו"ג | 15 days | August 25, 2021 8:00 AM | September 14, 2021 5:00 PM | 0 | 4728 | 15h | 02.23.BP.01.01.33 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4730 |  | Auto Scheduled | אישור מקל"ר | 4 days | September 15, 2021 8:00 AM | September 20, 2021 5:00 PM | 0 | 4729 | 4h | 02.23.BP.01.01.34 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4731 |  | Auto Scheduled | אישור המנהלת | 9 days | September 21, 2021 8:00 AM | October 1, 2021 5:00 PM | 0 | 4730 | 9h | 02.23.BP.01.01.35 | בוצע | סיגל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4732 |  | Auto Scheduled | אישור שגיב שרביט | 45 days | October 4, 2021 8:00 AM | December 3, 2021 5:00 PM | 0 | 4731 | 3h | 02.23.BP.01.01.36 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4733 |  | Auto Scheduled | אישור מפקדת | 13 days | December 6, 2021 8:00 AM | December 22, 2021 5:00 PM | 0 | 4732 | 13h | 02.23.BP.01.01.37 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4734 |  | Auto Scheduled | אישור ניר בשן | 1 day | December 23, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 | 4733 | 1h | 02.23.BP.01.01.38 | בוצע | פריאל | MoM | פריאל | תע = שרשרת | BP | NA | As Soon As Possible | 7
4735 |  | Auto Scheduled | LifeCycle Tasks | 158 days | May 18, 2021 8:00 AM | December 23, 2021 5:00 PM | 0 |  | 40h | 02.23.BP.01.02 |  | מאיה | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4736 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 4734 | 0h | 02.23.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4737 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.23.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4738 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4737 | 10h | 02.23.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4739 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4738 | 5h | 02.23.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4740 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4739 | 10h | 02.23.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4741 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4740 | 10h | 02.23.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4742 |  | Auto Scheduled | בחתימה | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 4741,4736 | 0h | 02.23.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4743 |  | Auto Scheduled | חתום | 0 days | December 23, 2021 5:00 PM | December 23, 2021 5:00 PM | 0 | 4742 | 0h | 02.23.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4744 |  | Auto Scheduled | 02.23: MRP.SAP | 248 days | January 6, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 140h | 02.23.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4745 |  | Auto Scheduled | מערכת הsap תתמוך ביצירת המלצות לייצור כנגזרת מריצות MRP. - SAP | 224 days | January 6, 2021 8:00 AM | November 15, 2021 5:00 PM | 0 |  | 70h | 02.23.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4746 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.23.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4747 |  | Auto Scheduled | LifeCycle Tasks | 224 days | January 6, 2021 8:00 AM | November 15, 2021 5:00 PM | 0 |  | 70h | 02.23.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4748 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.23.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4749 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7687 | 20h | 02.23.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4750 |  | Manually Scheduled | יישום ופיתוח סאפ | 174 days | January 6, 2021 8:00 AM | September 6, 2021 5:00 PM | 0 | 4749 | 0h | 02.23.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4751 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | September 7, 2021 8:00 AM | October 11, 2021 5:00 PM | 0 | 4750 | 25h | 02.23.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4752 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | October 12, 2021 8:00 AM | October 25, 2021 5:00 PM | 0 | 4751 | 10h | 02.23.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4753 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | October 26, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 4752 | 10h | 02.23.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4754 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | November 9, 2021 8:00 AM | November 15, 2021 5:00 PM | 0 | 4753 | 5h | 02.23.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4755 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | November 15, 2021 5:00 PM | November 15, 2021 5:00 PM | 0 | 4754,4748 | 0h | 02.23.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4756 |  | Auto Scheduled | מערכת הsap תתמוך בהקמת אזורי MRP חדשים - SAP | 154 days | May 18, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 70h | 02.23.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4757 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.23.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4758 |  | Auto Scheduled | LifeCycle Tasks | 154 days | May 18, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 |  | 70h | 02.23.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4759 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.23.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4760 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7687 | 20h | 02.23.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4761 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | September 6, 2021 8:00 AM | October 8, 2021 5:00 PM | 0 | 4760 | 0h | 02.23.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4762 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 11, 2021 8:00 AM | November 12, 2021 5:00 PM | 0 | 4761 | 25h | 02.23.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4763 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 15, 2021 8:00 AM | November 26, 2021 5:00 PM | 0 | 4762 | 10h | 02.23.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4764 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 29, 2021 8:00 AM | December 10, 2021 5:00 PM | 0 | 4763 | 10h | 02.23.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4765 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 13, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 | 4764 | 5h | 02.23.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4766 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 17, 2021 5:00 PM | December 17, 2021 5:00 PM | 0 | 4765,4759 | 0h | 02.23.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4767 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין | 378 days | October 8, 2020 8:00 AM | March 21, 2022 5:00 PM | 0.16 |  | 536h | 02.24 | סיכום מסמך | פריאל ישי | hd | פריאל |  | BP | NA | As Soon As Possible | 3
4768 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.BP | 378 days | October 8, 2020 8:00 AM | March 21, 2022 5:00 PM | 0 |  | 156h | 02.24.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4769 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין - BP | 378 days | October 8, 2020 8:00 AM | March 21, 2022 5:00 PM | 0 |  | 156h | 02.24.BP.01 | סיכום מסמך | פריאל ישי | parent | פריאל |  | BP | NA | As Soon As Possible | 5
4770 |  | Auto Scheduled | Sub Tasks | 378 days | October 8, 2020 8:00 AM | March 21, 2022 5:00 PM | 0 |  | 116h | 02.24.BP.01.01 |  | פריאל ישי | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4771 |  | Auto Scheduled | 3. יש לקבוע את החוקות על פיהם נאחד/נפצל אספקות ע"פ נהלים/פקודות/או"ש. באחריות אמלח למול משתמשים | 1 day | October 8, 2020 8:00 AM | October 8, 2020 5:00 PM | 0 |  | 1h | 02.24.BP.01.01.12 | בוצע | פריאל | MoM | פריאל | מאיה | BP | NA | Must Start On | 7
4772 |  | Auto Scheduled | 4. יש לקבוע את החוקות על פיהם יקבע וקטור הניפוק ע"פ נהלים/פקודות/או"ש. באחריות אמלח למול משתמשים | 1 day | May 18, 2021 8:00 AM | May 18, 2021 5:00 PM | 0 |  | 1h | 02.24.BP.01.01.13 | בוצע | פריאל | MoM | פריאל | מאיה | BP | NA | As Soon As Possible | 7
4773 |  | Auto Scheduled | כתיבת מסמך | 23 days | May 18, 2021 8:00 AM | June 17, 2021 5:00 PM | 0 |  | 23h | 02.24.BP.01.01.30 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4774 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 21 days | June 18, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 4773 | 21h | 02.24.BP.01.01.31 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4775 |  | Auto Scheduled | אישור המנהלת | 110 days | July 19, 2021 8:00 AM | December 17, 2021 5:00 PM | 0 | 4774 | 4h | 02.24.BP.01.01.32 | בוצע | סיגל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4776 |  | Auto Scheduled | אישור מקל"ר | 15 days | December 20, 2021 8:00 AM | January 7, 2022 5:00 PM | 0 | 4775 | 15h | 02.24.BP.01.01.33 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4777 |  | Auto Scheduled | אישור אבי | 8 days | January 10, 2022 8:00 AM | January 19, 2022 5:00 PM | 0 | 4776 | 8h | 02.24.BP.01.01.34 | בוצע | אבי | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4778 |  | Auto Scheduled | אישור מפקדת | 15 days | January 20, 2022 8:00 AM | February 9, 2022 5:00 PM | 0 | 4777 | 15h | 02.24.BP.01.01.35 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4779 |  | Auto Scheduled | אישור שגיב שרביט | 4 days | February 10, 2022 8:00 AM | February 15, 2022 5:00 PM | 0 | 4778 | 4h | 02.24.BP.01.01.36 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4780 |  | Auto Scheduled | אישור ניר בשן | 23 days | February 16, 2022 8:00 AM | March 18, 2022 5:00 PM | 0 | 4779 | 23h | 02.24.BP.01.01.37 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4781 |  | Auto Scheduled | אישור חטלו"ג | 1 day | March 21, 2022 8:00 AM | March 21, 2022 5:00 PM | 0 | 4780 | 1h | 02.24.BP.01.01.38 | בוצע | פריאל | MoM | פריאל |  | BP | NA | As Soon As Possible | 7
4782 |  | Auto Scheduled | LifeCycle Tasks | 220 days | May 18, 2021 8:00 AM | March 21, 2022 5:00 PM | 0 |  | 40h | 02.24.BP.01.02 |  | פריאל ישי | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4783 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | March 21, 2022 5:00 PM | March 21, 2022 5:00 PM | 0 | 4781 | 0h | 02.24.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4784 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 02.24.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4785 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4784 | 10h | 02.24.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4786 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4785 | 5h | 02.24.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4787 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4786 | 10h | 02.24.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4788 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4787 | 10h | 02.24.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4789 |  | Auto Scheduled | בחתימה | 0 days | March 21, 2022 5:00 PM | March 21, 2022 5:00 PM | 0 | 4788,4783 | 0h | 02.24.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4790 |  | Auto Scheduled | חתום | 0 days | March 21, 2022 5:00 PM | March 21, 2022 5:00 PM | 0 | 4789 | 0h | 02.24.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4791 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.24.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4792 |  | Auto Scheduled | נדרש לבדוק מול תחום אחזקה מענה לפתיחת אספקה אוטומטית מול תהליכי הבחינה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.24.GEN.03 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
4793 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.GEN.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4794 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 02.24.GEN.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4795 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.GEN.03.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4796 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 4795 | 10h | 02.24.GEN.03.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4797 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4796 | 20h | 02.24.GEN.03.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4798 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 4797,4795 | 0h | 02.24.GEN.03.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
4799 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.INT | 170 days | January 5, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 140h | 02.24.INT |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4800 |  | Auto Scheduled | מערכת הSAP תאפשר שליחת אספקה ללא סימוכין למערכת הWMS של הזכיין רק לאחר אישורה (לא אוטומטי). - INT | 115 days | January 5, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 02.24.INT.01 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4801 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.INT.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4802 |  | Auto Scheduled | LifeCycle Tasks | 115 days | January 5, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 70h | 02.24.INT.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4803 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.INT.01.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4804 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7779 | 20h | 02.24.INT.01.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4805 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | January 5, 2021 8:00 AM | February 8, 2021 5:00 PM | 0 | 4804 | 0h | 02.24.INT.01.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4806 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | February 9, 2021 8:00 AM | March 15, 2021 5:00 PM | 0 | 4805 | 25h | 02.24.INT.01.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4807 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | March 16, 2021 8:00 AM | March 29, 2021 5:00 PM | 0 | 4806 | 10h | 02.24.INT.01.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4808 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | March 30, 2021 8:00 AM | April 12, 2021 5:00 PM | 0 | 4807 | 10h | 02.24.INT.01.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4809 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | April 13, 2021 8:00 AM | April 19, 2021 5:00 PM | 0 | 4808 | 5h | 02.24.INT.01.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4810 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 | 4809,4803 | 0h | 02.24.INT.01.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4811 |  | Auto Scheduled | מערכת הWMS תאפשר קבלת שדר עדכון לאספקה ממערכת הSAP לטובת עדכון ביצוע תהליכים שהוגדרו לעיל. - INT | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.24.INT.02 | יישום ופיתוח משימת ממשק |  | parent |  | requirements | INT | NA | As Soon As Possible | 5
4812 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.INT.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4813 |  | Auto Scheduled | LifeCycle Tasks | 75 days | May 18, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 |  | 70h | 02.24.INT.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4814 |  | Auto Scheduled | סיום משימות משנה לממשק | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.INT.02.02.01 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4815 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7779 | 20h | 02.24.INT.02.02.02 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4816 |  | Manually Scheduled | יישום ופיתוח משימת ממשק | 25 days | 13/07/2021 | 18/08/2021 | 0 | 4815 | 0h | 02.24.INT.02.02.03 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4817 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | June 22, 2021 8:00 AM | July 26, 2021 5:00 PM | 0 | 4816 | 25h | 02.24.INT.02.02.04 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4818 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | July 27, 2021 8:00 AM | August 9, 2021 5:00 PM | 0 | 4817 | 10h | 02.24.INT.02.02.05 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4819 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 10, 2021 8:00 AM | August 23, 2021 5:00 PM | 0 | 4818 | 10h | 02.24.INT.02.02.06 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4820 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | August 24, 2021 8:00 AM | August 30, 2021 5:00 PM | 0 | 4819 | 5h | 02.24.INT.02.02.07 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4821 |  | Auto Scheduled | משימת ממשק עלתה לאויר | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4820,4814 | 0h | 02.24.INT.02.02.08 |  |  | rule |  |  | INT | NA | As Soon As Possible | 7
4822 |  | Auto Scheduled | 02.24: אספקה ללא סימוכין.SAP | 223 days | February 5, 2021 8:00 AM | December 14, 2021 5:00 PM | 0.33000000000000002 |  | 210h | 02.24.SAP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4823 |  | Auto Scheduled | מערכת הSAP תאפשר ליצור אספקה ללא סימוכין עם סיבה רלוונטית ושדה "אישור שליחת אספקה" . - SAP | 223 days | February 5, 2021 8:00 AM | December 14, 2021 5:00 PM | 0.58999999999999997 |  | 70h | 02.24.SAP.01 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4824 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.SAP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4825 |  | Auto Scheduled | LifeCycle Tasks | 223 days | February 5, 2021 8:00 AM | December 14, 2021 5:00 PM | 0.58999999999999997 |  | 70h | 02.24.SAP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4826 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.SAP.01.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4827 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7779 | 20h | 02.24.SAP.01.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4828 |  | Manually Scheduled | יישום ופיתוח סאפ | 173 days | February 5, 2021 8:00 AM | October 5, 2021 5:00 PM | 0.82999999999999996 | 4827 | 0h | 02.24.SAP.01.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4829 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | October 6, 2021 8:00 AM | November 9, 2021 5:00 PM | 0 | 4828 | 25h | 02.24.SAP.01.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4830 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | November 10, 2021 8:00 AM | November 23, 2021 5:00 PM | 0 | 4829 | 10h | 02.24.SAP.01.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4831 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | November 24, 2021 8:00 AM | December 7, 2021 5:00 PM | 0 | 4830 | 10h | 02.24.SAP.01.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4832 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | December 8, 2021 8:00 AM | December 14, 2021 5:00 PM | 0 | 4831 | 5h | 02.24.SAP.01.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4833 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | December 14, 2021 5:00 PM | December 14, 2021 5:00 PM | 0 | 4832,4826 | 0h | 02.24.SAP.01.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4834 |  | Auto Scheduled | מערכת הSAP תאפשר לעלות לאישור אספקות עם סיבה הדורשת אישור על פי הטבלה לעיל. יוגדר בטבלת BRF - SAP | 88 days | May 18, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 |  | 70h | 02.24.SAP.02 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4835 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.SAP.02.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4836 |  | Auto Scheduled | LifeCycle Tasks | 88 days | May 18, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 |  | 70h | 02.24.SAP.02.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4837 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.SAP.02.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4838 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7779 | 20h | 02.24.SAP.02.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4839 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | June 5, 2021 8:00 AM | July 8, 2021 5:00 PM | 0 | 4838 | 0h | 02.24.SAP.02.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4840 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | July 9, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 4839 | 25h | 02.24.SAP.02.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4841 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | August 13, 2021 8:00 AM | August 26, 2021 5:00 PM | 0 | 4840 | 10h | 02.24.SAP.02.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4842 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | August 27, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 | 4841 | 10h | 02.24.SAP.02.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4843 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | September 10, 2021 8:00 AM | September 16, 2021 5:00 PM | 0 | 4842 | 5h | 02.24.SAP.02.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4844 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | September 16, 2021 5:00 PM | September 16, 2021 5:00 PM | 0 | 4843,4837 | 0h | 02.24.SAP.02.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4845 |  | Auto Scheduled | מערכת הSAP תאפשר צפייה בדוח אספקות ללא סימוכין בסטאטוס טרם אושר (במסך zdeln או מסך שיוחלט בשלב הREAL ) ושינוי סטאטוס באספקה ל "אושר" - SAP | 75 days | April 5, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 |  | 70h | 02.24.SAP.03 | יישום ופיתוח סאפ |  | parent |  | requirements | SAP | NA | As Soon As Possible | 5
4846 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.SAP.03.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4847 |  | Auto Scheduled | LifeCycle Tasks | 75 days | April 5, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 |  | 70h | 02.24.SAP.03.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4848 |  | Auto Scheduled | סיום משימות משנה לסאפ | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 02.24.SAP.03.02.01 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4849 |  | Auto Scheduled | תכנון והתחלת פיתוח | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 7779 | 20h | 02.24.SAP.03.02.02 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4850 |  | Manually Scheduled | יישום ופיתוח סאפ | 25 days | April 5, 2021 8:00 AM | May 7, 2021 5:00 PM | 0 | 4849 | 0h | 02.24.SAP.03.02.03 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4851 |  | Auto Scheduled | פיתוח בדיקות קבלה | 25 days | May 10, 2021 8:00 AM | June 11, 2021 5:00 PM | 0 | 4850 | 25h | 02.24.SAP.03.02.04 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4852 |  | Auto Scheduled | בדיקת קבלה ע״י מנהל המוצר | 10 days | June 14, 2021 8:00 AM | June 25, 2021 5:00 PM | 0 | 4851 | 10h | 02.24.SAP.03.02.05 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4853 |  | Auto Scheduled | בדיקת קבלה ע״י המשתמשים | 10 days | June 28, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 4852 | 10h | 02.24.SAP.03.02.06 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4854 |  | Auto Scheduled | הכנות להעלאה לאויר | 5 days | July 12, 2021 8:00 AM | July 16, 2021 5:00 PM | 0 | 4853 | 5h | 02.24.SAP.03.02.07 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4855 |  | Auto Scheduled | משימת סאפ עלתה לאויר | 0 days | July 16, 2021 5:00 PM | July 16, 2021 5:00 PM | 0 | 4854,4848 | 0h | 02.24.SAP.03.02.08 |  |  | rule |  |  | SAP | NA | As Soon As Possible | 7
4856 |  | Auto Scheduled | 03: אחזקה | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 03 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
4857 |  | Auto Scheduled | 03.01: שכר עידוד | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 03.01 | בעבודה | איהאב | hd | איהאב |  | BP | NA | As Soon As Possible | 3
4858 |  | Auto Scheduled | 03.01: שכר עידוד.BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 03.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4859 |  | Auto Scheduled | 03.01: שכר עידוד - BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 03.01.BP.01 | בעבודה | איהאב | parent | איהאב |  | BP | NA | As Soon As Possible | 5
4860 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 03.01.BP.01.01 |  | איהאב | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4861 |  | Auto Scheduled | LifeCycle Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 03.01.BP.01.02 |  | איהאב | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4862 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 03.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4863 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 03.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4864 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4863 | 10h | 03.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4865 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4864 | 5h | 03.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4866 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4865 | 10h | 03.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4867 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4866 | 10h | 03.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4868 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4867,4862 | 0h | 03.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4869 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4868 | 0h | 03.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4870 |  | Auto Scheduled | 04: תקציב ורכש | 284 days | June 12, 2020 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 152h | 04 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
4871 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש | 42 days | May 18, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 82h | 04.01 | בעבודה |  | hd | תהילה |  | BP | NA | As Soon As Possible | 3
4872 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש.BP | 42 days | May 18, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 82h | 04.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4873 |  | Auto Scheduled | 04.01: מבנה ארגוני - תקציב ורכש - BP | 42 days | May 18, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 82h | 04.01.BP.01 | בעבודה |  | parent | תהילה |  | BP | NA | As Soon As Possible | 5
4874 |  | Auto Scheduled | Sub Tasks | 42 days | May 18, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 42h | 04.01.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4875 |  | Auto Scheduled | כתיבת מסמך | 20 days | May 18, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 |  | 20h | 04.01.BP.01.01.20 | בתהליך |  | MoM |  |  | BP | NA | Must Start On | 7
4876 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 5 days | June 15, 2021 8:00 AM | June 21, 2021 5:00 PM | 0 | 4875 | 5h | 04.01.BP.01.01.21 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4877 |  | Auto Scheduled | אישור אבי | 2 days | June 22, 2021 8:00 AM | June 23, 2021 5:00 PM | 0 | 4876 | 2h | 04.01.BP.01.01.22 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4878 |  | Auto Scheduled | אישור המנהלת | 3 days | June 24, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4877 | 3h | 04.01.BP.01.01.23 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4879 |  | Auto Scheduled | אישור מקל"ר | 2 days | June 29, 2021 8:00 AM | June 30, 2021 5:00 PM | 0 | 4878 | 2h | 04.01.BP.01.01.24 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4880 |  | Auto Scheduled | אישור מפקדת | 2 days | July 1, 2021 8:00 AM | July 2, 2021 5:00 PM | 0 | 4879 | 2h | 04.01.BP.01.01.25 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4881 |  | Auto Scheduled | אישור חטלו"ג | 2 days | July 5, 2021 8:00 AM | July 6, 2021 5:00 PM | 0 | 4880 | 2h | 04.01.BP.01.01.26 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4882 |  | Auto Scheduled | אישור ניר בשן | 3 days | July 7, 2021 8:00 AM | July 9, 2021 5:00 PM | 0 | 4881 | 3h | 04.01.BP.01.01.27 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4883 |  | Auto Scheduled | אישור שגיב שרביט | 3 days | July 12, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 4882 | 3h | 04.01.BP.01.01.28 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4884 |  | Auto Scheduled | LifeCycle Tasks | 42 days | May 18, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 40h | 04.01.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4885 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 14, 2021 5:00 PM | July 14, 2021 5:00 PM | 0 | 4883 | 0h | 04.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4886 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 04.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4887 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4886 | 10h | 04.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4888 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4887 | 5h | 04.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4889 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4888 | 10h | 04.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4890 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4889 | 10h | 04.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4891 |  | Auto Scheduled | בחתימה | 0 days | July 14, 2021 5:00 PM | July 14, 2021 5:00 PM | 0 | 4890,4885 | 0h | 04.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4892 |  | Auto Scheduled | חתום | 0 days | July 14, 2021 5:00 PM | July 14, 2021 5:00 PM | 0 | 4891 | 0h | 04.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4893 |  | Auto Scheduled | 04.02: סבב אישורים | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 04.02 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
4894 |  | Auto Scheduled | 04.02: סבב אישורים.BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 04.02.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4895 |  | Auto Scheduled | 04.02: סבב אישורים - BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 04.02.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
4896 |  | Auto Scheduled | Sub Tasks | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 04.02.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4897 |  | Auto Scheduled | כתיבת מסמך | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 04.02.BP.01.01.20 | טרם החל |  | MoM |  |  | BP | NA | Must Start On | 7
4898 |  | Auto Scheduled | LifeCycle Tasks | 252 days | July 23, 2020 5:00 PM | July 12, 2021 5:00 PM | 0 |  | 40h | 04.02.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4899 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 23, 2020 5:00 PM | July 23, 2020 5:00 PM | 0 | 4897 | 0h | 04.02.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4900 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 04.02.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4901 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4900 | 10h | 04.02.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4902 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4901 | 5h | 04.02.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4903 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4902 | 10h | 04.02.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4904 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4903 | 10h | 04.02.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4905 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4904,4899 | 0h | 04.02.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4906 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4905 | 0h | 04.02.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4907 |  | Auto Scheduled | 05: ממשקים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 05 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
4908 |  | Auto Scheduled | 06: קטלוג | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 287h | 06 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
4909 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג | 134 days | May 18, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 97h | 06.01 | בעבודה |  | hd | קטיה |  | BP | NA | As Soon As Possible | 3
4910 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג.BP | 134 days | May 18, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 97h | 06.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4911 |  | Auto Scheduled | 06.01: מבנה ארגוני - קטלוג - BP | 134 days | May 18, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 97h | 06.01.BP.01 | בעבודה |  | parent | קטיה |  | BP | NA | As Soon As Possible | 5
4912 |  | Auto Scheduled | Sub Tasks | 57 days | September 2, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 57h | 06.01.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4913 |  | Auto Scheduled | כתיבת מסמך | 6 days | September 2, 2021 8:00 AM | September 9, 2021 5:00 PM | 0 |  | 6h | 06.01.BP.01.01.20 | בתהליך |  | MoM |  |  | BP | NA | Must Start On | 7
4914 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 9 days | September 10, 2021 8:00 AM | September 22, 2021 5:00 PM | 0 | 4913 | 9h | 06.01.BP.01.01.21 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4915 |  | Auto Scheduled | אישור אבי | 5 days | September 23, 2021 8:00 AM | September 29, 2021 5:00 PM | 0 | 4914 | 5h | 06.01.BP.01.01.22 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4916 |  | Auto Scheduled | אישור המנהלת | 5 days | September 30, 2021 8:00 AM | October 6, 2021 5:00 PM | 0 | 4915 | 5h | 06.01.BP.01.01.23 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4917 |  | Auto Scheduled | אישור מפקדת | 3 days | October 7, 2021 8:00 AM | October 11, 2021 5:00 PM | 0 | 4916 | 3h | 06.01.BP.01.01.24 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4918 |  | Auto Scheduled | אישור חטלו"ג | 4 days | October 12, 2021 8:00 AM | October 15, 2021 5:00 PM | 0 | 4917 | 4h | 06.01.BP.01.01.25 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4919 |  | Auto Scheduled | אישור מקל"ר | 2 days | October 18, 2021 8:00 AM | October 19, 2021 5:00 PM | 0 | 4918 | 2h | 06.01.BP.01.01.26 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4920 |  | Auto Scheduled | אישור ניר בשן | 22 days | October 20, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 4919 | 22h | 06.01.BP.01.01.27 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4921 |  | Auto Scheduled | אישור שגיב שרביט | 1 day | November 19, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 | 4920 | 1h | 06.01.BP.01.01.28 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4922 |  | Auto Scheduled | LifeCycle Tasks | 134 days | May 18, 2021 8:00 AM | November 19, 2021 5:00 PM | 0 |  | 40h | 06.01.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4923 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | November 19, 2021 5:00 PM | November 19, 2021 5:00 PM | 0 | 4921 | 0h | 06.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4924 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 06.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4925 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4924 | 10h | 06.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4926 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4925 | 5h | 06.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4927 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4926 | 10h | 06.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4928 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4927 | 10h | 06.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4929 |  | Auto Scheduled | בחתימה | 0 days | November 19, 2021 5:00 PM | November 19, 2021 5:00 PM | 0 | 4928,4923 | 0h | 06.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4930 |  | Auto Scheduled | חתום | 0 days | November 19, 2021 5:00 PM | November 19, 2021 5:00 PM | 0 | 4929 | 0h | 06.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4931 |  | Auto Scheduled | 06.02: ממשק נתוני קטלוג לזכיין | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 95h | 06.02 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
4932 |  | Auto Scheduled | 06.02: ממשק נתוני קטלוג לזכיין.BP | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 95h | 06.02.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4933 |  | Auto Scheduled | 06.02: ממשק נתוני קטלוג לזכיין - BP | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 95h | 06.02.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
4934 |  | Auto Scheduled | Sub Tasks | 55 days | November 2, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 55h | 06.02.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4935 |  | Auto Scheduled | כתיבת מסמך | 4 days | November 2, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 |  | 4h | 06.02.BP.01.01.20 | בתהליך |  | MoM |  |  | BP | NA | Must Start On | 7
4936 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 9 days | November 8, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 4935 | 9h | 06.02.BP.01.01.21 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4937 |  | Auto Scheduled | אישור אבי | 5 days | November 19, 2021 8:00 AM | November 25, 2021 5:00 PM | 0 | 4936 | 5h | 06.02.BP.01.01.22 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4938 |  | Auto Scheduled | אישור המנהלת | 5 days | November 26, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 4937 | 5h | 06.02.BP.01.01.23 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4939 |  | Auto Scheduled | אישור מפקדת | 3 days | December 3, 2021 8:00 AM | December 7, 2021 5:00 PM | 0 | 4938 | 3h | 06.02.BP.01.01.24 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4940 |  | Auto Scheduled | אישור חטלו"ג | 4 days | December 8, 2021 8:00 AM | December 13, 2021 5:00 PM | 0 | 4939 | 4h | 06.02.BP.01.01.25 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4941 |  | Auto Scheduled | אישור מקל"ר | 2 days | December 14, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 4940 | 2h | 06.02.BP.01.01.26 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4942 |  | Auto Scheduled | אישור ניר בשן | 22 days | December 16, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 4941 | 22h | 06.02.BP.01.01.27 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4943 |  | Auto Scheduled | אישור שגיב שרביט | 1 day | January 17, 2022 8:00 AM | January 17, 2022 5:00 PM | 0 | 4942 | 1h | 06.02.BP.01.01.28 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4944 |  | Auto Scheduled | LifeCycle Tasks | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 40h | 06.02.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4945 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4943 | 0h | 06.02.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4946 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 06.02.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4947 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4946 | 10h | 06.02.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4948 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4947 | 5h | 06.02.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4949 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4948 | 10h | 06.02.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4950 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4949 | 10h | 06.02.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4951 |  | Auto Scheduled | בחתימה | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4950,4945 | 0h | 06.02.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4952 |  | Auto Scheduled | חתום | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4951 | 0h | 06.02.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4953 |  | Auto Scheduled | 06.03: שינויים במערכות הקטלוג | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 95h | 06.03 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
4954 |  | Auto Scheduled | 06.03: שינויים במערכות הקטלוג.BP | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 95h | 06.03.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4955 |  | Auto Scheduled | 06.03: שינויים במערכות הקטלוג - BP | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 95h | 06.03.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
4956 |  | Auto Scheduled | Sub Tasks | 55 days | November 2, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 55h | 06.03.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4957 |  | Auto Scheduled | כתיבת מסמך | 4 days | November 2, 2021 8:00 AM | November 5, 2021 5:00 PM | 0 |  | 4h | 06.03.BP.01.01.20 | בתהליך |  | MoM |  |  | BP | NA | Must Start On | 7
4958 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 9 days | November 8, 2021 8:00 AM | November 18, 2021 5:00 PM | 0 | 4957 | 9h | 06.03.BP.01.01.21 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4959 |  | Auto Scheduled | אישור אבי | 5 days | November 19, 2021 8:00 AM | November 25, 2021 5:00 PM | 0 | 4958 | 5h | 06.03.BP.01.01.22 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4960 |  | Auto Scheduled | אישור המנהלת | 5 days | November 26, 2021 8:00 AM | December 2, 2021 5:00 PM | 0 | 4959 | 5h | 06.03.BP.01.01.23 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4961 |  | Auto Scheduled | אישור מפקדת | 3 days | December 3, 2021 8:00 AM | December 7, 2021 5:00 PM | 0 | 4960 | 3h | 06.03.BP.01.01.24 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4962 |  | Auto Scheduled | אישור חטלו"ג | 4 days | December 8, 2021 8:00 AM | December 13, 2021 5:00 PM | 0 | 4961 | 4h | 06.03.BP.01.01.25 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4963 |  | Auto Scheduled | אישור מקל"ר | 2 days | December 14, 2021 8:00 AM | December 15, 2021 5:00 PM | 0 | 4962 | 2h | 06.03.BP.01.01.26 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4964 |  | Auto Scheduled | אישור ניר בשן | 22 days | December 16, 2021 8:00 AM | January 14, 2022 5:00 PM | 0 | 4963 | 22h | 06.03.BP.01.01.27 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4965 |  | Auto Scheduled | אישור שגיב שרביט | 1 day | January 17, 2022 8:00 AM | January 17, 2022 5:00 PM | 0 | 4964 | 1h | 06.03.BP.01.01.28 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4966 |  | Auto Scheduled | LifeCycle Tasks | 175 days | May 18, 2021 8:00 AM | January 17, 2022 5:00 PM | 0 |  | 40h | 06.03.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4967 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4965 | 0h | 06.03.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4968 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 06.03.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4969 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4968 | 10h | 06.03.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4970 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4969 | 5h | 06.03.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4971 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4970 | 10h | 06.03.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4972 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4971 | 10h | 06.03.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4973 |  | Auto Scheduled | בחתימה | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4972,4967 | 0h | 06.03.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4974 |  | Auto Scheduled | חתום | 0 days | January 17, 2022 5:00 PM | January 17, 2022 5:00 PM | 0 | 4973 | 0h | 06.03.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4975 |  | Auto Scheduled | 07: הובלה | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 110h | 07 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
4976 |  | Auto Scheduled | 07.01: הזמנת הובלה | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 110h | 07.01 | ממתין לאישור |  | hd | יורם |  | BP | NA | As Soon As Possible | 3
4977 |  | Auto Scheduled | 07.01: הזמנת הובלה.BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 80h | 07.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4978 |  | Auto Scheduled | 07.01: הזמנת הובלה - BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 80h | 07.01.BP.01 | ממתין לאישור |  | parent | יורם |  | BP | NA | As Soon As Possible | 5
4979 |  | Auto Scheduled | Sub Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 07.01.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
4980 |  | Auto Scheduled | כתיבת מסמך | 11 days | May 18, 2021 8:00 AM | June 1, 2021 5:00 PM | 0 |  | 11h | 07.01.BP.01.01.20 | בוצע |  | MoM |  |  | BP | NA | Must Start On | 7
4981 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 5 days | June 2, 2021 8:00 AM | June 8, 2021 5:00 PM | 0 | 4980 | 5h | 07.01.BP.01.01.21 | בוצע |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4982 |  | Auto Scheduled | אישור אבי | 10 days | June 9, 2021 8:00 AM | June 22, 2021 5:00 PM | 0 | 4981 | 10h | 07.01.BP.01.01.22 | בתהליך |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4983 |  | Auto Scheduled | אישור המנהלת | 2 days | June 23, 2021 8:00 AM | June 24, 2021 5:00 PM | 0 | 4982 | 2h | 07.01.BP.01.01.23 | בתהליך |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4984 |  | Auto Scheduled | אישור מפקדת | 2 days | June 25, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4983 | 2h | 07.01.BP.01.01.24 | בתהליך |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4985 |  | Auto Scheduled | אישור חטלו"ג | 2 days | June 29, 2021 8:00 AM | June 30, 2021 5:00 PM | 0 | 4984 | 2h | 07.01.BP.01.01.25 | בתהליך |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4986 |  | Auto Scheduled | אישור מקל"ר | 2 days | July 1, 2021 8:00 AM | July 2, 2021 5:00 PM | 0 | 4985 | 2h | 07.01.BP.01.01.26 | בתהליך |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4987 |  | Auto Scheduled | אישור ניר בשן | 3 days | July 5, 2021 8:00 AM | July 7, 2021 5:00 PM | 0 | 4986 | 3h | 07.01.BP.01.01.27 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4988 |  | Auto Scheduled | אישור שגיב שרביט | 3 days | July 8, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4987 | 3h | 07.01.BP.01.01.28 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
4989 |  | Auto Scheduled | LifeCycle Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 07.01.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
4990 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4988 | 0h | 07.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4991 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 07.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4992 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 4991 | 10h | 07.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4993 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 4992 | 5h | 07.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4994 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 4993 | 10h | 07.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4995 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 4994 | 10h | 07.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4996 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4995,4990 | 0h | 07.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4997 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 4996 | 0h | 07.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
4998 |  | Auto Scheduled | 07.01: הזמנת הובלה.GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 07.01.GEN |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
4999 |  | Auto Scheduled | אפיון חוקת ההפצה - GEN | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 07.01.GEN.01 | טרם החל |  | parent |  | tasks | GEN | NA | As Soon As Possible | 5
5000 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 07.01.GEN.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5001 |  | Auto Scheduled | LifeCycle Tasks | 30 days | May 18, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 |  | 30h | 07.01.GEN.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5002 |  | Auto Scheduled | סיום משימות משנה למשימה הראשית | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 07.01.GEN.01.02.01 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
5003 |  | Auto Scheduled | טרם החל | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 | 5002 | 10h | 07.01.GEN.01.02.02 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
5004 |  | Auto Scheduled | משימה בעבודה | 20 days | June 1, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5003 | 20h | 07.01.GEN.01.02.03 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
5005 |  | Auto Scheduled | משימה בוצעה במלואה | 0 days | June 28, 2021 5:00 PM | June 28, 2021 5:00 PM | 0 | 5004,5002 | 0h | 07.01.GEN.01.02.04 |  |  | rule |  |  | GEN | NA | As Soon As Possible | 7
5006 |  | Auto Scheduled | 10: רחבי | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 470h | 10 |  |  | hd_domain |  |  |  | NA | As Soon As Possible | 2
5007 |  | Auto Scheduled | 10.01: ממשק עיתוד | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.01 | בעבודה |  | hd | מוריה |  | BP | NA | As Soon As Possible | 3
5008 |  | Auto Scheduled | 10.01: ממשק עיתוד.BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.01.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5009 |  | Auto Scheduled | 10.01: ממשק עיתוד - BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.01.BP.01 | בעבודה |  | parent | מוריה |  | BP | NA | As Soon As Possible | 5
5010 |  | Auto Scheduled | Sub Tasks | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 10.01.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5011 |  | Auto Scheduled | כתיבת מסמך | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 10.01.BP.01.01.20 | טרם החל |  | MoM |  |  | BP | NA | Must Start On | 7
5012 |  | Auto Scheduled | LifeCycle Tasks | 252 days | July 23, 2020 5:00 PM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.01.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5013 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 23, 2020 5:00 PM | July 23, 2020 5:00 PM | 0 | 5011 | 0h | 10.01.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5014 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.01.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5015 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5014 | 10h | 10.01.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5016 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5015 | 5h | 10.01.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5017 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5016 | 10h | 10.01.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5018 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5017 | 10h | 10.01.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5019 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5018,5013 | 0h | 10.01.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5020 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5019 | 0h | 10.01.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5021 |  | Auto Scheduled | 10.02: ממשק יהלום - שובל | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.02 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
5022 |  | Auto Scheduled | 10.02: ממשק יהלום - שובל.BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.02.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5023 |  | Auto Scheduled | 10.02: ממשק יהלום - שובל - BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.02.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
5024 |  | Auto Scheduled | Sub Tasks | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 10.02.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5025 |  | Auto Scheduled | כתיבת מסמך | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 10.02.BP.01.01.20 | טרם החל |  | MoM |  |  | BP | NA | Must Start On | 7
5026 |  | Auto Scheduled | LifeCycle Tasks | 252 days | July 23, 2020 5:00 PM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.02.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5027 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 23, 2020 5:00 PM | July 23, 2020 5:00 PM | 0 | 5025 | 0h | 10.02.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5028 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.02.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5029 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5028 | 10h | 10.02.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5030 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5029 | 5h | 10.02.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5031 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5030 | 10h | 10.02.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5032 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5031 | 10h | 10.02.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5033 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5032,5027 | 0h | 10.02.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5034 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5033 | 0h | 10.02.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5035 |  | Auto Scheduled | 10.03: הרשאות | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.03 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
5036 |  | Auto Scheduled | 10.03: הרשאות.BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.03.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5037 |  | Auto Scheduled | 10.03: הרשאות - BP | 282 days | June 12, 2020 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 70h | 10.03.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
5038 |  | Auto Scheduled | Sub Tasks | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 10.03.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5039 |  | Auto Scheduled | כתיבת מסמך | 30 days | June 12, 2020 8:00 AM | July 23, 2020 5:00 PM | 0 |  | 30h | 10.03.BP.01.01.20 | טרם החל |  | MoM |  |  | BP | NA | Must Start On | 7
5040 |  | Auto Scheduled | LifeCycle Tasks | 252 days | July 23, 2020 5:00 PM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.03.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5041 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | July 23, 2020 5:00 PM | July 23, 2020 5:00 PM | 0 | 5039 | 0h | 10.03.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5042 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.03.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5043 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5042 | 10h | 10.03.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5044 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5043 | 5h | 10.03.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5045 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5044 | 10h | 10.03.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5046 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5045 | 10h | 10.03.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5047 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5046,5041 | 0h | 10.03.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5048 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5047 | 0h | 10.03.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5049 |  | Auto Scheduled | 10.04: BW | 96 days | March 1, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 78h | 10.04 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
5050 |  | Auto Scheduled | 10.04: BW.BP | 96 days | March 1, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 78h | 10.04.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5051 |  | Auto Scheduled | 10.04: BW - BP | 96 days | March 1, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 78h | 10.04.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
5052 |  | Auto Scheduled | Sub Tasks | 38 days | March 1, 2021 8:00 AM | April 21, 2021 5:00 PM | 0 |  | 38h | 10.04.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5053 |  | Auto Scheduled | כתיבת מסמך | 10 days | March 1, 2021 8:00 AM | March 12, 2021 5:00 PM | 0 |  | 10h | 10.04.BP.01.01.20 | בתהליך |  | MoM |  |  | BP | NA | Must Start On | 7
5054 |  | Auto Scheduled | תיקוף מסמך אמל"ח | 10 days | March 15, 2021 8:00 AM | March 26, 2021 5:00 PM | 0 | 5053 | 10h | 10.04.BP.01.01.21 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5055 |  | Auto Scheduled | אישור אבי | 3 days | March 29, 2021 8:00 AM | March 31, 2021 5:00 PM | 0 | 5054 | 3h | 10.04.BP.01.01.22 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5056 |  | Auto Scheduled | אישור המנהלת | 4 days | April 1, 2021 8:00 AM | April 6, 2021 5:00 PM | 0 | 5055 | 4h | 10.04.BP.01.01.23 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5057 |  | Auto Scheduled | אישור מפקדת | 2 days | April 7, 2021 8:00 AM | April 8, 2021 5:00 PM | 0 | 5056 | 2h | 10.04.BP.01.01.24 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5058 |  | Auto Scheduled | אישור חטלו"ג | 2 days | April 9, 2021 8:00 AM | April 12, 2021 5:00 PM | 0 | 5057 | 2h | 10.04.BP.01.01.25 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5059 |  | Auto Scheduled | אישור מקל"ר | 2 days | April 13, 2021 8:00 AM | April 14, 2021 5:00 PM | 0 | 5058 | 2h | 10.04.BP.01.01.26 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5060 |  | Auto Scheduled | אישור ניר בשן | 2 days | April 15, 2021 8:00 AM | April 16, 2021 5:00 PM | 0 | 5059 | 2h | 10.04.BP.01.01.27 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5061 |  | Auto Scheduled | אישור שגיב שרביט | 3 days | April 19, 2021 8:00 AM | April 21, 2021 5:00 PM | 0 | 5060 | 3h | 10.04.BP.01.01.28 | טרם החל |  | MoM |  |  | BP | NA | As Soon As Possible | 7
5062 |  | Auto Scheduled | LifeCycle Tasks | 58 days | April 21, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.04.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5063 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | April 21, 2021 5:00 PM | April 21, 2021 5:00 PM | 0 | 5061 | 0h | 10.04.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5064 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.04.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5065 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5064 | 10h | 10.04.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5066 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5065 | 5h | 10.04.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5067 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5066 | 10h | 10.04.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5068 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5067 | 10h | 10.04.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5069 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5068,5063 | 0h | 10.04.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5070 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5069 | 0h | 10.04.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5071 |  | Auto Scheduled | 10.05: ZMEATED | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 71h | 10.05 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
5072 |  | Auto Scheduled | 10.05: ZMEATED.BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 71h | 10.05.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5073 |  | Auto Scheduled | 10.05: ZMEATED - BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 71h | 10.05.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
5074 |  | Auto Scheduled | Sub Tasks | 31 days | May 18, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 |  | 31h | 10.05.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5075 |  | Auto Scheduled | כתיבת מסמך | 31 days | May 18, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 |  | 31h | 10.05.BP.01.01.20 | טרם החל |  | MoM |  |  | BP | NA | Must Start On | 7
5076 |  | Auto Scheduled | LifeCycle Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.05.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5077 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | June 29, 2021 5:00 PM | June 29, 2021 5:00 PM | 0 | 5075 | 0h | 10.05.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5078 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.05.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5079 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5078 | 10h | 10.05.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5080 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5079 | 5h | 10.05.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5081 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5080 | 10h | 10.05.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5082 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5081 | 10h | 10.05.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5083 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5082,5077 | 0h | 10.05.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5084 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5083 | 0h | 10.05.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5085 |  | Auto Scheduled | 10.06: POD | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 71h | 10.06 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
5086 |  | Auto Scheduled | 10.06: POD.BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 71h | 10.06.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5087 |  | Auto Scheduled | 10.06: POD - BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 71h | 10.06.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
5088 |  | Auto Scheduled | Sub Tasks | 31 days | May 18, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 |  | 31h | 10.06.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5089 |  | Auto Scheduled | כתיבת מסמך | 31 days | May 18, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 |  | 31h | 10.06.BP.01.01.20 | טרם החל |  | MoM |  |  | BP | NA | Must Start On | 7
5090 |  | Auto Scheduled | LifeCycle Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.06.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5091 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | June 29, 2021 5:00 PM | June 29, 2021 5:00 PM | 0 | 5089 | 0h | 10.06.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5092 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.06.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5093 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5092 | 10h | 10.06.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5094 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5093 | 5h | 10.06.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5095 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5094 | 10h | 10.06.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5096 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5095 | 10h | 10.06.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5097 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5096,5091 | 0h | 10.06.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5098 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5097 | 0h | 10.06.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5099 |  | Auto Scheduled | 10.07: מורשי כניסה | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.07 | בעבודה |  | hd |  |  | BP | NA | As Soon As Possible | 3
5100 |  | Auto Scheduled | 10.07: מורשי כניסה.BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.07.BP |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5101 |  | Auto Scheduled | 10.07: מורשי כניסה - BP | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.07.BP.01 | בעבודה |  | parent |  |  | BP | NA | As Soon As Possible | 5
5102 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 10.07.BP.01.01 |  |  | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5103 |  | Auto Scheduled | LifeCycle Tasks | 40 days | May 18, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 |  | 40h | 10.07.BP.01.02 |  |  | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5104 |  | Auto Scheduled | סיום משימות בלו-פרינט | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | 10.07.BP.01.02.01 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5105 |  | Auto Scheduled | טרם החל | 5 days | May 18, 2021 8:00 AM | May 24, 2021 5:00 PM | 0 |  | 5h | 10.07.BP.01.02.02 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5106 |  | Auto Scheduled | בעבודה | 10 days | May 25, 2021 8:00 AM | June 7, 2021 5:00 PM | 0 | 5105 | 10h | 10.07.BP.01.02.03 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5107 |  | Auto Scheduled | ממתין להצגה | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5106 | 5h | 10.07.BP.01.02.04 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5108 |  | Auto Scheduled | סיכום מסמך | 10 days | June 15, 2021 8:00 AM | June 28, 2021 5:00 PM | 0 | 5107 | 10h | 10.07.BP.01.02.05 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5109 |  | Auto Scheduled | ממתין לאישור | 10 days | June 29, 2021 8:00 AM | July 12, 2021 5:00 PM | 0 | 5108 | 10h | 10.07.BP.01.02.06 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5110 |  | Auto Scheduled | בחתימה | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5109,5104 | 0h | 10.07.BP.01.02.07 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5111 |  | Auto Scheduled | חתום | 0 days | July 12, 2021 5:00 PM | July 12, 2021 5:00 PM | 0 | 5110 | 0h | 10.07.BP.01.02.08 |  |  | rule |  |  | BP | NA | As Soon As Possible | 7
5112 |  | Auto Scheduled | ניהול הממשקים | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 11,165h | I-00 | [6 empty] | NA | As Soon As Possible | 2
5113 |  | Auto Scheduled | I-01.01: ממשק קבלה למלאי | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.01 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5114 |  | Auto Scheduled | I-01.01: ממשק קבלה למלאי.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.01.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5115 |  | Auto Scheduled | מערכת ה- WMS ומערכת תיאום ההספקות יקבלו בממשק אוטומטי ממערכת ה- ERP, את כל נתוני הספקים ומאפייניהם, כפי שיהיו קיימים במערכת ה- ERP, לרבות סוג הספק, פרטי הקשר, מאפייני התקשרות של המזמין עם הספק ופרטים נוספים, כפי שיאופיינו באפיון המפורט. - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.01.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5116 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.01.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5117 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.01.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5118 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 142,153,164,175,186,197,208,219,230,241,252,263,274,285 | 0h | I-01.01.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5119 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.01.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5120 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.01.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5121 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5120 | 10h | I-01.01.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5122 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5121 | 1h | I-01.01.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5123 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.01.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5124 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5122 | 10h | I-01.01.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5125 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5124 | 10h | I-01.01.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5126 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5125 | 1h | I-01.01.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5127 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5126 | 21h | I-01.01.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5128 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5127 | 21h | I-01.01.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5129 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5128 | 5h | I-01.01.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5130 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5129 | 21h | I-01.01.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5131 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5130 | 15h | I-01.01.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5132 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5131 | 10h | I-01.01.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5133 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5132,5129 | 10h | I-01.01.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5134 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5133,5118 | 0h | I-01.01.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5135 |  | Auto Scheduled | I-01.02: תיאום אספקות יוצאות | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.02 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5136 |  | Auto Scheduled | I-01.02: תיאום אספקות יוצאות.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.02.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5137 |  | Auto Scheduled | מערכת ה- WMS ומערכת ה- TMS תקבלנה בממשק אוטומטי ממערכת ה- ERP, את כל נתוני הלקוחות ומאפייניהם, כפי שיהיו קיימים במערכת ה- ERP, לרבות סוג הלקוח, דרישות למאפייני יחידות ניטול באספקה, הערות לבקרה ואריזה בהפצה, מגבלות לליקוט ואריזה של הזמנות, כתובות, אנשי קש | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.02.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5138 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.02.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5139 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.02.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5140 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 3388,3399,3410,3421,3432,3443,3454,3465,3476,3487,3498,3509,3520,3758,3769,4042,4153,4164,4175,4186,4197,4208,4219,4459,4470,4481,4492,4503,4514,4810,4821 | 0h | I-01.02.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5141 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.02.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5142 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.02.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5143 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5142 | 10h | I-01.02.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5144 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5143 | 1h | I-01.02.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5145 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.02.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5146 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5144 | 10h | I-01.02.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5147 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5146 | 10h | I-01.02.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5148 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5147 | 1h | I-01.02.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5149 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5148 | 21h | I-01.02.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5150 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5149 | 21h | I-01.02.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5151 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5150 | 5h | I-01.02.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5152 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5151 | 21h | I-01.02.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5153 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5152 | 15h | I-01.02.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5154 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5153 | 10h | I-01.02.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5155 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5154,5151 | 10h | I-01.02.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5156 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5155,5140 | 0h | I-01.02.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5157 |  | Auto Scheduled | I-01.03: תכנון ושליטה בהפצה | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.03 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5158 |  | Auto Scheduled | I-01.03: תכנון ושליטה בהפצה.INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.03.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5159 |  | Auto Scheduled | מערכת ה- TMS תקבל בממשק אוטומטי ממערכת ה- ERP/מערכת ההובלה, את כל הנתונים הנדרשים לצורך תכנון ההפצה, לרבות סוגי הפלטפורמות להפצה, נתוני נפח ומשקל העמסה מותר לפלטפורמות ההפצה, צירי נסיעה, מגבלות צירי נסיעה, בתצורה שתהיה קיימת במערכת ה- ERP/מערכת ההובלה בע | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.03.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5160 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.03.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5161 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.03.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5162 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.03.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5163 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.03.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5164 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.03.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5165 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5164 | 10h | I-01.03.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5166 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5165 | 1h | I-01.03.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5167 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.03.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5168 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5166 | 10h | I-01.03.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5169 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5168 | 10h | I-01.03.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5170 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5169 | 1h | I-01.03.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5171 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5170 | 21h | I-01.03.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5172 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5171 | 21h | I-01.03.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5173 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5172 | 5h | I-01.03.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5174 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5173 | 21h | I-01.03.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5175 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5174 | 15h | I-01.03.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5176 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5175 | 10h | I-01.03.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5177 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5176,5173 | 10h | I-01.03.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5178 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5177,5162 | 0h | I-01.03.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5179 |  | Auto Scheduled | I-01.04: ממשק צפי אספקה נכנסת ומשלוח | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.04 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5180 |  | Auto Scheduled | I-01.04: ממשק צפי אספקה נכנסת ומשלוח.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.04.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5181 |  | Auto Scheduled | מערכת ה- WMS תקבל בממשק אוטומטי ממערכת ה- ERP את נתוני צפי האספקה הנכנסת והמשלוח לרבות נתוני הספק, רכב, נהג, תאריך אספקה מבוקש, תכולת המשלוח – פריטים, כמות, יחידות ניטול ומארזים, סטאטוס המלאי/אצווה, הוראות קליטה וכל נתון נוסף אשר יידרש לקבלת המלאי באופן | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.04.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5182 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.04.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5183 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.04.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5184 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 142,153,164,175,186,197,208,219,230,241,252,263,274,2824,2835,285,3758,3769,4042,4153,4164,4175,4186,4197,4208,4219 | 0h | I-01.04.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5185 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.04.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5186 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.04.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5187 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5186 | 10h | I-01.04.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5188 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5187 | 1h | I-01.04.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5189 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.04.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5190 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5188 | 10h | I-01.04.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5191 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5190 | 10h | I-01.04.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5192 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5191 | 1h | I-01.04.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5193 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5192 | 21h | I-01.04.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5194 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5193 | 21h | I-01.04.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5195 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5194 | 5h | I-01.04.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5196 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5195 | 21h | I-01.04.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5197 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5196 | 15h | I-01.04.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5198 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5197 | 10h | I-01.04.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5199 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5198,5195 | 10h | I-01.04.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5200 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5199,5184 | 0h | I-01.04.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5201 |  | Auto Scheduled | I-01.05: הזמנות/אספקה נכנסת | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.05 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5202 |  | Auto Scheduled | I-01.05: הזמנות/אספקה נכנסת.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.05.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5203 |  | Auto Scheduled | נתוני ספקים והזמנות - קבלה בממשק אוטומטי ממערכת ה- ERP של נתוני הספקים וההזמנות כגון: מספר הזמנה, תכולת ההזמנה, מועד אספקה אחרון וכד', ויציג לספקים את ההזמנות (לכל ספק תוצגנה ההזמנות הרלבנטיות). - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.05.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5204 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.05.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5205 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.05.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5206 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 142,153,164,175,186,197,208,219,230,241,252,263,274,285,3758,3769,4042,4153,4164,4175,4186,4197,4208,4219 | 0h | I-01.05.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5207 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.05.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5208 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.05.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5209 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5208 | 10h | I-01.05.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5210 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5209 | 1h | I-01.05.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5211 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.05.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5212 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5210 | 10h | I-01.05.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5213 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5212 | 10h | I-01.05.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5214 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5213 | 1h | I-01.05.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5215 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5214 | 21h | I-01.05.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5216 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5215 | 21h | I-01.05.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5217 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5216 | 5h | I-01.05.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5218 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5217 | 21h | I-01.05.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5219 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5218 | 15h | I-01.05.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5220 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5219 | 10h | I-01.05.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5221 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5220,5217 | 10h | I-01.05.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5222 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5221,5206 | 0h | I-01.05.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5223 |  | Auto Scheduled | I-01.06: פעולות ערך מוסף | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.06 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5224 |  | Auto Scheduled | I-01.06: פעולות ערך מוסף.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.06.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5225 |  | Auto Scheduled | באמצעות ממשק אוטומטי ממערכת ה- ERP לרבות בממשק הוראות אריזה, ממשק מדיניות תחזוקה, ממשק מפרט בדיקה, ממשק מנת בדיקה ובממשק האספקה הנכנסת והיוצאת. - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.06.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5226 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.06.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5227 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.06.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5228 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 1150,1161,1172,1406,1417,1428,1439,2358,2369,2501,2512,2523,2534,2545,2824,2835,4459,4470,4481,4492,4503,4514,678,689,700,711,722,733,744,755,766,777 | 0h | I-01.06.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5229 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.06.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5230 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.06.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5231 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5230 | 10h | I-01.06.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5232 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5231 | 1h | I-01.06.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5233 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.06.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5234 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5232 | 10h | I-01.06.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5235 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5234 | 10h | I-01.06.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5236 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5235 | 1h | I-01.06.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5237 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5236 | 21h | I-01.06.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5238 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5237 | 21h | I-01.06.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5239 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5238 | 5h | I-01.06.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5240 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5239 | 21h | I-01.06.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5241 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5240 | 15h | I-01.06.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5242 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5241 | 10h | I-01.06.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5243 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5242,5239 | 10h | I-01.06.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5244 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5243,5228 | 0h | I-01.06.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5245 |  | Auto Scheduled | I-01.07: יצירה ופירוק ערכות (קיטים) | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5246 |  | Auto Scheduled | I-01.07: יצירה ופירוק ערכות (קיטים) | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5247 |  | Auto Scheduled | I-01.07: יצירה ופירוק ערכות (קיטים) | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 435h | I-01.07 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5248 |  | Auto Scheduled | I-01.07: יצירה ופירוק ערכות (קיטים).INT_Main | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 435h | I-01.07.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5249 |  | Auto Scheduled | מערכת ה- WMS תקבל בממשק אוטומטי ממערכת ה- ERP את עצי המוצר המנחים כיצד ליצור את הערכות. - INT_Main | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 145h | I-01.07.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5250 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5251 |  | Auto Scheduled | LifeCycle Tasks | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 145h | I-01.07.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5252 |  | Auto Scheduled | Interface Milestone | 0 days | January 17, 2023 5:00 PM | January 17, 2023 5:00 PM | 0 | 1150,1161,1172,2358,2369,2824,2835,678,689,700,711,722,733,744,755,766,777 | 0h | I-01.07.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5253 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.07.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5254 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.07.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5255 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5254 | 10h | I-01.07.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5256 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5255 | 1h | I-01.07.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5257 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.07.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5258 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5256 | 10h | I-01.07.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5259 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5258 | 10h | I-01.07.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5260 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5259 | 1h | I-01.07.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5261 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5260 | 21h | I-01.07.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5262 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5261 | 21h | I-01.07.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5263 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5262 | 5h | I-01.07.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5264 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5263 | 21h | I-01.07.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5265 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5264 | 15h | I-01.07.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5266 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5265 | 10h | I-01.07.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5267 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5266,5263 | 10h | I-01.07.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5268 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | January 17, 2023 5:00 PM | January 17, 2023 5:00 PM | 0 | 5267,5252 | 0h | I-01.07.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5269 |  | Auto Scheduled | מערכת ה- WMS תשלח בממשק אוטומטי למערכת ה- ERP את המק"טים/סדרות/מס"דים שנופקו בפועל. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.07.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5270 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5271 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.07.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5272 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5273 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.07.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5274 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.07.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5275 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5274 | 10h | I-01.07.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5276 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5275 | 1h | I-01.07.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5277 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.07.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5278 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5276 | 10h | I-01.07.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5279 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5278 | 10h | I-01.07.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5280 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5279 | 1h | I-01.07.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5281 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5280 | 21h | I-01.07.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5282 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5281 | 21h | I-01.07.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5283 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5282 | 5h | I-01.07.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5284 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5283 | 21h | I-01.07.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5285 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5284 | 15h | I-01.07.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5286 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5285 | 10h | I-01.07.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5287 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5286,5283 | 10h | I-01.07.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5288 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5287,5272 | 0h | I-01.07.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5289 |  | Auto Scheduled | מערכת ה- WMS תשלח בממשק אוטומטי למערכת ה- ERP את הכמויות שהתקבלו למלאי (לרבות מצב שבו הכמות הסופית של הקיטים שנוצרה אינה הכמות הצפויה), וכן את סיום הפעילות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.07.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5290 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5291 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.07.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5292 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.07.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5293 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.07.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5294 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.07.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5295 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5294 | 10h | I-01.07.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5296 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5295 | 1h | I-01.07.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5297 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.07.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5298 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5296 | 10h | I-01.07.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5299 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5298 | 10h | I-01.07.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5300 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5299 | 1h | I-01.07.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5301 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5300 | 21h | I-01.07.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5302 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5301 | 21h | I-01.07.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5303 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5302 | 5h | I-01.07.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5304 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5303 | 21h | I-01.07.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5305 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5304 | 15h | I-01.07.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5306 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5305 | 10h | I-01.07.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5307 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5306,5303 | 10h | I-01.07.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5308 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5307,5292 | 0h | I-01.07.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5309 |  | Auto Scheduled | I-01.08: ממשק ראשי 8 - קבלה למלאי/ בקרת איכות/בחינה/QA | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5310 |  | Auto Scheduled | I-01.08: ממשק ראשי 8 - קבלה למלאי/ בקרת איכות/בחינה/QA | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5311 |  | Auto Scheduled | I-01.08: ממשק ראשי 8 - קבלה למלאי/ בקרת איכות/בחינה/QA | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 435h | I-01.08 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5312 |  | Auto Scheduled | I-01.08: ממשק ראשי 8 - קבלה למלאי/ בקרת איכות/בחינה/QA.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 435h | I-01.08.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5313 |  | Auto Scheduled | מערכת ה- WMS תקבל (בממשק אוטומטי) ממערכת ה- ERP הנחייה ליצירת מנת איכות לאצוות רלבנטיות. - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.08.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5314 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5315 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.08.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5316 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 1150,1161,1172,142,153,164,175,186,197,208,219,230,241,252,263,274,2824,2835,285,3758,3769 | 0h | I-01.08.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5317 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.08.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5318 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.08.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5319 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5318 | 10h | I-01.08.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5320 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5319 | 1h | I-01.08.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5321 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.08.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5322 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5320 | 10h | I-01.08.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5323 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5322 | 10h | I-01.08.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5324 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5323 | 1h | I-01.08.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5325 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5324 | 21h | I-01.08.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5326 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5325 | 21h | I-01.08.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5327 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5326 | 5h | I-01.08.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5328 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5327 | 21h | I-01.08.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5329 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5328 | 15h | I-01.08.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5330 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5329 | 10h | I-01.08.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5331 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5330,5327 | 10h | I-01.08.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5332 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5331,5316 | 0h | I-01.08.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5333 |  | Auto Scheduled | מערכת ה- WMS תקבל (בממשק אוטומטי) ממערכת ה- ERP הנחייה לשינוי סטאטוס המלאי למלאי תחת בקרת איכות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.08.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5334 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5335 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.08.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5336 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5337 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.08.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5338 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.08.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5339 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5338 | 10h | I-01.08.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5340 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5339 | 1h | I-01.08.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5341 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.08.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5342 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5340 | 10h | I-01.08.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5343 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5342 | 10h | I-01.08.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5344 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5343 | 1h | I-01.08.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5345 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5344 | 21h | I-01.08.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5346 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5345 | 21h | I-01.08.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5347 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5346 | 5h | I-01.08.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5348 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5347 | 21h | I-01.08.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5349 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5348 | 15h | I-01.08.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5350 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5349 | 10h | I-01.08.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5351 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5350,5347 | 10h | I-01.08.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5352 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5351,5336 | 0h | I-01.08.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5353 |  | Auto Scheduled | מערכת ה- WMS תקבל את תוצאות מנת האיכות (בממשק אוטומטי) ממערכת ה- ERP ותעדכן את סטאטוס המלאי הרלבנטי בהתאם (מלאי חסום, מלאי בלתי מוגבל, ניפוק לגריטה של הדגימות וכד'), ועדכון לגבי סטאטוס מנת האיכות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.08.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5354 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5355 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.08.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5356 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.08.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5357 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.08.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5358 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.08.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5359 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5358 | 10h | I-01.08.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5360 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5359 | 1h | I-01.08.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5361 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.08.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5362 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5360 | 10h | I-01.08.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5363 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5362 | 10h | I-01.08.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5364 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5363 | 1h | I-01.08.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5365 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5364 | 21h | I-01.08.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5366 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5365 | 21h | I-01.08.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5367 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5366 | 5h | I-01.08.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5368 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5367 | 21h | I-01.08.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5369 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5368 | 15h | I-01.08.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5370 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5369 | 10h | I-01.08.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5371 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5370,5367 | 10h | I-01.08.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5372 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5371,5356 | 0h | I-01.08.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5373 |  | Auto Scheduled | I-01.09: אספקה נכנסת/קבלה למלאי | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5374 |  | Auto Scheduled | I-01.09: אספקה נכנסת/קבלה למלאי | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5375 |  | Auto Scheduled | I-01.09: אספקה נכנסת/קבלה למלאי | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5376 |  | Auto Scheduled | I-01.09: אספקה נכנסת/קבלה למלאי | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5377 |  | Auto Scheduled | I-01.09: אספקה נכנסת/קבלה למלאי | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 725h | I-01.09 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5378 |  | Auto Scheduled | I-01.09: אספקה נכנסת/קבלה למלאי.INT_Main | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 725h | I-01.09.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5379 |  | Auto Scheduled | תהליך החזרות למלאי מלקוחות המרה"ס ייושם במערכת ה- WMS, בהתאם לסעיף זה ולדרישות המפורטות בתהליך אספקה נכנסת. - INT_Main | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5380 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5381 |  | Auto Scheduled | LifeCycle Tasks | 198 days | May 18, 2021 8:00 AM | February 17, 2022 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5382 |  | Auto Scheduled | Interface Milestone | 0 days | February 17, 2022 5:00 PM | February 17, 2022 5:00 PM | 0 | 1150,1161,1172,1406,1417,1428,1439,3758,3769 | 0h | I-01.09.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5383 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5384 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.09.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5385 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5384 | 10h | I-01.09.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5386 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5385 | 1h | I-01.09.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5387 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5388 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5386 | 10h | I-01.09.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5389 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5388 | 10h | I-01.09.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5390 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5389 | 1h | I-01.09.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5391 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5390 | 21h | I-01.09.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5392 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5391 | 21h | I-01.09.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5393 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5392 | 5h | I-01.09.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5394 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5393 | 21h | I-01.09.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5395 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5394 | 15h | I-01.09.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5396 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5395 | 10h | I-01.09.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5397 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5396,5393 | 10h | I-01.09.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5398 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | February 17, 2022 5:00 PM | February 17, 2022 5:00 PM | 0 | 5397,5382 | 0h | I-01.09.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5399 |  | Auto Scheduled | החזרות במערכת ה- WMS יתבצעו על בסיס צפי אספקה נכנסת המתקבל ממערכת ה- ERP מלקוח פנימי, ועל פי הסטאטוס שנקבע באספקה הנכנסת. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5400 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5401 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5402 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5403 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5404 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.09.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5405 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5404 | 10h | I-01.09.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5406 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5405 | 1h | I-01.09.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5407 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5408 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5406 | 10h | I-01.09.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5409 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5408 | 10h | I-01.09.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5410 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5409 | 1h | I-01.09.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5411 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5410 | 21h | I-01.09.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5412 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5411 | 21h | I-01.09.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5413 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5412 | 5h | I-01.09.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5414 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5413 | 21h | I-01.09.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5415 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5414 | 15h | I-01.09.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5416 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5415 | 10h | I-01.09.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5417 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5416,5413 | 10h | I-01.09.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5418 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5417,5402 | 0h | I-01.09.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5419 |  | Auto Scheduled | מערכת ה- WMS תבצע את תהליך הקבלה למלאי בהתאם לפריט, לכמות והסדרה שהתקבלה בפועל, ותשלח בממשק אוטומטי עדכון למערכת ה- ERP לחיוב המלאי במרה"ס וזיכוי הלקוח בהתאם. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5420 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5421 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5422 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5423 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5424 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.09.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5425 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5424 | 10h | I-01.09.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5426 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5425 | 1h | I-01.09.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5427 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5428 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5426 | 10h | I-01.09.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5429 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5428 | 10h | I-01.09.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5430 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5429 | 1h | I-01.09.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5431 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5430 | 21h | I-01.09.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5432 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5431 | 21h | I-01.09.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5433 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5432 | 5h | I-01.09.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5434 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5433 | 21h | I-01.09.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5435 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5434 | 15h | I-01.09.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5436 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5435 | 10h | I-01.09.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5437 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5436,5433 | 10h | I-01.09.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5438 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5437,5422 | 0h | I-01.09.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5439 |  | Auto Scheduled | מערכת ה WMS תאפשר סימון וזיהוי מלאי שהתקבל בהחזרה מלקוחות המרה"ס, באופן אשר יאפשר מעקב ובקרה על המלאי שהתקבל, כך שניתן יהיה להחזירו ללקוח השולח למרה"ס לאחר ביצוע תהליך ערך מוסף, כגון כביסה או תיקון. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.04 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5440 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.04.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5441 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.04.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5442 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.04.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5443 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.04.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5444 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.09.INT_Main.04.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5445 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5444 | 10h | I-01.09.INT_Main.04.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5446 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5445 | 1h | I-01.09.INT_Main.04.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5447 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.04.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5448 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5446 | 10h | I-01.09.INT_Main.04.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5449 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5448 | 10h | I-01.09.INT_Main.04.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5450 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5449 | 1h | I-01.09.INT_Main.04.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5451 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5450 | 21h | I-01.09.INT_Main.04.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5452 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5451 | 21h | I-01.09.INT_Main.04.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5453 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5452 | 5h | I-01.09.INT_Main.04.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5454 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5453 | 21h | I-01.09.INT_Main.04.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5455 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5454 | 15h | I-01.09.INT_Main.04.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5456 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5455 | 10h | I-01.09.INT_Main.04.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5457 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5456,5453 | 10h | I-01.09.INT_Main.04.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5458 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5457,5442 | 0h | I-01.09.INT_Main.04.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5459 |  | Auto Scheduled | בטרם העמסת המלאי על המשאית, מערכת ה- POD תאפשר לנהג לחתום על המלאי שנלקח להחזרה, חתימה זו תעדכן את סטאטוס האספקה הנכנסת ב- ERP, ומערכת ה- WMS תקבל בממשק אוטומטי ממערכת ה- ERP את הסטאטוס המתאים לקליטה. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.05 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5460 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.05.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5461 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.09.INT_Main.05.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5462 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.09.INT_Main.05.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5463 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.05.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5464 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.09.INT_Main.05.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5465 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5464 | 10h | I-01.09.INT_Main.05.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5466 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5465 | 1h | I-01.09.INT_Main.05.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5467 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.09.INT_Main.05.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5468 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5466 | 10h | I-01.09.INT_Main.05.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5469 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5468 | 10h | I-01.09.INT_Main.05.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5470 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5469 | 1h | I-01.09.INT_Main.05.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5471 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5470 | 21h | I-01.09.INT_Main.05.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5472 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5471 | 21h | I-01.09.INT_Main.05.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5473 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5472 | 5h | I-01.09.INT_Main.05.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5474 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5473 | 21h | I-01.09.INT_Main.05.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5475 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5474 | 15h | I-01.09.INT_Main.05.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5476 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5475 | 10h | I-01.09.INT_Main.05.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5477 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5476,5473 | 10h | I-01.09.INT_Main.05.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5478 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5477,5462 | 0h | I-01.09.INT_Main.05.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5479 |  | Auto Scheduled | I-01.10: ניהול מלאי/טיפול בפג"תים | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 145h | I-01.10 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5480 |  | Auto Scheduled | I-01.10: ניהול מלאי/טיפול בפג"תים.INT_Main | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 145h | I-01.10.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5481 |  | Auto Scheduled | המערכת תעדכן את מערכת ה-ERP במק"ט פריט הפגום וכמות המלאי אשר הוגדר לו, לניהול הפריט במחסן פגומים ב ERP. - INT_Main | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 145h | I-01.10.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5482 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.10.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5483 |  | Auto Scheduled | LifeCycle Tasks | 436 days | May 18, 2021 8:00 AM | January 17, 2023 5:00 PM | 0 |  | 145h | I-01.10.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5484 |  | Auto Scheduled | Interface Milestone | 0 days | January 17, 2023 5:00 PM | January 17, 2023 5:00 PM | 0 | 1406,1417,1428,1439,2358,2369,2824,2835,678,689,700,711,722,733,744,755,766,777 | 0h | I-01.10.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5485 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.10.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5486 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.10.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5487 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5486 | 10h | I-01.10.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5488 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5487 | 1h | I-01.10.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5489 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.10.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5490 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5488 | 10h | I-01.10.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5491 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5490 | 10h | I-01.10.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5492 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5491 | 1h | I-01.10.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5493 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5492 | 21h | I-01.10.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5494 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5493 | 21h | I-01.10.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5495 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5494 | 5h | I-01.10.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5496 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5495 | 21h | I-01.10.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5497 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5496 | 15h | I-01.10.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5498 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5497 | 10h | I-01.10.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5499 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5498,5495 | 10h | I-01.10.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5500 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | January 17, 2023 5:00 PM | January 17, 2023 5:00 PM | 0 | 5499,5484 | 0h | I-01.10.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5501 |  | Auto Scheduled | I-01.11: גריטה,החזרה לספקים ומכירת מלאי | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.11 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5502 |  | Auto Scheduled | I-01.11: גריטה,החזרה לספקים ומכירת מלאי.INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.11.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5503 |  | Auto Scheduled | תהליכי גריטה, החזרה לספקים ומכירת מלאי ייושם במערכת ה- WMS, בהתאם לסעיף זה ולדרישות המפורטות בתהליך אספקה יוצאת. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.11.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5504 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.11.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5505 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.11.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5506 |  | Auto Scheduled | Interface Milestone | 0 days | August 30, 2021 5:00 PM | August 30, 2021 5:00 PM | 0 | 4810,4821 | 0h | I-01.11.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5507 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.11.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5508 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.11.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5509 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5508 | 10h | I-01.11.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5510 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5509 | 1h | I-01.11.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5511 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.11.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5512 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5510 | 10h | I-01.11.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5513 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5512 | 10h | I-01.11.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5514 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5513 | 1h | I-01.11.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5515 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5514 | 21h | I-01.11.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5516 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5515 | 21h | I-01.11.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5517 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5516 | 5h | I-01.11.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5518 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5517 | 21h | I-01.11.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5519 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5518 | 15h | I-01.11.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5520 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5519 | 10h | I-01.11.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5521 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5520,5517 | 10h | I-01.11.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5522 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5521,5506 | 0h | I-01.11.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5523 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5524 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5525 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5526 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5527 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5528 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 870h | I-01.12 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5529 |  | Auto Scheduled | I-01.12: הזמנות/אספקה יוצאת.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 870h | I-01.12.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5530 |  | Auto Scheduled | מערכת ה- WMS תקבל (בממשק אוטומטי) ממערכת ה- ERP את הזמנות ה- ERP לרבות הזמנות לקוח והזמנות העברה, הכוללות שורות שבכל אחת מהן פירוט של הפריטים, כמות, סטאטוס, אתר מנפק, נקודת היעד לניפוק, תאריך אספקה נדרש, כושר נדרש, סדרה/אצווה נדרשת ונתונים נוספים אשר ידר | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן | מסמכי המכרז - כרך התקשוב | INT_Main | NA | As Soon As Possible | 5
5531 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5532 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5533 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 2358,2369,2824,2835,3388,3399,3410,3421,3432,3443,3454,3465,3476,3487,3498,3509,3520,4459,4470,4481,4492,4503,4514 | 0h | I-01.12.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5534 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5535 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.12.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5536 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5535 | 10h | I-01.12.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5537 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5536 | 1h | I-01.12.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5538 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5539 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5537 | 10h | I-01.12.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5540 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5539 | 10h | I-01.12.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5541 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5540 | 1h | I-01.12.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5542 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5541 | 21h | I-01.12.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5543 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5542 | 21h | I-01.12.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5544 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5543 | 5h | I-01.12.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5545 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5544 | 21h | I-01.12.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5546 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5545 | 15h | I-01.12.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5547 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5546 | 10h | I-01.12.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5548 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5547,5544 | 10h | I-01.12.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5549 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5548,5533 | 0h | I-01.12.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5550 |  | Auto Scheduled | מערכת ה- WMS תאפשר קבלת הזמנות אשר יסומנו כהזמנות לתכנון בלבד של תוכנית ההפצה. הזמנות אלו לא יהיו ניתנות לשחרור לליקוט כל עוד הסימון של ההזמנה הינו לתכנון בלבד. ניתן יהיה לעדכן את תכולת ההזמנות לרבות פריטים וכמויות, נתוני ההפצה וכו' ולתכנן את ההפצה מחדש | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5551 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5552 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5553 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5554 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5555 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.12.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5556 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5555 | 10h | I-01.12.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5557 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5556 | 1h | I-01.12.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5558 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5559 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5557 | 10h | I-01.12.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5560 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5559 | 10h | I-01.12.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5561 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5560 | 1h | I-01.12.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5562 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5561 | 21h | I-01.12.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5563 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5562 | 21h | I-01.12.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5564 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5563 | 5h | I-01.12.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5565 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5564 | 21h | I-01.12.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5566 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5565 | 15h | I-01.12.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5567 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5566 | 10h | I-01.12.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5568 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5567,5564 | 10h | I-01.12.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5569 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5568,5553 | 0h | I-01.12.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5570 |  | Auto Scheduled | מערכת ה- WMS תקבל (בממשק אוטומטי) ממערכת ה- ERP עדכון של ההזמנות בהיבט הכמויות הנדרשות לפריט, ביטול, החלפה או הוספה של פריטים, ותאפשר את העדכון, בהתאם לסטאטוס ההזמנה. מערכת ה- WMS תסמן ותציג הזמנות אשר עברו עדכון. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5571 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5572 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5573 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5574 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5575 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.12.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5576 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5575 | 10h | I-01.12.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5577 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5576 | 1h | I-01.12.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5578 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5579 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5577 | 10h | I-01.12.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5580 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5579 | 10h | I-01.12.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5581 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5580 | 1h | I-01.12.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5582 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5581 | 21h | I-01.12.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5583 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5582 | 21h | I-01.12.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5584 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5583 | 5h | I-01.12.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5585 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5584 | 21h | I-01.12.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5586 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5585 | 15h | I-01.12.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5587 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5586 | 10h | I-01.12.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5588 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5587,5584 | 10h | I-01.12.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5589 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5588,5573 | 0h | I-01.12.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5590 |  | Auto Scheduled | במקרים של עדכון ההזמנות לאחר סיום אישור תכנית ההפצה, מערכת ה- WMS ומערכת ה- TMS יאפשרו לבצע תכנון מחדש מבלי למחוק את התכנית שאושרה, כדי לבדוק את השפעת העדכון על התכנית החדשה, ואישורה רק תחת החלטת משתמש לרבות תכנון הליקוט מחדש של ההזמנות הללו. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.04 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5591 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.04.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5592 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.04.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5593 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.04.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5594 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.04.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5595 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.12.INT_Main.04.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5596 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5595 | 10h | I-01.12.INT_Main.04.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5597 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5596 | 1h | I-01.12.INT_Main.04.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5598 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.04.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5599 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5597 | 10h | I-01.12.INT_Main.04.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5600 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5599 | 10h | I-01.12.INT_Main.04.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5601 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5600 | 1h | I-01.12.INT_Main.04.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5602 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5601 | 21h | I-01.12.INT_Main.04.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5603 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5602 | 21h | I-01.12.INT_Main.04.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5604 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5603 | 5h | I-01.12.INT_Main.04.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5605 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5604 | 21h | I-01.12.INT_Main.04.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5606 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5605 | 15h | I-01.12.INT_Main.04.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5607 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5606 | 10h | I-01.12.INT_Main.04.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5608 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5607,5604 | 10h | I-01.12.INT_Main.04.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5609 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5608,5593 | 0h | I-01.12.INT_Main.04.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5610 |  | Auto Scheduled | עבור אוכלוסיות פריטים שיוגדרו לרבות מזון, מערכת ה- WMS תאפשר קבלת הזמנות ממערכת ה- ERP גם כאשר אין מלאי זמין לניפוק, ותאפשר לבצע תכנון הפצה ע"פ נתוני ברירות המחדל של המלאי. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.05 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5611 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.05.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5612 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.05.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5613 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.05.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5614 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.05.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5615 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.12.INT_Main.05.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5616 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5615 | 10h | I-01.12.INT_Main.05.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5617 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5616 | 1h | I-01.12.INT_Main.05.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5618 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.05.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5619 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5617 | 10h | I-01.12.INT_Main.05.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5620 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5619 | 10h | I-01.12.INT_Main.05.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5621 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5620 | 1h | I-01.12.INT_Main.05.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5622 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5621 | 21h | I-01.12.INT_Main.05.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5623 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5622 | 21h | I-01.12.INT_Main.05.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5624 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5623 | 5h | I-01.12.INT_Main.05.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5625 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5624 | 21h | I-01.12.INT_Main.05.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5626 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5625 | 15h | I-01.12.INT_Main.05.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5627 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5626 | 10h | I-01.12.INT_Main.05.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5628 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5627,5624 | 10h | I-01.12.INT_Main.05.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5629 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5628,5613 | 0h | I-01.12.INT_Main.05.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5630 |  | Auto Scheduled | מערכת ה- WMS תודיע למערכת ה- ERP על דחיית עדכון הזמנות כאשר נדרש לרבות במצב של נתוני תשתית לא תקינים, סטאטוס הזמנה שעברה לליקוט, ומקרים נוספים בהם לא נדרש לבצע עדכון של ההזמנות כתוצאה מסטטוס התהליך התפעולי אל מול השינוי הנדרש. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.06 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5631 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.06.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5632 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.12.INT_Main.06.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5633 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.12.INT_Main.06.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5634 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.06.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5635 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.12.INT_Main.06.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5636 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5635 | 10h | I-01.12.INT_Main.06.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5637 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5636 | 1h | I-01.12.INT_Main.06.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5638 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.12.INT_Main.06.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5639 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5637 | 10h | I-01.12.INT_Main.06.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5640 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5639 | 10h | I-01.12.INT_Main.06.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5641 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5640 | 1h | I-01.12.INT_Main.06.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5642 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5641 | 21h | I-01.12.INT_Main.06.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5643 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5642 | 21h | I-01.12.INT_Main.06.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5644 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5643 | 5h | I-01.12.INT_Main.06.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5645 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5644 | 21h | I-01.12.INT_Main.06.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5646 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5645 | 15h | I-01.12.INT_Main.06.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5647 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5646 | 10h | I-01.12.INT_Main.06.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5648 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5647,5644 | 10h | I-01.12.INT_Main.06.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5649 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5648,5633 | 0h | I-01.12.INT_Main.06.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5650 |  | Auto Scheduled | I-01.13: הזמנות/אספקה יוצאת | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.13 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5651 |  | Auto Scheduled | I-01.13: הזמנות/אספקה יוצאת.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.13.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5652 |  | Auto Scheduled | מערכת ה- WMS תשלח (בממשק אוטומטי) למערכת ה-ERP את הזמנות ה- WMS כולל נתוני התכולה המתוכננים ומועד אספקה מתוכנן. - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.13.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5653 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.13.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5654 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.13.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5655 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 3388,3399,3410,3421,3432,3443,3454,3465,3476,3487,3498,3509,3520,4459,4470,4481,4492,4503,4514,4810,4821 | 0h | I-01.13.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5656 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.13.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5657 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.13.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5658 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5657 | 10h | I-01.13.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5659 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5658 | 1h | I-01.13.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5660 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.13.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5661 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5659 | 10h | I-01.13.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5662 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5661 | 10h | I-01.13.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5663 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5662 | 1h | I-01.13.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5664 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5663 | 21h | I-01.13.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5665 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5664 | 21h | I-01.13.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5666 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5665 | 5h | I-01.13.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5667 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5666 | 21h | I-01.13.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5668 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5667 | 15h | I-01.13.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5669 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5668 | 10h | I-01.13.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5670 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5669,5666 | 10h | I-01.13.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5671 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5670,5655 | 0h | I-01.13.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5672 |  | Auto Scheduled | I-01.14: הזמנות/אספקה יוצאת | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.14 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5673 |  | Auto Scheduled | I-01.14: הזמנות/אספקה יוצאת | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 290h | I-01.14 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5674 |  | Auto Scheduled | I-01.14: הזמנות/אספקה יוצאת.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 290h | I-01.14.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5675 |  | Auto Scheduled | מערכת ה- WMS תשלח (בממשק אוטומטי) למערכת ה- ERP את נתוני התכולה שהועמסה בפועל ומזהה יחידות הניטול וסוג יחידות הניטול להפצה (מספרי חבילות) אל מול הזמנות ה- WMS (במערכת ה- ERP - אספקה יוצאת). למול נתונים אלו מערכת ה- ERP תבצע את הניפוק. - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.14.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5676 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.14.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5677 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.14.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5678 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 3388,3399,3410,3421,3432,3443,3454,3465,3476,3487,3498,3509,3520,3758,3769,4459,4470,4481,4492,4503,4514 | 0h | I-01.14.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5679 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.14.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5680 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.14.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5681 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5680 | 10h | I-01.14.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5682 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5681 | 1h | I-01.14.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5683 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.14.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5684 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5682 | 10h | I-01.14.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5685 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5684 | 10h | I-01.14.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5686 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5685 | 1h | I-01.14.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5687 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5686 | 21h | I-01.14.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5688 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5687 | 21h | I-01.14.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5689 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5688 | 5h | I-01.14.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5690 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5689 | 21h | I-01.14.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5691 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5690 | 15h | I-01.14.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5692 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5691 | 10h | I-01.14.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5693 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5692,5689 | 10h | I-01.14.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5694 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5693,5678 | 0h | I-01.14.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5695 |  | Auto Scheduled | מערכת ה-WMS תשלח (בממשק אוטומטי) למערכת ה-ERP את המשלוחים (Shipment) הכולל את פלטפורמות ההפצה שקושרו ולמול כל משלוח את הזמנות ה- WMS המקושרות ותכולתן, לרבות מזהי יחידות הניטול להפצה. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.14.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5696 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.14.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5697 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.14.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5698 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.14.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5699 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.14.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5700 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.14.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5701 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5700 | 10h | I-01.14.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5702 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5701 | 1h | I-01.14.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5703 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.14.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5704 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5702 | 10h | I-01.14.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5705 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5704 | 10h | I-01.14.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5706 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5705 | 1h | I-01.14.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5707 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5706 | 21h | I-01.14.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5708 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5707 | 21h | I-01.14.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5709 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5708 | 5h | I-01.14.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5710 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5709 | 21h | I-01.14.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5711 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5710 | 15h | I-01.14.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5712 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5711 | 10h | I-01.14.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5713 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5712,5709 | 10h | I-01.14.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5714 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5713,5698 | 0h | I-01.14.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5715 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5716 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5717 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5718 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5719 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5720 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5721 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5722 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5723 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5724 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 1,450h | I-01.15 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5725 |  | Auto Scheduled | I-01.15: הזמנות/אספקה יוצאת POD.INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 1,450h | I-01.15.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5726 |  | Auto Scheduled | מערכת ה- POD תקבל את נתוני תעודות המשלוח (אספקות יוצאות), מזהה יחידות הניטול להפצה (חבילות) למול כל תעודה, שם נקודת היעד וסדר המסלול. - INT_Main | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5727 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5728 |  | Auto Scheduled | LifeCycle Tasks | 477 days | May 18, 2021 8:00 AM | March 15, 2023 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5729 |  | Auto Scheduled | Interface Milestone | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 3388,3399,3410,3421,3432,3443,3454,3465,3476,3487,3498,3509,3520,3758,3769,4459,4470,4481,4492,4503,4514,4810,4821 | 0h | I-01.15.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5730 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5731 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5732 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5731 | 10h | I-01.15.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5733 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5732 | 1h | I-01.15.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5734 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5735 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5733 | 10h | I-01.15.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5736 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5735 | 10h | I-01.15.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5737 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5736 | 1h | I-01.15.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5738 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5737 | 21h | I-01.15.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5739 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5738 | 21h | I-01.15.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5740 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5739 | 5h | I-01.15.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5741 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5740 | 21h | I-01.15.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5742 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5741 | 15h | I-01.15.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5743 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5742 | 10h | I-01.15.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5744 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5743,5740 | 10h | I-01.15.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5745 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | March 15, 2023 5:00 PM | March 15, 2023 5:00 PM | 0 | 5744,5729 | 0h | I-01.15.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5746 |  | Auto Scheduled | הצגת המשלוחים - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5747 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5748 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5749 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5750 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5751 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5752 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5751 | 10h | I-01.15.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5753 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5752 | 1h | I-01.15.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5754 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5755 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5753 | 10h | I-01.15.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5756 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5755 | 10h | I-01.15.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5757 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5756 | 1h | I-01.15.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5758 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5757 | 21h | I-01.15.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5759 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5758 | 21h | I-01.15.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5760 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5759 | 5h | I-01.15.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5761 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5760 | 21h | I-01.15.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5762 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5761 | 15h | I-01.15.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5763 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5762 | 10h | I-01.15.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5764 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5763,5760 | 10h | I-01.15.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5765 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5764,5749 | 0h | I-01.15.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5766 |  | Auto Scheduled | מערכת ה- POD תציג למשתמש את כלל נקודות היעד ע"פ סדר ההפצה לפלטפורמת ההפצה המשויכת אליו, ולכל אחת מהן את מזהה האספקות היוצאות (תעודת משלוח), מזהה יחידות הניטול להפצה (חבילות) למול כל תעודה ושם נקודת היעד. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5767 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5768 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5769 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5770 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5771 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5772 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5771 | 10h | I-01.15.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5773 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5772 | 1h | I-01.15.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5774 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5775 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5773 | 10h | I-01.15.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5776 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5775 | 10h | I-01.15.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5777 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5776 | 1h | I-01.15.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5778 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5777 | 21h | I-01.15.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5779 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5778 | 21h | I-01.15.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5780 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5779 | 5h | I-01.15.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5781 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5780 | 21h | I-01.15.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5782 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5781 | 15h | I-01.15.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5783 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5782 | 10h | I-01.15.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5784 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5783,5780 | 10h | I-01.15.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5785 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5784,5769 | 0h | I-01.15.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5786 |  | Auto Scheduled | בקרת תכולה, אישור קבלה ודיווח חריגים - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.04 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5787 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.04.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5788 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.04.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5789 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.04.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5790 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.04.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5791 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.04.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5792 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5791 | 10h | I-01.15.INT_Main.04.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5793 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5792 | 1h | I-01.15.INT_Main.04.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5794 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.04.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5795 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5793 | 10h | I-01.15.INT_Main.04.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5796 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5795 | 10h | I-01.15.INT_Main.04.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5797 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5796 | 1h | I-01.15.INT_Main.04.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5798 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5797 | 21h | I-01.15.INT_Main.04.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5799 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5798 | 21h | I-01.15.INT_Main.04.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5800 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5799 | 5h | I-01.15.INT_Main.04.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5801 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5800 | 21h | I-01.15.INT_Main.04.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5802 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5801 | 15h | I-01.15.INT_Main.04.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5803 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5802 | 10h | I-01.15.INT_Main.04.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5804 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5803,5800 | 10h | I-01.15.INT_Main.04.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5805 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5804,5789 | 0h | I-01.15.INT_Main.04.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5806 |  | Auto Scheduled | מסופון ה- POD יזהה את נציג הלקוח באופן אוטומטי באמצעות העברת כל תעודה מזהה שתהיה קיימת ברשות המזמין (סוגי התעודות ופורמט הנתונים יקבעו באפיון המפורט), והשוואה למול רשימת תעודות שיתקבלו מעת לעת מהמזמין בממשק אוטומטי ממוכן. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.05 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5807 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.05.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5808 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.05.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5809 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.05.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5810 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.05.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5811 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.05.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5812 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5811 | 10h | I-01.15.INT_Main.05.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5813 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5812 | 1h | I-01.15.INT_Main.05.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5814 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.05.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5815 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5813 | 10h | I-01.15.INT_Main.05.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5816 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5815 | 10h | I-01.15.INT_Main.05.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5817 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5816 | 1h | I-01.15.INT_Main.05.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5818 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5817 | 21h | I-01.15.INT_Main.05.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5819 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5818 | 21h | I-01.15.INT_Main.05.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5820 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5819 | 5h | I-01.15.INT_Main.05.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5821 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5820 | 21h | I-01.15.INT_Main.05.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5822 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5821 | 15h | I-01.15.INT_Main.05.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5823 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5822 | 10h | I-01.15.INT_Main.05.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5824 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5823,5820 | 10h | I-01.15.INT_Main.05.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5825 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5824,5809 | 0h | I-01.15.INT_Main.05.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5826 |  | Auto Scheduled | מסופון ה- POD יאפשר לבצע בקרת מלאי ע"י נציג הלקוח באמצעות סריקת ברקוד של יחידות הניטול להפצה, ויציג למשתמש בכל עת את החבילות שנסרקו ואת יתרת החבילות לסריקה. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.06 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5827 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.06.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5828 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.06.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5829 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.06.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5830 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.06.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5831 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.06.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5832 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5831 | 10h | I-01.15.INT_Main.06.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5833 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5832 | 1h | I-01.15.INT_Main.06.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5834 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.06.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5835 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5833 | 10h | I-01.15.INT_Main.06.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5836 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5835 | 10h | I-01.15.INT_Main.06.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5837 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5836 | 1h | I-01.15.INT_Main.06.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5838 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5837 | 21h | I-01.15.INT_Main.06.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5839 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5838 | 21h | I-01.15.INT_Main.06.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5840 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5839 | 5h | I-01.15.INT_Main.06.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5841 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5840 | 21h | I-01.15.INT_Main.06.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5842 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5841 | 15h | I-01.15.INT_Main.06.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5843 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5842 | 10h | I-01.15.INT_Main.06.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5844 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5843,5840 | 10h | I-01.15.INT_Main.06.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5845 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5844,5829 | 0h | I-01.15.INT_Main.06.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5846 |  | Auto Scheduled | מסופון ה- POD יאפשר למשתמש לדווח על פערים בין המלאי הצפוי להתקבל למלאי שהתקבל בפועל. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.07 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5847 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.07.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5848 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.07.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5849 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.07.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5850 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.07.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5851 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.07.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5852 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5851 | 10h | I-01.15.INT_Main.07.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5853 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5852 | 1h | I-01.15.INT_Main.07.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5854 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.07.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5855 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5853 | 10h | I-01.15.INT_Main.07.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5856 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5855 | 10h | I-01.15.INT_Main.07.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5857 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5856 | 1h | I-01.15.INT_Main.07.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5858 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5857 | 21h | I-01.15.INT_Main.07.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5859 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5858 | 21h | I-01.15.INT_Main.07.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5860 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5859 | 5h | I-01.15.INT_Main.07.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5861 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5860 | 21h | I-01.15.INT_Main.07.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5862 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5861 | 15h | I-01.15.INT_Main.07.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5863 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5862 | 10h | I-01.15.INT_Main.07.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5864 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5863,5860 | 10h | I-01.15.INT_Main.07.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5865 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5864,5849 | 0h | I-01.15.INT_Main.07.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5866 |  | Auto Scheduled | מערכת ה POD תעדכן את כל נתוני בקרת הלקוח, לרבות הפערים, נקודת ה- GPS ממנה התבצעה פעולת הבקרה ותמונות אשר יצולמו ע"י יחידת הקצה של ה- POD במידת הצורך. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.08 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5867 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.08.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5868 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.08.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5869 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.08.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5870 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.08.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5871 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.08.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5872 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5871 | 10h | I-01.15.INT_Main.08.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5873 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5872 | 1h | I-01.15.INT_Main.08.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5874 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.08.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5875 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5873 | 10h | I-01.15.INT_Main.08.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5876 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5875 | 10h | I-01.15.INT_Main.08.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5877 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5876 | 1h | I-01.15.INT_Main.08.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5878 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5877 | 21h | I-01.15.INT_Main.08.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5879 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5878 | 21h | I-01.15.INT_Main.08.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5880 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5879 | 5h | I-01.15.INT_Main.08.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5881 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5880 | 21h | I-01.15.INT_Main.08.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5882 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5881 | 15h | I-01.15.INT_Main.08.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5883 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5882 | 10h | I-01.15.INT_Main.08.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5884 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5883,5880 | 10h | I-01.15.INT_Main.08.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5885 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5884,5869 | 0h | I-01.15.INT_Main.08.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5886 |  | Auto Scheduled | הצגת מיקום גאוגרפי ע"ג מפה לרבות נתוני המלאי - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.09 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5887 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.09.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5888 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.09.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5889 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.09.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5890 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.09.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5891 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.09.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5892 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5891 | 10h | I-01.15.INT_Main.09.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5893 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5892 | 1h | I-01.15.INT_Main.09.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5894 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.09.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5895 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5893 | 10h | I-01.15.INT_Main.09.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5896 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5895 | 10h | I-01.15.INT_Main.09.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5897 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5896 | 1h | I-01.15.INT_Main.09.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5898 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5897 | 21h | I-01.15.INT_Main.09.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5899 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5898 | 21h | I-01.15.INT_Main.09.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5900 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5899 | 5h | I-01.15.INT_Main.09.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5901 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5900 | 21h | I-01.15.INT_Main.09.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5902 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5901 | 15h | I-01.15.INT_Main.09.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5903 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5902 | 10h | I-01.15.INT_Main.09.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5904 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5903,5900 | 10h | I-01.15.INT_Main.09.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5905 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5904,5889 | 0h | I-01.15.INT_Main.09.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5906 |  | Auto Scheduled | על מערכת הPOD להציג באופן גרפי ע"ג מפה את כלל הנתונים הנדרשים לשליטה בפלטפורמות המבצעות בפועל את תהליכי האספקות היוצאות, לרבות סוג הפלטפורמה, נתוני הפלטפורמה, נתוני הנהג, מיקום הפלטפורמה בכל רגע בזמן, מסלול מתוכנן לפלטפורמה למול המסלול בפועל וכל נתון נוס | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.10 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5907 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.10.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5908 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.15.INT_Main.10.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5909 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.15.INT_Main.10.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5910 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.10.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5911 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.15.INT_Main.10.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5912 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5911 | 10h | I-01.15.INT_Main.10.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5913 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5912 | 1h | I-01.15.INT_Main.10.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5914 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.15.INT_Main.10.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5915 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5913 | 10h | I-01.15.INT_Main.10.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5916 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5915 | 10h | I-01.15.INT_Main.10.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5917 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5916 | 1h | I-01.15.INT_Main.10.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5918 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5917 | 21h | I-01.15.INT_Main.10.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5919 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5918 | 21h | I-01.15.INT_Main.10.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5920 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5919 | 5h | I-01.15.INT_Main.10.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5921 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5920 | 21h | I-01.15.INT_Main.10.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5922 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5921 | 15h | I-01.15.INT_Main.10.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5923 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5922 | 10h | I-01.15.INT_Main.10.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5924 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5923,5920 | 10h | I-01.15.INT_Main.10.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5925 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5924,5909 | 0h | I-01.15.INT_Main.10.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5926 |  | Auto Scheduled | I-01.16: ספירות | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.16 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5927 |  | Auto Scheduled | I-01.16: ספירות | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 290h | I-01.16 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5928 |  | Auto Scheduled | I-01.16: ספירות.INT_Main | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 290h | I-01.16.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5929 |  | Auto Scheduled | ספירת כלל פריטי המלאי באופן שוטף ובתדירות שתקבע על פי מאפייני הפריט ע"י המזמין. - INT_Main | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 145h | I-01.16.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5930 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.16.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5931 |  | Auto Scheduled | LifeCycle Tasks | 236 days | May 18, 2021 8:00 AM | April 12, 2022 5:00 PM | 0 |  | 145h | I-01.16.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5932 |  | Auto Scheduled | Interface Milestone | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 1150,1161,1172,2501,2512,2523,2534,2545,2824,2835 | 0h | I-01.16.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5933 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.16.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5934 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.16.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5935 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5934 | 10h | I-01.16.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5936 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5935 | 1h | I-01.16.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5937 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.16.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5938 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5936 | 10h | I-01.16.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5939 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5938 | 10h | I-01.16.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5940 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5939 | 1h | I-01.16.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5941 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5940 | 21h | I-01.16.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5942 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5941 | 21h | I-01.16.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5943 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5942 | 5h | I-01.16.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5944 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5943 | 21h | I-01.16.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5945 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5944 | 15h | I-01.16.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5946 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5945 | 10h | I-01.16.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5947 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5946,5943 | 10h | I-01.16.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5948 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | April 12, 2022 5:00 PM | April 12, 2022 5:00 PM | 0 | 5947,5932 | 0h | I-01.16.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5949 |  | Auto Scheduled | מערכת ה- WMS תקבל (בממשק אוטומטי) ממערכת ה- ERP את תדירות הספירה הנדרשת לכל פריט. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.16.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5950 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.16.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5951 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.16.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5952 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.16.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5953 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.16.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5954 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.16.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5955 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5954 | 10h | I-01.16.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5956 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5955 | 1h | I-01.16.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5957 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.16.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5958 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5956 | 10h | I-01.16.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5959 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 5958 | 10h | I-01.16.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5960 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 5959 | 1h | I-01.16.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5961 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 5960 | 21h | I-01.16.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5962 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 5961 | 21h | I-01.16.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5963 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 5962 | 5h | I-01.16.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5964 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 5963 | 21h | I-01.16.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5965 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 5964 | 15h | I-01.16.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5966 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 5965 | 10h | I-01.16.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5967 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 5966,5963 | 10h | I-01.16.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5968 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 5967,5952 | 0h | I-01.16.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5969 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5970 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5971 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5972 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5973 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5974 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5975 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5976 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5977 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5978 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5979 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5980 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5981 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5982 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5983 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5984 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5985 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5986 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5987 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5988 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5989 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5990 |  | Auto Scheduled | I-01.17: דוחות תפעוליים | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 3,190h | I-01.17 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
5991 |  | Auto Scheduled | I-01.17: דוחות תפעוליים.INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 3,190h | I-01.17.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
5992 |  | Auto Scheduled | דוחות תפוסת מיקומים. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
5993 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
5994 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
5995 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5996 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
5997 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5998 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 5997 | 10h | I-01.17.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
5999 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 5998 | 1h | I-01.17.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6000 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6001 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 5999 | 10h | I-01.17.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6002 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6001 | 10h | I-01.17.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6003 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6002 | 1h | I-01.17.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6004 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6003 | 21h | I-01.17.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6005 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6004 | 21h | I-01.17.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6006 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6005 | 5h | I-01.17.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6007 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6006 | 21h | I-01.17.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6008 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6007 | 15h | I-01.17.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6009 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6008 | 10h | I-01.17.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6010 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6009,6006 | 10h | I-01.17.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6011 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6010,5995 | 0h | I-01.17.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6012 |  | Auto Scheduled | דוחות המלצה לריענון. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6013 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6014 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6015 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6016 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6017 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6018 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6017 | 10h | I-01.17.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6019 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6018 | 1h | I-01.17.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6020 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6021 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6019 | 10h | I-01.17.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6022 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6021 | 10h | I-01.17.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6023 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6022 | 1h | I-01.17.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6024 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6023 | 21h | I-01.17.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6025 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6024 | 21h | I-01.17.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6026 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6025 | 5h | I-01.17.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6027 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6026 | 21h | I-01.17.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6028 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6027 | 15h | I-01.17.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6029 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6028 | 10h | I-01.17.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6030 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6029,6026 | 10h | I-01.17.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6031 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6030,6015 | 0h | I-01.17.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6032 |  | Auto Scheduled | המלצות לעדכון מיקום וסידור למלאי. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6033 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6034 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6035 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6036 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6037 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6038 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6037 | 10h | I-01.17.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6039 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6038 | 1h | I-01.17.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6040 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6041 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6039 | 10h | I-01.17.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6042 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6041 | 10h | I-01.17.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6043 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6042 | 1h | I-01.17.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6044 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6043 | 21h | I-01.17.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6045 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6044 | 21h | I-01.17.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6046 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6045 | 5h | I-01.17.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6047 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6046 | 21h | I-01.17.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6048 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6047 | 15h | I-01.17.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6049 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6048 | 10h | I-01.17.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6050 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6049,6046 | 10h | I-01.17.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6051 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6050,6035 | 0h | I-01.17.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6052 |  | Auto Scheduled | דוחות רישום תנועות בהיסטורית הפעילות בחתכים שונים של, פריט, אצווה, סוגי פעילות, עובדים, הזמנות, מסמכי קבלה למלאי, בחתכי זמן שונים, איתורים אזורים ומחסנים. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.04 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6053 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.04.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6054 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.04.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6055 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.04.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6056 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.04.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6057 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.04.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6058 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6057 | 10h | I-01.17.INT_Main.04.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6059 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6058 | 1h | I-01.17.INT_Main.04.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6060 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.04.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6061 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6059 | 10h | I-01.17.INT_Main.04.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6062 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6061 | 10h | I-01.17.INT_Main.04.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6063 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6062 | 1h | I-01.17.INT_Main.04.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6064 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6063 | 21h | I-01.17.INT_Main.04.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6065 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6064 | 21h | I-01.17.INT_Main.04.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6066 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6065 | 5h | I-01.17.INT_Main.04.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6067 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6066 | 21h | I-01.17.INT_Main.04.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6068 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6067 | 15h | I-01.17.INT_Main.04.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6069 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6068 | 10h | I-01.17.INT_Main.04.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6070 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6069,6066 | 10h | I-01.17.INT_Main.04.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6071 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6070,6055 | 0h | I-01.17.INT_Main.04.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6072 |  | Auto Scheduled | דוחות הזמנות עם בעיות וחריגי מלאי. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.05 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6073 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.05.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6074 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.05.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6075 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.05.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6076 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.05.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6077 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.05.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6078 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6077 | 10h | I-01.17.INT_Main.05.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6079 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6078 | 1h | I-01.17.INT_Main.05.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6080 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.05.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6081 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6079 | 10h | I-01.17.INT_Main.05.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6082 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6081 | 10h | I-01.17.INT_Main.05.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6083 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6082 | 1h | I-01.17.INT_Main.05.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6084 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6083 | 21h | I-01.17.INT_Main.05.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6085 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6084 | 21h | I-01.17.INT_Main.05.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6086 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6085 | 5h | I-01.17.INT_Main.05.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6087 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6086 | 21h | I-01.17.INT_Main.05.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6088 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6087 | 15h | I-01.17.INT_Main.05.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6089 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6088 | 10h | I-01.17.INT_Main.05.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6090 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6089,6086 | 10h | I-01.17.INT_Main.05.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6091 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6090,6075 | 0h | I-01.17.INT_Main.05.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6092 |  | Auto Scheduled | דוחות התקדמות איסוף הזמנות לפי קווים, לקוחות, מחסנים, תאריכים. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.06 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6093 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.06.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6094 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.06.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6095 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.06.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6096 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.06.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6097 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.06.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6098 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6097 | 10h | I-01.17.INT_Main.06.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6099 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6098 | 1h | I-01.17.INT_Main.06.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6100 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.06.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6101 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6099 | 10h | I-01.17.INT_Main.06.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6102 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6101 | 10h | I-01.17.INT_Main.06.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6103 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6102 | 1h | I-01.17.INT_Main.06.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6104 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6103 | 21h | I-01.17.INT_Main.06.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6105 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6104 | 21h | I-01.17.INT_Main.06.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6106 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6105 | 5h | I-01.17.INT_Main.06.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6107 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6106 | 21h | I-01.17.INT_Main.06.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6108 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6107 | 15h | I-01.17.INT_Main.06.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6109 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6108 | 10h | I-01.17.INT_Main.06.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6110 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6109,6106 | 10h | I-01.17.INT_Main.06.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6111 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6110,6095 | 0h | I-01.17.INT_Main.06.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6112 |  | Auto Scheduled | דו"חות מלאי, לרבות רמות מלאי לריענון, סה"כ מלאי באיתור/אזור, מלאי זמין, מלאי מוקצה להזמנות, מלאי שהוקצה לריענון וכד'. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.07 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6113 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.07.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6114 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.07.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6115 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.07.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6116 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.07.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6117 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.07.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6118 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6117 | 10h | I-01.17.INT_Main.07.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6119 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6118 | 1h | I-01.17.INT_Main.07.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6120 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.07.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6121 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6119 | 10h | I-01.17.INT_Main.07.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6122 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6121 | 10h | I-01.17.INT_Main.07.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6123 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6122 | 1h | I-01.17.INT_Main.07.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6124 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6123 | 21h | I-01.17.INT_Main.07.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6125 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6124 | 21h | I-01.17.INT_Main.07.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6126 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6125 | 5h | I-01.17.INT_Main.07.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6127 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6126 | 21h | I-01.17.INT_Main.07.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6128 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6127 | 15h | I-01.17.INT_Main.07.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6129 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6128 | 10h | I-01.17.INT_Main.07.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6130 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6129,6126 | 10h | I-01.17.INT_Main.07.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6131 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6130,6115 | 0h | I-01.17.INT_Main.07.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6132 |  | Auto Scheduled | דו"חות להזמנות לאיסוף עתידי. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.08 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6133 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.08.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6134 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.08.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6135 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.08.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6136 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.08.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6137 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.08.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6138 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6137 | 10h | I-01.17.INT_Main.08.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6139 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6138 | 1h | I-01.17.INT_Main.08.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6140 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.08.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6141 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6139 | 10h | I-01.17.INT_Main.08.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6142 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6141 | 10h | I-01.17.INT_Main.08.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6143 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6142 | 1h | I-01.17.INT_Main.08.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6144 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6143 | 21h | I-01.17.INT_Main.08.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6145 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6144 | 21h | I-01.17.INT_Main.08.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6146 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6145 | 5h | I-01.17.INT_Main.08.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6147 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6146 | 21h | I-01.17.INT_Main.08.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6148 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6147 | 15h | I-01.17.INT_Main.08.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6149 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6148 | 10h | I-01.17.INT_Main.08.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6150 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6149,6146 | 10h | I-01.17.INT_Main.08.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6151 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6150,6135 | 0h | I-01.17.INT_Main.08.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6152 |  | Auto Scheduled | דו"חות לצפי קליטת מלאי מרכש. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.09 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6153 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.09.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6154 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.09.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6155 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.09.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6156 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.09.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6157 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.09.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6158 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6157 | 10h | I-01.17.INT_Main.09.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6159 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6158 | 1h | I-01.17.INT_Main.09.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6160 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.09.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6161 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6159 | 10h | I-01.17.INT_Main.09.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6162 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6161 | 10h | I-01.17.INT_Main.09.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6163 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6162 | 1h | I-01.17.INT_Main.09.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6164 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6163 | 21h | I-01.17.INT_Main.09.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6165 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6164 | 21h | I-01.17.INT_Main.09.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6166 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6165 | 5h | I-01.17.INT_Main.09.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6167 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6166 | 21h | I-01.17.INT_Main.09.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6168 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6167 | 15h | I-01.17.INT_Main.09.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6169 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6168 | 10h | I-01.17.INT_Main.09.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6170 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6169,6166 | 10h | I-01.17.INT_Main.09.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6171 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6170,6155 | 0h | I-01.17.INT_Main.09.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6172 |  | Auto Scheduled | דו"חות לצפי קבלת מלאי מהחזרות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.10 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6173 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.10.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6174 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.10.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6175 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.10.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6176 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.10.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6177 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.10.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6178 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6177 | 10h | I-01.17.INT_Main.10.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6179 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6178 | 1h | I-01.17.INT_Main.10.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6180 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.10.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6181 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6179 | 10h | I-01.17.INT_Main.10.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6182 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6181 | 10h | I-01.17.INT_Main.10.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6183 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6182 | 1h | I-01.17.INT_Main.10.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6184 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6183 | 21h | I-01.17.INT_Main.10.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6185 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6184 | 21h | I-01.17.INT_Main.10.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6186 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6185 | 5h | I-01.17.INT_Main.10.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6187 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6186 | 21h | I-01.17.INT_Main.10.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6188 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6187 | 15h | I-01.17.INT_Main.10.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6189 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6188 | 10h | I-01.17.INT_Main.10.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6190 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6189,6186 | 10h | I-01.17.INT_Main.10.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6191 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6190,6175 | 0h | I-01.17.INT_Main.10.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6192 |  | Auto Scheduled | דו"חות לסטטוס מלאי בבדיקות קבלה. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.11 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6193 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.11.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6194 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.11.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6195 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.11.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6196 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.11.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6197 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.11.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6198 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6197 | 10h | I-01.17.INT_Main.11.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6199 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6198 | 1h | I-01.17.INT_Main.11.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6200 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.11.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6201 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6199 | 10h | I-01.17.INT_Main.11.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6202 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6201 | 10h | I-01.17.INT_Main.11.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6203 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6202 | 1h | I-01.17.INT_Main.11.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6204 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6203 | 21h | I-01.17.INT_Main.11.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6205 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6204 | 21h | I-01.17.INT_Main.11.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6206 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6205 | 5h | I-01.17.INT_Main.11.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6207 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6206 | 21h | I-01.17.INT_Main.11.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6208 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6207 | 15h | I-01.17.INT_Main.11.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6209 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6208 | 10h | I-01.17.INT_Main.11.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6210 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6209,6206 | 10h | I-01.17.INT_Main.11.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6211 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6210,6195 | 0h | I-01.17.INT_Main.11.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6212 |  | Auto Scheduled | דו"חות למשימות פתוחות ובאיחור. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.12 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6213 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.12.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6214 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.12.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6215 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.12.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6216 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.12.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6217 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.12.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6218 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6217 | 10h | I-01.17.INT_Main.12.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6219 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6218 | 1h | I-01.17.INT_Main.12.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6220 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.12.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6221 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6219 | 10h | I-01.17.INT_Main.12.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6222 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6221 | 10h | I-01.17.INT_Main.12.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6223 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6222 | 1h | I-01.17.INT_Main.12.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6224 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6223 | 21h | I-01.17.INT_Main.12.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6225 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6224 | 21h | I-01.17.INT_Main.12.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6226 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6225 | 5h | I-01.17.INT_Main.12.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6227 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6226 | 21h | I-01.17.INT_Main.12.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6228 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6227 | 15h | I-01.17.INT_Main.12.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6229 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6228 | 10h | I-01.17.INT_Main.12.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6230 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6229,6226 | 10h | I-01.17.INT_Main.12.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6231 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6230,6215 | 0h | I-01.17.INT_Main.12.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6232 |  | Auto Scheduled | דו"חות ניהוליים - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.13 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6233 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.13.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6234 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.13.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6235 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.13.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6236 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.13.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6237 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.13.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6238 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6237 | 10h | I-01.17.INT_Main.13.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6239 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6238 | 1h | I-01.17.INT_Main.13.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6240 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.13.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6241 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6239 | 10h | I-01.17.INT_Main.13.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6242 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6241 | 10h | I-01.17.INT_Main.13.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6243 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6242 | 1h | I-01.17.INT_Main.13.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6244 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6243 | 21h | I-01.17.INT_Main.13.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6245 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6244 | 21h | I-01.17.INT_Main.13.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6246 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6245 | 5h | I-01.17.INT_Main.13.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6247 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6246 | 21h | I-01.17.INT_Main.13.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6248 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6247 | 15h | I-01.17.INT_Main.13.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6249 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6248 | 10h | I-01.17.INT_Main.13.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6250 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6249,6246 | 10h | I-01.17.INT_Main.13.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6251 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6250,6235 | 0h | I-01.17.INT_Main.13.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6252 |  | Auto Scheduled | דו"חות בקרת תפוקות עובדים. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.14 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6253 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.14.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6254 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.14.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6255 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.14.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6256 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.14.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6257 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.14.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6258 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6257 | 10h | I-01.17.INT_Main.14.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6259 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6258 | 1h | I-01.17.INT_Main.14.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6260 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.14.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6261 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6259 | 10h | I-01.17.INT_Main.14.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6262 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6261 | 10h | I-01.17.INT_Main.14.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6263 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6262 | 1h | I-01.17.INT_Main.14.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6264 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6263 | 21h | I-01.17.INT_Main.14.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6265 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6264 | 21h | I-01.17.INT_Main.14.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6266 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6265 | 5h | I-01.17.INT_Main.14.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6267 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6266 | 21h | I-01.17.INT_Main.14.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6268 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6267 | 15h | I-01.17.INT_Main.14.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6269 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6268 | 10h | I-01.17.INT_Main.14.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6270 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6269,6266 | 10h | I-01.17.INT_Main.14.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6271 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6270,6255 | 0h | I-01.17.INT_Main.14.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6272 |  | Auto Scheduled | דו"חות בקרת SLA לקבלת מלאי ולאספקת הזמנות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.15 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6273 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.15.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6274 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.15.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6275 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.15.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6276 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.15.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6277 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.15.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6278 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6277 | 10h | I-01.17.INT_Main.15.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6279 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6278 | 1h | I-01.17.INT_Main.15.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6280 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.15.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6281 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6279 | 10h | I-01.17.INT_Main.15.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6282 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6281 | 10h | I-01.17.INT_Main.15.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6283 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6282 | 1h | I-01.17.INT_Main.15.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6284 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6283 | 21h | I-01.17.INT_Main.15.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6285 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6284 | 21h | I-01.17.INT_Main.15.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6286 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6285 | 5h | I-01.17.INT_Main.15.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6287 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6286 | 21h | I-01.17.INT_Main.15.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6288 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6287 | 15h | I-01.17.INT_Main.15.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6289 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6288 | 10h | I-01.17.INT_Main.15.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6290 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6289,6286 | 10h | I-01.17.INT_Main.15.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6291 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6290,6275 | 0h | I-01.17.INT_Main.15.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6292 |  | Auto Scheduled | דו"חות סטאטוס ספירות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.16 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6293 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.16.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6294 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.16.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6295 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.16.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6296 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.16.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6297 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.16.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6298 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6297 | 10h | I-01.17.INT_Main.16.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6299 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6298 | 1h | I-01.17.INT_Main.16.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6300 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.16.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6301 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6299 | 10h | I-01.17.INT_Main.16.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6302 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6301 | 10h | I-01.17.INT_Main.16.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6303 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6302 | 1h | I-01.17.INT_Main.16.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6304 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6303 | 21h | I-01.17.INT_Main.16.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6305 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6304 | 21h | I-01.17.INT_Main.16.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6306 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6305 | 5h | I-01.17.INT_Main.16.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6307 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6306 | 21h | I-01.17.INT_Main.16.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6308 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6307 | 15h | I-01.17.INT_Main.16.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6309 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6308 | 10h | I-01.17.INT_Main.16.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6310 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6309,6306 | 10h | I-01.17.INT_Main.16.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6311 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6310,6295 | 0h | I-01.17.INT_Main.16.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6312 |  | Auto Scheduled | דו"חות אי הילום. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.17 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6313 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.17.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6314 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.17.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6315 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.17.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6316 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.17.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6317 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.17.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6318 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6317 | 10h | I-01.17.INT_Main.17.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6319 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6318 | 1h | I-01.17.INT_Main.17.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6320 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.17.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6321 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6319 | 10h | I-01.17.INT_Main.17.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6322 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6321 | 10h | I-01.17.INT_Main.17.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6323 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6322 | 1h | I-01.17.INT_Main.17.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6324 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6323 | 21h | I-01.17.INT_Main.17.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6325 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6324 | 21h | I-01.17.INT_Main.17.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6326 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6325 | 5h | I-01.17.INT_Main.17.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6327 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6326 | 21h | I-01.17.INT_Main.17.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6328 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6327 | 15h | I-01.17.INT_Main.17.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6329 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6328 | 10h | I-01.17.INT_Main.17.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6330 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6329,6326 | 10h | I-01.17.INT_Main.17.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6331 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6330,6315 | 0h | I-01.17.INT_Main.17.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6332 |  | Auto Scheduled | דו"חות סטאטוס משימות. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.18 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6333 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.18.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6334 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.18.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6335 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.18.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6336 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.18.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6337 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.18.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6338 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6337 | 10h | I-01.17.INT_Main.18.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6339 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6338 | 1h | I-01.17.INT_Main.18.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6340 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.18.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6341 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6339 | 10h | I-01.17.INT_Main.18.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6342 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6341 | 10h | I-01.17.INT_Main.18.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6343 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6342 | 1h | I-01.17.INT_Main.18.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6344 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6343 | 21h | I-01.17.INT_Main.18.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6345 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6344 | 21h | I-01.17.INT_Main.18.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6346 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6345 | 5h | I-01.17.INT_Main.18.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6347 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6346 | 21h | I-01.17.INT_Main.18.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6348 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6347 | 15h | I-01.17.INT_Main.18.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6349 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6348 | 10h | I-01.17.INT_Main.18.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6350 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6349,6346 | 10h | I-01.17.INT_Main.18.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6351 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6350,6335 | 0h | I-01.17.INT_Main.18.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6352 |  | Auto Scheduled | דוחות מלאי הקרוב לפג תוקף. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.19 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6353 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.19.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6354 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.19.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6355 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.19.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6356 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.19.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6357 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.19.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6358 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6357 | 10h | I-01.17.INT_Main.19.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6359 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6358 | 1h | I-01.17.INT_Main.19.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6360 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.19.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6361 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6359 | 10h | I-01.17.INT_Main.19.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6362 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6361 | 10h | I-01.17.INT_Main.19.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6363 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6362 | 1h | I-01.17.INT_Main.19.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6364 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6363 | 21h | I-01.17.INT_Main.19.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6365 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6364 | 21h | I-01.17.INT_Main.19.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6366 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6365 | 5h | I-01.17.INT_Main.19.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6367 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6366 | 21h | I-01.17.INT_Main.19.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6368 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6367 | 15h | I-01.17.INT_Main.19.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6369 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6368 | 10h | I-01.17.INT_Main.19.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6370 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6369,6366 | 10h | I-01.17.INT_Main.19.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6371 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6370,6355 | 0h | I-01.17.INT_Main.19.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6372 |  | Auto Scheduled | דוחות מלאי הקרוב לפג תוקף לפי קווים, לקוחות, מחסנים, תאריכים. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.20 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6373 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.20.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6374 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.20.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6375 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.20.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6376 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.20.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6377 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.20.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6378 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6377 | 10h | I-01.17.INT_Main.20.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6379 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6378 | 1h | I-01.17.INT_Main.20.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6380 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.20.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6381 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6379 | 10h | I-01.17.INT_Main.20.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6382 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6381 | 10h | I-01.17.INT_Main.20.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6383 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6382 | 1h | I-01.17.INT_Main.20.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6384 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6383 | 21h | I-01.17.INT_Main.20.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6385 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6384 | 21h | I-01.17.INT_Main.20.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6386 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6385 | 5h | I-01.17.INT_Main.20.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6387 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6386 | 21h | I-01.17.INT_Main.20.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6388 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6387 | 15h | I-01.17.INT_Main.20.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6389 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6388 | 10h | I-01.17.INT_Main.20.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6390 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6389,6386 | 10h | I-01.17.INT_Main.20.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6391 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6390,6375 | 0h | I-01.17.INT_Main.20.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6392 |  | Auto Scheduled | דוחות מלאי לפי סטאטוס. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.21 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6393 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.21.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6394 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.21.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6395 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.21.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6396 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.21.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6397 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.21.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6398 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6397 | 10h | I-01.17.INT_Main.21.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6399 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6398 | 1h | I-01.17.INT_Main.21.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6400 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.21.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6401 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6399 | 10h | I-01.17.INT_Main.21.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6402 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6401 | 10h | I-01.17.INT_Main.21.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6403 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6402 | 1h | I-01.17.INT_Main.21.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6404 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6403 | 21h | I-01.17.INT_Main.21.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6405 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6404 | 21h | I-01.17.INT_Main.21.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6406 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6405 | 5h | I-01.17.INT_Main.21.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6407 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6406 | 21h | I-01.17.INT_Main.21.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6408 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6407 | 15h | I-01.17.INT_Main.21.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6409 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6408 | 10h | I-01.17.INT_Main.21.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6410 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6409,6406 | 10h | I-01.17.INT_Main.21.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6411 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6410,6395 | 0h | I-01.17.INT_Main.21.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6412 |  | Auto Scheduled | דוחות תנועת מלאי לפי פרטו במחסנים. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.22 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6413 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.22.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6414 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.17.INT_Main.22.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6415 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.17.INT_Main.22.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6416 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.22.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6417 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.17.INT_Main.22.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6418 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6417 | 10h | I-01.17.INT_Main.22.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6419 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6418 | 1h | I-01.17.INT_Main.22.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6420 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.17.INT_Main.22.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6421 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6419 | 10h | I-01.17.INT_Main.22.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6422 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6421 | 10h | I-01.17.INT_Main.22.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6423 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6422 | 1h | I-01.17.INT_Main.22.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6424 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6423 | 21h | I-01.17.INT_Main.22.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6425 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6424 | 21h | I-01.17.INT_Main.22.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6426 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6425 | 5h | I-01.17.INT_Main.22.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6427 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6426 | 21h | I-01.17.INT_Main.22.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6428 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6427 | 15h | I-01.17.INT_Main.22.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6429 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6428 | 10h | I-01.17.INT_Main.22.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6430 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6429,6426 | 10h | I-01.17.INT_Main.22.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6431 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6430,6415 | 0h | I-01.17.INT_Main.22.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6432 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6433 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6434 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6435 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6436 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6437 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6438 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6439 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6440 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6441 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6442 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6443 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6444 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6445 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6446 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 2,175h | I-01.18 |  |  | hd |  |  |  | NA | As Soon As Possible | 3
6447 |  | Auto Scheduled | I-01.18: לוח מחוונים KPI, BI.INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 2,175h | I-01.18.INT_Main |  |  | hd_1 |  |  |  | NA | As Soon As Possible | 4
6448 |  | Auto Scheduled | לוח מחוונים KPI, BI - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.01 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6449 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.01.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6450 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.01.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6451 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.01.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6452 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.01.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6453 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.01.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6454 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6453 | 10h | I-01.18.INT_Main.01.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6455 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6454 | 1h | I-01.18.INT_Main.01.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6456 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.01.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6457 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6455 | 10h | I-01.18.INT_Main.01.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6458 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6457 | 10h | I-01.18.INT_Main.01.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6459 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6458 | 1h | I-01.18.INT_Main.01.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6460 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6459 | 21h | I-01.18.INT_Main.01.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6461 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6460 | 21h | I-01.18.INT_Main.01.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6462 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6461 | 5h | I-01.18.INT_Main.01.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6463 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6462 | 21h | I-01.18.INT_Main.01.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6464 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6463 | 15h | I-01.18.INT_Main.01.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6465 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6464 | 10h | I-01.18.INT_Main.01.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6466 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6465,6462 | 10h | I-01.18.INT_Main.01.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6467 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6466,6451 | 0h | I-01.18.INT_Main.01.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6468 |  | Auto Scheduled | מערכת ה- WMS תקבל בממשק אוטומטי ממערכת ה- ERP או מכל מקור אחר, את כל נתוני הפריטים ומאפייניהם כפי שיהיו קיימים במערכת ה- ERP בעת הקמת המערכת. כמו כן המערכת תאפשר הוספת מאפיינים ככל שידרשו ועדכון שוטף שלהם בכל תקופת הזיכיון. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.02 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6469 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.02.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6470 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.02.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6471 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6472 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6473 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.02.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6474 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6473 | 10h | I-01.18.INT_Main.02.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6475 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6474 | 1h | I-01.18.INT_Main.02.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6476 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6477 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6475 | 10h | I-01.18.INT_Main.02.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6478 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6477 | 10h | I-01.18.INT_Main.02.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6479 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6478 | 1h | I-01.18.INT_Main.02.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6480 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6479 | 21h | I-01.18.INT_Main.02.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6481 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6480 | 21h | I-01.18.INT_Main.02.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6482 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6481 | 5h | I-01.18.INT_Main.02.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6483 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6482 | 21h | I-01.18.INT_Main.02.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6484 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6483 | 15h | I-01.18.INT_Main.02.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6485 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6484 | 10h | I-01.18.INT_Main.02.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6486 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6485,6482 | 10h | I-01.18.INT_Main.02.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6487 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6486,6471 | 0h | I-01.18.INT_Main.02.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6488 |  | Auto Scheduled | מערכת ה- WMS תאפשר לקבל בממשק אוטומטי ממערכת ה- ERP מידע הנוגע לשינוי במספר קטלוגי של פריטים, וכן מיזוג בין מספרים קטלוגיים שונים, כולל כאלו שקיים עבורם מלאי, הזמנות פתוחות, צפי אספקה נכנסת, וכל תהליך פתוח עבורם, למספר קטלוגי יחיד. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.03 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6489 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.03.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6490 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.03.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6491 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.03.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6492 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.03.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6493 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.03.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6494 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6493 | 10h | I-01.18.INT_Main.03.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6495 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6494 | 1h | I-01.18.INT_Main.03.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6496 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.03.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6497 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6495 | 10h | I-01.18.INT_Main.03.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6498 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6497 | 10h | I-01.18.INT_Main.03.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6499 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6498 | 1h | I-01.18.INT_Main.03.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6500 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6499 | 21h | I-01.18.INT_Main.03.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6501 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6500 | 21h | I-01.18.INT_Main.03.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6502 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6501 | 5h | I-01.18.INT_Main.03.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6503 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6502 | 21h | I-01.18.INT_Main.03.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6504 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6503 | 15h | I-01.18.INT_Main.03.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6505 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6504 | 10h | I-01.18.INT_Main.03.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6506 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6505,6502 | 10h | I-01.18.INT_Main.03.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6507 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6506,6491 | 0h | I-01.18.INT_Main.03.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6508 |  | Auto Scheduled | מערכת ה- WMS תאפשר לשמור את המידע ההיסטורי לגבי מספרים קטלוגיים ששונו, מוזגו וכד'. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.04 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6509 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.04.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6510 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.04.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6511 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.04.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6512 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.04.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6513 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.04.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6514 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6513 | 10h | I-01.18.INT_Main.04.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6515 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6514 | 1h | I-01.18.INT_Main.04.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6516 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.04.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6517 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6515 | 10h | I-01.18.INT_Main.04.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6518 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6517 | 10h | I-01.18.INT_Main.04.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6519 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6518 | 1h | I-01.18.INT_Main.04.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6520 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6519 | 21h | I-01.18.INT_Main.04.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6521 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6520 | 21h | I-01.18.INT_Main.04.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6522 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6521 | 5h | I-01.18.INT_Main.04.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6523 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6522 | 21h | I-01.18.INT_Main.04.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6524 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6523 | 15h | I-01.18.INT_Main.04.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6525 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6524 | 10h | I-01.18.INT_Main.04.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6526 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6525,6522 | 10h | I-01.18.INT_Main.04.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6527 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6526,6511 | 0h | I-01.18.INT_Main.04.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6528 |  | Auto Scheduled | מערכת ה- WMS לא תוכל לשנות את מאפייני הפריטים שהתקבלו מה- ERP, אלא רק ע"י בקשה לשינוי ב- ERP שתופנה למזמין, כחלק מתהליך עבודה מובנה הדורש את אישור המזמין. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.05 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6529 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.05.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6530 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.05.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6531 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.05.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6532 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.05.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6533 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.05.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6534 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6533 | 10h | I-01.18.INT_Main.05.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6535 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6534 | 1h | I-01.18.INT_Main.05.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6536 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.05.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6537 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6535 | 10h | I-01.18.INT_Main.05.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6538 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6537 | 10h | I-01.18.INT_Main.05.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6539 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6538 | 1h | I-01.18.INT_Main.05.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6540 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6539 | 21h | I-01.18.INT_Main.05.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6541 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6540 | 21h | I-01.18.INT_Main.05.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6542 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6541 | 5h | I-01.18.INT_Main.05.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6543 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6542 | 21h | I-01.18.INT_Main.05.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6544 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6543 | 15h | I-01.18.INT_Main.05.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6545 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6544 | 10h | I-01.18.INT_Main.05.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6546 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6545,6542 | 10h | I-01.18.INT_Main.05.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6547 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6546,6531 | 0h | I-01.18.INT_Main.05.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6548 |  | Auto Scheduled | ככל שידרשו מאפיינים נוספים לניהול הפריטים לתפעול המרה"ס, יוכל הזכיין להוסיפם למערכת ה- WMS, ובלבד שלא יצרו סתירה עם מאפייני הפריטים שהתקבלו ממערכת ה- ERP. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.06 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6549 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.06.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6550 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.06.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6551 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.06.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6552 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.06.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6553 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.06.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6554 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6553 | 10h | I-01.18.INT_Main.06.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6555 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6554 | 1h | I-01.18.INT_Main.06.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6556 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.06.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6557 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6555 | 10h | I-01.18.INT_Main.06.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6558 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6557 | 10h | I-01.18.INT_Main.06.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6559 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6558 | 1h | I-01.18.INT_Main.06.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6560 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6559 | 21h | I-01.18.INT_Main.06.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6561 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6560 | 21h | I-01.18.INT_Main.06.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6562 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6561 | 5h | I-01.18.INT_Main.06.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6563 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6562 | 21h | I-01.18.INT_Main.06.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6564 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6563 | 15h | I-01.18.INT_Main.06.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6565 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6564 | 10h | I-01.18.INT_Main.06.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6566 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6565,6562 | 10h | I-01.18.INT_Main.06.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6567 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6566,6551 | 0h | I-01.18.INT_Main.06.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6568 |  | Auto Scheduled | מערכת ה- WMS תעביר בממשק אוטומטי למערכות הרלבנטיות את העדכונים הרלבנטיים במאפייני הפריטים ונתוניהם, לרבות מערכת ה- ERP, מערכות ה- WCS, מערכת ה- TMS וכד'. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.07 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6569 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.07.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6570 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.07.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6571 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.07.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6572 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.07.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6573 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.07.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6574 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6573 | 10h | I-01.18.INT_Main.07.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6575 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6574 | 1h | I-01.18.INT_Main.07.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6576 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.07.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6577 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6575 | 10h | I-01.18.INT_Main.07.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6578 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6577 | 10h | I-01.18.INT_Main.07.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6579 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6578 | 1h | I-01.18.INT_Main.07.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6580 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6579 | 21h | I-01.18.INT_Main.07.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6581 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6580 | 21h | I-01.18.INT_Main.07.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6582 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6581 | 5h | I-01.18.INT_Main.07.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6583 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6582 | 21h | I-01.18.INT_Main.07.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6584 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6583 | 15h | I-01.18.INT_Main.07.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6585 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6584 | 10h | I-01.18.INT_Main.07.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6586 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6585,6582 | 10h | I-01.18.INT_Main.07.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6587 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6586,6571 | 0h | I-01.18.INT_Main.07.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6588 |  | Auto Scheduled | מערכת ה- WMS תאפשר לנהל כל פריט בהתאם למאפיינים הנדרשים, ניהול כמותי, סידורי וסידרתי, לרבות שילוב בין סידורי וסידרתי, אצווה ותאריכי תוקף. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.08 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6589 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.08.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6590 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.08.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6591 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.08.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6592 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.08.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6593 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.08.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6594 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6593 | 10h | I-01.18.INT_Main.08.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6595 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6594 | 1h | I-01.18.INT_Main.08.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6596 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.08.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6597 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6595 | 10h | I-01.18.INT_Main.08.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6598 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6597 | 10h | I-01.18.INT_Main.08.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6599 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6598 | 1h | I-01.18.INT_Main.08.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6600 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6599 | 21h | I-01.18.INT_Main.08.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6601 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6600 | 21h | I-01.18.INT_Main.08.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6602 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6601 | 5h | I-01.18.INT_Main.08.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6603 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6602 | 21h | I-01.18.INT_Main.08.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6604 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6603 | 15h | I-01.18.INT_Main.08.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6605 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6604 | 10h | I-01.18.INT_Main.08.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6606 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6605,6602 | 10h | I-01.18.INT_Main.08.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6607 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6606,6591 | 0h | I-01.18.INT_Main.08.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6608 |  | Auto Scheduled | מערכת ה- WMS תאפשר הגדרה וניהול של מדיניות וחוקה לפי חתכים של מאפייני קטלוג הפריט (לדוגמא: מדיניות ניהול מלאי, מדיניות אחסנה, מדיניות ליקוט, מדיניות ספירה, מדיניות תחזוקה תקופתית וכד'). - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.09 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6609 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.09.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6610 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.09.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6611 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.09.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6612 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.09.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6613 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.09.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6614 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6613 | 10h | I-01.18.INT_Main.09.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6615 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6614 | 1h | I-01.18.INT_Main.09.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6616 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.09.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6617 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6615 | 10h | I-01.18.INT_Main.09.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6618 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6617 | 10h | I-01.18.INT_Main.09.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6619 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6618 | 1h | I-01.18.INT_Main.09.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6620 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6619 | 21h | I-01.18.INT_Main.09.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6621 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6620 | 21h | I-01.18.INT_Main.09.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6622 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6621 | 5h | I-01.18.INT_Main.09.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6623 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6622 | 21h | I-01.18.INT_Main.09.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6624 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6623 | 15h | I-01.18.INT_Main.09.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6625 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6624 | 10h | I-01.18.INT_Main.09.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6626 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6625,6622 | 10h | I-01.18.INT_Main.09.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6627 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6626,6611 | 0h | I-01.18.INT_Main.09.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6628 |  | Auto Scheduled | המערכת תאפשר לזכיין הוספה של כללים נוספים ובתנאי שלא יסתרו את מדיניות המזמין. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.10 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6629 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.10.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6630 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.10.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6631 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.10.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6632 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.10.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6633 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.10.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6634 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6633 | 10h | I-01.18.INT_Main.10.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6635 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6634 | 1h | I-01.18.INT_Main.10.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6636 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.10.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6637 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6635 | 10h | I-01.18.INT_Main.10.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6638 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6637 | 10h | I-01.18.INT_Main.10.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6639 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6638 | 1h | I-01.18.INT_Main.10.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6640 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6639 | 21h | I-01.18.INT_Main.10.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6641 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6640 | 21h | I-01.18.INT_Main.10.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6642 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6641 | 5h | I-01.18.INT_Main.10.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6643 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6642 | 21h | I-01.18.INT_Main.10.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6644 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6643 | 15h | I-01.18.INT_Main.10.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6645 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6644 | 10h | I-01.18.INT_Main.10.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6646 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6645,6642 | 10h | I-01.18.INT_Main.10.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6647 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6646,6631 | 0h | I-01.18.INT_Main.10.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6648 |  | Auto Scheduled | המערכת תאפשר לנהל ולהציג בשקיפות את כלל המדיניות והחוקה בכלים ומסכים ייעודיים ע"י משתמש ללא צורך בכתיבת קוד, לרבות אבחנה בין מדיניות והחוקה שנובע מדרישות המזמין לבין מדיניות והחוקה שיישם הזכיין לצרכיו. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.11 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6649 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.11.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6650 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.11.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6651 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.11.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6652 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.11.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6653 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.11.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6654 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6653 | 10h | I-01.18.INT_Main.11.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6655 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6654 | 1h | I-01.18.INT_Main.11.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6656 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.11.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6657 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6655 | 10h | I-01.18.INT_Main.11.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6658 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6657 | 10h | I-01.18.INT_Main.11.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6659 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6658 | 1h | I-01.18.INT_Main.11.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6660 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6659 | 21h | I-01.18.INT_Main.11.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6661 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6660 | 21h | I-01.18.INT_Main.11.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6662 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6661 | 5h | I-01.18.INT_Main.11.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6663 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6662 | 21h | I-01.18.INT_Main.11.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6664 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6663 | 15h | I-01.18.INT_Main.11.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6665 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6664 | 10h | I-01.18.INT_Main.11.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6666 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6665,6662 | 10h | I-01.18.INT_Main.11.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6667 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6666,6651 | 0h | I-01.18.INT_Main.11.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6668 |  | Auto Scheduled | בנוסף, מערכת ה- WMS תאפשר לנהל ברמת הפריט לפחות את כל האמור להלן: - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.12 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6669 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.12.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6670 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.12.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6671 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.12.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6672 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.12.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6673 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.12.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6674 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6673 | 10h | I-01.18.INT_Main.12.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6675 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6674 | 1h | I-01.18.INT_Main.12.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6676 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.12.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6677 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6675 | 10h | I-01.18.INT_Main.12.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6678 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6677 | 10h | I-01.18.INT_Main.12.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6679 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6678 | 1h | I-01.18.INT_Main.12.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6680 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6679 | 21h | I-01.18.INT_Main.12.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6681 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6680 | 21h | I-01.18.INT_Main.12.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6682 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6681 | 5h | I-01.18.INT_Main.12.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6683 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6682 | 21h | I-01.18.INT_Main.12.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6684 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6683 | 15h | I-01.18.INT_Main.12.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6685 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6684 | 10h | I-01.18.INT_Main.12.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6686 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6685,6682 | 10h | I-01.18.INT_Main.12.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6687 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6686,6671 | 0h | I-01.18.INT_Main.12.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6688 |  | Auto Scheduled | סדר המרת יחידות מידה בין מארזים רבות לכל פריט, לרבות בהתאם לספק, אצווה וכד', וכן ניהול של כל המידות ומשקל לכל מארז. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.13 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6689 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.13.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6690 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.13.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6691 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.13.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6692 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.13.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6693 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.13.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6694 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6693 | 10h | I-01.18.INT_Main.13.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6695 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6694 | 1h | I-01.18.INT_Main.13.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6696 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.13.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6697 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6695 | 10h | I-01.18.INT_Main.13.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6698 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6697 | 10h | I-01.18.INT_Main.13.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6699 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6698 | 1h | I-01.18.INT_Main.13.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6700 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6699 | 21h | I-01.18.INT_Main.13.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6701 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6700 | 21h | I-01.18.INT_Main.13.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6702 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6701 | 5h | I-01.18.INT_Main.13.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6703 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6702 | 21h | I-01.18.INT_Main.13.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6704 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6703 | 15h | I-01.18.INT_Main.13.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6705 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6704 | 10h | I-01.18.INT_Main.13.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6706 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6705,6702 | 10h | I-01.18.INT_Main.13.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6707 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6706,6691 | 0h | I-01.18.INT_Main.13.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6708 |  | Auto Scheduled | פעילות ערך מוסף – VAS. - INT_Main | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.14 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6709 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.14.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6710 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.14.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6711 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.14.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6712 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.14.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6713 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.14.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6714 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6713 | 10h | I-01.18.INT_Main.14.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6715 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6714 | 1h | I-01.18.INT_Main.14.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6716 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.14.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6717 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6715 | 10h | I-01.18.INT_Main.14.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6718 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6717 | 10h | I-01.18.INT_Main.14.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6719 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6718 | 1h | I-01.18.INT_Main.14.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6720 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6719 | 21h | I-01.18.INT_Main.14.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6721 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6720 | 21h | I-01.18.INT_Main.14.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6722 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6721 | 5h | I-01.18.INT_Main.14.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6723 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6722 | 21h | I-01.18.INT_Main.14.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6724 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6723 | 15h | I-01.18.INT_Main.14.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6725 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6724 | 10h | I-01.18.INT_Main.14.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6726 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6725,6722 | 10h | I-01.18.INT_Main.14.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6727 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6726,6711 | 0h | I-01.18.INT_Main.14.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6728 |  | Auto Scheduled | ניהול פריטים גנריים - פריטים שווי ערך פונקציונאלי אחד לשני המאוגדים תחת פריט אב (המערכת תאפשר לקבל בהזמנה פריט אב ולאפשר בחירה וליקוט של פריטים גנריים). בניהול המלאי הרגיל תנהל המערכת את הפריטים הגנריים ככל פריט אחר בנפרד אך בהתייחס למלאי זמין להזמנות הם | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.15 | כתיבת מסמך דרישות הממשק | זכיין | parent | אבי פרישמן |  | INT_Main | NA | As Soon As Possible | 5
6729 |  | Auto Scheduled | Sub Tasks | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.15.01 |  | זכיין | Sub Tasks |  |  |  | NA | As Soon As Possible | 6
6730 |  | Auto Scheduled | LifeCycle Tasks | 145 days | May 18, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 |  | 145h | I-01.18.INT_Main.15.02 |  | זכיין | LC Tasks |  |  |  | NA | As Soon As Possible | 6
6731 |  | Auto Scheduled | Interface Milestone | 0 days | May 18, 2021 8:00 AM | May 18, 2021 8:00 AM | 0 |  | 0h | I-01.18.INT_Main.15.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6732 |  | Auto Scheduled | דרישות עסקיות לממשק | 21 days | May 18, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.15.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6733 |  | Auto Scheduled | כתיבת מסמך דרישות הממשק | 10 days | May 18, 2021 8:00 AM | May 31, 2021 5:00 PM | 0 |  | 10h | I-01.18.INT_Main.15.02.02.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6734 |  | Auto Scheduled | ניהול סיכומי הדיון ועדכון המסמכים בהתאם | 10 days | June 1, 2021 8:00 AM | June 14, 2021 5:00 PM | 0 | 6733 | 10h | I-01.18.INT_Main.15.02.02.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6735 |  | Auto Scheduled | חתימה על מסמך דרישות ממשק | 1 day | June 15, 2021 8:00 AM | June 15, 2021 5:00 PM | 0 | 6734 | 1h | I-01.18.INT_Main.15.02.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6736 |  | Auto Scheduled | איפיון הממשק | 21 days | June 16, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 |  | 21h | I-01.18.INT_Main.15.02.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6737 |  | Auto Scheduled | תיעוד שלם של Use Cases | 10 days | June 16, 2021 8:00 AM | June 29, 2021 5:00 PM | 0 | 6735 | 10h | I-01.18.INT_Main.15.02.03.01 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6738 |  | Auto Scheduled | תיעוד שלם של ניתוח משמעויות | 10 days | June 30, 2021 8:00 AM | July 13, 2021 5:00 PM | 0 | 6737 | 10h | I-01.18.INT_Main.15.02.03.02 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6739 |  | Auto Scheduled | חתימה על מסמך איפיון ממשק | 1 day | July 14, 2021 8:00 AM | July 14, 2021 5:00 PM | 0 | 6738 | 1h | I-01.18.INT_Main.15.02.03.03 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 8
6740 |  | Auto Scheduled | פיתוח הממשק | 21 days | July 15, 2021 8:00 AM | August 12, 2021 5:00 PM | 0 | 6739 | 21h | I-01.18.INT_Main.15.02.04 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6741 |  | Auto Scheduled | פיתוח בדיקות קבלה | 21 days | August 13, 2021 8:00 AM | September 10, 2021 5:00 PM | 0 | 6740 | 21h | I-01.18.INT_Main.15.02.05 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6742 |  | Auto Scheduled | בדיקות קבלה פנימיות ומכנות להעברה לבדיקות | 5 days | September 13, 2021 8:00 AM | September 17, 2021 5:00 PM | 0 | 6741 | 5h | I-01.18.INT_Main.15.02.06 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6743 |  | Auto Scheduled | בדיקות קבלה אחד לאחד על פי Use Cases שהוגדרו | 21 days | September 20, 2021 8:00 AM | October 18, 2021 5:00 PM | 0 | 6742 | 21h | I-01.18.INT_Main.15.02.07 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6744 |  | Auto Scheduled | בדיקות קבלה ועומסים בהתאם ל-SLA שהוגדר | 15 days | October 19, 2021 8:00 AM | November 8, 2021 5:00 PM | 0 | 6743 | 15h | I-01.18.INT_Main.15.02.08 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6745 |  | Auto Scheduled | מוכנות לעליה לסביבת אינטגרציה | 10 days | November 9, 2021 8:00 AM | November 22, 2021 5:00 PM | 0 | 6744 | 10h | I-01.18.INT_Main.15.02.09 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6746 |  | Auto Scheduled | מוכנות הממשק לעליה לאויר | 10 days | November 23, 2021 8:00 AM | December 6, 2021 5:00 PM | 0 | 6745,6742 | 10h | I-01.18.INT_Main.15.02.10 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6747 |  | Auto Scheduled | משימת ממשק ראשי עלתה לאויר | 0 days | December 6, 2021 5:00 PM | December 6, 2021 5:00 PM | 0 | 6746,6731 | 0h | I-01.18.INT_Main.15.02.11 |  |  | rule |  |  | INT_Main | NA | As Soon As Possible | 7
6748 | [6 empty] | 0 | [11 empty] | 7
6749 | [6 empty] | 0 | [11 empty] | 7
6750 | [6 empty] | 0 | [11 empty] | 7
6751 | [6 empty] | 0 | [11 empty] | 7
6752 | [6 empty] | 0 | [11 empty] | 7
6753 | [6 empty] | 0 | [11 empty] | 7
6754 | [6 empty] | 0 | [11 empty] | 7
6755 | [6 empty] | 0 | [11 empty] | 7
6756 | [6 empty] | 0 | [11 empty] | 7
6757 | [6 empty] | 0 | [11 empty] | 7
6758 | [6 empty] | 0 | [11 empty] | 7
6759 | [6 empty] | 0 | [11 empty] | 7
6760 | [6 empty] | 0 | [11 empty] | 7
6761 | [6 empty] | 0 | [11 empty] | 7
6762 | [6 empty] | 0 | [11 empty] | 7
6763 | [6 empty] | 0 | [11 empty] | 7
6764 | [6 empty] | 0 | [11 empty] | 7
6765 | [6 empty] | 0 | [11 empty] | 7
6766 | [6 empty] | 0 | [11 empty] | 7
6767 | [6 empty] | 0 | [11 empty] | 7
6768 | [6 empty] | 0 | [11 empty] | 7
6769 | [6 empty] | 0 | [11 empty] | 7
6770 | [6 empty] | 0 | [11 empty] | 7
6771 | [6 empty] | 0 | [11 empty] | 7
6772 | [6 empty] | 0 | [11 empty] | 7
6773 | [6 empty] | 0 | [11 empty] | 7
6774 | [6 empty] | 0 | [11 empty] | 7
6775 | [6 empty] | 0 | [11 empty] | 7
6776 | [6 empty] | 0 | [11 empty] | 7
6777 | [6 empty] | 0 | [11 empty] | 7
6778 | [6 empty] | 0 | [11 empty] | 7
6779 | [6 empty] | 0 | [11 empty] | 7
6780 | [6 empty] | 0 | [11 empty] | 7
6781 | [6 empty] | 0 | [11 empty] | 7
6782 | [6 empty] | 0 | [11 empty] | 7
6783 | [6 empty] | 0 | [11 empty] | 7
6784 | [6 empty] | 0 | [11 empty] | 7
6785 | [6 empty] | 0 | [11 empty] | 7
6786 | [6 empty] | 0 | [11 empty] | 7
6787 | [6 empty] | 0 | [11 empty] | 7
6788 | [6 empty] | 0 | [11 empty] | 7
6789 | [6 empty] | 0 | [11 empty] | 7
6790 | [6 empty] | 0 | [11 empty] | 7
6791 | [6 empty] | 0 | [11 empty] | 7
6792 | [6 empty] | 0 | [11 empty] | 7
6793 | [6 empty] | 0 | [11 empty] | 7
6794 | [6 empty] | 0 | [11 empty] | 7
6795 | [6 empty] | 0 | [11 empty] | 7
6796 | [6 empty] | 0 | [11 empty] | 7
6797 | [6 empty] | 0 | [11 empty] | 7
6798 | [6 empty] | 0 | [11 empty] | 7
6799 | [6 empty] | 0 | [11 empty] | 7
6800 | [6 empty] | 0 | [11 empty] | 7
6801 | [6 empty] | 0 | [11 empty] | 7
6802 | [6 empty] | 0 | [11 empty] | 7
6803 | [6 empty] | 0 | [11 empty] | 7
6804 | [6 empty] | 0 | [11 empty] | 7
6805 | [6 empty] | 0 | [11 empty] | 7
6806 | [6 empty] | 0 | [11 empty] | 7
6807 | [6 empty] | 0 | [11 empty] | 7
6808 | [6 empty] | 0 | [11 empty] | 7
6809 | [6 empty] | 0 | [11 empty] | 7
6810 | [6 empty] | 0 | [11 empty] | 7
6811 | [6 empty] | 0 | [11 empty] | 7
6812 | [6 empty] | 0 | [11 empty] | 7
6813 | [6 empty] | 0 | [11 empty] | 7
6814 | [6 empty] | 0 | [11 empty] | 7
6815 | [6 empty] | 0 | [11 empty] | 7
6816 | [6 empty] | 0 | [11 empty] | 7
6817 | [6 empty] | 0 | [11 empty] | 7
6818 | [6 empty] | 0 | [11 empty] | 7
6819 | [6 empty] | 0 | [11 empty] | 7
6820 | [6 empty] | 0 | [11 empty] | 7
6821 | [6 empty] | 0 | [11 empty] | 7
6822 | [6 empty] | 0 | [11 empty] | 7
6823 | [6 empty] | 0 | [11 empty] | 7
6824 | [6 empty] | 0 | [11 empty] | 7
6825 | [6 empty] | 0 | [11 empty] | 7
6826 | [6 empty] | 0 | [11 empty] | 7
6827 | [6 empty] | 0 | [11 empty] | 7
6828 | [6 empty] | 0 | [11 empty] | 7
6829 | [6 empty] | 0 | [11 empty] | 7
6830 | [6 empty] | 0 | [11 empty] | 7
6831 | [6 empty] | 0 | [11 empty] | 7
6832 | [6 empty] | 0 | [11 empty] | 7
6833 | [6 empty] | 0 | [11 empty] | 7
6834 | [6 empty] | 0 | [11 empty] | 7
6835 | [6 empty] | 0 | [11 empty] | 7
6836 | [6 empty] | 0 | [11 empty] | 7
6837 | [6 empty] | 0 | [11 empty] | 7
6838 | [6 empty] | 0 | [11 empty] | 7
6839 | [6 empty] | 0 | [11 empty] | 7
6840 | [6 empty] | 0 | [11 empty] | 7
6841 | [6 empty] | 0 | [11 empty] | 7
6842 | [6 empty] | 0 | [11 empty] | 7
6843 | [6 empty] | 0 | [11 empty] | 7
6844 | [6 empty] | 0 | [11 empty] | 7
6845 | [6 empty] | 0 | [11 empty] | 7
6846 | [6 empty] | 0 | [11 empty] | 7
6847 | [6 empty] | 0 | [11 empty] | 7
6848 | [6 empty] | 0 | [11 empty] | 7
6849 | [6 empty] | 0 | [11 empty] | 7
6850 | [6 empty] | 0 | [11 empty] | 7
6851 | [6 empty] | 0 | [11 empty] | 7
6852 | [6 empty] | 0 | [11 empty] | 7
6853 | [6 empty] | 0 | [11 empty] | 7
6854 | [6 empty] | 0 | [11 empty] | 7
6855 | [6 empty] | 0 | [11 empty] | 7
6856 | [6 empty] | 0 | [11 empty] | 7
6857 | [6 empty] | 0 | [11 empty] | 7
6858 | [6 empty] | 0 | [11 empty] | 7
6859 | [6 empty] | 0 | [11 empty] | 7
6860 | [6 empty] | 0 | [11 empty] | 7
6861 | [6 empty] | 0 | [11 empty] | 7
6862 | [6 empty] | 0 | [11 empty] | 7
6863 | [6 empty] | 0 | [11 empty] | 7
6864 | [6 empty] | 0 | [11 empty] | 7
6865 | [6 empty] | 0 | [11 empty] | 7
6866 | [6 empty] | 0 | [11 empty] | 7
6867 | [6 empty] | 0 | [11 empty] | 7
6868 | [6 empty] | 0 | [11 empty] | 7
6869 | [6 empty] | 0 | [11 empty] | 7
6870 | [6 empty] | 0 | [11 empty] | 7
6871 | [6 empty] | 0 | [11 empty] | 7
6872 | [6 empty] | 0 | [11 empty] | 7
6873 | [6 empty] | 0 | [11 empty] | 7
6874 | [6 empty] | 0 | [11 empty] | 7
6875 | [6 empty] | 0 | [11 empty] | 7
6876 | [6 empty] | 0 | [11 empty] | 7
6877 | [6 empty] | 0 | [11 empty] | 7
6878 | [6 empty] | 0 | [11 empty] | 7
6879 | [6 empty] | 0 | [11 empty] | 7
6880 | [6 empty] | 0 | [11 empty] | 7
6881 | [6 empty] | 0 | [11 empty] | 7
6882 | [6 empty] | 0 | [11 empty] | 7
6883 | [6 empty] | 0 | [11 empty] | 7
6884 | [6 empty] | 0 | [11 empty] | 7
6885 | [6 empty] | 0 | [11 empty] | 7
6886 | [6 empty] | 0 | [11 empty] | 7
6887 | [6 empty] | 0 | [11 empty] | 7
6888 | [6 empty] | 0 | [11 empty] | 7
6889 | [6 empty] | 0 | [11 empty] | 7
6890 | [6 empty] | 0 | [11 empty] | 7
6891 | [6 empty] | 0 | [11 empty] | 7
6892 | [6 empty] | 0 | [11 empty] | 7
6893 | [6 empty] | 0 | [11 empty] | 7
6894 | [6 empty] | 0 | [11 empty] | 7
6895 | [6 empty] | 0 | [11 empty] | 7
6896 | [6 empty] | 0 | [11 empty] | 7
6897 | [6 empty] | 0 | [11 empty] | 7
6898 | [6 empty] | 0 | [11 empty] | 7
6899 | [6 empty] | 0 | [11 empty] | 7
6900 | [6 empty] | 0 | [11 empty] | 7
6901 | [6 empty] | 0 | [11 empty] | 7
6902 | [6 empty] | 0 | [11 empty] | 7
6903 | [6 empty] | 0 | [11 empty] | 7
6904 | [6 empty] | 0 | [11 empty] | 7
6905 | [6 empty] | 0 | [11 empty] | 7
6906 | [6 empty] | 0 | [11 empty] | 7
6907 | [6 empty] | 0 | [11 empty] | 7
6908 | [6 empty] | 0 | [11 empty] | 7
6909 | [6 empty] | 0 | [11 empty] | 7
6910 | [6 empty] | 0 | [11 empty] | 7
6911 | [6 empty] | 0 | [11 empty] | 7
6912 | [6 empty] | 0 | [11 empty] | 7
6913 | [6 empty] | 0 | [11 empty] | 7
6914 | [6 empty] | 0 | [11 empty] | 7
6915 | [6 empty] | 0 | [11 empty] | 7
6916 | [6 empty] | 0 | [11 empty] | 7
6917 | [6 empty] | 0 | [11 empty] | 7
6918 | [6 empty] | 0 | [11 empty] | 7
6919 | [6 empty] | 0 | [11 empty] | 7
6920 | [6 empty] | 0 | [11 empty] | 7
6921 | [6 empty] | 0 | [11 empty] | 7
6922 | [6 empty] | 0 | [11 empty] | 7
6923 | [6 empty] | 0 | [11 empty] | 7
6924 | [6 empty] | 0 | [11 empty] | 7
6925 | [6 empty] | 0 | [11 empty] | 7
6926 | [6 empty] | 0 | [11 empty] | 7
6927 | [6 empty] | 0 | [11 empty] | 7
6928 | [6 empty] | 0 | [11 empty] | 7
6929 |  | Manually Scheduled |  |  |  |  | 0 |  | 0h | [7 empty] | NA | As Soon As Possible | 7
6930 | [6 empty] | 0 | [11 empty] | 7
6931 | [6 empty] | 0 | [11 empty] | 7
6932 | [6 empty] | 0 | [11 empty] | 7
6933 | [6 empty] | 0 | [11 empty] | 7
6934 | [6 empty] | 0 | [11 empty] | 7
6935 | [6 empty] | 0 | [11 empty] | 7
6936 | [6 empty] | 0 | [11 empty] | 7
6937 | [6 empty] | 0 | [11 empty] | 7
6938 | [6 empty] | 0 | [11 empty] | 7
6939 | [6 empty] | 0 | [11 empty] | 7
6940 | [6 empty] | 0 | [11 empty] | 7
6941 | [6 empty] | 0 | [11 empty] | 7
6942 | [6 empty] | 0 | [11 empty] | 7
6943 | [6 empty] | 0 | [11 empty] | 7
6944 | [6 empty] | 0 | [11 empty] | 7
6945 | [6 empty] | 0 | [11 empty] | 7
6946 | [6 empty] | 0 | [11 empty] | 7
6947 | [6 empty] | 0 | [11 empty] | 7
6948 | [6 empty] | 0 | [11 empty] | 7
6949 | [6 empty] | 0 | [11 empty] | 7
6950 | [6 empty] | 0 | [11 empty] | 7
6951 | [6 empty] | 0 | [11 empty] | 7
6952 | [6 empty] | 0 | [11 empty] | 7
6953 | [6 empty] | 0 | [11 empty] | 7
6954 | [6 empty] | 0 | [11 empty] | 7
6955 | [6 empty] | 0 | [11 empty] | 7
6956 | [6 empty] | 0 | [11 empty] | 7
6957 | [6 empty] | 0 | [11 empty] | 7
6958 | [6 empty] | 0 | [11 empty] | 7
6959 | [6 empty] | 0 | [11 empty] | 7
6960 | [6 empty] | 0 | [11 empty] | 7
6961 | [6 empty] | 0 | [11 empty] | 7
6962 | [6 empty] | 0 | [11 empty] | 7
6963 | [6 empty] | 0 | [11 empty] | 7
6964 | [6 empty] | 0 | [11 empty] | 7
6965 | [6 empty] | 0 | [11 empty] | 7
6966 | [6 empty] | 0 | [11 empty] | 7
6967 | [6 empty] | 0 | [11 empty] | 7
6968 | [6 empty] | 0 | [11 empty] | 7
6969 | [6 empty] | 0 | [11 empty] | 7
6970 | [6 empty] | 0 | [11 empty] | 7
6971 | [6 empty] | 0 | [11 empty] | 7
6972 | [6 empty] | 0 | [11 empty] | 7
6973 | [6 empty] | 0 | [11 empty] | 7
6974 | [6 empty] | 0 | [11 empty] | 7
6975 | [6 empty] | 0 | [11 empty] | 7
6976 | [6 empty] | 0 | [11 empty] | 7
6977 | [6 empty] | 0 | [11 empty] | 7
6978 | [6 empty] | 0 | [11 empty] | 7
6979 | [6 empty] | 0 | [11 empty] | 7
6980 | [6 empty] | 0 | [11 empty] | 7
6981 | [6 empty] | 0 | [11 empty] | 7
6982 | [6 empty] | 0 | [11 empty] | 7
6983 | [6 empty] | 0 | [11 empty] | 7
6984 | [6 empty] | 0 | [11 empty] | 7
6985 | [6 empty] | 0 | [11 empty] | 7
6986 | [6 empty] | 0 | [11 empty] | 7
6987 | [6 empty] | 0 | [11 empty] | 7
6988 | [6 empty] | 0 | [11 empty] | 7
6989 | [6 empty] | 0 | [11 empty] | 7
6990 | [6 empty] | 0 | [11 empty] | 7
6991 | [6 empty] | 0 | [11 empty] | 7
6992 | [6 empty] | 0 | [11 empty] | 7
6993 | [6 empty] | 0 | [11 empty] | 7
6994 | [6 empty] | 0 | [11 empty] | 7
6995 | [6 empty] | 0 | [11 empty] | 7
6996 | [6 empty] | 0 | [11 empty] | 7
6997 | [6 empty] | 0 | [11 empty] | 7
6998 | [6 empty] | 0 | [11 empty] | 7
6999 | [6 empty] | 0 | [11 empty] | 7
7000 | [6 empty] | 0 | [11 empty] | 7
7001 | [6 empty] | 0 | [11 empty] | 7
7002 | [6 empty] | 0 | [11 empty] | 7
7003 | [6 empty] | 0 | [11 empty] | 7
7004 | [6 empty] | 0 | [11 empty] | 7
7005 | [6 empty] | 0 | [11 empty] | 7
7006 | [6 empty] | 0 | [11 empty] | 7
7007 | [6 empty] | 0 | [11 empty] | 7
7008 | [6 empty] | 0 | [11 empty] | 7
7009 | [6 empty] | 0 | [11 empty] | 7
7010 | [6 empty] | 0 | [11 empty] | 7
7011 | [6 empty] | 0 | [11 empty] | 7
7012 | [6 empty] | 0 | [11 empty] | 7
7013 | [6 empty] | 0 | [11 empty] | 7
7014 | [6 empty] | 0 | [11 empty] | 7
7015 | [6 empty] | 0 | [11 empty] | 7
7016 | [6 empty] | 0 | [11 empty] | 7
7017 | [6 empty] | 0 | [11 empty] | 7
7018 | [6 empty] | 0 | [11 empty] | 7
7019 | [6 empty] | 0 | [11 empty] | 7
7020 | [6 empty] | 0 | [11 empty] | 7
7021 | [6 empty] | 0 | [11 empty] | 7
7022 | [6 empty] | 0 | [11 empty] | 7
7023 | [6 empty] | 0 | [11 empty] | 7
7024 | [6 empty] | 0 | [11 empty] | 7
7025 | [6 empty] | 0 | [11 empty] | 7
7026 | [6 empty] | 0 | [11 empty] | 7
7027 | [6 empty] | 0 | [11 empty] | 7
7028 | [6 empty] | 0 | [11 empty] | 7
7029 | [6 empty] | 0 | [11 empty] | 7
7030 | [6 empty] | 0 | [11 empty] | 7
7031 | [6 empty] | 0 | [11 empty] | 7
7032 | [6 empty] | 0 | [11 empty] | 7
7033 | [6 empty] | 0 | [11 empty] | 7
7034 | [6 empty] | 0 | [11 empty] | 7
7035 | [6 empty] | 0 | [11 empty] | 7
7036 | [6 empty] | 0 | [11 empty] | 7
7037 | [6 empty] | 0 | [11 empty] | 7
7038 | [6 empty] | 0 | [11 empty] | 7
7039 | [6 empty] | 0 | [11 empty] | 7
7040 | [6 empty] | 0 | [11 empty] | 7
7041 | [6 empty] | 0 | [11 empty] | 7
7042 | [6 empty] | 0 | [11 empty] | 7
7043 | [6 empty] | 0 | [11 empty] | 7
7044 | [6 empty] | 0 | [11 empty] | 7
7045 | [6 empty] | 0 | [11 empty] | 7
7046 | [6 empty] | 0 | [11 empty] | 7
7047 | [6 empty] | 0 | [11 empty] | 7
7048 | [6 empty] | 0 | [11 empty] | 7
7049 | [6 empty] | 0 | [11 empty] | 7
7050 | [6 empty] | 0 | [11 empty] | 7
7051 | [6 empty] | 0 | [11 empty] | 7
7052 | [6 empty] | 0 | [11 empty] | 7
7053 | [6 empty] | 0 | [11 empty] | 7
7054 | [6 empty] | 0 | [11 empty] | 7
7055 | [6 empty] | 0 | [11 empty] | 7
7056 | [6 empty] | 0 | [11 empty] | 7
7057 | [6 empty] | 0 | [11 empty] | 7
7058 | [6 empty] | 0 | [11 empty] | 7
7059 | [6 empty] | 0 | [11 empty] | 7
7060 | [6 empty] | 0 | [11 empty] | 7
7061 | [6 empty] | 0 | [11 empty] | 7
7062 | [6 empty] | 0 | [11 empty] | 7
7063 | [6 empty] | 0 | [11 empty] | 7
7064 | [6 empty] | 0 | [11 empty] | 7
7065 | [6 empty] | 0 | [11 empty] | 7
7066 | [6 empty] | 0 | [11 empty] | 7
7067 | [6 empty] | 0 | [11 empty] | 7
7068 | [6 empty] | 0 | [11 empty] | 7
7069 | [6 empty] | 0 | [11 empty] | 7
7070 | [6 empty] | 0 | [11 empty] | 7
7071 | [6 empty] | 0 | [11 empty] | 7
7072 | [6 empty] | 0 | [11 empty] | 7
7073 | [6 empty] | 0 | [11 empty] | 7
7074 | [6 empty] | 0 | [11 empty] | 7
7075 | [6 empty] | 0 | [11 empty] | 7
7076 | [6 empty] | 0 | [11 empty] | 7
7077 | [6 empty] | 0 | [11 empty] | 7
7078 | [6 empty] | 0 | [11 empty] | 7
7079 | [6 empty] | 0 | [11 empty] | 7
7080 | [6 empty] | 0 | [11 empty] | 7
7081 | [6 empty] | 0 | [11 empty] | 7
7082 | [6 empty] | 0 | [11 empty] | 7
7083 | [6 empty] | 0 | [11 empty] | 7
7084 | [6 empty] | 0 | [11 empty] | 7
7085 | [6 empty] | 0 | [11 empty] | 7
7086 | [6 empty] | 0 | [11 empty] | 7
7087 | [6 empty] | 0 | [11 empty] | 7
7088 | [6 empty] | 0 | [11 empty] | 7
7089 | [6 empty] | 0 | [11 empty] | 7
7090 | [6 empty] | 0 | [11 empty] | 7
7091 | [6 empty] | 0 | [11 empty] | 7
7092 | [6 empty] | 0 | [11 empty] | 7
7093 | [6 empty] | 0 | [11 empty] | 7
7094 | [6 empty] | 0 | [11 empty] | 7
7095 | [6 empty] | 0 | [11 empty] | 7
7096 | [6 empty] | 0 | [11 empty] | 7
7097 | [6 empty] | 0 | [11 empty] | 7
7098 | [6 empty] | 0 | [11 empty] | 7
7099 | [6 empty] | 0 | [11 empty] | 7
7100 | [6 empty] | 0 | [11 empty] | 7
7101 | [6 empty] | 0 | [11 empty] | 7
7102 | [6 empty] | 0 | [11 empty] | 7
7103 | [6 empty] | 0 | [11 empty] | 7
7104 | [6 empty] | 0 | [11 empty] | 7
7105 | [6 empty] | 0 | [11 empty] | 7
7106 | [6 empty] | 0 | [11 empty] | 7
7107 | [6 empty] | 0 | [11 empty] | 7
7108 | [6 empty] | 0 | [11 empty] | 7
7109 | [6 empty] | 0 | [11 empty] | 7
7110 | [6 empty] | 0 | [11 empty] | 7
7111 | [6 empty] | 0 | [11 empty] | 7
7112 | [6 empty] | 0 | [11 empty] | 7
7113 | [6 empty] | 0 | [11 empty] | 7
7114 | [6 empty] | 0 | [11 empty] | 7
7115 | [6 empty] | 0 | [11 empty] | 7
7116 | [6 empty] | 0 | [11 empty] | 7
7117 | [6 empty] | 0 | [11 empty] | 7
7118 | [6 empty] | 0 | [11 empty] | 7
7119 |  | Manually Scheduled |  |  |  |  | 0 |  | 0h | [7 empty] | NA | As Soon As Possible | 7
7120 | [6 empty] | 0 | [11 empty] | 7
7121 | [6 empty] | 0 | [11 empty] | 7
7122 | [6 empty] | 0 | [11 empty] | 7
7123 | [6 empty] | 0 | [11 empty] | 7
7124 | [6 empty] | 0 | [11 empty] | 7
7125 | [6 empty] | 0 | [11 empty] | 7
7126 | [6 empty] | 0 | [11 empty] | 7
7127 | [6 empty] | 0 | [11 empty] | 7
7128 | [6 empty] | 0 | [11 empty] | 7
7129 | [6 empty] | 0 | [11 empty] | 7
7130 | [6 empty] | 0 | [11 empty] | 7
7131 | [6 empty] | 0 | [11 empty] | 7
7132 | [6 empty] | 0 | [11 empty] | 7
7133 | [6 empty] | 0 | [11 empty] | 7
7134 | [6 empty] | 0 | [11 empty] | 7
7135 | [6 empty] | 0 | [11 empty] | 7
7136 | [6 empty] | 0 | [11 empty] | 7
7137 | [6 empty] | 0 | [11 empty] | 7
7138 | [6 empty] | 0 | [11 empty] | 7
7139 | [6 empty] | 0 | [11 empty] | 7
7140 | [6 empty] | 0 | [11 empty] | 7
7141 | [6 empty] | 0 | [11 empty] | 7
7142 | [6 empty] | 0 | [11 empty] | 7
7143 | [6 empty] | 0 | [11 empty] | 7
7144 | [6 empty] | 0 | [11 empty] | 7
7145 | [6 empty] | 0 | [11 empty] | 7
7146 | [6 empty] | 0 | [11 empty] | 7
7147 | [6 empty] | 0 | [11 empty] | 7
7148 | [6 empty] | 0 | [11 empty] | 7
7149 | [6 empty] | 0 | [11 empty] | 7
7150 | [6 empty] | 0 | [11 empty] | 7
7151 | [6 empty] | 0 | [11 empty] | 7
7152 | [6 empty] | 0 | [11 empty] | 7
7153 | [6 empty] | 0 | [11 empty] | 7
7154 | [6 empty] | 0 | [11 empty] | 7
7155 | [6 empty] | 0 | [11 empty] | 7
7156 | [6 empty] | 0 | [11 empty] | 7
7157 | [6 empty] | 0 | [11 empty] | 7
7158 | [6 empty] | 0 | [11 empty] | 7
7159 | [6 empty] | 0 | [11 empty] | 7
7160 | [6 empty] | 0 | [11 empty] | 7
7161 | [6 empty] | 0 | [11 empty] | 7
7162 | [6 empty] | 0 | [11 empty] | 7
7163 | [6 empty] | 0 | [11 empty] | 7
7164 | [6 empty] | 0 | [11 empty] | 7
7165 | [6 empty] | 0 | [11 empty] | 7
7166 | [6 empty] | 0 | [11 empty] | 7
7167 | [6 empty] | 0 | [11 empty] | 7
7168 | [6 empty] | 0 | [11 empty] | 7
7169 | [6 empty] | 0 | [11 empty] | 7
7170 | [6 empty] | 0 | [11 empty] | 7
7171 | [6 empty] | 0 | [11 empty] | 7
7172 | [6 empty] | 0 | [11 empty] | 7
7173 | [6 empty] | 0 | [11 empty] | 7
7174 | [6 empty] | 0 | [11 empty] | 7
7175 | [6 empty] | 0 | [11 empty] | 7
7176 | [6 empty] | 0 | [11 empty] | 7
7177 | [6 empty] | 0 | [11 empty] | 7
7178 | [6 empty] | 0 | [11 empty] | 7
7179 | [6 empty] | 0 | [11 empty] | 7
7180 | [6 empty] | 0 | [11 empty] | 7
7181 | [6 empty] | 0 | [11 empty] | 7
7182 | [6 empty] | 0 | [11 empty] | 7
7183 | [6 empty] | 0 | [11 empty] | 7
7184 | [6 empty] | 0 | [11 empty] | 7
7185 | [6 empty] | 0 | [11 empty] | 7
7186 | [6 empty] | 0 | [11 empty] | 7
7187 | [6 empty] | 0 | [11 empty] | 7
7188 | [6 empty] | 0 | [11 empty] | 7
7189 | [6 empty] | 0 | [11 empty] | 7
7190 | [6 empty] | 0 | [11 empty] | 7
7191 | [6 empty] | 0 | [11 empty] | 7
7192 | [6 empty] | 0 | [11 empty] | 7
7193 | [6 empty] | 0 | [11 empty] | 7
7194 | [6 empty] | 0 | [11 empty] | 7
7195 | [6 empty] | 0 | [11 empty] | 7
7196 | [6 empty] | 0 | [11 empty] | 7
7197 | [6 empty] | 0 | [11 empty] | 7
7198 | [6 empty] | 0 | [11 empty] | 7
7199 | [6 empty] | 0 | [11 empty] | 7
7200 | [6 empty] | 0 | [11 empty] | 7
7201 | [6 empty] | 0 | [11 empty] | 7
7202 | [6 empty] | 0 | [11 empty] | 7
7203 | [6 empty] | 0 | [11 empty] | 7
7204 | [6 empty] | 0 | [11 empty] | 7
7205 | [6 empty] | 0 | [11 empty] | 7
7206 | [6 empty] | 0 | [11 empty] | 7
7207 | [6 empty] | 0 | [11 empty] | 7
7208 | [6 empty] | 0 | [11 empty] | 7
7209 | [6 empty] | 0 | [11 empty] | 7
7210 | [6 empty] | 0 | [11 empty] | 7
7211 | [6 empty] | 0 | [11 empty] | 7
7212 | [6 empty] | 0 | [11 empty] | 7
7213 | [6 empty] | 0 | [11 empty] | 7
7214 | [6 empty] | 0 | [11 empty] | 7
7215 | [6 empty] | 0 | [11 empty] | 7
7216 | [6 empty] | 0 | [11 empty] | 7
7217 | [6 empty] | 0 | [11 empty] | 7
7218 | [6 empty] | 0 | [11 empty] | 7
7219 | [6 empty] | 0 | [11 empty] | 7
7220 | [6 empty] | 0 | [11 empty] | 7
7221 | [6 empty] | 0 | [11 empty] | 7
7222 | [6 empty] | 0 | [11 empty] | 7
7223 | [6 empty] | 0 | [11 empty] | 7
7224 | [6 empty] | 0 | [11 empty] | 7
7225 | [6 empty] | 0 | [11 empty] | 7
7226 | [6 empty] | 0 | [11 empty] | 7
7227 | [6 empty] | 0 | [11 empty] | 7
7228 | [6 empty] | 0 | [11 empty] | 7
7229 | [6 empty] | 0 | [11 empty] | 7
7230 | [6 empty] | 0 | [11 empty] | 7
7231 | [6 empty] | 0 | [11 empty] | 7
7232 | [6 empty] | 0 | [11 empty] | 7
7233 | [6 empty] | 0 | [11 empty] | 7
7234 | [6 empty] | 0 | [11 empty] | 7
7235 | [6 empty] | 0 | [11 empty] | 7
7236 | [6 empty] | 0 | [11 empty] | 7
7237 | [6 empty] | 0 | [11 empty] | 7
7238 | [6 empty] | 0 | [11 empty] | 7
7239 | [6 empty] | 0 | [11 empty] | 7
7240 | [6 empty] | 0 | [11 empty] | 7
7241 | [6 empty] | 0 | [11 empty] | 7
7242 | [6 empty] | 0 | [11 empty] | 7
7243 | [6 empty] | 0 | [11 empty] | 7
7244 | [6 empty] | 0 | [11 empty] | 7
7245 | [6 empty] | 0 | [11 empty] | 7
7246 | [6 empty] | 0 | [11 empty] | 7
7247 | [6 empty] | 0 | [11 empty] | 7
7248 | [6 empty] | 0 | [11 empty] | 7
7249 | [6 empty] | 0 | [11 empty] | 7
7250 | [6 empty] | 0 | [11 empty] | 7
7251 | [6 empty] | 0 | [11 empty] | 7
7252 | [6 empty] | 0 | [11 empty] | 7
7253 | [6 empty] | 0 | [11 empty] | 7
7254 | [6 empty] | 0 | [11 empty] | 7
7255 | [6 empty] | 0 | [11 empty] | 7
7256 | [6 empty] | 0 | [11 empty] | 7
7257 | [6 empty] | 0 | [11 empty] | 7
7258 | [6 empty] | 0 | [11 empty] | 7
7259 | [6 empty] | 0 | [11 empty] | 7
7260 | [6 empty] | 0 | [11 empty] | 7
7261 | [6 empty] | 0 | [11 empty] | 7
7262 | [6 empty] | 0 | [11 empty] | 7
7263 | [6 empty] | 0 | [11 empty] | 7
7264 | [6 empty] | 0 | [11 empty] | 7
7265 | [6 empty] | 0 | [11 empty] | 7
7266 | [6 empty] | 0 | [11 empty] | 7
7267 | [6 empty] | 0 | [11 empty] | 7
7268 | [6 empty] | 0 | [11 empty] | 7
7269 | [6 empty] | 0 | [11 empty] | 7
7270 | [6 empty] | 0 | [11 empty] | 7
7271 | [6 empty] | 0 | [11 empty] | 7
7272 | [6 empty] | 0 | [11 empty] | 7
7273 | [6 empty] | 0 | [11 empty] | 7
7274 | [6 empty] | 0 | [11 empty] | 7
7275 | [6 empty] | 0 | [11 empty] | 7
7276 | [6 empty] | 0 | [11 empty] | 7
7277 | [6 empty] | 0 | [11 empty] | 7
7278 | [6 empty] | 0 | [11 empty] | 7
7279 | [6 empty] | 0 | [11 empty] | 7
7280 | [6 empty] | 0 | [11 empty] | 7
7281 | [6 empty] | 0 | [11 empty] | 7
7282 | [6 empty] | 0 | [11 empty] | 7
7283 | [6 empty] | 0 | [11 empty] | 7
7284 | [6 empty] | 0 | [11 empty] | 7
7285 | [6 empty] | 0 | [11 empty] | 7
7286 | [6 empty] | 0 | [11 empty] | 7
7287 | [6 empty] | 0 | [11 empty] | 7
7288 | [6 empty] | 0 | [11 empty] | 7
7289 | [6 empty] | 0 | [11 empty] | 7
7290 | [6 empty] | 0 | [11 empty] | 7
7291 | [6 empty] | 0 | [11 empty] | 7
7292 | [6 empty] | 0 | [11 empty] | 7
7293 | [6 empty] | 0 | [11 empty] | 7
7294 | [6 empty] | 0 | [11 empty] | 7
7295 | [6 empty] | 0 | [11 empty] | 7
7296 | [6 empty] | 0 | [11 empty] | 7
7297 | [6 empty] | 0 | [11 empty] | 7
7298 | [6 empty] | 0 | [11 empty] | 7
7299 | [6 empty] | 0 | [11 empty] | 7
7300 | [6 empty] | 0 | [11 empty] | 7
7301 | [6 empty] | 0 | [11 empty] | 7
7302 | [6 empty] | 0 | [11 empty] | 7
7303 | [6 empty] | 0 | [11 empty] | 7
7304 | [6 empty] | 0 | [11 empty] | 7
7305 | [6 empty] | 0 | [11 empty] | 7
7306 | [6 empty] | 0 | [11 empty] | 7
7307 | [6 empty] | 0 | [11 empty] | 7
7308 | [6 empty] | 0 | [11 empty] | 7
7309 | [6 empty] | 0 | [11 empty] | 7
7310 | [6 empty] | 0 | [11 empty] | 7
7311 | [6 empty] | 0 | [11 empty] | 7
7312 | [6 empty] | 0 | [11 empty] | 7
7313 | [6 empty] | 0 | [11 empty] | 7
7314 | [6 empty] | 0 | [11 empty] | 7
7315 | [6 empty] | 0 | [11 empty] | 7
7316 | [6 empty] | 0 | [11 empty] | 7
7317 | [6 empty] | 0 | [11 empty] | 7
7318 | [6 empty] | 0 | [11 empty] | 7
7319 | [6 empty] | 0 | [11 empty] | 7
7320 | [6 empty] | 0 | [11 empty] | 7
7321 | [6 empty] | 0 | [11 empty] | 7
7322 | [6 empty] | 0 | [11 empty] | 7
7323 | [6 empty] | 0 | [11 empty] | 7
7324 | [6 empty] | 0 | [11 empty] | 7
7325 | [6 empty] | 0 | [11 empty] | 7
7326 | [6 empty] | 0 | [11 empty] | 7
7327 | [6 empty] | 0 | [11 empty] | 7
7328 | [6 empty] | 0 | [11 empty] | 7
7329 | [6 empty] | 0 | [11 empty] | 7
7330 | [6 empty] | 0 | [11 empty] | 7
7331 | [6 empty] | 0 | [11 empty] | 7
7332 | [6 empty] | 0 | [11 empty] | 7
7333 | [6 empty] | 0 | [11 empty] | 7
7334 | [6 empty] | 0 | [11 empty] | 7
7335 | [6 empty] | 0 | [11 empty] | 7
7336 | [6 empty] | 0 | [11 empty] | 7
7337 | [6 empty] | 0 | [11 empty] | 7
7338 | [6 empty] | 0 | [11 empty] | 7
7339 | [6 empty] | 0 | [11 empty] | 7
7340 | [6 empty] | 0 | [11 empty] | 7
7341 | [6 empty] | 0 | [11 empty] | 7
7342 | [6 empty] | 0 | [11 empty] | 7
7343 | [6 empty] | 0 | [11 empty] | 7
7344 | [6 empty] | 0 | [11 empty] | 7
7345 | [6 empty] | 0 | [11 empty] | 7
7346 | [6 empty] | 0 | [11 empty] | 7
7347 | [6 empty] | 0 | [11 empty] | 7
7348 | [6 empty] | 0 | [11 empty] | 7
7349 | [6 empty] | 0 | [11 empty] | 7
7350 | [6 empty] | 0 | [11 empty] | 7
7351 | [6 empty] | 0 | [11 empty] | 7
7352 | [6 empty] | 0 | [11 empty] | 7
7353 | [6 empty] | 0 | [11 empty] | 7
7354 | [6 empty] | 0 | [11 empty] | 7
7355 | [6 empty] | 0 | [11 empty] | 7
7356 | [6 empty] | 0 | [11 empty] | 7
7357 | [6 empty] | 0 | [11 empty] | 7
7358 | [6 empty] | 0 | [11 empty] | 7
7359 | [6 empty] | 0 | [11 empty] | 7
7360 | [6 empty] | 0 | [11 empty] | 7
7361 | [6 empty] | 0 | [11 empty] | 7
7362 | [6 empty] | 0 | [11 empty] | 7
7363 | [6 empty] | 0 | [11 empty] | 7
7364 | [6 empty] | 0 | [11 empty] | 7
7365 | [6 empty] | 0 | [11 empty] | 7
7366 | [6 empty] | 0 | [11 empty] | 7
7367 | [6 empty] | 0 | [11 empty] | 7
7368 | [6 empty] | 0 | [11 empty] | 7
7369 | [6 empty] | 0 | [11 empty] | 7
7370 | [6 empty] | 0 | [11 empty] | 7
7371 | [6 empty] | 0 | [11 empty] | 7
7372 | [6 empty] | 0 | [11 empty] | 7
7373 | [6 empty] | 0 | [11 empty] | 7
7374 | [6 empty] | 0 | [11 empty] | 7
7375 | [6 empty] | 0 | [11 empty] | 7
7376 | [6 empty] | 0 | [11 empty] | 7
7377 | [6 empty] | 0 | [11 empty] | 7
7378 | [6 empty] | 0 | [11 empty] | 7
7379 | [6 empty] | 0 | [11 empty] | 7
7380 | [6 empty] | 0 | [11 empty] | 7
7381 | [6 empty] | 0 | [11 empty] | 7
7382 | [6 empty] | 0 | [11 empty] | 7
7383 | [6 empty] | 0 | [11 empty] | 7
7384 | [6 empty] | 0 | [11 empty] | 7
7385 | [6 empty] | 0 | [11 empty] | 7
7386 | [6 empty] | 0 | [11 empty] | 7
7387 | [6 empty] | 0 | [11 empty] | 7
7388 | [6 empty] | 0 | [11 empty] | 7
7389 | [6 empty] | 0 | [11 empty] | 7
7390 | [6 empty] | 0 | [11 empty] | 7
7391 | [6 empty] | 0 | [11 empty] | 7
7392 | [6 empty] | 0 | [11 empty] | 7
7393 | [6 empty] | 0 | [11 empty] | 7
7394 | [6 empty] | 0 | [11 empty] | 7
7395 | [6 empty] | 0 | [11 empty] | 7
7396 | [6 empty] | 0 | [11 empty] | 7
7397 | [6 empty] | 0 | [11 empty] | 7
7398 | [6 empty] | 0 | [11 empty] | 7
7399 | [6 empty] | 0 | [11 empty] | 7
7400 | [6 empty] | 0 | [11 empty] | 7
7401 | [6 empty] | 0 | [11 empty] | 7
7402 | [6 empty] | 0 | [11 empty] | 7
7403 | [6 empty] | 0 | [11 empty] | 7
7404 | [6 empty] | 0 | [11 empty] | 7
7405 | [6 empty] | 0 | [11 empty] | 7
7406 | [6 empty] | 0 | [11 empty] | 7
7407 | [6 empty] | 0 | [11 empty] | 7
7408 | [6 empty] | 0 | [11 empty] | 7
7409 | [6 empty] | 0 | [11 empty] | 7
7410 | [6 empty] | 0 | [11 empty] | 7
7411 | [6 empty] | 0 | [11 empty] | 7
7412 | [6 empty] | 0 | [11 empty] | 7
7413 | [6 empty] | 0 | [11 empty] | 7
7414 | [6 empty] | 0 | [11 empty] | 7
7415 | [6 empty] | 0 | [11 empty] | 7
7416 | [6 empty] | 0 | [11 empty] | 7
7417 | [6 empty] | 0 | [11 empty] | 7
7418 | [6 empty] | 0 | [11 empty] | 7
7419 | [6 empty] | 0 | [11 empty] | 7
7420 | [6 empty] | 0 | [11 empty] | 7
7421 | [6 empty] | 0 | [11 empty] | 7
7422 | [6 empty] | 0 | [11 empty] | 7
7423 | [6 empty] | 0 | [11 empty] | 7
7424 | [6 empty] | 0 | [11 empty] | 7
7425 | [6 empty] | 0 | [11 empty] | 7
7426 | [6 empty] | 0 | [11 empty] | 7
7427 | [6 empty] | 0 | [11 empty] | 7
7428 | [6 empty] | 0 | [11 empty] | 7
7429 | [6 empty] | 0 | [11 empty] | 7
7430 | [6 empty] | 0 | [11 empty] | 7
7431 | [6 empty] | 0 | [11 empty] | 7
7432 | [6 empty] | 0 | [11 empty] | 7
7433 | [6 empty] | 0 | [11 empty] | 7
7434 | [6 empty] | 0 | [11 empty] | 7
7435 | [6 empty] | 0 | [11 empty] | 7
7436 | [6 empty] | 0 | [11 empty] | 7
7437 | [6 empty] | 0 | [11 empty] | 7
7438 | [6 empty] | 0 | [11 empty] | 7
7439 | [6 empty] | 0 | [11 empty] | 7
7440 | [6 empty] | 0 | [11 empty] | 7
7441 | [6 empty] | 0 | [11 empty] | 7
7442 | [6 empty] | 0 | [11 empty] | 7
7443 | [6 empty] | 0 | [11 empty] | 7
7444 | [6 empty] | 0 | [11 empty] | 7
7445 | [6 empty] | 0 | [11 empty] | 7
7446 | [6 empty] | 0 | [11 empty] | 7
7447 | [6 empty] | 0 | [11 empty] | 7
7448 | [6 empty] | 0 | [11 empty] | 7
7449 | [6 empty] | 0 | [11 empty] | 7
7450 | [6 empty] | 0 | [11 empty] | 7
7451 | [6 empty] | 0 | [11 empty] | 7
7452 | [6 empty] | 0 | [11 empty] | 7
7453 | [6 empty] | 0 | [11 empty] | 7
7454 | [6 empty] | 0 | [11 empty] | 7
7455 | [6 empty] | 0 | [11 empty] | 7
7456 | [6 empty] | 0 | [11 empty] | 7
7457 | [6 empty] | 0 | [11 empty] | 7
7458 | [6 empty] | 0 | [11 empty] | 7
7459 | [6 empty] | 0 | [11 empty] | 7
7460 | [6 empty] | 0 | [11 empty] | 7
7461 | [6 empty] | 0 | [11 empty] | 7
7462 | [6 empty] | 0 | [11 empty] | 7
7463 | [6 empty] | 0 | [11 empty] | 7
7464 | [6 empty] | 0 | [11 empty] | 7
7465 | [6 empty] | 0 | [11 empty] | 7
7466 | [6 empty] | 0 | [11 empty] | 7
7467 | [6 empty] | 0 | [11 empty] | 7
7468 | [6 empty] | 0 | [11 empty] | 7
7469 | [6 empty] | 0 | [11 empty] | 7
7470 | [6 empty] | 0 | [11 empty] | 7
7471 | [6 empty] | 0 | [11 empty] | 7
7472 | [6 empty] | 0 | [11 empty] | 7
7473 | [6 empty] | 0 | [11 empty] | 7
7474 | [6 empty] | 0 | [11 empty] | 7
7475 | [6 empty] | 0 | [11 empty] | 7
7476 | [6 empty] | 0 | [11 empty] | 7
7477 | [6 empty] | 0 | [11 empty] | 7
7478 | [6 empty] | 0 | [11 empty] | 7
7479 | [6 empty] | 0 | [11 empty] | 7
7480 | [6 empty] | 0 | [11 empty] | 7
7481 | [6 empty] | 0 | [11 empty] | 7
7482 | [6 empty] | 0 | [11 empty] | 7
7483 | [6 empty] | 0 | [11 empty] | 7
7484 | [6 empty] | 0 | [11 empty] | 7
7485 | [6 empty] | 0 | [11 empty] | 7
7486 | [6 empty] | 0 | [11 empty] | 7
7487 | [6 empty] | 0 | [11 empty] | 7
7488 | [6 empty] | 0 | [11 empty] | 7
7489 | [6 empty] | 0 | [11 empty] | 7
7490 | [6 empty] | 0 | [11 empty] | 7
7491 | [6 empty] | 0 | [11 empty] | 7
7492 | [6 empty] | 0 | [11 empty] | 7
7493 | [6 empty] | 0 | [11 empty] | 7
7494 | [6 empty] | 0 | [11 empty] | 7
7495 | [6 empty] | 0 | [11 empty] | 7
7496 | [6 empty] | 0 | [11 empty] | 7
7497 | [6 empty] | 0 | [11 empty] | 7
7498 | [6 empty] | 0 | [11 empty] | 7
7499 | [6 empty] | 0 | [11 empty] | 7
7500 | [6 empty] | 0 | [11 empty] | 7
7501 | [6 empty] | 0 | [11 empty] | 7
7502 | [6 empty] | 0 | [11 empty] | 7
7503 | [6 empty] | 0 | [11 empty] | 7
7504 | [6 empty] | 0 | [11 empty] | 7
7505 | [6 empty] | 0 | [11 empty] | 7
7506 | [6 empty] | 0 | [11 empty] | 7
7507 | [6 empty] | 0 | [11 empty] | 7
7508 | [6 empty] | 0 | [11 empty] | 7
7509 | [6 empty] | 0 | [11 empty] | 7
7510 | [6 empty] | 0 | [11 empty] | 7
7511 | [6 empty] | 0 | [11 empty] | 7
7512 | [6 empty] | 0 | [11 empty] | 7
7513 | [6 empty] | 0 | [11 empty] | 7
7514 | [6 empty] | 0 | [11 empty] | 7
7515 | [6 empty] | 0 | [11 empty] | 7
7516 | [6 empty] | 0 | [11 empty] | 7
7517 | [6 empty] | 0 | [11 empty] | 7
7518 | [6 empty] | 0 | [11 empty] | 7
7519 | [6 empty] | 0 | [11 empty] | 7
7520 | [6 empty] | 0 | [11 empty] | 7
7521 | [6 empty] | 0 | [11 empty] | 7
7522 | [6 empty] | 0 | [11 empty] | 7
7523 | [6 empty] | 0 | [11 empty] | 7
7524 | [6 empty] | 0 | [11 empty] | 7
7525 | [6 empty] | 0 | [11 empty] | 7
7526 | [6 empty] | 0 | [11 empty] | 7
7527 | [6 empty] | 0 | [11 empty] | 7
7528 | [6 empty] | 0 | [11 empty] | 7
7529 | [6 empty] | 0 | [11 empty] | 7
7530 | [6 empty] | 0 | [11 empty] | 7
7531 | [6 empty] | 0 | [11 empty] | 7
7532 | [6 empty] | 0 | [11 empty] | 7
7533 | [6 empty] | 0 | [11 empty] | 7
7534 | [6 empty] | 0 | [11 empty] | 7
7535 | [6 empty] | 0 | [11 empty] | 7
7536 | [6 empty] | 0 | [11 empty] | 7
7537 | [6 empty] | 0 | [11 empty] | 7
7538 | [6 empty] | 0 | [11 empty] | 7
7539 | [6 empty] | 0 | [11 empty] | 7
7540 | [6 empty] | 0 | [11 empty] | 7
7541 | [6 empty] | 0 | [11 empty] | 7
7542 | [6 empty] | 0 | [11 empty] | 7
7543 | [6 empty] | 0 | [11 empty] | 7
7544 | [6 empty] | 0 | [11 empty] | 7
7545 | [6 empty] | 0 | [11 empty] | 7
7546 | [6 empty] | 0 | [11 empty] | 7
7547 | [6 empty] | 0 | [11 empty] | 7
7548 | [6 empty] | 0 | [11 empty] | 7
7549 | [6 empty] | 0 | [11 empty] | 7
7550 | [6 empty] | 0 | [11 empty] | 7
7551 | [6 empty] | 0 | [11 empty] | 7
7552 | [6 empty] | 0 | [11 empty] | 7
7553 | [6 empty] | 0 | [11 empty] | 7
7554 | [6 empty] | 0 | [11 empty] | 7
7555 | [6 empty] | 0 | [11 empty] | 7
7556 | [6 empty] | 0 | [11 empty] | 7
7557 | [6 empty] | 0 | [11 empty] | 7
7558 | [6 empty] | 0 | [11 empty] | 7
7559 | [6 empty] | 0 | [11 empty] | 7
7560 | [6 empty] | 0 | [11 empty] | 7
7561 | [6 empty] | 0 | [11 empty] | 7
7562 | [6 empty] | 0 | [11 empty] | 7
7563 | [6 empty] | 0 | [11 empty] | 7
7564 | [6 empty] | 0 | [11 empty] | 7
7565 | [6 empty] | 0 | [11 empty] | 7
7566 | [6 empty] | 0 | [11 empty] | 7
7567 | [6 empty] | 0 | [11 empty] | 7
7568 | [6 empty] | 0 | [11 empty] | 7
7569 | [6 empty] | 0 | [11 empty] | 7
7570 | [6 empty] | 0 | [11 empty] | 7
7571 | [6 empty] | 0 | [11 empty] | 7
7572 | [6 empty] | 0 | [11 empty] | 7
7573 | [6 empty] | 0 | [11 empty] | 7
7574 | [6 empty] | 0 | [11 empty] | 7
7575 | [6 empty] | 0 | [11 empty] | 7
7576 | [6 empty] | 0 | [11 empty] | 7
7577 | [6 empty] | 0 | [11 empty] | 7
7578 | [6 empty] | 0 | [11 empty] | 7
7579 | [6 empty] | 0 | [11 empty] | 7
7580 | [6 empty] | 0 | [11 empty] | 7
7581 | [6 empty] | 0 | [11 empty] | 7
7582 | [6 empty] | 0 | [11 empty] | 7
7583 | [6 empty] | 0 | [11 empty] | 7
7584 | [6 empty] | 0 | [11 empty] | 7
7585 | [6 empty] | 0 | [11 empty] | 7
7586 | [6 empty] | 0 | [11 empty] | 7
7587 | [6 empty] | 0 | [11 empty] | 7
7588 | [6 empty] | 0 | [11 empty] | 7
7589 | [6 empty] | 0 | [11 empty] | 7
7590 | [6 empty] | 0 | [11 empty] | 7
7591 | [6 empty] | 0 | [11 empty] | 7
7592 | [6 empty] | 0 | [11 empty] | 7
7593 | [6 empty] | 0 | [11 empty] | 7
7594 | [6 empty] | 0 | [11 empty] | 7
7595 | [6 empty] | 0 | [11 empty] | 7
7596 | [6 empty] | 0 | [11 empty] | 7
7597 | [6 empty] | 0 | [11 empty] | 7
7598 | [6 empty] | 0 | [11 empty] | 7
7599 | [6 empty] | 0 | [11 empty] | 7
7600 | [6 empty] | 0 | [11 empty] | 7
7601 | [6 empty] | 0 | [11 empty] | 7
7602 | [6 empty] | 0 | [11 empty] | 7
7603 | [6 empty] | 0 | [11 empty] | 7
7604 | [6 empty] | 0 | [11 empty] | 7
7605 | [6 empty] | 0 | [11 empty] | 7
7606 | [6 empty] | 0 | [11 empty] | 7
7607 | [6 empty] | 0 | [11 empty] | 7
7608 | [6 empty] | 0 | [11 empty] | 7
7609 | [6 empty] | 0 | [11 empty] | 7
7610 | [6 empty] | 0 | [11 empty] | 7
7611 | [6 empty] | 0 | [11 empty] | 7
7612 | [6 empty] | 0 | [11 empty] | 7
7613 | [6 empty] | 0 | [11 empty] | 7
7614 | [6 empty] | 0 | [11 empty] | 7
7615 | [6 empty] | 0 | [11 empty] | 7
7616 | [6 empty] | 0 | [11 empty] | 7
7617 | [6 empty] | 0 | [11 empty] | 7
7618 | [6 empty] | 0 | [11 empty] | 7
7619 | [6 empty] | 0 | [11 empty] | 7
7620 | [6 empty] | 0 | [11 empty] | 7
7621 | [6 empty] | 0 | [11 empty] | 7
7622 | [6 empty] | 0 | [11 empty] | 7
7623 | [6 empty] | 0 | [11 empty] | 7
7624 | [6 empty] | 0 | [11 empty] | 7
7625 | [6 empty] | 0 | [11 empty] | 7
7626 | [6 empty] | 0 | [11 empty] | 7
7627 | [6 empty] | 0 | [11 empty] | 7
7628 | [6 empty] | 0 | [11 empty] | 7
7629 | [6 empty] | 0 | [11 empty] | 7
7630 | [6 empty] | 0 | [11 empty] | 7
7631 | [6 empty] | 0 | [11 empty] | 7
7632 | [6 empty] | 0 | [11 empty] | 7
7633 | [6 empty] | 0 | [11 empty] | 7
7634 | [6 empty] | 0 | [11 empty] | 7
7635 | [6 empty] | 0 | [11 empty] | 7
7636 | [6 empty] | 0 | [11 empty] | 7
7637 | [6 empty] | 0 | [11 empty] | 7
7638 | [6 empty] | 0 | [11 empty] | 7
7639 | [6 empty] | 0 | [11 empty] | 7
7640 | [6 empty] | 0 | [11 empty] | 7
7641 | [6 empty] | 0 | [11 empty] | 7
7642 | [6 empty] | 0 | [11 empty] | 7
7643 | [6 empty] | 0 | [11 empty] | 7
7644 | [6 empty] | 0 | [11 empty] | 7
7645 | [6 empty] | 0 | [11 empty] | 7
7646 | [6 empty] | 0 | [11 empty] | 7
7647 | [6 empty] | 0 | [11 empty] | 7
7648 | [6 empty] | 0 | [11 empty] | 7
7649 | [6 empty] | 0 | [11 empty] | 7
7650 | [6 empty] | 0 | [11 empty] | 7
7651 | [6 empty] | 0 | [11 empty] | 7
7652 | [6 empty] | 0 | [11 empty] | 7
7653 | [6 empty] | 0 | [11 empty] | 7
7654 | [6 empty] | 0 | [11 empty] | 7
7655 | [6 empty] | 0 | [11 empty] | 7
7656 | [6 empty] | 0 | [11 empty] | 7
7657 | [6 empty] | 0 | [11 empty] | 7
7658 | [6 empty] | 0 | [11 empty] | 7
7659 | [6 empty] | 0 | [11 empty] | 7
7660 | [6 empty] | 0 | [11 empty] | 7
7661 | [6 empty] | 0 | [11 empty] | 7
7662 | [6 empty] | 0 | [11 empty] | 7
7663 | [6 empty] | 0 | [11 empty] | 7
7664 | [6 empty] | 0 | [11 empty] | 7
7665 | [6 empty] | 0 | [11 empty] | 7
7666 | [6 empty] | 0 | [11 empty] | 7
7667 | [6 empty] | 0 | [11 empty] | 7
7668 | [6 empty] | 0 | [11 empty] | 7
7669 | [6 empty] | 0 | [11 empty] | 7
7670 | [6 empty] | 0 | [11 empty] | 7
7671 | [6 empty] | 0 | [11 empty] | 7
7672 | [6 empty] | 0 | [11 empty] | 7
7673 | [6 empty] | 0 | [11 empty] | 7
7674 | [6 empty] | 0 | [11 empty] | 7
7675 | [6 empty] | 0 | [11 empty] | 7
7676 | [6 empty] | 0 | [11 empty] | 7
7677 | [6 empty] | 0 | [11 empty] | 7
7678 | [6 empty] | 0 | [11 empty] | 7
7679 | [6 empty] | 0 | [11 empty] | 7
7680 | [6 empty] | 0 | [11 empty] | 7
7681 | [6 empty] | 0 | [11 empty] | 7
7682 | [6 empty] | 0 | [11 empty] | 7
7683 | [6 empty] | 0 | [11 empty] | 7
7684 | [6 empty] | 0 | [11 empty] | 7
7685 | [6 empty] | 0 | [11 empty] | 7
7686 | [6 empty] | 0 | [11 empty] | 7
7687 |  | Manually Scheduled |  |  |  |  | 0 |  | 0h | [7 empty] | NA | As Soon As Possible | 7
7688 | [6 empty] | 0 | [11 empty] | 7
7689 | [6 empty] | 0 | [11 empty] | 7
7690 | [6 empty] | 0 | [11 empty] | 7
7691 | [6 empty] | 0 | [11 empty] | 7
7692 | [6 empty] | 0 | [11 empty] | 7
7693 | [6 empty] | 0 | [11 empty] | 7
7694 | [6 empty] | 0 | [11 empty] | 7
7695 | [6 empty] | 0 | [11 empty] | 7
7696 | [6 empty] | 0 | [11 empty] | 7
7697 | [6 empty] | 0 | [11 empty] | 7
7698 | [6 empty] | 0 | [11 empty] | 7
7699 | [6 empty] | 0 | [11 empty] | 7
7700 | [6 empty] | 0 | [11 empty] | 7
7701 | [6 empty] | 0 | [11 empty] | 7
7702 | [6 empty] | 0 | [11 empty] | 7
7703 | [6 empty] | 0 | [11 empty] | 7
7704 | [6 empty] | 0 | [11 empty] | 7
7705 | [6 empty] | 0 | [11 empty] | 7
7706 | [6 empty] | 0 | [11 empty] | 7
7707 | [6 empty] | 0 | [11 empty] | 7
7708 | [6 empty] | 0 | [11 empty] | 7
7709 | [6 empty] | 0 | [11 empty] | 7
7710 | [6 empty] | 0 | [11 empty] | 7
7711 | [6 empty] | 0 | [11 empty] | 7
7712 | [6 empty] | 0 | [11 empty] | 7
7713 | [6 empty] | 0 | [11 empty] | 7
7714 | [6 empty] | 0 | [11 empty] | 7
7715 | [6 empty] | 0 | [11 empty] | 7
7716 | [6 empty] | 0 | [11 empty] | 7
7717 | [6 empty] | 0 | [11 empty] | 7
7718 | [6 empty] | 0 | [11 empty] | 7
7719 | [6 empty] | 0 | [11 empty] | 7
7720 | [6 empty] | 0 | [11 empty] | 7
7721 | [6 empty] | 0 | [11 empty] | 7
7722 | [6 empty] | 0 | [11 empty] | 7
7723 | [6 empty] | 0 | [11 empty] | 7
7724 | [6 empty] | 0 | [11 empty] | 7
7725 | [6 empty] | 0 | [11 empty] | 7
7726 | [6 empty] | 0 | [11 empty] | 7
7727 | [6 empty] | 0 | [11 empty] | 7
7728 | [6 empty] | 0 | [11 empty] | 7
7729 | [6 empty] | 0 | [11 empty] | 7
7730 | [6 empty] | 0 | [11 empty] | 7
7731 | [6 empty] | 0 | [11 empty] | 7
7732 | [6 empty] | 0 | [11 empty] | 7
7733 | [6 empty] | 0 | [11 empty] | 7
7734 | [6 empty] | 0 | [11 empty] | 7
7735 | [6 empty] | 0 | [11 empty] | 7
7736 | [6 empty] | 0 | [11 empty] | 7
7737 | [6 empty] | 0 | [11 empty] | 7
7738 | [6 empty] | 0 | [11 empty] | 7
7739 | [6 empty] | 0 | [11 empty] | 7
7740 | [6 empty] | 0 | [11 empty] | 7
7741 | [6 empty] | 0 | [11 empty] | 7
7742 | [6 empty] | 0 | [11 empty] | 7
7743 | [6 empty] | 0 | [11 empty] | 7
7744 | [6 empty] | 0 | [11 empty] | 7
7745 | [6 empty] | 0 | [11 empty] | 7
7746 | [6 empty] | 0 | [11 empty] | 7
7747 | [6 empty] | 0 | [11 empty] | 7
7748 | [6 empty] | 0 | [11 empty] | 7
7749 | [6 empty] | 0 | [11 empty] | 7
7750 | [6 empty] | 0 | [11 empty] | 7
7751 | [6 empty] | 0 | [11 empty] | 7
7752 | [6 empty] | 0 | [11 empty] | 7
7753 | [6 empty] | 0 | [11 empty] | 7
7754 | [6 empty] | 0 | [11 empty] | 7
7755 | [6 empty] | 0 | [11 empty] | 7
7756 | [6 empty] | 0 | [11 empty] | 7
7757 | [6 empty] | 0 | [11 empty] | 7
7758 | [6 empty] | 0 | [11 empty] | 7
7759 | [6 empty] | 0 | [11 empty] | 7
7760 | [6 empty] | 0 | [11 empty] | 7
7761 | [6 empty] | 0 | [11 empty] | 7
7762 | [6 empty] | 0 | [11 empty] | 7
7763 | [6 empty] | 0 | [11 empty] | 7
7764 | [6 empty] | 0 | [11 empty] | 7
7765 | [6 empty] | 0 | [11 empty] | 7
7766 | [6 empty] | 0 | [11 empty] | 7
7767 | [6 empty] | 0 | [11 empty] | 7
7768 | [6 empty] | 0 | [11 empty] | 7
7769 | [6 empty] | 0 | [11 empty] | 7
7770 | [6 empty] | 0 | [11 empty] | 7
7771 | [6 empty] | 0 | [11 empty] | 7
7772 | [6 empty] | 0 | [11 empty] | 7
7773 | [6 empty] | 0 | [11 empty] | 7
7774 | [6 empty] | 0 | [11 empty] | 7
7775 | [6 empty] | 0 | [11 empty] | 7
7776 | [6 empty] | 0 | [11 empty] | 7
7777 | [6 empty] | 0 | [11 empty] | 7
7778 | [6 empty] | 0 | [11 empty] | 7
7779 |  | Manually Scheduled |  |  |  |  | 0 |  | 0h | [7 empty] | NA | As Soon As Possible | 7